## Open
TICKET # | REPORTED BY | DATE REPORTED | TOOL | Issue | Comments | Resolution
901/6 | Alfvin | 2011-08-30 | ePoll | ePoll Invitation must contain the link to the ePoll |  | To be developed in 2011
902/7 | 802.11 | 2011-08-30 | ePoll | UX | After casting the vote, I would prefer to be dropped back to where I came from (even though the next action is possible, i.e. make comment) | 10/26 2012 development of UX revamp of myProject
902/7 | 802.11 | 2011-08-30 | ePoll | Comments Page & SubClause | Allow Roman Numberals for page and subclause. AS: Our frontmatter uses Roman numbering. But we get few comments on front matter. I would rather see an integer syntax to prevent ranges such as "10-11", which people otherwise seem to love. | Need more information from additional groups before additional features/enhancements are to be made
902/7 | 802.11 | 2011-08-30 | ePoll | Comment Category | Category should have 'standard' entries. Devise a standard entry scheme for 'Categories' such as E, T, G. Single comment entry should have the same checking rules as file upload. | Need more information from additional groups before additional features/enhancements are to be made
902/7 | 802.11 | 2011-08-30 | ePoll | Comment Numbering | Comments should have a number for tracking. Devise a numbering scheme and template. AS: We do need tracking numbering, however, I'm happy to add this myself, because we need non-overlapping numbering withing a recirculation series. | Need more information from additional groups before additional features/enhancements are to be made
902/7 | 802.11 | 2011-08-30 | ePoll | Comment fields | All fields in the comment form should be mandatory | Need more information from additional groups before additional features/enhancements are to be made
902/7 | 802.11 | 2011-08-30 | ePoll | Comment CSV | It would be nice if the CSV file format had a header with the Ballot identified (Ballot number, question asked, etc.), so I can save it for my records, and remember what it was about a year from now. AS: I agree with the commenter, but only weakly. | Need more information from additional groups before additional features/enhancements are to be made
902/7 | 802.11 | 2011-08-30 | ePoll | Abstain | My abstain didn't ask for a reason. I believe our P&P requires a reason to abstain. We need a process/method (and instructions) on how to provide a reason along with an Abstain vote. AS: In 802.11 "abstain for lack of experience" is the only valid abstain. I think it's sufficient though to indicate in our 802.11 supplied instructions that this is the only valid abstain. | Need more information from additional groups before additional features/enhancements are to be made
902/7 | 802.11 | 2011-08-30 | ePoll | Comment Upload | What are valid Category column entries? Need a header (or a drop-list) to control entry in that column. It's way too hard to guess what's appropriate. And, the error message when uploading an invalid entry in Categoy is very obtuse ('Column "category": not found'). AS: More work needed on making this user-friendly | Need more information from additional groups before additional features/enhancements are to be made
878 | Stephens | 2011-08-16 | ePoll | Comment csv vs xls | Working with comment upload files is important, because some users submit hundreds of comments. The biggest omission from the features that I wanted was the ability for a voter to import comments from an .xls file. The reason for this is that the ".csv" template has no formatting. As a result the voter has to mess around with word wrap and column width, save it as .xls, work on comments over a 2-week period. Eventually save it as .csv and upload. I don't want to create impediments for our users, and this, IMHO is an impediment, knowing that even the simplest operations will defeat some people.(You might claim that they don't deserve to vote in that case, but we don't get to choose our volunteers :0). Anyhow, I may just be making a mountain out of a mole-hill. Our voters might not care. We'll see what kind of feedback we get. | Need more information from additional groups before additional features/enhancements are to be made
915 | Christina | 2011-08-01 | IMAT | Murphy server replacement | New server for murphy to be configured for Atlanta meeting. Walter and tech team is working with Rick @ Verilan and his team to organize. | Oct. 3, 2011 this project is underway per Walter P. Oct. 17 new Murphy is almost ready - team is working on load testing this week. CB contacted Verilan to find out when newMurphy needs to be packed up for shipment to Atlanta. Tech Team advised that the hosted version of IMAT is also working and ready to use in Atlanta if new Murphy is not ready. 10/26 New murphy server has been shipped to Atlanta in preparation for plenary session.
915 | Christina | 2011-08-01 | IMAT | Seabass server replacement | New server for IMAT/seabass needs to be replaced. Luigi is working with IEEE IT on setting up the server. Walter and tech team will get involved when IEEE IT has the machine ready. The plan is to have this machine ready for use in Atlanta as well. | Oct. 4 2011 Seabass server to be replaced after Atlanta.
24 | Alfvin | 2011-09-22 | IMAT | The ability to delete ALL meetings for a session | For example, if I import a schedule with 100 individual meetings and realize I imported the wrong schedule or decide to completely change the schedule, I currently have no means to delete all 100 meetings other than having to individually select and click on every single meeting on multiple screens (time consuming and annoying when a delete all or delete schedule would solve the problem.) CB-->You can click the first box, hold down the shift key then click the last box to check all boxes in the list. I believe (from my view) all of the meetings show up on one page and therefore this action (3 key strokes) only needs to be done once to delete all. This does not completely solve your problem but does reduce the key strokes. | Thank you for your quick and courteous reply. I can live with the 3 keystrokes to delete all meetings (assuming it works). 10/26 To be discussed at IMAT Meeting with Stephens and Alfvin
24 | Alfvin | 2011-09-22 | IMAT | The ability to delete a meeting that has attendance logged to it. | For example, often a meeting is cancelled by the chair and I'm not told about the cancellation until after that time slot has passed. Since the meeting did not occur, anyone who claimed attendance for that meeting is either, lying, cheating or stupid, therefore I should be able to delete the meeting from the schedule along with all the erroneous attendance logged to the meeting that never happened. CB--> The specification was written to prevent the deletion of a meeting where attendance was logged. This feature acts as a preventative measure so "real" meetings with actual attendees are not deleted by mistake. The correct process should be: a) identify the errant attendees and scold them b) go into the Manager feature and remove them c) delete the empty meeting. RA: I am however not ok with the process you described to delete a meeting that didn't occur and has people signed in erroneously. The correct process should be not to waste copious amounts of my time and cause unbridled frustration: a) identify the errant attendees and scold them I am not a babysitter or a parent of these people and do not have enough time in my day to spend it scolding intelligent adults about the errors in their ways. b) go into the Manager feature and remove them Try doing this for 10 people. It is tedious and ridiculously time consuming, not to say frustrating because it should be unnecessary. c) delete the empty meeting. This should be the only step in the process. BTW...I am willing to sign a document releasing you of any responsibility or liability for my actions. Seriously though, if you are really worried about accidentally deleting a real meeting with real attendance then build a confirmation prompt that requires the admin (me) to type in their password or something to cause the person to have a moment to reflect and verify that what they are doing is correct. Thank you for your kind understanding and consideration of my rational and completely reasonable requests that would significantly improve the quality of the user interface for many future generations of volunteers who selflessly contribute their time so IEEE can make money they will never see. | 10/26 To be discussed at IMAT Meeting with Stephens and Alfvin
26 | Stephens | 2011-09-23 | IMAT | Delete a meeting | While you’re on this subject. Previously I’d wanted to delete all the 802.11 meetings and then upload a fresh set, as being the quickest way to make a bunch of changes. I discovered that even though a meeting is deleted, it is still remembered by the system. It would not let me re-create the meeting without quoting a matching Breakout ID of the deleted meeting. This is a bug – i.e., the system should truly forget deleted meetings. | 10/26 To be discussed at IMAT Meeting with Stephens and Alfvin
680 | Christina | 2011-01-11 | IMAT | Problems with Tom's code | Yes, the bug was fixed in Tom's code. Rob and I have discussed it and found the following shortcomings: * the download.pl file isn't run with strict "-w" mode from cron. When running under strict manually, it shows several uninitialized and other warnings. These could be sources for other bugs. * download.pl isn't fail-fast. If it encounters and error, it dies, but leaves the database in a half updated state. Instead it should use a SQL transaction and rollback if it fails. That would help narrow problems when the database is half populated and the application is limping along - for example, the app shows meetings but doesn't allow login, or the app allows login but doesn't have the user permissions loaded yet. * The download.pl cron entry needs to alert us when an import fails. As a myProject example, we receive an email summary after the ballot states are updated each night. If the update fails, it rolls back and includes the failure information in the message. * IMAT Local doesn't have any automated tests, so any changes to myProject which might cause bugs will only show up on the live application. For myProject we have automated tests which run against the test system each night, and new cases are added for each bug which is found on production. | CB: Plan to schedule and budget for the code fix in 2012. Need 802 volunteer to assist with this project (documentation, testing, etc.) (Alfvin/Stephens) 10/17 CB sent email contact to Adrian and Rick. Reach out for assistance. 10/26 CB scheduled meeting with Alfvin, Stephens, Rosdahl, for 11/8.
929/28 | 802.1 Teener | 2011-09-20 | Mentor | Mentor usability and feature comments | Gee, it's awfully crude. I'd love to use it for the 802.1AVB or 1722.1 groups since it has some integration with myProject, and the documents interface is pretty good, but … 0) The navigation is useless. We need some kind of navigation sidebar for the "wiki" … at the very least allow for a kind of universal navigation link header such as the existing 802.1 pages use. 1) The "wiki" isn't a wiki … it's a bunch of pages. If you are going to call it a wiki, please use MediaWiki or some other reasonable facsimile that is at least vaguely powerful. 2) The document submission/revision process does not automatically populate the contributor information (name/affiliation). The information is required, and should be available, so why don't we use it? … it would also be nice if there was a "proxy" field for something like "submitted by name (affiliation) for name (affiliation)". Or make it mandatory 3) The calendaring system is very, very weak. 4) The epoll is useful feature, but once again, it should at *least* have the features of the various free online polling systems (multiple choices, graphs, reminders … blah, blah). I can't help but thinking that this is a lost cause. Staff needs to spend it's time on added value on top of an existing and continually updated web platform such as Google Apps, Kavi, Huddle, etc. There are *so* many things we can already get via these platforms (scalability, reliability, etc.), and I would expect that the IEEE could negotiate a really good deal that could get staff out from underneath a bunch of mundane low-level management to a more architectural and system management approach.
899/4 | Thaler/Law | 2011-08-29 | myProject | Outstanding negative voters roll-up of comments |  | Oct. 3, 2011 System change write up sent to PT and approved. Waiting for RevCom approval before moving to develop
865/9 | Nikolich | 2011-08-09 | myProject | Send Notifications in myProject |  | Assigned to bivio to fix bug.
816/717 | 802EC | 2011-06-20 | myProject | Satisfied Comments | There should also be a mechanism provided for a voter who isn’t completely satisfied but has been satisfied on some comments to mark those comments as satisfied. Again, this would help focus voters and reviewers on the comments that are unsatisfied and remove the chaff from that review. Allow a disapprove voter to mark satisfied comments with a check box. And Provide a display all remaining disapprove comments | This is very complicated and I'm not sure how useful it would be.
728 | 802 + | 2011-03-17 | myProject | Enhanced Comment Features | Includes: Roman Numerals, fixing comment errors, | CB: We plan on fixing issues with the sponsor ballot comment tool and need 802 volunteer to participate in team meetings to document change requests for development in 2012. (Adrian/Law) 10/26 CB in process of setting up meeting with team (Law, Stephens, Vogel, Bennett, Marchini, Gerdon)
728 | 802+ | 2011-06-01 | myProject | Enhance Comment Resolution Tool | Can we use 802.3 or 802.16 comment resolution tool? Should we reprogram? Should we just make it available?
31 | Nikolich | 2011-10-02 | ALL | APIs | Per email from Face to Face regarding a request to Paul to add an item to the EC for discussion the SA needs to address how it wants to handle APIs/an a potential registration system/process (and communications) for those groups who implement APIs. Action is for SA IT team to discuss/determine how to proceed and respond to 802/Face to Face. In my one on one w/ Paul he wants us to coordinate with Tom Sklyehouse vs Dawn at Face to Face. Since Face to Face brought the issues up, I suggest we start by responding to Face to Face. | CB: this needs to be discussed/planned in SA Tech group. Project lead is Luigi. The SA will need to look at esablishing policies around APIs and build a method for registration for API developers.

## Complete
TICKET # | REPORTED BY | DATE REPORTED | TOOL | Issue | Comments | Resolution
29 | Shellhammer | 2011-09-26 | Mentor | Needs Training | Steve would like training on Mentor ePolls. CB is trying to set up time, or suggest Steve to contact Kathryn B for assistance. | CLOSED Oct. 3