## Slide 1: Action Item Summary @ Start of IEEE 802 Mar 2017 Plenary
John D’Ambrosia
Recording Secretary, IEEE 802 LMSC
Futurewei, Subsidiary of Huawei
Mar 13, 2016

## Slide 2: Action Item Summary – July 2016 Closing
Item 7.042
Gilb – determine in Chair’s Guideline how to resolve how to progress documents, including liaisons, from subgroups of the sponsor and the sponsor.
Status – in process. To be discussed at Nov 2016 Plenary.
Updated Status - Proposed rule changes to be sent out and reviewed at March 2017 Plenary.
Updated Status – Gilb to provide update of rules meeting discussion.
Item 8.0451
DAmbrosia / Stephens / Marks / Thaler to develop a motion template file that contains common different motions used in the EC.
Status – in process. Update uploaded to Mentor – see https://mentor.ieee.org/802-ec/dcn/16/ec-16-0170-02-00EC-802-ec-motion-template.pptx. Remaining issues to be resolved at Mar Plenary.
Status – Remaining issues resolved. Gilb to provide one rules reference. File uploaded for use - https://mentor.ieee.org/802-ec/dcn/16/ec-16-0170-03-00EC-802-ec-motion-template.pptx

## Slide 3: Action Item Summary – July 2016 Closing (1/2)
July 2016 Closing – Gilb – determine in Chair’s Guideline how to resolve how to progress documents, including liaisons, from subgroups of the sponsor and the sponsor. Proposed rule changes to be sent out and reviewed at March 2017 Plenary.
Nov 2016 Closing – Thaler - work with IEEE-SA Staff to resolve any IEEE / IETF copyright issues. Update @ March Plenary. Status in process – letter to be brought forward at IEEE 802 March Plenary.
  Status Update Completed - The IETF folks involved decided to do a rewrite of the draft to replace the copied material with references. If the OPS and Management groups find the resulting draft acceptable, they will move forward with that. So there isn't a driving IETF interest in working further on the issue for now.
Feb 2017 EC Tele. – Item 5.00 - Parsons to revisit verbiage “IEEE 802 standards referenced in regulation.
  Status Update – Completed - Recommended “IEEE 802 standards referenced in government documents, e.g., regulations, procurement”.
Feb 2017 EC Tele. – Item 5.00 - Parsons to form Steering Committee
  Status Update – Completed - Done. Adrian, Rich, Apurva & Subir join

## Slide 4: Action Item Summary – July 2016 Closing (1/2)
Feb 2017 EC Tele. – Item 5.00 - EC members should contact Glenn offline to participate in the Steering Committee.
  Status Update - Completed. First meeting was March 8th.
Feb 2017 EC Tele. – Item 8.01 - Nikolich to define 802 LMSC's criteria for selecting meeting venues.
Feb 2017 EC Tele. – Item 8.01 - Thaler to lead the collection of meeting venue selection criteria from 802 EC members, due not later than 10 Feb 2017.
  Status Update – Draft of considerations to be posted.
Feb 2017 EC Tele. – Item 9.01 - Chaplin to send document to Nikolich for signature when completed.
  Status – letter to be brought forward at IEEE 802 March Plenary.