## Slide 1: IEEE 802 status report to ISO/IEC JTC1/SC6 for SC6 meeting in April 2019 in Beijing, China
22 March 2019
Author:
Name | Company | Phone | email
Paul Nikolich | IEEE 802 Chair | +1 857 205 0050 | p.nikolich@ieee.org
Andrew Myles (Chair) | Cisco | +61 418 656587 | amyles@cisco.com
Peter Yee (Vice Chair) | AKAYLA | +1 415 215 7733 | peter@akayla.com

## Slide 2: This report from IEEE 802 summarizes issues of mutual interest to IEEE 802 and SC6
  This status report has been developed for:
    The information of ISO/IEC JTC1/SC6
    Consideration at SC6 meeting in April 2019 in Beijing, China
  Items addressed by this report include:
    Summary of IEEE 802 standards administered through the PSDO process
    Summary of standards currently in the PSDO process
      IEEE 802.1/3/11/15/16/21/22
  SC6 is requested to provide any feedback or ask questions related to this status report through:
    Any IEEE 802 representatives attending the SC6 meeting (probably via teleconference)
    The Chair of the IEEE 802 JTC1 Standing Committee (Andrew Myles, amyles@cisco.com)

## Slide 3: Summary of IEEE 802 standards administered through the PSDO process

## Slide 4: IEEE 802 has sent 58 standards through to PSDO ratification with 27 in-process
WG | Completed | In-process
802.1 | 27 | 11
802.3 | 15 | 5
802.11 | 8 | 10
802.15 | 2 | 1
802.16 | 0 | 0
802.21 | 3 | 0
802.22 | 3 | 0
All | 58 | 27

## Slide 5: IEEE 802.1 WG has sent 27 standards completely through the PSDO ratification process
IEEE 802 standard | 60-day pre-ballot | 5-month FDIS ballot | Comments resolved by IEEE
802 | Oct 2014 | Nov 2015 | Jan 2016
802.1X | 2013 | Oct 2013 | Jan 2014
802.1AE | 2013 | Oct 2013 | Jan 2014
802.1AB | May 2013 | Dec 2013 | May 2014
802.1AR | May 2013 | Dec 2013 | May 2014
802.1AS | May 2013 | Dec 2013 | May 2014
802.1AEbw | Jan 2014 | Feb 2015 | Apr 2015
802.1AEbn | Jan 2014 | Feb 2015 | Apr 2015
802.1AX | May 2015 | Nov 2015 | n/a
802.1Xbx | Mar 2015 | Dec 2015 | May 2016
802.1Q-Rev | Mar 2015 | Jan 2016 | May 2016
802.1BA | Sep 2015 | Aug 2016 | n/a

## Slide 6: IEEE 802.1 WG has sent 27 standards completely through the PSDO ratification process
IEEE 802 standard | 60-day pre-ballot | 5-month FDIS ballot | Comments resolved by IEEE
802.1BR | Sep 2015 | Aug 2016 | n/a
802.1Qbv | May 2016 | Apr 2017 | Jul 2017
802.1AB | Jul 2016 | Apr 2017 | Jul 2017
802.1Qca | Jul 2016 | Apr 2017 | Jul 2017
802.1Qbu | Feb 2017 | Oct 2017 | n/a
802.1Qbz | Feb 2017 | Oct 2017 | n/a
802.1Qcd | Oct 2016 | Dec 2017 | n/a
802.1Q-Cor1 | - | Mar 2017 | Jul 2017
802.1AC-Rev | May 2017 | Mar 2018 | Apr 2018
802d | Jun 2017 | Mar 2018 | n/a
802.1AX/Cor1 | - | Jul 2018 | n/a
802.1AEcg | Sep 17 | Aug 18 | Jan 19

## Slide 7: IEEE 802.1 WG has sent 27 standards completely through the PSDO ratification process
IEEE 802 standard | 60-day pre-ballot | 5-month FDIS ballot | Comments resolved by IEEE
.1CB | 20 Jan 18 | 26 Dec 18 | n/a
.1Qci | 9 Dec 17 | 3 Jan 19 | n/a
.1Qch | 20 Jan 18 | 3 Jan 19 | n/a

## Slide 8: IEEE 802.3 WG has sent 15 standards completely through the PSDO ratification process
IEEE 802 standard | 60-day pre-ballot | 5-month FDIS ballot | Comments resolved by IEEE
802.3 | 2013 | Feb 2014 | n/a
802.3 | Jul 2016 | Mar 2017 | Mar 2017
802.3.1 | Oct 2014 | Jun 2015 | Apr 2015
802.3bw | Sep 2016 | Sep 2017 | Nov 2017
802.3bp | Jan 2017 | Oct 2017 | n/a
802.3bq | Jan 2017 | Oct 2017 | n/a
802.3br | Feb 2017 | Oct 2017 | n/a
802.3by | Jan 2017 | Oct 2017 | n/a
802.3bz | Feb 2017 | Oct 2017 | n/a
802.3/Cor 1 | - | Nov 2017 | n/a

## Slide 9: IEEE 802.3 WG has sent 15 standards completely through the PSDO ratification process
IEEE 802 standard | 60-day pre-ballot | 5-month FDIS ballot | Comments resolved by IEEE
802.3bn | 16 Apr 17 | 3 Sep 18 | n/a
802.3bv | 18 Aug 17 | 3 Sep 18 | n/a
802.3bu | 18 Aug 17 | 3 Sep 18 | n/a
802.3bs | 12 Apr 18 | 26 Dec 18 | n/a
802.3cc | 12 Apr 18 | 26 Dec 18 | n/a

## Slide 10: IEEE 802.11 WG has sent 8 standards completely through the PSDO ratification process
IEEE 802 standard | 60-day pre-ballot | 5-month FDIS ballot | Comments resolved by IEEE
802.11 | 2012 | 2012 | Nov 2013
802.11aa | Feb 2013 | Jan 2014 | July 2014
802.11ad | Feb 2013 | Jan 2014 | July 2014
802.11ae | Feb 2013 | Jan 2014 | July 2014
802.11ac | Sep 2014 | Jul 2015 | Jul 2015
802.11af | Sep 2014 | Jul 2015 | Jul 2015
802.11-2016 | Apr 2017 | Apr 2018 | May 2018
802.11ai | 1 Sep 17 | 26 Dec 18 | Feb 2019

## Slide 11: IEEE 802.15 WG has sent two standards completely through the PSDO ratification process
IEEE 802 standard | 60-day pre-ballot | 5-month FDIS ballot | Comments resolved by IEEE
802.15.3 | Oct 2016 | Sep 2017 | n/a
802.15.4 | Apr 2017 | Jan 2018 | n/a

## Slide 12: IEEE 802.16 WG has sent zero standards completely through the PSDO ratification process
IEEE 802 standard | 60-day pre-ballot | 5-month FDIS ballot | Comments resolved by IEEE

## Slide 13: IEEE 802.21 WG has sent three standards completely through the PSDO ratification process
IEEE 802 standard | 60-day pre-ballot | 5-month FDIS ballot | Comments resolved by IEEE
802.21-2017 | Jul 2017 | Feb 2018 | Mar 2018
802.21.1 | Jul 2017 | Mar 2018 | Jul 2017
802.21/Cor1 | - | Jun 2018 | n/a

## Slide 14: IEEE 802.22 WG has sent three standards completely through the PSDO ratification process
IEEE 802 standard | 60-day pre-ballot | 5-month FDIS ballot | Comments resolved by IEEE
802.22 | May 2014 | Feb 2015 | n/a
802.22a | April 2016 | Jul 2017 | n/a
802.22b | April 2016 | July 2017 | Mar 2018

## Slide 15: Summary of IEEE 802.1 standards currently in the PSDO process

## Slide 16: IEEE 802.1 has 11 standards in the pipeline for ratification under the PSDO
802 | Last draft liaised |  | 60-day pre-ballot |  | 5-month FDIS ballot |  | Comments resolved
802c | D2.1 | Mar 17 | Passed | 2 Feb 18 | Passed | 26 Dec 18 | Mar 19
.1Q-2018 | D2.0 | Jul 17 | Passed | 11 Mar 19 | Waiting | - | Mar 19
.1Qcc | D2.0 | Dec 17 | - | - | - | - | -
.1Qcp | D2.0 | Dec 17 | - | - | - | - | -
.1AR-Rev | D2.6 | Apr 18 | Passed | 14 Oct 18 | Waiting | - | Jan 19
.1CM | D2.2 | Apr 18 | Passed | 14 Oct 18 | Closes | 26 Jun 19 | n/a
.1Qcy | D2.1 | Apr 18 | - | - | - | - | -
.1AC/Cor-1 | D2.0 | Apr 18 | n/a | n/a | Passed | 17 Mar 19 | n/a
.1Xck | D2.0 | Apr 18 | Passed | 11 Mar 19 | - | - | Waiting
.1AE-Rev | D2.0 | Apr 18 | Passed | 11 Mar 19 | - | - | Waiting
.1AS-Rev | D8.0 | Mar 19 | - | - | - | - | -

## Slide 17: IEEE 802c has been published as ISO/IEC/IEEE 8802-A:2015/Amd 2:2019 but requires a response
Drafts sent to SC6: sent
  802c/D2.1 was liaised for information in Mar 2017 (N16598)
60-day pre-ballot: passed and response sent
  802c 60-day ballot passed on 2 Feb 2018 (N16765)
    Passed 10/0/12 on need for ISO standard
    Passed 9/0/13 on support for submission to FDIS
  China NB and US NB provided comments
    A response was sent in Apr 2018 (N16797)
FDIS ballot: passed & published but requires a response
  FDIS ballot passed 9/1/9 on 26 Dec 2018
  China NB voted “no” & provided comments
    A response was approved in Mar 2019
  Published as ISO/IEC/IEEE 8802-A:2015/Amd 2:2019

## Slide 18: IEEE 802.1Q-2018 60-day ballot passed and responses are required
Drafts sent to SC6: sent
  802.1Q-REV/D2.0 was liaised for information in Jul 2017 (N16688)
  802.1Q-2018 was published in June 2018
60-day pre-ballot: passed and response required
  802.1Q-2018 60-day ballot passed on 11 March 2019 (N??????)
    Passed 10/0/8 on need for ISO standard
    Passed 8/1/9 on support for submission to FDIS
  China voted “no” with 1 comment
    A response was approved in Mar 2019
FDIS ballot: waiting

## Slide 19: IEEE 802.1Qcc PSDO process will be delayed until previous amendments are approved
Drafts sent to SC6: sent
  D2.0 liaised in Dec 2017 (WG1-N119)
  802.1Qcc was approved by RevCom in June 2018
60-day pre-ballot: will start soon
  PSDO start will be delayed until 802.1Q-2018 is approved
FDIS ballot: waiting

## Slide 20: IEEE 802.1Qcp PSDO process will be delayed until previous amendments are approved
Drafts sent to SC6: sent
  D2.6 liaised in Dec 2017 (WG1-N119)
  802.1Qcp was published in Sept 2018
60-day pre-ballot: will start soon
  PSDO start will be delayed until 802.1Q-2018 is approved
FDIS ballot: waiting

## Slide 21: IEEE 802.1AR-Rev is waiting start of FDIS ballot
Drafts sent to SC6: sent
  D2.0 was liaised in Apr 2018 (WG1N124)
60-day pre-ballot: passed & responses sent
  802.1AR-Rev 60-day ballot passed on 14 Oct 2018 (N16858)
    Passed 8/0/10 on need for ISO standard
    Passed 5/1/12 on support for submission to FDIS
  China NB provided comments
    Response were sent in Jan 2019 (N??????)
FDIS ballot: waiting for start

## Slide 22: IEEE 802.1CM FDIS ballot closes on 26 June 2019
Drafts sent to SC6: sent
  D2.2 was liaised in Apr 2018 (WG1N124)
60-day pre-ballot: passed
  802.1CM 60-day ballot passed on 14 Oct 2018 (N16859)
    Passed 7/0/11 on need for ISO standard
    Passed 5/0/13 on support for submission to FDIS
  No comments were submitted
FDIS ballot: closes on 26 June 2019

## Slide 23: IEEE 802.1Qcy PSDO process will be delayed until previous amendments are approved
Drafts sent to SC6: sent
  D2.1 was liaised in Apr 2018 (WG1N124)
60-day pre-ballot: waiting
  PSDO start will be delayed until 802.1Q-2018 is approved
FDIS ballot: waiting

## Slide 24: IEEE 802.1AC/Cor-1 90-day PSDO ballot closes 17 Mar 2019
Drafts sent to SC6: sent
  D2.0 was liaised in Apr 2018 (WG1N124)
90-day FDIS ballot: closes 17 Mar 2019
  A request to start ballot was sent to SC6 in Dec 2018

## Slide 25: IEEE 802.1Xck 60-day ballot passed but a response is required
Drafts sent to SC6: sent
  IEEE 802.1Xck D2.0 was liaised in Apr 2018 (WG1N124)
60-day pre-ballot: passed but response required
  802.1Xck 60-day ballot passed on 11 March 2019 (N??????)
    Passed 10/0/8 on need for ISO standard
    Passed 8/1/9 on support for submission to FDIS
  China voted “no” with 2 comments
FDIS ballot: waiting

## Slide 26: IEEE 802.1AE-Rev 60-day ballot passed but a response is required
Drafts sent to SC6: sent
  IEEE 802.1AE-Rev D1.1 was liaised in Apr 2018 (WG1N124)
60-day pre-ballot: passed but response required
  802.1AE-Rev 60-day ballot passed on 11 March 2019 (N??????)
    Passed 10/0/8 on need for ISO standard
    Passed 8/1/9 on support for submission to FDIS
  China voted “no” with 6 comments
FDIS ballot: waiting

## Slide 27: IEEE 802.1AS-Rev was liaised for information in Marc 2019
Drafts sent to SC6: sent
  802.1AS-Rev D8 was liaised in Mar 2019
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 28: Summary of IEEE 802.3 standards currently in the PSDO process

## Slide 29: IEEE 802.3 has 5 standards in the pipeline for ratification under the PSDO process
802 | Last draft liaised |  | 60-day pre-ballot |  | 5-month FDIS ballot |  | Comments resolved
.3cb | D3.0 | Jun 17 | Closes | 8 Apr 19 | - | - | -
.3cd | D3.0 | Feb 18 | Waiting | - | - | - | -
.3-rev | D3.0 | Feb 18 | Closes | 14 Apr 19 | - | - | -
.3bt | D3.2 | Feb 18 | Waiting | - | - | - | -
.3.2 | D3.0 | Feb 19 | - | - | - | - | -

## Slide 30: IEEE 802.3cd is waiting for start of 60-day ballot
Drafts sent to SC6: sent
  802.3cd D3.0 was liaised in Feb 2018
60-day pre-ballot: waiting
  Submission approved in Mar 2019, but will be held until 802.3-REV is adopted
FDIS ballot: waiting

## Slide 31: IEEE 802.3-REV 60-day ballot closes on 14 April 2019
Drafts sent to SC6: sent
  802.3 D3.0 (802.3cj) was liaised in Feb 2018
60-day pre-ballot: closes on 14 April 2019
  Submitted in Feb 2019 (N16892)
FDIS ballot: waiting

## Slide 32: IEEE 802.3bt is waiting for start of 60-day ballot
Drafts sent to SC6: sent
  802.3bt D3.2 was liaised in Feb 2018
60-day pre-ballot: waiting
  Submission approved in Mar 2019, but will be held until 802.3-REV is adopted
FDIS ballot: waiting
  Will be known as ISO/IEC/IEEE 8802-3:2019/Amd 1?

## Slide 33: IEEE 802.3.2 was liaised for information in Feb 2019
Drafts sent to SC6: sent
  802.3.2 D3.0 was liaised for information in Feb 2019 (N16893)
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 34: Summary of IEEE 802.11 standards currently in the PSDO process

## Slide 35: IEEE 802.11 has ten standards in the pipeline for ratification under the PSDO
Std | Last draft liaised |  | 60-day pre-ballot |  | 5-month FDIS ballot |  | Comments resolved
11ah | D9.0 | Sep 16 | Passed | 20 Jul 17 | Passed | 8 Feb 19 | Mar 19
11ai | D8.0 | Jul 16 | Passed | 1 Sep 17 | Passed | 26 Dec 18 | Feb 2019
11aj | D5.0 | Jun 17 | Passed | 10 Feb 19 | - | - | Waiting
11ak | D4.0 | Jun 17 | Passed | 10 Feb 19 | Waiting | - | Mar 19
11aq | D8.0 | Mar 17 | Passed | 10 Feb 19 | Waiting | - | Mar 19
11ax | D4.0 | Mar 19 | - | - | - | - | -
11ay | D3.0 | Mar 19 | - | - | - | - | -
11az | Waiting | - | - | - | - | - | -
11ba | Waiting | - | - | - | - | - | -
11bb | Waiting | - | - | - | - | - | -

## Slide 36: IEEE 802.11ah is waiting for publication
Drafts sent to SC6: sent
  802.11ah drafts were liaised for information
    D5.0 in Oct 2015
    D9.0 in Sep 2016
60-day pre-ballot: passed
  802.11ah passed 60-day pre-ballot (N16685) on 20 July 2017
    Need? 10/0/10
    Submission? 9/0/11
FDIS ballot: waiting for publication
  802.11ah passed FDIS ballot (N16685) on 8 Feb 2019
    Passed 9/1/9
  There was a negative vote and comments from China NB
    Response sent in Mar 2019
  Will be known as ISO/IEC/IEEE 8802-11:2018/Amd 2

## Slide 37: IEEE 802.11aj 60-day ballot passed but requires a response
Drafts sent to SC6: sent
  802.11aj drafts were liaised for information
    D5.0 in Jun 2017
    Published version liaised in July 2018 (N16817)
60-day pre-ballot: passed & requires response
  802.11aj-2018 passed 60-day pre-ballot (N16897) on 10 Feb 2019
    Need? 7/0/12
    Submission? 6/0/13
  China NB voted “yes”/”abstain” but submitted a comment
    The response will be written by the TGaj Chair (from China)
FDIS ballot: waiting

## Slide 38: IEEE 802.11ak is waiting for start of FDIS ballot
Drafts sent to SC6: sent
  802.11ak drafts were liaised for information
    D4.0 in Jun 2017
    Published version liaised in July 2018 (N16817)
60-day pre-ballot: passed & response sent
  802.11ak-2018 passed 60-day pre-ballot (N16898) on 10 Feb 2019
    Need? 7/0/12
    Submission? 5/1/13
  China NB voted “no” and submitted a comment
    Response sent in Mar 2019 (N?????)
FDIS ballot: waiting for start

## Slide 39: IEEE 802.11aq is waiting for start of FDIS ballot
Drafts sent to SC6: sent
  802.11aq D8.0 was sent for liaison in Mar 2017
  Published version was liaised in Sept 2018 (N16854)
60-day pre-ballot: passed & response sent
  802.11ak-2018 passed 60-day pre-ballot (N16899) on 10 Feb 2019
    Need? 7/0/12
    Submission? 5/1/13
  China NB voted “no” and submitted a comment
    Response sent in Mar 2019 (N?????)
FDIS ballot: waiting for start

## Slide 40: IEEE 802.11ax will be liaised for information soon
Drafts sent to SC6: sent
  D4.0 will be liaised in March or April 2019
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 41: IEEE 802.11ay will be liaised for information soon
Drafts sent to SC6: sent
  D3.0 will be liaised in March or April 2019
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 42: IEEE 802.11az will be liaised in the future
Drafts sent to SC6: waiting
  Will liaise draft out later than March 2019 meeting
    Requires WG and EC approval
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 43: IEEE 802.11ba will be liaised in the future
Drafts sent to SC6: waiting
  Will be liaised in the future
    Requires WG and EC approval
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 44: IEEE 802.11bb will be liaised when appropriate
Drafts sent to SC6: waiting
  No approved draft yet
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 45: Summary of IEEE 802.15 standards currently in the PSDO process

## Slide 46: IEEE 802.15 has one standard in the pipeline for ratification under the PSDO
Std | Last draft liaised |  | 60-day pre-ballot |  | 5-month FDIS ballot |  | Comments resolved
.15.6 | Std | Jul 16 | Passed | 23 Nov 16 | Passed | 7 Sep 17 | Waiting

## Slide 47: IEEE 802.15.6-2012 published as ISO/IEC/IEEE 8802-15-6:2017 but comment responses are required
Drafts sent to SC6: sent
  The 802.15.6 standard was supposed to be liaised in Apr 2016 for information but was eventually liaised in late July 2016
60-day pre-ballot: passed & responses sent
  The 60-day ballot passed on 23 Nov 2016
    Need for IS on topic: 9/0/10
    Submission of this proposal as IS: 6/3/10, with “no” from Germany, Japan & UK
  Responses were sent in Feb 2017 (see 15-17-0107-02)
FDIS ballot: passed & published, but response required
  Passed on 7 Sep 17 by 12/2/14 (N16711)
    China NB and Japan NB voted “no” with comments
  Response will be sent after March 2019 meeting
  Published as ISO/IEC/IEEE 8802-15-6:2017

## Slide 48: Some interest has been expressed in submitting 802.15.4 (and 802.15.3)
  A number of 802.15.4 participants have contacted the SC Chair expressing an interest in submitting 802.15.4 into the PSDO process
    An enquiry was also received in relation to 802.15.3
  The SC Chair has advised them of the appropriate processes
  Ultimately, it is question for the 802.15 WG

## Slide 49: Summary of IEEE 802.16 standards currently in the PSDO process

## Slide 50: IEEE 802.16 has zero standards in the pipeline for ratification under the PSDO
Std | Last draft liaised |  | 60-day pre-ballot |  | 5-month FDIS ballot |  | Comments resolved
- | - | - | - | - | - | - | -

## Slide 51: Summary of IEEE 802.21 standards currently in the PSDO process

## Slide 52: IEEE 802.21 has no standards in the pipeline for ratification under the PSDO
802 | Last draft liaised |  | 60-day pre-ballot |  | 5-month FDIS ballot |  | Comments resolved
- | - | - | - | - | - | - | -

## Slide 53: Summary of IEEE 802.22 standards currently in the PSDO process

## Slide 54: IEEE 802.22 has zero standards in the pipeline for ratification under the PSDO
802 | Last draft liaised |  | 60-day pre-ballot |  | 5-month FDIS ballot |  | Comments resolved