## Slide 1: Mixed Mode Ad Hoc Agenda
G. Zimmerman 4/12/2022
ec-22-0082-00-00EC

## Slide 2: Meeting Goals
Communicate July meeting mixed-mode plans
Identify volunteer interfaces (e.g. computer adapters) needed
Identify key points of volunteer training
Identify any key points to test on EC dry run

## Slide 3: Assumptions – from Guidelines doc Reminder from prior work…
‘Webcast live meeting’ model (Not ‘Co-located virtual)
  Guiding principle – including remote participants should minimally impact the nature of the face-to-face meeting
Leave long-term decisions open
  Not discussing in this meeting
Leave policy decisions for the EC if they wish to set them
  Not discussing in this meeting
Rely on Chair to control the conversation in the room
Participants can give presentations, question/debate, and vote remotely or in person
  Chair/mixed-mode manager will monitor & provide access
  NO VIDEO from room

## Slide 4
From April 2022 Exec Secretary Report 802-EC-22-0080-01

## Slide 5
From April 2022 Exec Secretary Report 802-EC-22-0080-01

## Slide 6
From April 2022 Exec Secretary Report 802-EC-22-0080-01

## Slide 7: Meeting Details/Presentation/Voting
WG Chair needs to identify a point person to host the ‘room computer’ for each meeting (block - e.g., WG, Task Force, etc.)
  One computer per meeting (block) plugged into the presentation
    Don’t want to be switching presenter computers
    Connected to conference tool
    Computer interface requirements: – HDMI + optional audio-jack (to be finalized)
WG Chair needs to determine and communicate document upload requirements so that the room computer can access it
  Preferably with deadline before start of meeting
  For example – upload to mentor, or to chair for posting to website
WG Chair to decide and communicate rules and logistics for voting and participation (e.g., WG voters only? All in room?)
Please let Face-to-Face, Exec Secretary & Treasurer know any assumed needs

## Slide 8: Draft Room Resource Allocation
Big meetings (≥ 100, e.g., WG plenaries)
Head table (4)
Sound system (speakers, sound board, etc.)
Medium meetings (35-100, e.g., Task Forces)
Head table (2)
Sound system (speakers, sound board, etc.)
Smaller meetings (30 or less)
U-shaped or board meeting setup
1 projector/screen
1 table mic
1 floor mic
1 projector/screen
2 tables mics
1 or 2 floor mics
1 room microphone
Sound system (speakers, sound board, etc.)
Portable or speakerphone-type

## Slide 9: Testing and Training
Test with EC members on site during May telecon
Training session with short-deck (provided to WG chairs) in Mid June (try for first week of June)
  Suggested for meeting leaders (TF chairs, vice chairs, etc.)
  Discussion of key questions (to be filled in):

## Slide 10: Further Meeting Details
Subgroup meeting size & needs will need to be set in advance of the meeting
  Poll your groups… * need typical, not worst-case
  Communicate to your Working Group’s meeting planning representative
  Need soon… Email forthcoming to WG chairs

## Slide 11: Summary of Key Points/Goals/Reminders
Meeting is to be run as an in-person meeting.
  Local time zone schedule for meetings
  Local participants attend as an in-person meeting
  Remote access is provided to remote participants to view/present/interact similarly to on-line meetings (best effort)
In-person participants are admonished (stronger than encouraged) to stay OFF the Webex/zoom/teams/conference tool of your choice
Presentation/room computer is logged into conference tool (ideally from a volunteer-supplied PC), and projector is showing web-conferencing tool view
A chair, vice-chair, or designate, is logged into the conference tool and monitoring the queue (based on experience this is probably a second room log in, since monitoring the queue doesn’t work well when presenting) – this person manages the online queue for the chair to integrate with the floor queue.
Audio comes from a floor mic or the chair/dias mic which is mixed into room speakers and outgoing sound by the sound board.
Working groups need to decide voting rules, etc. for subgroups (some use different rules for electronic meetings than in person – what to use for hybrid?)
Meeting Planning/Exec Secretary/Treasurer will provide an update after the EC meeting test-run in May