## Slide 1: IEEE 802 JTC1 Standing Committee July 2024 (mixed-mode) closing report
Date: 2024-07-19
Author:

## Slide 2: The IEEE 802 JTC1 SC reviewed the PSDO process status, including IPR issues holding up 802.11
Agenda - ec-24/0149r02; Minutes – ec-24/0177
802.11 IPR issue
Situation: IPR holding up PSDO process
  Going forward, 802.11 will not be shown as in-process
Next steps: keep waiting
  Resolution appears to be down to patent holders supplying LOAs under the ISO patent policy
  Observe how IEEE 802.3 fares in the parallel ITU-T SG15 process
WG | Completed | In-process | Stalled
802.1 | 50 | 14 | 0
802.3 | 32 | 8 | 0
802.11 | 13 | 0 | 14
802.15 | 3 | 14 | 0
802.16 | 0 | 0 | 0
802.19 | 0 | 1 | 0
802.21 | 3 | 0 | 0
802.22 | 4 | 0 | 0
All | 105 | 37 | 14

## Slide 3: The IEEE 802 JTC1 SC will undertake its usual work at its mixed-mode meeting in Waikoloa in September 2024
IEEE 802 JTC1 SC plans for September 2024 …
  Execute PSDO process, to the extent possible
    There are current ballots open for IEEE 802.1CS/Cor1 (DCOR: 7 August), IEEE 802.1AEdk (FDIS: 25 September), IEEE 802.1Qcz (FDIS: 25 September), IEEE 802.15.7-2018 (CIB: 23 July), IEEE 802.15.9 (FDIS: 8 November)
  Monitor ISO/IEC JTC 1/SC 6 activities