## Slide 1: IEEE 802 LMSC History Ad Hoc Report
14 March 2025 IEEE 802 LMSC Closing Meeting
Paul Nikolich

## Slide 2: 802 History Ad Hoc Plan: 11 March 2025 Status Update
Prioritize preserving the first 15 years (1979-1994) of historical material
Next Steps
  Flesh out Ad Hoc logistics – IN PROCESS
    Create a list of material to be archived – IN PROCESS
      Geoff to investigate preservation of documents in his possession -- OPEN
      Obtained estimate to ship documents in his possession to NJ: $5-$7k.
      Action Item: GOT to obtain estimate to bulk digitize the documents.
    Initiate Accumulation of Historical Material
      Action item: Paul to investigate obtaining staff support to build and maintain on-line history inventory system
  Identify Potential Archive Repositories
    Action item: Follow up on Charles Babbage Institute in Minnesota – IN PROCESS
    Action Item: Paul to contact InfoAge Science & History Museums -- CLOSED
    Decide on a repository by JULY2025
  Peter to investigate Ethernet Alliance collaboration – IN PROCESS
  Paul to continue Computer Society collaboration – IN PROCESS
    Action item: Paul to follow up with CS Staff on Charles Babbage Institute in Minnesota – IN PROCESS
    Action item: Paul to reach out to CS History Committee Chair, Thomas Haigh
  Tuncer/802 Public Visibility Ad Hoc to support activity as needed – ONGOING

## Slide 3: IEEE 802 LMSC History Ad Hoc Pending Action Items
Attendees: James Gilb, Geoff Thompson, Peter Jones, Paul Nikolich, Tuncer Baykas, Dawn Slykhouse, Gary Robinson, Bob Love, Yvette Ho Sang, Nathan Brewer, Mario Costa, Yuan Qiu Luo, Edward Au
Action Items:
Peter Jones to determine if the Computer History Museum has interest in supporting this effort JULY2025
Dawn Slykhouse to contact Alpha Graphics and Don Loughry’s family for potential contributions unable to locate Alpha Graphics sources, DL family a challenge, unable to connect with their family, will reach out to Geoff Thompson. JULY2025
Yvette Ho Sang to obtain clarity on IEEE copyright permissions for old (>15yo draft and published standards) JULY2025
James Gilb and Michael Fischer to search for/identify relevant interviews (journals, magazines, aural, etc.) Due MAY2025
Geoff Thompson to draft criteria to qualify potential repositories JULY2025
Gary Robinson to inventory items of interest in his possession (original DIX doc, mementos, videos) JULY2025
Bob Love to reach out early 802.5 WG participants, Unable to reach John Messenger. inventory items Bob may possess – does not have anything left, everything on floppy disk
Paul Nikolich to contact Vic Hayes to obtain permission to use recently recorded video MAY2025