## Slide 1: IC17-001 IEEE 802 Network Enhancements for the Next Decade Type: Individual Report Date: February 2020
Chair: Roger Marks (Huawei)
Participants: Varying between 30 – 100 people
Procedures:
IEEE 802 Policies & Procedures
IEEE 802 LMSC Operations Manual
IEEE 802 Working Group Policies & Procedures
IEEE 802 Nendica Report Development Process:
https://1.ieee802.org/802-nendica/ieee-802-nendica-procedures
Deliverables Listed in the Approved ICAID: (Do not modify)
Records of the meetings, including minutes and supporting presentations.
A set of reports documenting the findings of the IC activity, with recommendations regarding new standardization topics, documentation of use cases and user needs for those topics, and proposed organizational approaches to ensure effective participation from user communities

## Slide 2: IC17-001 IEEE 802 Network Enhancements for the Next Decade
Status of Deliverables:
  Records of the meetings, including minutes and supporting presentations:
    Posted regularly; see https://mentor.ieee.org/802.1/documents?is_group=ICne and https://1.ieee802.org/802-nendica
  A set of Nendica Reports
    First Nendica Report (Lossless Data Center Networks): published August 2018
    Second Nendica Report (Flexible Factory IoT): Approval of draft expected March 2020
    Prospective Work Items toward Nendica Reports
      Ongoing Study Item: Managed LAN as a Service
      Planning to initiate two new Work Items (toward new reports) in March 2020
        "The Lossless Network for Data Centers” (revision of published Nendica Report)
        “Network Stream and Flow Interworking”
Additional Accomplishments:
    Organized presentation (2019-02) and track (2019-06) at North American Network Operator’s Group (NANOG) to highlight Lossless Data Center Networks report and activity
Future Meetings:
In-person meetings in 7-9 locations in 2020; see https://1.ieee802.org/802-nendica
Frequent teleconferences (4 scheduled in Feb-March 2020)
Issues: Editorial support has been greatly appreciated and will be requested again
2020-02-05 IEEE 802.1-20-0013-01-ICne