## Sheet1
ID | Commenter | Clause | T or E | Part of a "No" Vote | Comment | Suggested Remedy | Resolution | .pdf Page | Line | CommentStatus | CommentRes | EditStatusNotes | Notes | History | Assigned To
1 | Housley | 7.3.2.26 | T | Y | Page 29, Lines 29 and 30. I think that pointing to 802.11F is a mistake. I recognize that an other alternative is being suggested as well, but advocating the deployment of 802.11F is not desirable. | Eliminate reference to 802.11F. | [6 empty] | Probably need to reword to resolve issue 8/18/04
2 | Housley | All | T | Y | 802.11k very helpful to a STA in selecting the next access point to which it will associate. However, 802.11k messages are subject to forgery. A mechanism for authentication and integrity is needed. | Specify a mechanism for authentication and integrity protection. | [6 empty] | 8/18/04 telecon participants do not agree, but think Jesse Walker needs to discuss with Russ Housley on merits of not adding authentication and integrity for action frames (8/18/04).
3 | Lanzl | 5.4.4.1 | T | Y | The TPC service's main purpose is to ensure that the requirements of ERC/DEC(99)23 are met. It may have a secondary use of measurement of the link path loss and link margin. | Change the underlined text on lines 30-31 to read: "The transmit power control (TPC) service may be used in both the 2.4GHz and 5GHz bands for the purpose of radio measurement of link path loss and link margin." | [6 empty] | Probably OK - 8/18/04
4 | Lanzl | 7.3.2.21.6 | T | Y | This request requires any participating STA to return data on both the RSSI and RCPI. This theme is repeated throughout the 802.11k draft 1.0 document. The requested (and reported) data is redundant: the RSSI measurements clearly are a subset of the RCPI measurements. Asking for and transferring both sets of information is a poor use of network bandwidth. I could perhaps understand reporting RSSI for legacy STA, as they may currently have no provision for RCPI, but then the draft should state that the STA has the option of either RSSI or RCPI depending on which it supports. I do not subscribe to the theory that the combination of RSSI and RCPI provides some measure of signal quality, for example as stated in 15.4.5.16; this is simply repetition of existing data. I also realize that RCPI can be generated from RSSI with some sort of calibration factor. In that case, why not simply report RCPI and be done? | Re-structure the entire document to only request and return RCPI, allowing the substitution of RSSI for legacy PHY STA. | [6 empty] | Probably OK, but restructure the document might be a little harsh - 8/18/04
5 | Lanzl | 7.3.2.21.9 | T | Y | the text and tables k5 and k6 refer to an entity "RPI" that is undefined. From the context, it appears that "RPI" could be "RCPI", but that is not entirely clear. | Either define RPI prior to its use and place that abbreviation in section 4 or change all references to RPI in all text and tables to RCPI. Note that RPI is used elsewhere as well (for example, in table 20b).
6 | Lanzl | 7.3.2.21.9 | T | Y | The state of CCA is either BUSY or IDLE. There is no need to provide both the CCA BUSY and IDLE histograms as one set of data can be deduced from the other. | Remove all references to either the CCA Busy Time Histogram or CCA Idle Time Histogram in the text and table k5. | [6 empty] | Probably OK - 8/18/04
7 | Lanzl | 7.3.2.21.9 | T | Y | The threshold values for table k6 do not make sense in the context of the base standard: 5dB steps are the wrong value. See my comment below concerning 7.3.2.22.5 for the rationale. | Change the starting value and steps in table 6 from -87dBm and 5dB to -85dBm and 3dB; so, RCPI threshold of 0 would correspond to -85dBm, 1 would correspond to -82dBm, 2 would correspond to -79dBm, 3 would correspond to -76dBm, 4 would correspond to -73dBm, 5 would correspond to -70dBm and 6 would correspond to -67dBm. It might also make sense to add the following two threshold values: 7 would correspond to -64dBm and 8 would correspond to -61dBm, leaving thresholds 9-254 reserved and threshold 255 as the table currently reads. | [6 empty] | Klein - 3db increments looks right. 8/18/04
8 | Lanzl | 7.3.2.22.5 | T | Y | The choices for RCPI measured power thresholds in conjunction with the CCA state of IDLE do not make sense. In the base standard, there are various input power requirements for CCA to indicate BUSY. For the legacy 802.11 DS PHY, the CCA must indicate BUSY for received powers > -80dBm (Tx >100mW), >-76dBm (50mW <= Tx <=100mW) and >-70dBm (Tx < 50mW). For the 802.11b PHY, the CCA must indicate BUSY for received powers >-76dBm (Tx >100mW), >-73dBm (50mW <= Tx <= 100mW) and >-70dBm (Tx < 50mW). For the 802.11g PHY, the CCA must indicate BUSY for received powers >-76dBm. For the 802.11a PHY, the CCA must indicate BUSY for received powers >-82dBm for a valid OFDM symbol or -42dBm for any input signal. Re-structuring the table to capture the noise in finer-grain RCPI bins following baseline standard CCA ranges makes more sense. | Change the starting value and steps in table k8 from -87dBm and 5dB to -85dBm and 3dB; so, RCPI threshold of 0 would correspond to <=-85dBm, 1 would correspond to -85dBm<RCPI<=-82dBm, 2 would correspond to -82dBm<RCPI<=-79dBm, 3 would correspond to -79dBm<RCPI<=-76dBm, 4 would correspond to -76dBm<RCPI<=-73dBm, 5 would correspond to -73dBm<RCPI<=-70dBm, 6 would correspond to -70dBm<RCPI<=-67dBm and 7 would correspond to -67dBm<RCPI. This choice gives better granularity to the measurement of noise when CCA is IDLE for most of the baseline standard PHYs. | [6 empty] | Klein - 3db increments looks right. 8/18/04
9 | Lanzl | 7.3.2.22.6 | E | N | It is not clear in this section that the report should only cover one beacon. This is hinted in later text. Without that clarity, it is confusing how to report multiple RCPI, TSF and timestamps in this report. | Add some text clarifying that this beacon report can only apply to one beacon measurement. | [6 empty] | Report the last thing you saw? Olson
10 | Lanzl | 7.3.2.22.7 | E | N | It is not clear in this section that the report should only cover one frame. This is hinted in later text. Without that clarity, it is confusing how to report multiple RCPI in this report. | Add some text clarifying that this beacon report can only apply to one frame measurement. | [6 empty] | RCPI is defined as an average - reject comment!
11 | Lanzl | 15.4.5.16.2 | E | N | The text "RCPI indications of 8 bits (221 levels) are supported." is confusing. In fact, RCPI indications of 8 bits are supported and 221 states are assigned to RCPI levels. | Change the text to read: "RCPI indications of 8 bits are supported, as defined in 15.4.8.5. | [6 empty] | Makes sense - 8/18/04
12 | Lanzl | 15.4.5.16.4 | E | N | The text states that RCPI may be used in conjunction with RSSI to measure input signal quality. This is confusing in the face of the baseline standard's use of the SQ parameter. | Remove the line reading: "The RCPI may be used in conjunction with RSSI to measure input signal quality." | [6 empty] | Joe says the section doesn't make sense without the sentence - 8/18/04
13 | Lanzl | 15.4.8.5 | T | Y | The definition of assignment of RCPI levels to RCPI indicator bits is sloppy. Either provide a complete table or some algorithm that fully describes the states with no ambiguity. | Change lines 18-24 to read: "RCPI indicator = int{(received power in dBm +110)*2} for received powers 0dBm or less and where the RCPI indicator of 0 is used for received signal power less than -110dBm. RCPI indicators 221-254: reserved. RCPI indicator 255: Measurement not available. | [6 empty] | Add the formula as well as the table (Kwak) - 8/18/04
14 | Lanzl | 17.2.3.5 | E | N | The text "RCPI indications of 8 bits (221 levels) are supported..." is confusing. In fact, RCPI indications of 8 bits are supported and 221 states are assigned to RCPI levels. | Change the text to read: "RCPI indications of 8 bits are supported, as defined in 17.3.10.6. | [6 empty] | Makes sense - 8/18/04
15 | Lanzl | 17.3.10.6 | T | Y | The definition of assignment of RCPI levels to RCPI indicator bits is sloppy. Either provide a complete table or some algorithm that fully describes the states with no ambiguity. | Change lines 24-29 on page 56 and line 1 on page 57 to read: "RCPI indicator = int{(received power in dBm +110)*2} for received powers 0dBm or less and where the RCPI indicator of 0 is used for received signal power less than -110dBm. RCPI indicators 221-254: reserved. RCPI indicator 255: Measurement not available. | [6 empty] | Add the formula as well as the table - 8/18/04
16 | Lanzl | 17.5.5.8.2 | E | N | The text "RCPI indications of 8 bits (221 levels) are supported..." is confusing. In fact, RCPI indications of 8 bits are supported and 221 states are assigned to RCPI levels. | Change the text to read: "RCPI indications of 8 bits are supported, as defined in 17.3.10.6. | [6 empty] | Makes sense - 8/18/04
17 | Lanzl | 17.5.5.X.4 | E | N | The section number for this should read 17.5.5.8.4. Also, the text states that RCPI may be used in conjunction with RSSI to measure input signal quality. This is confusing in the face of the baseline standard's use of the SQ parameter. | Change the numbering of this section to 17.5.5.8.4. Remove the text that reads: "RCPI may be used in conjunction with RSSI to measure input signal quality."
18 | Lanzl | 18.4.5.16.4 | E | N | The text states that RCPI may be used in conjunction with RSSI to measure input signal quality. This is confusing in the face of the baseline standard's use of the SQ parameter. | Remove the text that reads: "RCPI may be used in conjunction with RSSI to measure input signal quality."
19 | Lanzl | 18.4.8.5 | T | Y | The definition of assignment of RCPI levels to RCPI indicator bits is sloppy. Either provide a complete table or some algorithm that fully describes the states with no ambiguity. | Change lines 14-20 to read: "RCPI indicator = int{(received power in dBm +110)*2} for received powers 0dBm or less and where the RCPI indicator of 0 is used for received signal power less than -110dBm. RCPI indicators 221-254: reserved. RCPI indicator 255: Measurement not available. | [6 empty] | Add the formula as well as the table - 8/18/04
20 | Kleindl | 7.2.3.4 | E | N | different order numbers in instruction and table | align order numbers
21 | Kleindl | 7.2.3.6 | E | N | different order numbers in instruction and table | align order numbers
22 | Kleindl | 7.3.1.4 | E | N | subfields 'Spectrum Management', 'Short Slot Time' and 'DSSS-OFDM' are missing in Figure 27 | add missing subfields in Figure 27
23 | Kleindl | 7.3.1.11 | E | N | Value '5' is missing in Table 19a | add missing value '5'
24 | Kleindl | 7.3.2.21.9 | E | N | On page 18 there are very similar wordings in lines 4-6 and 7-9, the first refering to Table k6 and the second refering to Table k8. I could not understand what is meant. | clarify what is meant
25 | Kleindl | 7.3.2.22 | E | N | On page 20 lines 30-31 the wordings '... measurement shall start ...' are suitable for the Request element but not for the Report element. | change to e.g. '... measurement has started ...'
26 | Kleindl | 7.4.2 | E | N | Value '6' is missing in Table k12 | add missing value '6'
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245