## Sheet1
ID | Commenter | Clause | T or E | Part of a "No" Vote | Comment | Suggested Remedy | Resolution | .pdf Page | Line | CommentStatus | CommentRes | EditStatusNotes | Notes | History | Assigned To
1 | Housley | 7.3.2.26 | T | Y | Page 29, Lines 29 and 30. I think that pointing to 802.11F is a mistake. I recognize that an other alternative is being suggested as well, but advocating the deployment of 802.11F is not desirable. | Eliminate reference to 802.11F. | [6 empty] | Probably need to reword to resolve issue 8/18/04
2 | Housley | All | T | Y | 802.11k very helpful to a STA in selecting the next access point to which it will associate. However, 802.11k messages are subject to forgery. A mechanism for authentication and integrity is needed. | Specify a mechanism for authentication and integrity protection. | [6 empty] | 8/18/04 telecon participants do not agree, but think Jesse Walker needs to discuss with Russ Housley on merits of not adding authentication and integrity for action frames (8/18/04).
3 | Lanzl | 5.4.4.1 | T | Y | The TPC service's main purpose is to ensure that the requirements of ERC/DEC(99)23 are met. It may have a secondary use of measurement of the link path loss and link margin. | Change the underlined text on lines 30-31 to read: "The transmit power control (TPC) service may be used in both the 2.4GHz and 5GHz bands for the purpose of radio measurement of link path loss and link margin." | [6 empty] | Probably OK - 8/18/04
4 | Lanzl | 7.3.2.21.6 | T | Y | This request requires any participating STA to return data on both the RSSI and RCPI. This theme is repeated throughout the 802.11k draft 1.0 document. The requested (and reported) data is redundant: the RSSI measurements clearly are a subset of the RCPI measurements. Asking for and transferring both sets of information is a poor use of network bandwidth. I could perhaps understand reporting RSSI for legacy STA, as they may currently have no provision for RCPI, but then the draft should state that the STA has the option of either RSSI or RCPI depending on which it supports. I do not subscribe to the theory that the combination of RSSI and RCPI provides some measure of signal quality, for example as stated in 15.4.5.16; this is simply repetition of existing data. I also realize that RCPI can be generated from RSSI with some sort of calibration factor. In that case, why not simply report RCPI and be done? | Re-structure the entire document to only request and return RCPI, allowing the substitution of RSSI for legacy PHY STA. | [6 empty] | Probably OK, but restructure the document might be a little harsh - 8/18/04
5 | Lanzl | 7.3.2.21.9 | T | Y | the text and tables k5 and k6 refer to an entity "RPI" that is undefined. From the context, it appears that "RPI" could be "RCPI", but that is not entirely clear. | Either define RPI prior to its use and place that abbreviation in section 4 or change all references to RPI in all text and tables to RCPI. Note that RPI is used elsewhere as well (for example, in table 20b).
6 | Lanzl | 7.3.2.21.9 | T | Y | The state of CCA is either BUSY or IDLE. There is no need to provide both the CCA BUSY and IDLE histograms as one set of data can be deduced from the other. | Remove all references to either the CCA Busy Time Histogram or CCA Idle Time Histogram in the text and table k5. | [6 empty] | Probably OK - 8/18/04
7 | Lanzl | 7.3.2.21.9 | T | Y | The threshold values for table k6 do not make sense in the context of the base standard: 5dB steps are the wrong value. See my comment below concerning 7.3.2.22.5 for the rationale. | Change the starting value and steps in table 6 from -87dBm and 5dB to -85dBm and 3dB; so, RCPI threshold of 0 would correspond to -85dBm, 1 would correspond to -82dBm, 2 would correspond to -79dBm, 3 would correspond to -76dBm, 4 would correspond to -73dBm, 5 would correspond to -70dBm and 6 would correspond to -67dBm. It might also make sense to add the following two threshold values: 7 would correspond to -64dBm and 8 would correspond to -61dBm, leaving thresholds 9-254 reserved and threshold 255 as the table currently reads. | [6 empty] | Klein - 3db increments looks right. 8/18/04
8 | Lanzl | 7.3.2.22.5 | T | Y | The choices for RCPI measured power thresholds in conjunction with the CCA state of IDLE do not make sense. In the base standard, there are various input power requirements for CCA to indicate BUSY. For the legacy 802.11 DS PHY, the CCA must indicate BUSY for received powers > -80dBm (Tx >100mW), >-76dBm (50mW <= Tx <=100mW) and >-70dBm (Tx < 50mW). For the 802.11b PHY, the CCA must indicate BUSY for received powers >-76dBm (Tx >100mW), >-73dBm (50mW <= Tx <= 100mW) and >-70dBm (Tx < 50mW). For the 802.11g PHY, the CCA must indicate BUSY for received powers >-76dBm. For the 802.11a PHY, the CCA must indicate BUSY for received powers >-82dBm for a valid OFDM symbol or -42dBm for any input signal. Re-structuring the table to capture the noise in finer-grain RCPI bins following baseline standard CCA ranges makes more sense. | Change the starting value and steps in table k8 from -87dBm and 5dB to -85dBm and 3dB; so, RCPI threshold of 0 would correspond to <=-85dBm, 1 would correspond to -85dBm<RCPI<=-82dBm, 2 would correspond to -82dBm<RCPI<=-79dBm, 3 would correspond to -79dBm<RCPI<=-76dBm, 4 would correspond to -76dBm<RCPI<=-73dBm, 5 would correspond to -73dBm<RCPI<=-70dBm, 6 would correspond to -70dBm<RCPI<=-67dBm and 7 would correspond to -67dBm<RCPI. This choice gives better granularity to the measurement of noise when CCA is IDLE for most of the baseline standard PHYs. | [6 empty] | Klein - 3db increments looks right. 8/18/04
9 | Lanzl | 7.3.2.22.6 | E | N | It is not clear in this section that the report should only cover one beacon. This is hinted in later text. Without that clarity, it is confusing how to report multiple RCPI, TSF and timestamps in this report. | Add some text clarifying that this beacon report can only apply to one beacon measurement. | [6 empty] | Report the last thing you saw? Olson
10 | Lanzl | 7.3.2.22.7 | E | N | It is not clear in this section that the report should only cover one frame. This is hinted in later text. Without that clarity, it is confusing how to report multiple RCPI in this report. | Add some text clarifying that this beacon report can only apply to one frame measurement. | [6 empty] | RCPI is defined as an average - reject comment!
11 | Lanzl | 15.4.5.16.2 | E | N | The text "RCPI indications of 8 bits (221 levels) are supported." is confusing. In fact, RCPI indications of 8 bits are supported and 221 states are assigned to RCPI levels. | Change the text to read: "RCPI indications of 8 bits are supported, as defined in 15.4.8.5. | [6 empty] | Makes sense - 8/18/04
12 | Lanzl | 15.4.5.16.4 | E | N | The text states that RCPI may be used in conjunction with RSSI to measure input signal quality. This is confusing in the face of the baseline standard's use of the SQ parameter. | Remove the line reading: "The RCPI may be used in conjunction with RSSI to measure input signal quality." | [6 empty] | Joe says the section doesn't make sense without the sentence - 8/18/04
13 | Lanzl | 15.4.8.5 | T | Y | The definition of assignment of RCPI levels to RCPI indicator bits is sloppy. Either provide a complete table or some algorithm that fully describes the states with no ambiguity. | Change lines 18-24 to read: "RCPI indicator = int{(received power in dBm +110)*2} for received powers 0dBm or less and where the RCPI indicator of 0 is used for received signal power less than -110dBm. RCPI indicators 221-254: reserved. RCPI indicator 255: Measurement not available. | [6 empty] | Add the formula as well as the table (Kwak) - 8/18/04
14 | Lanzl | 17.2.3.5 | E | N | The text "RCPI indications of 8 bits (221 levels) are supported..." is confusing. In fact, RCPI indications of 8 bits are supported and 221 states are assigned to RCPI levels. | Change the text to read: "RCPI indications of 8 bits are supported, as defined in 17.3.10.6. | [6 empty] | Makes sense - 8/18/04
15 | Lanzl | 17.3.10.6 | T | Y | The definition of assignment of RCPI levels to RCPI indicator bits is sloppy. Either provide a complete table or some algorithm that fully describes the states with no ambiguity. | Change lines 24-29 on page 56 and line 1 on page 57 to read: "RCPI indicator = int{(received power in dBm +110)*2} for received powers 0dBm or less and where the RCPI indicator of 0 is used for received signal power less than -110dBm. RCPI indicators 221-254: reserved. RCPI indicator 255: Measurement not available. | [6 empty] | Add the formula as well as the table - 8/18/04
16 | Lanzl | 17.5.5.8.2 | E | N | The text "RCPI indications of 8 bits (221 levels) are supported..." is confusing. In fact, RCPI indications of 8 bits are supported and 221 states are assigned to RCPI levels. | Change the text to read: "RCPI indications of 8 bits are supported, as defined in 17.3.10.6. | [6 empty] | Makes sense - 8/18/04
17 | Lanzl | 17.5.5.X.4 | E | N | The section number for this should read 17.5.5.8.4. Also, the text states that RCPI may be used in conjunction with RSSI to measure input signal quality. This is confusing in the face of the baseline standard's use of the SQ parameter. | Change the numbering of this section to 17.5.5.8.4. Remove the text that reads: "RCPI may be used in conjunction with RSSI to measure input signal quality."
18 | Lanzl | 18.4.5.16.4 | E | N | The text states that RCPI may be used in conjunction with RSSI to measure input signal quality. This is confusing in the face of the baseline standard's use of the SQ parameter. | Remove the text that reads: "RCPI may be used in conjunction with RSSI to measure input signal quality."
19 | Lanzl | 18.4.8.5 | T | Y | The definition of assignment of RCPI levels to RCPI indicator bits is sloppy. Either provide a complete table or some algorithm that fully describes the states with no ambiguity. | Change lines 14-20 to read: "RCPI indicator = int{(received power in dBm +110)*2} for received powers 0dBm or less and where the RCPI indicator of 0 is used for received signal power less than -110dBm. RCPI indicators 221-254: reserved. RCPI indicator 255: Measurement not available. | [6 empty] | Add the formula as well as the table - 8/18/04
20 | Kleindl | 7.2.3.4 | E | N | different order numbers in instruction and table | align order numbers
21 | Kleindl | 7.2.3.6 | E | N | different order numbers in instruction and table | align order numbers
22 | Kleindl | 7.3.1.4 | E | N | subfields 'Spectrum Management', 'Short Slot Time' and 'DSSS-OFDM' are missing in Figure 27 | add missing subfields in Figure 27
23 | Kleindl | 7.3.1.11 | E | N | Value '5' is missing in Table 19a | add missing value '5'
24 | Kleindl | 7.3.2.21.9 | E | N | On page 18 there are very similar wordings in lines 4-6 and 7-9, the first refering to Table k6 and the second refering to Table k8. I could not understand what is meant. | clarify what is meant
25 | Kleindl | 7.3.2.22 | E | N | On page 20 lines 30-31 the wordings '... measurement shall start ...' are suitable for the Request element but not for the Report element. | change to e.g. '... measurement has started ...'
26 | Kleindl | 7.4.2 | E | N | Value '6' is missing in Table k12 | add missing value '6'
27 | Hayes | 7.3.2.26 | T | Y | The TBTT fields of the neighbor report will not be viable in such a large number of implementations that their presence will be useless, even if they are marked as optional. | Delete the text regarding TBTT from clause 7.3.2.26
28 | Lefkowitz | 3 | T | Y | A Neighbor BSS does not have to be adjacent or overlap. A neighbor AP can be physically discontiguous at a particular site and still be in the Neighbor report | Change wording to include the possibility of a near by AP that is of interest to the ESS/site, while these AP's may not be part of the ESS, they are part of the site.
29 | Lefkowitz | 5.2.5 | E | N | Distinguish between AP's a Peer STA's | change "In the measured WLAN, stations can make measurements locally as well as request measurements from peer STAs with the results being stored in the MIB." to "In the measured WLAN, stations can make measurements locally as well as AP's requesting measurements from STA's in Infrastructure mode, as well as peer STAs requesting measurements from each other, with the results being stored in the MIB.
30 | Lefkowitz | 5.2.5 | T | Y | Information is communicated from the AP to the STA that contains the results of measurements. ""In the measured WLAN, stations can make measurements locally as well as request measurements from peer STAs with the results being stored in the MIB. The resulting information is then available for both the station and upper layers for any purpose." implies that it comes from the MIB only. The neighbor report can have measurements that are communicated by request to the STA from the AP. | remove the sentence fragment that says "with the results being stored in the MIB. You may want to optionally add here an overview of how important the MIB is for control of these measurments, and possibly the MIB is a repository for these measurements.
31 | Lefkowitz | 5.4 | E | Y | List the number of total services. What does several mean to you? 11? 3? 7? Why list theexact number of services for each function without listing the total number of services | List the exact amount of services -- 11?
32 | Lefkowitz | 5.4.4.1 | E | N | Take out the redundent (TPC) in the paragraph | see comment
33 | Lefkowitz | 5.4.4.1 | T | Y | What does the added sentence mean? | Change sentence to "TPC can also used in the 2.4 GHz Band"
34 | Lefkowitz | 5.5 | T | Y | Radio resource measurement actions should never be used as class 1 frames in infrastructure. | Add "in infrastructure." to the class 3 section sentence "ii) Radio Resource Action"
35 | Lefkowitz | Table 5 & Table 12 | T | Y | the channel report is not mandatory to send if there are channels to report | Change sentence from "19 AP Channel Report The AP Channel Report information element shall only be present within Beacon frames generated by a Radio Resource Measurement capable AP when dot11RadioMeasurementEnabled is true. The AP Channel Report Element may be omitted if there are no channels to report." to "19 AP Channel Report The AP Channel Report information element may be present within Beacon frames generated by a Radio Resource Measurement capable AP only when dot11RadioMeasurementEnabled is true."
36 | Lefkowitz | table 20 | T | Y | get the element id values | see comment
37 | Lefkowitz | 7.3.2.21 and beyond | E | N | Until this point I was under the assumption that the underlined text is text to be added to existing text. The text in 7.3.2.21 does not exist in the 2003 specification. I'm confused as to what is being added | Be consistant in the instructions to the editor.
38 | Lefkowitz | 7.3.2.21 | T | Y | "A value of 0 shall mean the measurement shall start immediately after the previous measurement completed. " is unclear in the context of many measurements requests within one measurement request packet. | Clarify the behavior in regards to single and periodic measurments.
39 | Lefkowitz | 7.3.2.21 | E | N | in regards to duration bit -- it's confusing to keep requesting STA without mentioning AP. | Change "requsting STA" to "requestor"
40 | Lefkowitz | Table 20a | E | N | see previous comment for 7.3.2.21 | change "transmitting STA" to "requestor"
41 | Lefkowitz | 7.3.2.22 | T | Y | "The Measurement Report field shall be null when the Late bit is set to 1, the Incapable bit is set to 1 or theRefused bit is set to 1. " How can you set a variable length field to NULL? | Clarify Maybe "packet shall not contain the measurement report field"
42 | Lefkowitz | 7 | T | Y | Is there any way to know if a request is unreasonable for a particular STA to fulfil. For example too long a time off channel, or excessive measurements that will interfere with the STA's "in band" operation? | Put limits, or ranges of limits on the measurement requests. Include a mechanism for the STA to indicate it will fulfil a request in a particular range, but not from another.
43 | Lefkowitz | 7.3.2.22.6 | T | Y | "All information elements that are present in the reported frame shall be included. " conflicts with the concept of IE's a STA can not parse are ignored. | change sentence to "All information elements, including unknown information elements, that are present in the reported frame shall be reported."
44 | Lefkowitz | 7.3.2.22.8 | T | Y | It is unclear in the hidden node report as to whether the BSSID is to remain the BSSID of the BSS. Today's Hardware filters based on BSSID, so there may be significant implications for this. | Clarify the behavior of the Hidden Node process in regards to BSSID
45 | Lefkowitz | 7.3.2.26 | T | Y | informative note: Determination of the neighboring APs can be accomplished be several means, -- include proprietary means. | add "c other proprietary means"
46 | Lefkowitz | 7.3.2.26 | T | Y | The Lower Timestamp Reference field should be defined when the TBTT offset was not requested or not reported in any list entry. | Add The Lower Timestamp Reference field shall be zero if there are no TBTT offsets to report.
47 | Lefkowitz | 7.3.2.26 | T | Y | "The BSSID is the address of the STA contained in the AP." conflicts with the definition of BSSID in 7.1.3.3.3 of the 2003 spec. | Change sentence to "The BSSID is the BSSID of the BSS being reported"
48 | Lefkowitz | 7.3.2.26 | T | Y | Reachable is defined in terms of a VLAN. The definition of a VLAN is not present in this document(, nor should it be). | remove the remaining text in paragraph after "The value "Reachable" implies that the AP represented by this BSSID are reachable by the STA for the purposes of pre-authentication. "
49 | Lefkowitz | 7.3.2.26 | T | Y | Capabilitieis Subfield --WPA WMX/EDCA and WMX/HCCA) are not defiend, or referenced in this specification (nor should they be) | Remove references to WiFi docs and procedures. This is their problem not ours.
50 | Lefkowitz | 7.3.2.26 | T | Y | Preauthentication - there is currently no mechanism to determine if the key has been dropped by the Neighbor due to resource issues. | Include an information element in the beacon that indicates the last time the Neighbor flushed it's cache such that the STA would know that all keys after a particular time are no longer kept by this AP. Indicate uptime in this IE for the event that the AP has reboot since the preauth.
51 | Lefkowitz | 7.4.2.4 | T | Y | "The Neighbor Report Response frame uses the Action frame body format and is transmitted by a STA in response to a Neighbor Report Request frame or by a STA autonomously providing Neighbor Report information. " The behavior for when an autonomous neighbor report would be sent is undefined this feature is useless/proprietary. The two known reasons are assoication and disassociation to send an unsolicitied neighbor report. However if sent at disassocation time it has little intended value because it can not be used to maintain a connection with the infrastructure | send the IE neighbor report as part of the association response. Put dissassociate imminent back into the sepcification
52 | Lefkowitz | 7.4.2.4 | T | Y | Be specific about the fact that this report is sent by an AP and received by a STA. | change "The Neighbor Report Response frame uses the Action frame body format and is transmitted by a STA in response to a Neighbor Report Request frame or by a STA autonomously providing Neighbor Report information. " to "The Neighbor Report Response frame uses the Action frame body format and is transmitted by an AP inresponse to a Neighbor Report Request frame or by an AP autonomously providing Neighbor Report information."
53 | Lefkowitz | 7.4.2.4 | T | Y | "The number and length of the Neighbor Report Elements in a Neighbor Report frame is limited by the maximum allowed MMPDU size." there should be a mechanism whereby more elements than the MMPDU side can be sent | Either use the more data bit in the 802.11 packet or define a more data bit in the IE that indicates there are more IE's in another packet.
54 | Lefkowitz | 11.1.3.2.1 | T | Y | Responding only if the channel number is correct when the DS parameter is inserted into the probe request limits flexibility in scanning algorithms. | make the inclusion of the DS parameter set in 7.2.3.8 optional (i.e may in both cases). This gives the RRM enabled STA the option of getting a response quicker, even if it is on the wrong channel.
55 | Lefkowitz | 11 | T | Y | Give the STA the ability to do a "Fast Scan" This allows the STA to only get RSSI data very quickly in a deterministic manner | adopt 11-03-0834
56 | Lefkowitz | 11.7.2 | T | Y | The first paragraph is implyng an alogoritm. How a STA handles off channel requests is outside the scope of the specificiation. | Remove clause, or state that a STA is responisble for receiving its data (obviously) and have an informative note about the risks slowing up the network, and getting disassociated (obvious and pedantic) Make second paragraph informative.
57 | Lefkowitz | 11.7.5 | T | Y | Why a reciever of a measurment request decides not to fulfil the measurement is outside the scope of the specification | remove first sentence.
58 | Lefkowitz | 11.7.5 | T | Y | It is unclear in this clause whether the STA is requred to send a response or the STA may igore the request (ignore implies to me not sending a response) | Clarify
59 | Lefkowitz | 11.7.5 | T | Y | Reasons why a STA may not fulfil a measurement request is outside the scope of the specification. | Remove everything in the clause after the second sentence up to the 3'rd paragraph
60 | Lefkowitz | 11.7.6 | E | N | Beexplicit about who is sending the request in infrastructure. If STA's can not send requests to each other in infrastructure then stat that the AP sends a request to the STA in infrastructure and that STA's can send requests to each other in Ad-Hoc. If there can not be two AP's in infrastructure mode then the wording in the begining of the clause is not clear about a STA sending to other STA's since the table states that a STA can send a request to an AP. | See comment
61 | Lefkowitz | General | E | N | Change the wording the document to say Sender of a request and reciever of a report. | see comment
62 | Lefkowitz | 11.7.2 | T | Y | Since powersave is broken in IBSS mode the specification needs to either address the issues with powersave in IBSS or take out any notion that powersave is an answer in the IBSS case | Remove first paragraph
63 | Lefkowitz | 11.7.6 | T | Y | line 28 Since powersave is broken in IBSS mode the specification needs to either address the issues with powersave in IBSS or take out any notion that powersave is an answer in the IBSS case | Remove any notion that powersave is an option for suspending traffic. Remove any suggestion about how to suspend traffic since there is already is a precidence for going off channel (scanning while associated)
64 | Lefkowitz | 11.7.6 | T | Y | "A STA that issues a measurement request to another STA to perform a measurement on the serving channel may transmit MPDUs and MMPDUs to that STA during the measurement itself." Clarify the behavior of the reciver of a request during the fulfillment of a previous measurement request. | see comment
65 | Lefkowitz | 11.7.6 | T | Y | A STA may refuse to make any requested measurement and may respond to such a unicast Measurement Request with an indication that the it is refusing the easurement request. A STA shall not respond to broadcast and multicast requests in this manner." Why may? Under what circumstances would it respond and under what circumstances would it not? | Clarify Reciever behavior,
66 | Lefkowitz | 11.7.6 | T | Y | Last paragraph should not be normative as it is implying an algorithm, purpose, or a supposed effect. | Either remove paragraph (preferred) or make it informative.
67 | Lefkowitz | 11.7.7 | T | Y | Why would a STA reject (implying sending a refuse?) or ignore implying do nothing? | Clarify
68 | Lefkowitz | 11.7.6 | T | Y | This clause does not specify what the behavior is while processing a periodic message and another request comes in | Clairfy behavior of the reciver of a measurment request while processing a periodic measurement request. Clarify the behavior of the reciever of a periodic measurement request when processing a periodic measurement reques
69 | Lefkowitz | 11.7.8.1 | T | Y | The way I am reading this clause it appears that you can not send a beacon measurment request if the channel is the same as the serving channel. | If this is the case change it such that you can measure beacons on the serving channel. Be explicit about what to do if the request is on the serving channel, or do not be explicit about what to do if it is not on the serving channel.
70 | Lefkowitz | 11.7.8.4 | T | Y | The noise histogram report does not take into account the devices that use energy detect only to set the CCA. | Automatically include in the report a bmedium time sensing report
71 | Lefkowitz | 11.7.8.6 | T | Y | the description of how the medium time sensing report can be used should not be part of the normative specification. Moreover this is the only measurement report that descibes how it can be used. | Take it out.
72 | Lefkowitz | 11.8 | T | Y | The Mib table is not the definitive source for compiling the neighbor report. It is a repository for the information and can be collected upon request as well as configured via the MIB mechanism (as also stated in this clause…) | Remove the line "The Neighbor Report contents shall be derived from the MIB table"
73 | Lefkowitz | 11.8.1 | E | N | "If the STA is interested in information concerning neighbor APs matching a specific SSID, it shall specify the SSID element in the Neighbor Report Request frame." Why would something made out of silicon be interested in a different SSID? | Change sentence to "A Neigbor report request may be sent with a specific SSID filled into the SSID field. If the SSID field is omitted the neigbor report list entries will concern the current ESS."
74 | Lefkowitz | 7.4.2.3 | T | Y | The SSID field is not a variable length | Say that the SSID field is 6 bytes
75 | Lefkowitz | 11.8.2 | T | Y | The information is not derived from the MIB it is only a repository for what the message is going to look like. It could be implemented that the MIB is derived from a table in the device. | Take out the mention of where the infomration comes from in this clause.
76 | Lefkowitz | 11.8.2 | T | Y | "An AP accepting a Neighbor Report Request shall respond with a Neighbor Report Response frame containing one or more Neighbor Report elements. " What if it has no information on a particular SSID? | change to "An AP accepting a Neighbor Report Request shall respond with a Neighbor Report Response frame. If there are no list entries available the AP shall send a Neighbor Report Response with no Neighbor List Entries "
77 | Lefkowitz | 11.8.2 | T | Y | Allow the Neighbor Report IE to be sent during association response. | Change the second paragraph to "A Neighbor Report IE may be sent with an Association Response.
78 | Lefkowitz
79 | Lefkowitz | 11.8.2 | T | Y | Since the neighbor report is used to facilitate a better and possibly faster roaming candidate selection, and since disassociation (implicit or explicit) is part of the roaming process, and that the disassociation is bi-directional, allow the AP to send the neighbor report before dissassociation. | Put dissassociate Imminent back into the draft amendment.
80 | Lefkowitz | 7 | T | Y | There is no reason to have a channel band. dot11PhyType and channel number should be enough in all cases. It seems excessive to have to keep up yet another item from now on. | Use phytype instead of channel band in all messages to be unambiguous in selection of channel.
81 | Faccin | 7.3.22.22.10 | T | Y | dot11APServiceLoad is given in the statistics returned column but is not in Dot11CountersEntry | Remove dot11APServiceLoad from table k10.
82 | Faccin | 11.7.5 | T | Y | This text states that pending unprocessed radio measurement requests are deleted on association, or reassociation. Should this not be disassociation, or re-association? If a STA is disassociated it cannot return the measurement result to the AP. | Pending unprocessed radio measurement requests should be deleted on disassociation, or re-association.
83 | Faccin | A.4.13 | T | Y | Power Constraint information for beacon and probe response frames is mandatory according to RRM17.1 and optional according to RRM17.2 | Remove power constraint from RRM17.1
84 | Faccin | A.4.13 | T | Y | In RRM15 there is no RCPI requirement specified for a clause 19 PHY (11g) | Add 11g RCPI requirement.
85 | Faccin | A.4.13 | T | Y | RRM16.2 states that AP service load is mandatory, but this is not in the MIB | Remove RRM16.2.
86 | Faccin | 11.5 | T | Y | The fifth bullet in the first group of this section (p45, l11) is supposed to be in 11h, but is not in the final 802.11h-2003. | Make imported 11h text consitent with published standard.
87 | Faccin | A.4.13 | E | N | What happened to RRM19-22? The table jumps from RRM18 to RRM23? | Correct numbering
88 | Thrasher | 7.3.2 | E | N | Table 20 Element ID's are TBD | Need to be determined….
89 | Thrasher | 7.3.2.21 | E | N | Table 20a width of "enable" column needs to be widened one character
90 | Thrasher | 7.3.2.21.9 | E | N | Need consistent field description format when describing the definition of the fields (applies throughout the entire document) sometimes worded as "The (field name) shall be…." sometimes it's just "(field name) shall be…." and sometimes it's "The (field name) field shall be...For example see page 17(of pdf) line 8 vs. line 24... or page 18 line 13...
91 | Thrasher | 7.3.22.5 | E | N | Table k8 bad grammer in heading…and there are no units defined for the RCPI Measured Power… | should read "RPI Definitions for a Noise Histogram Report"
92 | Thrasher | 11.5 | E | N | First sentence in second paragraph (line 39,40).. Need to remove the reference of "future regulatory requirements in Europe" I'd assume the TPC procedures could be used to satisfy future regulatory requirements in other places besides Europe…:) | should read ….This clause describes TPC procedures that may be used to satisfy this particular European regulatory requirement. The procedures may also satisfy comparable needs …..
93 | Thrasher | 11.7.6 | E | N | line 2,3 of page 48…"shall be returned without undue delay" and the definition of undue delay is……. | should read "should be returned without undue delay"
94 | Thrasher | 11.7.6 | E | N | line 9 of page 48 …Where a STA is permanently | should read "When a STA is….."
95 | Thrasher | 11.7.8.2 | E | N | Line 15 of page 50 If a station accepts……(STA is the acronym for station….) occurs multiple times in this section
96 | Myles | 11.7.8.1 | E | Y | The text uses both "station" and "STA" "STA" is the correct terminology | Fix No doubt other clauses have the same problem
97 | Myles | 11.7.8.4 | T | Y | The text specifies that the Noise Histogram Report shall only include non-802.11 energy by sampling when CCA indicates the channel is idle. However, this specification has a few problems: * 802.11 energy is possible when the CCA is idle * non 802.11 ener | Justify the use of this measurement and adjust or delete the measurement specification accordingly
98 | Myles | 11.7.8.5 | T | Y | The description in this clause (and in 7.3.2.22.8) disallows a hidden stations report that reports no hidden stations This is useful information that is being thrown away | Allow an empty hidden station report to be transmitted
99 | Myles | 11.7.6 | T | Y | The text specifies that a STA "may" respond with a refusal if it decided not to undertake a requested unicast measurement. Why is this not "shall"? | Clarify
100 | Visscher | Annex D | T | Y | The type of the the counters in dot11STAStatisticsReportTable defined as Integer32 is not capable of containing the internal counter size. | Use type Counter32 instead of Integer32 for counters. This is also consistent with the STA counters in dot11CountersTable.
101 | Visscher | Annex D | T | Y | dot11RRMNeighborReportBSSID is only defined as OID but not present in Dot11RRMNeighborReportEntry | Add dot11RRMNeighborReportBSSID to Dot11RRMNeighborReportEntry
102 | Visscher | Annex D | T | Y | dot11RRMNeighborReportRSN is only available in Dot11RRMNeighborReportEntry but not defined as OID. | Add definition for dot11RRMNeighborReportRSN
103 | Visscher | Annex D | T | Y | dot11peerWEPDecryptionFailureCount is only available in Dot11peerStatsEntry but not defined as OID. | Add definition for dot11peerWEPDecryptionFailureCount
104 | Visscher | Annex D | T | Y | dot11peerReceivedBeaconCount is only available in Dot11peerStatsEntry but not defined as OID. | Add definition for dot11peerRecievedBeaconCount
105 | Visscher | Annex D | T | Y | dot11peerReceivedByteCount is only available in Dot11peerStatsEntry but not defined as OID. | Add definition for dot11peerReceivedByteCount
106 | Visscher | Annex D | T | Y | dot11peerTransmittedByteCount is only available in Dot11peerStatsEntry but not defined as OID. | Add definition for dot11peerTransmittedByteCount
107 | Visscher | Annex D | T | Y | Compliance statement update missing. | Add a compliance state for Radio Resource management.
108 | Visscher | Annex D | T | Y | Module groups for radio resource management are missing. | Add module groups for the addes MIB objects.
109 | Cole | 5.3 | E | N | The inserted material is shown in isolation. | Please consider showing the entire list with the insertion underlined for clarify
110 | Cole | 5.3.1 | E | N | The inserted material is shown in isolation. | Please consider showing the entire list with the insertion underlined for clarify
111 | Cole | 7.2.3.4 | E | N | The order of the editing instruction and the order shown don't match. | Please change to match.
112 | Cole | 7.2.3.6 | E | N | The order of the editing instruction and the order shown don't match. | Please change to match.
113 | Cole | 7.2.3.8 | T | Y | Adding a new mandatory element to a probe response is not backward compatible with devices already existing. | Please modify this so that field is only present for purposes needed by 802.11k amendment and won't have effect on preexisting devices.
114 | Cole | 7.3.22.4 | E | N | This section is not part of the previous "change" editor instruction. | Please add an "insert" new material instruciton before this clause (and the ones that follow).
115 | Cole | 7.3.2.25 | E | N | The editing instructions and the sub-clause numbers don't match. | Please change to match for this and the subsequent sub-clause.
116 | Cole | 10.3.16.1.2 | E | N | The font for tables in this sub-clasue and those subsequent don't match the prior sub-clause tables. | Please change to match.
117 | Cole | 10.3.16.2.2 | E | N | Indentation inconsistency in the TPC element of the table. | Please change to match.
118 | Cole | 12.3.5.11.2 | T | Y | The change of adding RXVECTOR to the PHY-RXEND primitive is not backward compatible with preexisting devices. | Please modify this so that this paramter is only present for purposes needed by 802.11k amendment and won't have effect on preexisting devices.
119 | Cole | 15.2.7 | T | Y | The change of adding RXVECTOR to the PHY-RXEND primitive is not backward compatible with preexisting devices. | Please modify this so that this paramter is only present for purposes needed by 802.11k amendment and won't have effect on preexisting devices.
120 | Cole | 15.4 | T | Y | The change of adding RCPI to the RXVECTOR paramters is not backward compatible with preexisting devices. | Please modify this so that this changed paramter is only present for purposes needed by 802.11k amendment and won't have effect on preexisting devices.
121 | Cole | 17.2.3 | T | Y | The change of adding RXVECTOR to the PHY-RXEND primitive is not backward compatible with preexisting devices. | Please modify this so that this paramter is only present for purposes needed by 802.11k amendment and won't have effect on preexisting devices.
122 | Cole | 17.2.3.5 | T | Y | The change of adding RCPI to the RXVECTOR paramters is not backward compatible with preexisting devices. | Please modify this so that this changed paramter is only present for purposes needed by 802.11k amendment and won't have effect on preexisting devices.
123 | Cole | 17.10.3.6 | T | Y | The change of adding PMD required measurments for RCPI is not backward compatible with preexisting devices. | Please modify this so that this added procedure is only present for purposes needed by 802.11k amendment and won't have effect on preexisting devices.
124 | Cole | 17.3.12 | T | Y | The changes to the PLCP procedure are not backward compatible with preexisting devices. | Please modify this so that this added procedure is only present for purposes needed by 802.11k amendment and won't have effect on preexisting devices.
125 | Cole | 18.2.6 | T | Y | The changes to the PLCP procedure are not backward compatible with preexisting devices. | Please modify this so that this added procedure is only present for purposes needed by 802.11k amendment and won't have effect on preexisting devices.
126 | Cole | 18.4.5 | T | Y | The change of adding RCPI to the PMD SAT as a requirement is not backward compatible with preexisting devices. | Please modify this so that this changed paramter is only present for purposes needed by 802.11k amendment and won't have effect on preexisting devices.
127 | Cole | 18.4.8.5 | T | Y | The change of adding PMD required measurments for RCPI is not backward compatible with preexisting devices. | Please modify this so that this added procedure is only present for purposes needed by 802.11k amendment and won't have effect on preexisting devices.
128 | Cole | A.4.13 | T | Y | As shown, all of the PICS in this section are not conditional… they are mandatory. | Make all of these conditional on CF10
129 | Cole | D | E | N | In the first 4 sections of the MIB changes, the changes are shown without context. | Please consider showing the smallest but whole changed item with underscores. This is clearer.
130 | Cole | D | T | Y | In dot11StationConfigEntry, no chagnes are shown. | I think the last elements should be underlined. Please find the chagnes and underline them.
131 | Cole | D | E | N | in Dot11OperationEntry sequence list, the changes are shown without context. | Please consider showing the smallest but whole changed item with underscores. This is clearer.
132 | Kowalski | 5.4.4.1 | T | Y | Why would TPC be required at all in the 2.4GHz band? There seems to be no good engineering reason to include them. Furthermore, the lingua franca of a digital radio is not path loss per se, nor link margin, but rather bit or frame error rate (e.g., suppose the channel is non-white or non-gaussian, as will be typical in the 2.4GHz band). It is not clear how these measurements would be used by the network to do anything meaningful, and therefore there appears to be no reason to support them. | Remove TPC from 2.4GHz band.
133 | Kowalski | General | T | Y | I am interested in seeing rules as to how these features are integrated with Quality of Service- if there are frequent requests for measurement reports, these could impede QoS. | Please provide guidelines to ensure how these measurements can be implemented whilst maintaining QoS.
134 | Kowalski | 7.3.2.22.5 | T | Y | It is not clear why a Noise Histogram is being measured, nor what a network might do with such a measurement. | Please explain what its purpose is in the document or remove it.
135 | Kowalski | 7.3.2.22.5 | T | Y | Noise Histogram should include dependencies over time- the mere fact that one might detect non-Gaussian noise doesn't actually help improving radio design because time dependency in the noise may actually be a more serious issue. | Please provide a time-dependency in measurements of histogram or remove it & all references thereto.
136 | Kowalski | 7.3.2.22.5 | T | Y | Noise Histogram should have an adaptive threshold, to accommodate the wide dynamic range of signal/interference levels. | Please include dynamic thresholding, or remove histogram & all references thereto.
137 | Kowalski | 7.3.2.22.8 | T | Y | It is not clear from the text how a "hidden node report" is actually made. What if a node is hidden from both sender & receiver? Does this work in an IBSS? It certainly seem problematic for overlapped IBSSs. How does the sender know the addresses to whom it should send frames? | Please provide more detail on how this is done.
138 | Kowalski | 7.3.2.22.8 | T | Y | There are probably interactions with Security (such as security associations that exist amongst subsets of stations) that preclude the general usage of a "hidden node" reporting mechanism. | Please explain the security requirements necessary to achieve this.
139 | Kowalski | 7.3.2.22.9 | T | Y | This might be a useful metric IF the distribution of contiguous busy/idle time were provided. Otherwise, it actually is not very useful in terms of predicting whether or not a particular stream can be sustained on the BSS. | Please re-format this metric to include the distributions of *contiguous* idle/busy times.
140 | Kowalski | 7.3.2.26 | E | N | Line 20:The phrase "AP may choose to only believe…" is an anthropomorphism. | Rephrase.
141 | Kowalski | 7.3.2.26 | T | Y | There are probably interactions with Security (such as security associations that exist amongst subsets of stations) that preclude the general usage of this mechanism. | Please provide details as to how this interacts with Security mechanisms.
142 | Kowalski | 9 | T | Y | There need to be defined limits to these procedures that do not affect QoS. | Please include a Clause 9 reference that allows for these things to coexist with QoS.
143 | Kowalski | 7.3.22.9 | T | Y | If the dependency*between* idle and busy times was measured, this would actually be a useful statistic for QoS flow admission. IOW, an idle time of how long is preceded by a busy time of how long probablistically? You need, therefore a joint or conditional density/distribution function. | Instruct the editor to create normative next following the instructions given in 993r0.
144 | Kowalski | 7.3.2.22.9 (et al.?) | T | Y | If the total number of Medium Sensing Intervals is N octets, the number of octets/bin density should be N as well for consistency, to prevent overlfows, etc. Suppose there are 4 bins, e.g., and the distribution of, say, idle time is uniform. Then there's a high probability that frequently more than 1 bin will "max out." | Change as suggested.
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245