## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-05/22r0
Venue Date: | January 2005
First Author: | Bob O'Hara, Airespace
Subject: | Status of Work Items for 802.11m
Date: | January 2005
Author(s): | Bob O'Hara
Airespace
110 Nortech Pkwy, San Jose, CA 95134
Phone: +1 408 635 2025
Fax: +1 408 635 2020
email: bob@airespace.com
Abstract:
Disclaimer:
This is the current status of the work items accepted by TGm.
Notice: This document has been prepared to assist IEEE 802.11. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor grants a free, irrevocable license to the IEEE to incorporate material contained in this contribution, and any modifications thereof, in the creation of an IEEE Standards publication; to copyright in the IEEE’s name any IEEE Standards publication even though it may include portions of this contribution; and at the IEEE’s sole discretion to permit others to reproduce in whole or in part the resulting IEEE Standards publication. The contributor also acknowledges and accepts that this contribution may be made public by IEEE 802.11.
Patent Policy and Procedures: The contributor is familiar with the IEEE 802 Patent Policy and Procedures <http:// ieee802.org/guides/bylaws/sb-bylaws.pdf>, including the statement "IEEE standards may include the known use of patent(s), including patent applications, provided the IEEE receives assurance from the patent holder or applicant with respect to patents essential for compliance with both mandatory and optional portions of the standard." Early disclosure to the Working Group of patent information that might be relevant to the standard is essential to reduce the possibility for delays in the development process and increase the likelihood that the draft publication will be approved for publication. Please notify the Chair <stuart.kerry@philips.com> as early as possible, in written or electronic form, if patented technology (or technology under patent application) might be incorporated into a draft standard being developed within the IEEE 802.11 Working Group. If you have questions, contact the IEEE Patent Committee Administrator at <patcom@ieee.org>.

## Work Items
ID | Source | Citation | 802.11 Ref | Assessment | Recommendation | Status | Assigned | Text written | Text approved | Text in draft | Draft Approved
1 | 03-382r0 | Page 3, left | 5.4.2.2 | Beyond PAR of 802.11m project because it would be defining new functionality | Consider for future work and PARs. 802.11 WGTE to include in a database, if desired. | Closed | n/a | n/a | n/a | n/a | n/a
2 | 03-382r0 | Page 3 right, bullet 1 & 2 | 5.5 | Technically correct -- possible wording changes might improve text | Change text to "Data frames in an IBSS with frame control (FC) bits To DS and From DS both false." | Needs Draft Approval | Brian Mathews | yes | yes 5/11/04 | yes 0.3
3 | 03-382r0 | Page 3 right, bullet 2 | 5.5 | Incorrect conclusion because bits are subject to rules in section 7. Imroved wording may be warranted. | change of ID 2 recommendation also corrects this. | Closed | n/a | n/a | n/a | n/a | n/a
4 | 03-382r0 | Page 3 right, bullet 3 | 5.5 | We believe that the statement is not true. Research and editorial Clarification may be warranted. | This is true only in an IBSS. See rx_coord_2b in station SDL code for confirmation. No change required, unless we want to prohibit this behavior. Since authentication and association are both optional in an IBSS | Closed | n/a | n/a | n/a | n/a | n/a
5 | 03-382r0 | Page 4 left | 5.5 | Research and editorial Clarification may be warranted. | Remove "Management frame" text, including deauthentication frame from 5.5 c) 2) and move the text "Deauthentication notification when in State 3 implies disassociation as well, changing the STAs state from 3 to 1. The STA shall become authenticated again prior to another association." to 5.5 a) 2) iv). | Needs Draft Approval | n/a | yes | yes 5/11/04 | yes 0.3
6 | 03-382r0 | Page 4 right | 5.6 | More research is required to determine if association/disassociation is disallowed elsewhere in the document | Association is optional in an IBSS, making state 2 and both class 2 and class 2 frames possible in an IBSS. No text changes required. | Closed | n/a | n/a | n/a | n/a | n/a
7 | 03-382r0 | Page 5 | 5.5 & 5.6 | Same as 6 | Authentication is optional and needs to be described, as it is in the standard. No text changes are required. | Closed | n/a | n/a | n/a | n/a | n/a
8 | Internal Discussion | none | Figure 8 | Text labels incorrect from state 2 to 3. Needs simple fix. | Change "Successful Authentication or Reassociation" to "Successful Association or Reassociation" | Needs Draft Approval | n/a | yes | yes 5/11/04 | yes 0.3
9 | Internal Discussion | None | 5 | Section 5 largely is descriptive. Review of each may and shall is warranted for section 5. | Close without change to the document | Closed | n/a | n/a | n/a | n/a | n/a
10 | 03-382r0 | Page 6 | 6.2.1.2.2 | Further research required. | Leave it to Tge | Closed | n/a | n/a | n/a | n/a | n/a
11 | 03-382r0 | Page 7 left | 7.2.3.10 | We feel the spec is unambigous. Title of Table 14 will be ammended by adding Element at the end. | Change title of table 14 to "Presence of challenge text information element" | Needs Draft Approval | n/a | yes | yes 5/11/04 | yes 0.3
12 | Internal Discussion | None | 7.3.2.1, 10.3.2.1.2, 11.1.3 & 11.1.3.2.1 | Clarify the broadcast SSID is actually the wildcard SSID. | adopt document 04/759 | Needs Draft Approval | 2004-05-11 | 2004-07-12 | yes 7/13/2004 | yes 0.4
13 | 03-382r0 | Page 7 right bullet 1 | 7.3.2 | Correct. Statement should be added in 17 pointing out that this is correct and OK. We should state that the DS IE should not be used for this purpose. Clarification in section 10 needed that you must fill in the PHY paramter set even though it wasn't on air. | Resolve as part of item 71 | Closed | n/a | n/a | n/a | n/a | n/a
13a | 03-382r0 | Page 8 | 7.3.2.6 | A couple of examples, especially any special cases should be developed. | add examples and code from 05/69r2 to informative annex. | Needs Draft Approval | 2004-07-13 | 2005-01-19 | 2005-01-20 | yes 0.6
14 | 03-382r0 | Page 9 left | 8 | Beyond PAR of 802.11m project and is within the scope of PAR for P802.11i |  | Closed | n/a | n/a | n/a | n/a | n/a
15 | 03-382r0 | Page 9 right | 8.1.1.2 | Text should be chagned to match MIB. | Change dot11AuthenticationType to dot11AuthenticationAlgorithm, in two places in 8.2 of 802.11i | Needs Draft Approval | n/a | yes | 2004-07-13 | yes 0.3
16 | 03-382r0 | Page 10 | 8.3.2 | Text in MIB should be brought in line with 8.3.2 | The undecryptable counter must not be incremented, except as described in 8.3.2. There are no other frames that may validly carry the WEP bit set. | Closed | n/a | n/a | n/a | n/a | n/a
17 | 03-382r0 | Page 11 left | 9.1.4 | Research and editorial Clarification may be warranted espeically to align MIB and text. | Change the first sentence of the third paragraph of 9.1.4 to "When a directed MSDU, plus MAC header and FCS, is received from the LLC or a directed MMPDU is received from the MAC sublayer management entity (MLME) with a length greater than dot11FragmentationThreshold, ..." (two changes in this sentence!) Also change all "aFragmentationThreshold" to "dot11FragmentationThreshold"! | Needs Draft Approval | n/a | yes | yes 5/11/04 | yes 0.3
18 | 03-382r0 | Page 11 right | 9.2.3.3 & 9.2.3.4 | Research and editorial Clarification may be warranted. | The EIFS is not to be used on noise events. Clarify 9.2.3.3 by replacing everything from "A STA using DCF shall not transmit…" to the endo fhte paragraph with "A correctly received frame is one where the PHY-RXEND.indication does not indicate an error and the FCS indicates the frame is error free." Clarify 9.2.3.4 by replacing the first sentence with "A STA shall use EIFS before transmission when it determines that the medium is idle following reception of a frame for which the PHY-RXEND.indication primitive contained an error or a frame for which the MAC FCS value was not correct.", inserting "The STA shall not begin a transmission until the expiration of the later of the NAV and EIFS." after "without regard to the virtual CS mechanism.", and adding to the end of the paragraph "At the expiration or termination of the EIFS the station reverts to the NAV to control access to the medium." | Needs Draft Approval | 2004-11-18 | 2004-11-18 | 2004-11-18 | yes 0.5
19 | 03-382r0 | Page 12 left | 9.2.4 | Research and editorial Clarification may be warranted. | In the paragraph of 9.2.4 that begins "The contention window (CW) parameter shall take an…", replace all occurences of MSDU with "MPDU of type Data". Also, in the paragraph of 9.2.5.3 that begins "After transmitting a frame…" and the following paragraph, replace MSDU with "MPDU of type Data" in all but the very last occurence. | Needs Draft Approval | 2004-11-18 | 2004-11-18 | 2004-11-18 | yes 0.5
20 | 03-382r0 | Page 12 right | 9.2.5.4 | Research and editorial Clarification may be warranted. Perhaps look more deeply into 802.11a (and also g) | Add a new parameter to the PHY Characteristic tables for each PHY (Tables 78, 80, 97, 115, 146) named aPHY-RX-START-Delay. The value for this parameter is zero for all tables except 115 and 146. The value in table 115 is 24 microseconds. The value in table 146 is 24 microseconds for OFDM and zero for CCK-OFDM. In 9.2.5.4 in the paragraph below figure 128, insert “+aPHY-RX-START-Delay” before “+ (2 × aSlotTime) “. | Needs Draft Approval | 2004-11-18 | 2004-11-18 | 2004-11-18 | yes 0.5
21 | 03-382r0 | Page 13 left | 9.2.5.4 | Research and editorial Clarification may be warranted. | append to the last sentence of the first paragraph of 9.2.5.4: "for those PHYs that provide a PHY-CCARESET.request primitive." | Needs Draft Approval | n/a | yes | yes 5/11/04 | yes 0.3
22 | 03-382r0 | Page 13 right | 9.2.5.7 | Clarification and alignment of SDL with text may be warranted. | In the sentence beginning "After transmitting and RTS frame" in 9.2.5.7, insert "with a value of aSIFSTime + aSlotTime," after "CTSTimeout interval,". | Needs Draft Approval | 2004-11-18 | 2004-11-18 | 2004-11-18 | yes 0.5
23 | 03-382r0 | Page 14 left | 9.2.8 | Clarification and alignment of SDL with text may be warranted. | In 9.2.8, replace the sentence "The source STA shall wait ACKTimeout amount of time without receiving an ACK frame before concluding that the MPDU failed." with "The source STA shall wait for an ACKTimeout interval, with a value of aSIFSTime + aSlotTime, without receiving an ACK frame before concluding that the MPDU failed." | Needs Draft Approval | 2004-11-18 | 2004-11-18 | 2004-11-18 | yes 0.5
24 | 03-382r0 | Page 14 right | 9.3.2.1 | Research and Clarification is desired. | wait until Tge completes | closed | n/a | n/a | n/a | n/a | n/a
25 | 03-382r0 | Page 15 | 9.3.2.2 | SDL and text need alignment. | wait until Tge completes | closed | n/a | n/a | n/a | n/a | n/a
26 | Internal Discussion | none | 9.3.2.2 | The special exception for timing of PCF beacon is 9.3.3.2 should be tied to the normal situations. | wait until Tge completes | closed | n/a | n/a | n/a | n/a | n/a
27 | 03-382r0 | Page 20 | 10.3.2.1 | Research and editorial Clarification may be warranted. | Replace 11.1.3.2.2 c) with "Send a probe request to the broadcast destination address, with the SSID, and BSSID from the MLME-SCAN.request primitive" | Needs Draft Approval | n/a | yes | yes 5/11/04 (modified 7/14/04) | yes 0.3
28 | 03-382r0 | Page 21 left | 11.1.2 | Clarification is warranted. | Change "the value of the STA’s TSF timer at the time that the first bit of the timestamp" to "the value of the STA’s TSF timer at the time that data symbol containing the first bit of the timestamp" | Needs Draft Approval | 2004-11-18 | 2005-01-19 | 2005-01-19 | yes 0.6
29 | 03-382r0 | Page 21 right | 11.1.2 | Research required on how the 4us was derrived and is anything required for OFDM? | In the last sentence of 11.1.2, replace "us" with "symbols" and delete "for PHYs of 1 Mb/s, or greater". | Bob
30 | 03-382r0 | Page 22 left | 11.1.2.1 | Research and editorial Clarification may be warranted. | Change "aBeaconPeriod" to "dot11BeaconPeriod" and delete the word "basic" before "medium access". | Needs Draft Approval | n/a | yes | yes 5/13/04 | yes 0.3
31 | 03-382r0 | Page 22 right | 11.1.2.1 | Research and editorial Clarification may be warranted. | Delete "If the medium is determined by the CS mechanism (see 9.2.1) to be unavailable,unavailable, the AP shall delay the actual transmission of a beacon" and combine the remainder of that sentence with the previous sentence. | Needs Draft Approval |  |  |  | yes 0.3
32 | 03-382r0 | Page 23 left | 11.1.2.2 | Perverse interaction with 11.2.2, where ATIM transmission is not clearly specified | rewrite 11.2.2 to clearly specify the rules for ATIM transmission and make them normative. | Withdrawn by Andrew (closed) | n/a | n/a | n/a | n/a | n/a
33 | 03-382r0 | Page 23 right | 11.1.3.2.2 | Text seems clear. |  | Closed | n/a | n/a | n/a | n/a | n/a
34 | 03-382r0 | Page 24 left | 11.2.1.1 | Clarification desired but text is accurate. | In the penultimate paragraph of 11.2.1.1, change "To change Power Management modes, a STA shall inform the AP through a successful frame exchange" to "To change Power Management modes, a STA shall inform the AP through a successful Data frame frame exchange". At the end of that same paragraph of 11.2.1.1, add the following text: "The Power Management bit shall not be set in any management frame." | Needs Draft Approval | n/a | yes | 2004-09-01 | yes 0.4
35 | 03-382r0 | Page 24 right | 11.2.1.5 | Reserarch requried as to what the document specifies in text and/or SDL | Append to the end of the second paragraph of 9.3.2.1: If there are buffered multicast or broadcast frames, the PC shall transmit these prior to any unicast frames. | Needs Assignment |  | no |  | no… editor note asking for text in 0.3
36 | 03-382r0 | Page 25 left | 11.2.1.6 |  | Looks like it was corrected in the 2003 edition | Closed | n/a | n/a | n/a | n/a | n/a
37 | 03-382r0 | Page 25 right | 11.2.1.6 | Clarification Required to state that no back-off required if only one bit set in TIM. | In 11.2.1.6 b): delete "If more than one bit is set in the TIM," | Needs Draft Approval | n/a | yes | yes 5/13/04 | yes 0.3
38 | 03-754r0 |  | 7.3.2.9 | clarification is warranted | Add to 7.3.2.9, at the end of the description of the maximum transmit power level: "As the method of measurement for maximum transmit power level differs by regulatory domain, the value in this field shall be interpreted according to the regulations applicable for the domain identified by the Country String." | Needs Draft Approval | n/a | yes | yes 5/13/04 | yes 0.3
39 | Internal Discussion |  | 10 | Missing primitive in Associate sequence |  | adopt the text in 04/639r1 |  | Yes | yes
40 | Internal Discussion |  | Table 4 (7.2.2) | Clarify columns 1 and 2 with respect to RA and TA. | Text provided in discussion | Needs Draft Approval | Darwin | yes | yes 1/04 | yes 0.1
41 | Internal Discussion |  | 7.2.2 | Validate BSSID on all receive decisions? | No, validate BSSID only on multicast. In 7.2.2, change "originated in the same BSS" to "originated in the BSS to which the station is joined" | Needs Draft Approval | n/a | n/a | yes 5/13/04 | yes 0.3
42 | 03-667r0 |  | 6.2.1.3 | Discuss TGe changes to the primitives | To be dealt with in Tge | closed
43 | Internal Discussion |  | 11.2.1.6 | AP might discard frames before a STA would wake and request them | In 11.2.1.6 a), change "after" to "before". | Needs Draft Approval | n/a | yes | yes 9/13/04 | yes 0.4
44 | 03-382r0 | page 26 left | 11.2.1.6 | PS-Poll priority is not stated in the standard. Text seems clear and describes intended operation where first PS-Poll is sent immediately (after random (0,Cwmin) backoff) and subsequent PS-Polls are sent at discretion of STA. |  | Closed | n/a | n/a | n/a | n/a | n/a
45 | 03-382r0 | page 26 right | 11.2.2 | IBSS power save operation could be clarified with a few notes | Add the following at the end of the first paragraph of 11.2.2.1: "To maintain correct information on the power save state of other stations in an IBSS, a station needs to remain awake. If a station changes to the PS mode, it needs to assume that all other stations are in the PS mode also." | Needs Draft Approval | n/a | yes | 2004-09-01 | yes 0.4
46 | 03-382r0 | page 27 left | 11.2.2.1 | clarification is warranted | see #45 | Closed | n/a | n/a | n/a | n/a | n/a
47 | 03-382r0 | page 27 right | 11.2.2.1 | compare to SDL and clarify | Research of the original draft from 802.11/d5.0 and 802.11/d5.1 shows that aCWminx is a typo from an improper replacement of aCWmax. In 11.2.2.1, replace "aCWminx" with "aCWmin". | Needs Draft Approval | n/a | yes | yes 5/13/04 | yes 0.3
48 | 03-382r0 | page 28 left | 11.2.2.2 | clarification is warranted | In 11.2.2.2, replace "BeaconInterval" with "dot11BeaconPeriod" and append "where ATIMWindow is the value of the ATIM Window parameter of the IBSSParameter Set from the MLME-Start.request or MLME-JOIN.request primitive." | Needs Draft Approval | n/a | yes | yes 5/13/04 | yes 0.3
49 | 03-382r0 | page 29 left | 12.3.5.11.3 | clarification is warranted | In 12.3.5.11.3, delete "error check (HEC) CRC" | Needs Draft Approval | n/a | yes | yes 5/13/04 | yes 0.3
50 | 03-382r0 | page 30 | 17.4.4 table 99 | clarification is warranted | Change value of aPreambleLength from 20us to 16us in the table. | Needs Draft Approval | n/a | yes | 2004-05-01 | yes 0.3
51 | 03-382r0 | page 31 | table G.1 | determine if statement is correct and clarify if needed | Bob to check with Matthew Shoemake on author of annex G. | Needs Assignment
52 | 03-382r0 | page 32 | table g.14 | research and clarify if needed | resolved by interpretation response 01-1104 | closed | n/a | n/a | n/a | n/a
53 | 03-199r0 | row 2 | 7.1.3.3.2 | clarification is warranted | Delete "in the DA field" from 7.1.3.3.2 b) 2). | Needs Draft Approval | n/a | yes | 2004-05-01 | yes 0.3
54 | 03-199r0 | row 3 | 8 | research whether to include a warning on the weakness of WEP | left to TGi | Closed | n/a | n/a | n/a | n/a | n/a
55 | 03-199r0 | row 4 | all | out of scope |  | Closed | n/a | n/a | n/a | n/a | n/a
56 | 03-199r0 | row 5 | 17.1 | editorial removal of "all additions" | not in 2003 edition | Closed | n/a | n/a | n/a | n/a | n/a
57 | 03-199r0 | row 6 | 15.1 | clarification is warranted | In the second sentence, delete "initially" and from "as provided" to the end of the sentence. | Needs Draft Approval | n/a | yes | 2004-05-01 | yes 0.3
58 | 03-199r0 | row 7 | G.3.1 | correct equation | In the equation below Table G.3, change "1<=k<=160" to "1<=k<=159" | Needs Draft Approval | n/a | n/a | 2004-09-13 | yes 0.4
59 | 03-199r0 | row 7 | G.4.5 | correct equation | In the equation G.4.5, change "1<=k<=80" to "1<=k<=79" | Needs Draft Approval | n/a | n/a | 2004-09-13 | yes 0.4
60 | 03-199r0 | row 8 | 15.4.7.9 | correct equation | Replace equations in 15.4.7.9 and 18.4.7.8 with those in 03/199r0 | Needs Draft Approval |  | 2005-01-19 | 2005-01-19 | yes 0.6
61 | 03-199r0 | row 9 | various |  | Handled in the individual documents | closed | n/a | n/a | n/a | n/a | n/a
62 | 03-199r0 | row 10 | 9.3 | STA-STA traffic in BSS needs clarification/correction | In the first paragraph of 9.3 change "a CF-Pollable STA may transmit only one MPDU, which can be to any destination (not just to the PC)," to "a CF-Pollable STA may transmit only one MPDU, which shall be sent to the PC but may have any destination," | Needs Draft Approval | n/a | yes | 2004-09-01 | yes 0.4
63 | 03-199r0 | row 11 | C | "getElem" function correction |  | closed | n/a | n/a | n/a | n/a | n/a
64 | 03-199r0 | row 12 | C |  | Handled in the individual documents | closed | n/a | n/a | n/a | n/a | n/a
65 | 03-199r0 | row 13 | 12 | service primitives are not conformance items, but abstract definitions |  | Closed | n/a | n/a | n/a | n/a | n/a
66 | 03-199r0 | row 14 | 10.3.4 and D | clarification is warranted | Leave the definition as it is. It is clear for the function it describes. | Closed | n/a | n/a | n/a | n/a | n/a
67 | 03-199r0 | row 15 | 9.4 | clarification is warranted | Insert the following as the first sentence of the second paragraph: "A fragment is an MPDU, the payload of which carries all or a portion of an MSDU or MMPDU." Also replace "fragment MPDU" with "fragment" wherever it occurs. | Needs Draft Approval | n/a | yes | 2004-05-01 | yes 0.3
68 | 03-199r0 | row 16 | various | correction required | Replace the "a" prefix with "dot11" before LongRetryLimit in 6.2.1.3.2 b), 9.2.4, and 9.2.5.3. Also before MaxTransmitMSDULifetime in 6.2.1.3.2 h) and 9.4 (twice). Also before FragmentationThreshold in 9.1.4 (four times) and 9.4 (three times). | Needs Draft Approval | n/a | yes | 2004-05-01 | yes 0.3
69 | 03-199r0 | row 17 | various | investigate and clarify if needed | there is differentiation between MIB attributes (prefixed with "dot11") and parameters that are defined in one layer and used in another, e.g. slot time duration, (prefixed with "a") and also to parameters in service primitives (that have no prefix). We believe this is sufficient for the purposes of the standard. | Closed | n/a | n/a | n/a | n/a | n/a
70 | 03-199r0 | row 18 | C | correct variable naming | Change "dot11MultiDomainOperationImplemented" to dot11MultiDomainCapabilityImplemented" on page sta_Start_Ibss_3d(8) and 3201_d\StationConfig(5) and 14.8.2.20 | Needs Draft Approval | n/a | yes | 2004-05-01 | yes 0.3
71 | 02-092r0 |  | 10.3.2.2.2 | clarify what to do when returning BSSDescription Set for PHYs without a parameter set in the frame. | send back channel number stuff was received on | adopt text in 05/209r0 | 2004-07-13 | yes | yes
72 | 02-091r0 | item 1 | 14.8.2.20 | change MIB attribute name | change "operation" to "capability" | Closed (see item 70) | n/a | n/a | n/a | n/a | n/a
73 | 02-091r0 | item 2 | C | change MIB attribute name | change "operation" to "capability" | Closed (see item 70) | n/a | n/a | n/a | n/a | n/a
74 | 02-091r0 | item 3 | C | change "integer" back to "TU" | on page 3201_d\StationConfig(5), change "dot11AuthenticationResponseTimeout Integer nodelay;" to "dot11AuthenticationResponseTimeout TU nodelay;" | Needs Draft Approval | n/a | yes | yes, 9/15/04 | yes 0.4
75 | 02-091r0 | item 4 | C | change "true" to "false" | In 14.8.2.20, change "dot11MultiDomainOperationImplemented" to dot11MultiDomainCapabilityImplemented" and on page 3201_d\StationConfig(5), change "dot11MultiDomainOperationImplemented Boolean = true" to "dot11MultiDomainCapabilityImplemented Boolean = false" | Needs Draft Approval | n/a | yes | yes, 9/15/04 | yes 0.4
76 | 02-091r0 | item 5 | C | delete second definition | not found in current editors roll up | Closed | n/a | n/a | n/a | n/a | n/a
77 | Internal Discussion |  | C | "yBytp" should be "yBtyp" | On pages sta_Start_Ibss_3d(8) and ap_Start_Bss_2c(3), replace "yBytp" with "yBtp" in the decision symbol. | Needs Draft Approval | n/a | yes | yes, 9/15/04 | yes 0.4
78 | Internal Discussion |  | C | on same page as 77, change multidomainoperation to multidomaincpability |  | Closed (see item 70) | n/a | n/a | n/a | n/a | n/a
79 | 02-091r0 | item 6 | C | described operation is as intended, IBSS of 802.11d capable device shall not be started without valid information and being enabled |  | Closed | n/a | n/a | n/a | n/a | n/a
80 | 02-091r0 | item 7 | C | correct "enabled" to be "implemented" | See resolution to item 82 | closed | n/a | n/a | n/a | n/a | n/a
81 | 02-091r0 | item 8 | C | no clarification needed |  | Closed | n/a | n/a | n/a | n/a | n/a
82 | internal discussion |  | C | In AP_Start_Bss_2c, attribute name is incorrect | In AP_Start_Bss_2c, change "operation" to "capability" | Needs Draft Approval | n/a | yes | yes, 9/15/04 | yes 0.4
83 | 02-091r0 | item 9 | C | described operation is as intended, BSS of 802.11d capable device shall not be started without valid information and being enabled |  | Closed | n/a | n/a | n/a | n/a | n/a
84 | 02-091r0 | item 10 | D | The MIB attribute was misspelled in the instruction. The document has the correct spelling. | In 11.1.3.4, change dot11RegDomainsSupportEntry to dot11RegDomainsSupportedValue and add the value "Other (0)" to the "INTEGER SYNTAX" line for dot11RegDomainsSupportedValue. | Needs Draft Approval | n/a | yes | 2004-05-01 | yes 0.3
85 | 02-091r0 | item 11 | D and 11.1.3.4 | needs investigation, looks like description in MIB is incorrect. The values listed in the MIB entry should be in the "value" part of the table. "Other" needs to be added to the enumeration in the value entry. | Insert "and the dot11RegDomainsSupportEntry shall be set to Other" at the end of the sentence beginning "If the dot11MultiDomainCapabilityEnabled attribute is true". See item 84 and 86 for complete resolution. | Needs Draft Approval | n/a | yes | 2004-05-01 | yes 0.3
86 | 02-091r0 | item 12 | 11.1.3.4 and others | clarification is warranted, what is "adopt" | Use 04/425r1 as a template for modifying 11.1.3.4. | Needs Draft Approval | 2004-07-15 | no | n/a | yes 0.4
87 | 02-091r0 | item 13 | C | correct cross reference to 7.3.2.12 on page AP_TSF_bss_3 | On page ap_TSF_bss_3c(3), replace "7.3.2.14" with "7.3.2.12" | Needs Draft Approval | n/a | yes | 2004-09-01 | yes 0.4
88 | Internal Discussion |  | 7.3.2.x | 802.11d numbered IEs up to 15, but only 12 are in the 2003 edition. Investigate. | All IEs from 802.11d are incorporated into the 2003 edition | Closed | n/a | n/a | n/a | n/a | n/a
89 | 02-091r0 | item 14 | C | need to add requested information elements to probe response process | Close without change to the document | Closed | n/a | n/a | n/a | n/a | n/a
90 | 02-093r0 | item 1 | 7 | no clarification needed |  | Closed | n/a | n/a | n/a | n/a | n/a
91 | 02093r0 | item 2 | 17.3.8.3.2 | caught by editor in roll-up |  | Closed | n/a | n/a | n/a | n/a | n/a
92 | SDL bugs | item 1 | C | On sta_join_4, correct "start" to "confirm" | On page sta_join_4, change "MLMEStart.confirm" to "MLMEJoin.confirm" | Needs Draft Approval | n/a | yes | yes, 9/15/04 | yes 0.4
93 | SDL bugs | item 2 | C | investigate and clarify if needed | investigated and comment is correct. Probe Request seems to be passed to the DS in the AP SDL. | adopt text in 05/209r0 | 2004-07-13 | yes | yes
94 | SDL bugs | item 3 | C | investigate and clarify if needed |  | Closed | n/a | n/a | n/a | n/a | n/a
95 | SDL bugs | item 4 | C | investigate and clarify if needed |  | Closed | n/a | n/a | n/a | n/a | n/a
96 | SDL bugs | item 5 | C | investigate and clarify if needed |  | Closed | n/a | n/a | n/a | n/a | n/a
97 | SDL bugs | item 6 | C | investigate and clarify if needed |  | Closed | n/a | n/a | n/a | n/a | n/a
98 | SDL bugs | item 7 | C | investigate and clarify if needed |  | Closed | n/a | n/a | n/a | n/a | n/a
99 | SDL bugs | item 8 | tables 2 and 22 | conflicting STA to STA in BSS | In Table 29, delete the row containing "CF-Poll(no data){+CF-Ack} – Data(dir) – ACK" | Needs Draft Approval | n/a | yes | 2004-09-01 | yes 0.4
100 | PICS | internal discussion | PICS | "d" PICS is screwy |  | Simon Black | 2005-03-14
101 | Interp req | 04/425r1 | 11.1.4 | adoption of "all parameters" is unclear | Use 04/425r1 as a template for modifying 11.1.4. (See also item 86) | Needs Draft Approval | n/a | yes | 2004-09-01 | yes 0.4
102 | internal | 04/522r1 | 7.3, 7.2 | addition of vendor-specific IE | Adopt 04/522 test changes | Needs Draft Approval | Bob | yes | yes 5/11/04 | yes 0.4
103 | Richard P |  | 802.11d | country-independent country code, must be orthogonal to ISO 3166, for use in trains, planes, and ships, etc. | Adopt document 04/982 | Needs Draft Approval | n/a | yes (04/982) | yes 9/13/04 | yes 0.4
104 | Peter E | 802.11h MIB | 802.11h | dot11SMTbase3 does not have dot11SpectrumManagementImplemented nor dot11SpectrumManagementRequired |  | Needs Assignment
105 | Peter E | 802.11h MIB | 802.11h | dot11SpectrumManagement is missing from the Compliance Statements optional groups |  | Needs Assignment
106 | TGk | Table 66, clause 15 |  | Column 3 of table has paste error, putting "1, 2 Mbps" in rowas it does not belong | TX_Power is Level1-4, antenna is 1-256, RSSI is 0-255, SQ is 0-255 | Needs Draft Approval | 2004-11-18 | n/a | n/a | yes 0.5
107 |  | internal discussion | 11.2.2 | aATIMwindow should be dot11ATIMwindow |  | Needs Draft Approval | n/a | n/a | yes 5/13/04 | yes 0.3
108 |  | internal discussion | 10.3.3.1.2, 10.3.3.1.4 | change the "BSSDescription" as a parameter name to remove ambiguity. | In 10.3.3.1.2 and 10.3.3.1.4, change "BSSDescription" in all locations, except the Type column and the first occurrence in the Description column, to "SelectedBSS". | Needs Draft Approval | n/a | n/a | yes 5/13/04 | yes 0.3
109 |  | internal discussion | 7.3 | need status code for "ListenInterval too large" | Add a row to Table 20, placing the next available value in the "Status Code" column and "Association denied because the ListenInterval is too large" in the "Meaning" column. | Needs Draft Approval | n/a | yes | 2004-09-01 | yes 0.4
110 |  | internal discussion | 802.11-2003 figure 128 | This receive diagram indicates "PHY_TXEND" | Above the two bold arrows at the upper right of this figure, attach PHY_TXEND.request and PHY_TXEND.confirm, respectively. Also, replace "number supplied in the DSSS PHY preamble" with "number supplied in the TXVECTOR" in the second paragraph below the figure. | Needs Draft Approval | n/a | yes | 2004-09-01 | yes 0.4
111 | D | internal discussion | Annex D | the default values for dot11AuthenticationAlgorithmsEnable is incorrect | In the description of dot11AuthenticationAlgorithmsEnable in the MIB, replace "The default value of this attribute shall be 1 for the Open System table entry and 2 for all other table entries." with "The default value of this attribute shall be true when the value of dot11AuthenticationAlgorithm is Open System and false otherwise." | Needs Draft Approval | n/a | yes | 2004-09-01 | yes 0.4
112 |  | internal discussion |  | a note that describes the naming convention used ("a", "dot11", and none) to differentiate various objects might be nice to include. Where? | Close without change to the document | Closed | n/a | n/a | n/a | n/a | n/a
113 |  | internal discussion | 9.2.10 | use of rates/units and equation for EIFS (at least) are in need of work | Change "bits" to "microseconds" in Table 121 in clause 8.3.3 to make this consistent with all other uses. Also change "aPLCPHeaderLngth" to aPLCPHeaderLength" in all occurrences. In clause 9.2.10, replace "at 1Mbit/s" with "at the lowest Basic Rate". Replace the equation with "EIFS=aSIFSTime+DIFS+ACKTxTime, where ACKTxTime is equal to the time, in microseconds to transmit an ACK frame, including preamble, PLCP header and any additional PHY dependent information, at the lowest PHY mandatory rate." | Needs Draft Approval |  | 2005-01-19 | 2005-01-19 | yes 0.6
114 | Srini | internal discussion | 11.3.something | check on use of primitives and MAC driving association | Closed with same action as item 41. | Closed | n/a | n/a | n/a | n/a | n/a
115 | Mike Moreton | 04/985 | 9.6 | clarifications to the new text introduced to section 9.6 Multirate Support by 802.11g | Adopt 04/985 text changes | Needs Draft Approval | n/a | yes | 2004-09-01 | yes 0.4
116 | WG | 11-04/1454 | Table G.17 | Interpretation request requests that the FCS value in Table G.17 be calculated correctly. | The adopted interpretation response is in 11-04/1545. The full analysis is in 11-04/1198. Modify bits 818 and 320 of Table G.17 to 1. | Needs Draft Approval | 2004-11-18 | 2004-11-18 | 2004-11-18 | yes 0.5
117 | Kevin Hayes | email of 1/18/2005 | 802.11i clause 8.5.2 | "MIC of the EAPOL-Key frames, from and including the EAPOL protocol version" in 11iD10 was changed to "MIC of the EAPOL-Key frames, from and including the Key Descriptor Version field (of the Key Information field)" in the published standard. | This is a significant issue. Reverse the change. Issue an errata. | Needs Draft Approval |  | 2005-01-19 | 2005-01-19 | yes 0.6
118 | Interpretation Response. | 05/1648 | 15.2.3.4 | A PHY implementing clause 19 shall set bit B2 in the Service field, as required by 19.3.2.1 in all transmissions. A PHY implementing clause 15 that is dependent upon a particular value in a reserved field for its correct operation is not compliant with the standard. All implementations must ignore values of reserved fields upon reception. | The editor of the standard will be instructed to remove the sentence “The value of X'00' signifies IEEE 802.11(r) device compliance.” from clause 15.2.3.4. | Needs Draft Approval |  |  |  | yes 0.6
119 | Mike Moreton | email of 2/10/2005 | 5.7.1 & 5.7.2 | Only places that refer to ESS ID. | Given that they are not defined anywhere, I think both should be replaced by SSID. | Needs Draft Approval |  |  |  | yes 0.6
[5 empty] | Completion percentage: | 93.16%

## References
References: