## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-05/0853r7
Venue Date: | September 2005
First Author: | Clint Chaplin, TGr Chair
Subject: | To-Do List
Full Date: | 2005-09-18
Author(s): | Clint Chaplin
Symbol Technologies
6480 Via Del Oro, San Jose, CA 95119-1208
Phone: +1-408-528-2766
Fax:
email: clint.chaplin@gmail.com
Abstract:
To-Do List of Draft
Notice: This document has been prepared to assist IEEE 802.11. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor grants a free, irrevocable license to the IEEE to incorporate material contained in this contribution, and any modifications thereof, in the creation of an IEEE Standards publication; to copyright in the IEEE’s name any IEEE Standards publication even though it may include portions of this contribution; and at the IEEE’s sole discretion to permit others to reproduce in whole or in part the resulting IEEE Standards publication. The contributor also acknowledges and accepts that this contribution may be made public by IEEE 802.11.
Patent Policy and Procedures: The contributor is familiar with the IEEE 802 Patent Policy and Procedures <http:// ieee802.org/guides/bylaws/sb-bylaws.pdf>, including the statement "IEEE standards may include the known use of patent(s), including patent applications, provided the IEEE receives assurance from the patent holder or applicant with respect to patents essential for compliance with both mandatory and optional portions of the standard." Early disclosure to the Working Group of patent information that might be relevant to the standard is essential to reduce the possibility for delays in the development process and increase the likelihood that the draft publication will be approved for publication. Please notify the Chair <stuart.kerry@philips.com> as early as possible, in written or electronic form, if patented technology (or technology under patent application) might be incorporated into a draft standard being developed within the IEEE 802.11 Working Group. If you have questions, contact the IEEE Patent Committee Administrator at <patcom@ieee.org>.

## To-Do List
Title | Description | Action | People | Status
5.8: definition of RRSAP in architecture. |  |  | Michael
- 7.2.3.1 Beacon changes |  | 11-05-0956-00-000r-miscellaneous-updates.ppt |  | Accepted
- 7.2.3.4/7.2.3.5 Association Request/Association Response changes |  |  | Bill | Done
- 7.2.3.9 Probe response |  | 11-05-0956-00-000r-miscellaneous-updates.ppt |  | Accepted
- 7.3.1.9(and elsewhere) Status code for "come back later" |  | Not needed?
- 7.3.2.42 Key Holder IE |  | 11-05-0875-01-000r-Key-Holder-IE-Text | Kapil (with Bill) | Accepted
- 8.5A.4 PMK-R0 derivation from PSK |  | Remove PSK support? Develop presentation for Garden Grove listing three alternatives. 11-05-0884-00-000r-PSK-Treatment-In-Fast-Transition | Kapil, Nancy | Text in November
- 8.5A.9 State machine definition for Fast BSS Transition (FBT) Authentication message sequence
- 8A.1 intro text for section 8A.1 |  | 11-05-858 | Jon | Accepted
- 8A.2 explanatory text needed for differences in First Contact 4-way handshake |  | 11-05-0956-00-000r-miscellaneous-updates.ppt |  | Accepted
- 8A.6(or 11.7?) Broker function |  | 11-05-0672-04-000r-resource-request-response-description.doc | Michael | Accepted
- 11.3 MLME procedures for Authentication |  |  | Bill Marshall | Accepted
- 11.4 MLME procedures for (Re)-Association |  |  | Bill Marshall | Accepted
- 11.7(or 8A.6?) Broker function |  | 11-05-0672-04-000r-resource-request-response-description.doc | Michael | Accepted
- Annex A PICS |  | Text in November | Michael
- Annex D MIB |  |  | Frank Ciotti, Nancy Cam-Winget
Mobility Domain definition; 704r0, TGs, TGu Collapse into single domain? |  | 11-05-0866-01-000r-mobility-domain-definition-and-description.ppt 11-05-0867-00-000r-mobility-domain-definition-and-description.doc | Michael, Kapil, Jon | Accepted
Over the air vs. over the DS reservations: 11-05-0201, 11-05-0672 |  | 11-05-0819-00-000r-over-air-reservation.ppt | Kapil, Jesse, Mike, Bob | Keep over the Air, keep mandatory
Source address field in authentication frames |  | 11-05-0860-00-000r-FT-Authentication-Sequence-Fixes | Kapil | Accepted
"Target AP" vs. "Target address" |  | 11-05-0860-00-000r-FT-Authentication-Sequence-Fixes | Kapil | Accepted
Replay counters; same as 11i (start on message 3?) |  | Security Analysis of early replay counter use | Jesse, Nancy
Figure 121c: dotted box signifying co-located elements |  | Figure no longer exists
Length of timing | 16 vs. 32 bits, milliseconds vs. seconds (reservation time and key lifetime; possible comeback time) | Explicit 16 bit times in standard within descriptions 11-05-0928-00-000r-time-interval-ie.ppt | Nancy | Accepted
Extended Capability IE: needed? |  | Not needed
Define DS protocol? |  | Ethertype | Michael | Accepted
Domain Advertisement | Replacement of ESSID; use separate IE for mobility domain. | Combine TRIE and TSIE domain info into separate mobility domain IE 11-05-0903-00-000r-TRIE-TSIE-Integration-FTIE 11-05-0900-00-000r-TRIE-TSIE-Integration-FTIE-text | Kapil, Michael | Accepted
11-05-0858 Issue list | List of issues against D0.05; all editorial and non-controversial? |  | William | Accepted
State machine modifications | Collapse two states into one |  | Jon Edney, Kapil Sood
Key0-Name static while Key0 is not | Key lifetime is really key SA lifetime |  | Kapil Sood
PSK | Remove support for PSK? | 11-05-0884-00-000r-psk-treatment-in-fast-transition.ppt | Kapil Sood | Text in November
Explicit text for when key lifetime begins |  |  | Nancy Cam-Winget
Clean up Section Q |  |  | Michael Montemurro, Kapil Sood | Section Removed
8.5A.8 | Clarify who the "AP" is |  | Nancy Cam-Winget
Only a single key lifetime currently (PTK lifetime), do we need two lifetimes (PMK and PTK-SA)?
Currently, if R1 expires, implication is that the entire key heierarchy expires. Do we want to state this explicitly in the draft?
Reassociate to same AP; implications? | Currently has to be Fast Transition (see next to-do) Could we reuse the same PTK if it's key lifetime has not expired? Use message 3 and 4 with the replay counter?
Fast Transition to same AP; implications? | Currently, has to break the data connection during a Fast Transition to the same AP; this is a problem.
How could the station know the AP has been compromised? |  |  | Kapil Sood
Generate text to extend neighbor report of TGk to add TGr useful information |  |  | Kapil Sood

## References
References: