## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-05/0963r5
Venue Date: | September 2005
First Author: | Paul Gray (AirWave)
Subject: | LB73 Comment Spreadsheet
Full Date: | 2005-09-20
Author(s): | Paul Gray
AirWave Wireless, Inc.
1700 S. El Camino Real
Phone: 650-286-6107
Fax: 650-286-6101
email: paul@airwave.com
Abstract:
The spreadsheet contains MIB comment resolutions.
Notice: This document has been prepared to assist IEEE 802.11. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor grants a free, irrevocable license to the IEEE to incorporate material contained in this contribution, and any modifications thereof, in the creation of an IEEE Standards publication; to copyright in the IEEE’s name any IEEE Standards publication even though it may include portions of this contribution; and at the IEEE’s sole discretion to permit others to reproduce in whole or in part the resulting IEEE Standards publication. The contributor also acknowledges and accepts that this contribution may be made public by IEEE 802.11.
Patent Policy and Procedures: The contributor is familiar with the IEEE 802 Patent Policy and Procedures <http:// ieee802.org/guides/bylaws/sb-bylaws.pdf>, including the statement "IEEE standards may include the known use of patent(s), including patent applications, provided the IEEE receives assurance from the patent holder or applicant with respect to patents essential for compliance with both mandatory and optional portions of the standard." Early disclosure to the Working Group of patent information that might be relevant to the standard is essential to reduce the possibility for delays in the development process and increase the likelihood that the draft publication will be approved for publication. Please notify the Chair <stuart.kerry@philips.com> as early as possible, in written or electronic form, if patented technology (or technology under patent application) might be incorporated into a draft standard being developed within the IEEE 802.11 Working Group. If you have questions, contact the IEEE Patent Committee Administrator at <patcom@ieee.org>.

## Master
ID | Commenter | Clause | T or E | Part of a "No" Vote | Comment | Suggested Remedy | Resolution | Comment Resolution | Same As | Comment Status | Edit Status | Notes | History | Assigned To | Category | Subcategory
90 | Estrada | Annex D | E | Y | Page 83, line 49 contains an unresolved reference | Correct the unresolved reference | Accepted | Resolved in 05/0245r2 | 1556 |  |  | 438r0 - text 437r0 - xls |  | Kwak | Editorial
91 | Estrada | Annex D | E | Y | Page 84, line 13 contains an unresolved reference | Correct the unresolved reference | Accepted | Resolved in 05/0245r2 | 1556 |  |  | 438r0 - text 437r0 - xls |  |  | Editorial
345 | Malinen | Annex D | E | N | Complex description of what is included in dot11BeaconRprtReceivedElements. This LB71 comment was deferred. | Change "All fields, except Timestamp, Beacon interval and Capability Information" with "All information elements". Similar change was already done in text portion of beacon report. | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB | Conditional
354 | Malinen | Annex D | E | N | Reference source not found errors. | Fix references on page 83, line 49 and page 84, line 13. | Accepted | Resolved in 05/0245r2 | 1556 |  |  | 438r0 - text 437r0 - xls |  |  | Editorial
356 | Malinen | Annex D | E | N | Incorrect references. | Fix references ("TGk spec" and " ", should be "IEEE 802.11k"). | Accepted | Resolved in 05/0245r2 | [5 empty] | Gray | Editorial
357 | Malinen | Annex D | E | N | One dot11peer to dot11Peer change missed. | Use upper case P in "Peer" for dot11PeerWEPICVErrorCount on page 113, line 50. | Accepted | Resolved in 05/0245r2 | 357 |  |  |  |  | Gray | Editorial
494 | Gray | Annex D | E | N | “UNITS” declaration should be immediately under “SYNTAX” declaration | Move “UNITS” declaration immediately under “SYNTAX” declaration | Accepted | Resolved in 05/0245r2 | [5 empty] | Gray | Editorial
495 | Gray | Annex D | E | N | P104 L25 "max-accessible" is not valid | Change "max-accessible" to "not-accessible" | Accepted | Resolved in 05/0245r2 | [5 empty] | Gray | Editorial
496 | Gray | Annex D | E | N | P108 L66 ":=" should be "::=" | Change ":=" to "::=" | Accepted | Resolved in 05/0245r2 | [5 empty] | Gray | Editorial
497 | Gray | Annex D | E | N | P108 L75 ":=" should be "::=" | Change ":=" to "::=" | Accepted | Resolved in 05/0245r2 | [5 empty] | Gray | Editorial
498 | Gray | Annex D | E | N | P109 L45 ":=" should be "::=" | Change ":=" to "::=" | Accepted | Resolved in 05/0245r2 | [5 empty] | Gray | Editorial
499 | Gray | Annex D | E | N | P80 L23 "det11LCIRqstOctet" is incorrect | Change "det11LCIRqstOctet" to dot11LCIRqstOctet | Accepted | Resolved in 05/0245r2 | 499 |  |  |  |  | Gray | Editorial
500 | Gray | Annex D | E | N | P104 L21 dot11LCIDatum is incorrectly defined as "Integer32" in sequence - it should be changed to "INTEGER" | P104 L21 change "Integer32" to "INTEGER" | Accepted | Resolved in 05/0245r2 | [5 empty] | Gray | Editorial
501 | Gray | Annex D | E | N | P110 L64 dot11PeerStatsTableIBSSageing is misspelled | Change "dot11PeerStatsTableIBSSageing" to "dot11PeerStatsTableIBSSaging" | Accepted | Resolved in 05/0245r2 | [5 empty] | Gray | Editorial
502 | Gray | Annex D | E | N | P113 L50 dot11peerWEPICVErrorCount is not properly capitalized | Change "dot11peerWEPICVErrorCount" to "dot11PeerWEPICVErrorCount" | Accepted | Resolved in 05/0245r2 | 357 | [5 empty] | Editorial
503 | Gray | Annex D | E | N | P115 L7 dot11ChannelLoadRprtChannelLoad is missing "," in compliance statement | Add "," to dot11ChannelLoadRprtChannelLoad in compliance statement | Accepted | Resolved in 05/0245r2 | [5 empty] | Gray | Editorial
521 | Wang, Stephan | Annex D | E | N | On page 109, dot11NeighborReportNeighborTBTTOffset should be renamed as dot11NeighborReportNeighborTSFInfo | Change it accordingly. | Accepted | Resolved in 05/0245r2 |  |  |  | Comment resolved in the Seattle 3 Ad Hoc on 9/14/05 |  | Gray | MIB
1081 | Amman | Annex D | E | Y | Page 89, line 29: Grammar. | Remove the word "the" following the phrase "…number on which". This particular issue occurs several times within Annex D, and should be corrected in all cases (cut and paste error!). | Accepted | Resolved in 05/0245r2 | [5 empty] | Gray | MIB
1082 | Amman | Annex D | E | Y | Page 89, line 40: Sentence structure. | Remove the comma (",") following the phrase "…the frequency band". This particular issue occurs several times within Annex D, and should be corrected in all cases (cut and paste error!). | Accepted | Resolved in 05/0245r2 | [5 empty] | Gray | MIB
1220 | Black | Annex D | E | N | P80, L23: det11LCIRqstOctet = dot11LCIRqstOctet | Fix editorial | Accepted | Resolved in 05/0245r2 | 499 | [5 empty] | MIB
1221 | Black | Annex D | E | N | P80, L57: formating issue in dot11RRMRqstToken | Fix editorial | Accepted | Resolved in 05/0245r2 |  |  |  | Remove the hanging line in the description |  |  | MIB
1226 | Black | Annex D | E | N | P83, L21: Should be measurement mode, not scan mode. | Fix | Accepted | Resolved in 05/0245r2 | [5 empty] | Gray | MIB
1281 | Olson | Annex D | E | N | In dot11RRMRequestTable we should either preface all items in the table with RRM or none of the items. | Either remove RRM from each item in the table or update the medium sense elements to include RRM. | Accepted | All elements are now prefaced with RRMRqst |  |  |  | With removal of HiddenSTA and MedSense the elements remaining are dot11STAStatRqstGroupIDdot11LCIRqstOctet |  | Gray | MIB | Non Standard Elements dot11STAStatRqstGroupID dot11LCIRqstOctet dot11TransmitQoSMetricsPeerQSTAAddres dot11TransmitQoSMetricsTrafficIdentifier dot11TransmitQoSMetricsBin0Range
1284 | Olson | Annex D | E | N | There is typo in the definition of dot11LCIRqstOctet. | Change from "det11LCIRqstOctet" to "dot11LCIRqstOctet". | Accepted | Resolved in 05/0245r2 | 499 | [5 empty] | Editorial
1287 | Olson | Annex D | E | N | dot11RRMRqstChanNumber description should indicate to also ignore the channel number for the LCI Request and the Measurement Pause. | Add required text. | Accepted | Resolved in 05/0245r2 |  |  |  | Replace 2nd sentence of description with "This attribute is ignored if dot11RRMRequestType = 5 (STA Statistics Request), 6 (LCI Request), or 255 (Measurement Pause)." |  |  | Location
1288 | Olson | Annex D | E | N | dot11RRMRqstRegulatoryClass description should indicate to also ignore the regulatory class for the LCI Request and the Measurement Pause. | Add required text. | Accepted | Resolved in 05/0245r2 |  |  |  | Replace 2nd sentence of description with "This attribute is ignored if dot11RRMRequestType = 5 (STA Statistics Request), 6 (LCI Request), or 255 (Measurement Pause)." |  |  | Location
1289 | Olson | Annex D | E | N | dot11RRMRqstRndInterval description should indicate to also ignore the random interval for the LCI Request and the Measurement Pause. | Add required text. | Accepted | Resolved in 05/0245r2 |  |  |  | Replace 2nd sentence of description with "This attribute is ignored if dot11RRMRequestType = 5 (STA Statistics Request), 6 (LCI Request), or 255 (Measurement Pause)." |  |  | Location
1290 | Olson | Annex D | E | N | In dot11RRMBeaconRqstMode the description text should use Measurement Mode instead of Scan Mode. | Replace "Scan" with "Measurement". | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB
1299 | Olson | Annex D p88 l22 | E | N | The word report is missing an "s". | Add the "s". | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB
1300 | Olson | Annex D p88 l65 | E | N | The text should read "Noise Histogram" instead of Beacon Request. | Replace with Noise Histogram. | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB
1301 | Olson | Annex D p90 l75 | E | N | The word report is missing an "s". | Add the "s". | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB
1302 | Olson | Annex D p94 l64 | E | N | The text should read "Frame Report" instead of Frame Request. | Replace with Frame Report. | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB
1303 | Olson | Annex D p95 l50 | E | N | The text should read "Frame Report" instead of Beacon Report. | Replace with Frame Report. | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB
1304 | Olson | Annex D p96 l64 | E | N | The text should read "Hidden Station Report" instead of Beacon Request. | Replace with Hidden Station Report. | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB
1305 | Olson | Annex D p108 l6 | E | N | dot11RRMNeighborReportRSN should be named to match the corresponding field. | Change to dot11RRMNeighborReportSecurity. | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB
1308 | Olson | Annex D p108 l59 | E | N | dot11RRMNeighborReportRSN should be named to match the corresponding field. | Change to dot11RRMNeighborReportSecurity. | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB
1554 | Kwak | Annex D | E | N | GET and SET as operators should be all caps. | P78L13: Change "set" to "SET", in all places P78L16: Change "get" to "GET", in al places. | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB
1078 | Amman | Annex D | E | Y | Page 83, line 60: Grammar. | Replace the word "Periods" with "Period". | Counter | dot11RRMRqstMeasurementPeriod was removed from draft | [5 empty] | Gray | MIB
1283 | Olson | Annex D | E | N | dot11MedSenseRCPIThreshold does not match the textual description of this measurement. We should either change the text to RCPI or the MIB to RPI. | Change to dot11MedSenseRPIThreshold. | Counter | MedSense has been deleted from the draft. |  |  |  | Joe changed to ReceivedPower instead of RPI |  | Gray | MIB
1296 | Olson | Annex D p85 | E | N | Change references to RCPI to RPI to be consistent with the text that describes this measurement. | Make the change in dot11MedSenseType and dot11MedSenseRCPIThreshold | Counter | MedSense has been deleted from the draft. |  |  |  | SF2 Spreadsheet 05/686r0 |  | Kwak | RPI
315 | Oakes | Annex D | E | N | dot11RRMRequestTable, RFC 2579 referenced | Add to list (section 2) | Declined | RFC 2579 is not a normative reference and is used for informational purposes only | [6 empty] | Editorial
1084 | Amman | Annex D | E | Y | Page 94, line 72: The description provided for the MIB parameter dot11FrameRprtIfIndex is incomplete. | Correct this description. | Declined | Is identical to every other RprtIfIndex defined. Provide normative text | [6 empty] | MIB
141 | Jokela | Annex D | T | Y | Page 83. dot11RRMRqstMeasurementPeriod is not used anymore. | Remove | Accepted |  | 1556 | [5 empty] | Periodic
142 | Jokela | Annex D | T | Y | Page 84. dot11RRMRqstMeasIntervalUnit is not used anymore | Remove | Accepted |  | 1556 | [5 empty] | Periodic
143 | Jokela | Annex D | T | Y | Page 84. dot11RRMRqstMeasurementInterval is not used anymore | Remove | Accepted |  | 1556 | [5 empty] | Periodic
144 | Jokela | Annex D | T | Y | Page 91. dot11BeaconReportEntry shall be made consistent with the definition in 7.3.2.22.6. dot11BeaconRprtCFStatus, dot11BeaconRprtPrivacy and dot11BeaconRprtBSSMode shall be removed and dot11BeaconRprtCababilityInformation shall be added. | Modify. | Accepted | Resolved in 05/0245r2 |  |  |  | Simon made a presentation 948r0 |  | Gray | MIB
355 | Malinen | Annex D | T | Y | dot11BeaconRprtReceivedElements is limited to 100 octets. Is this long enough for all possible Beacon frames? If not, what will be done with the extra information? | Clarify possible truncation procedure or use a larger upper limit for the size of dot11BeaconRprtReceivedElements. | Accepted | Resolved in 05/0245r2 | 852 |  |  | Increased to 512 per Simon Barber recommendation |  |  | MIB | Misc
467 | Qi | Annex D | T | Y | P111 802.11k draft 2.0 lacks measurements or statistics which can capture the quality of service for Voice or Video traffics. 11e provides different access priorities for different traffic categories. 11e draft amendment contains a number of MIB counters relating to QoS operation (e.g. dot11QoSCounters). 11k should extend dot11PeerStatsTable to support the counters which are defined in dot11QoScounters. | Commenter will submit paper to support this | Accepted | The issue is addressed by 05/1635r4. Instruct the editor to incorporate normative text in 05/1635r4. - The document is 1637r4 | 467 |  |  | Invalid Document |  |  | QoS
630 | Myles | Annex D | T | Y | dot11ApChannelReportIfIndex object cannot be "MAX-ACCESS read-create" because the table does not include an object of type RowStatus and other objects in the table have MAX-ACCESS read-write. | Make one object read-create, and all objects in the table other than the index read-create. | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB | I think Myles meant one object read-only and the others read-create.
631 | Myles | Annex D | T | Y | dot11RRMNeighborReportEntry 4 to 11 objects, all cannot be "read-write" | Make objects "read-create" | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB
632 | Myles | Annex D | T | Y | A TEXTUAL-CONVENTION (enumerate data type) should be defined for "twoPointFourGHz" and "fiveGHz" | As in comment | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB
633 | Myles | Annex D | T | Y | dot11PeerAddress must be "MAX-ACCESS not-accessible" as it is a index for the table | As in comment | Accepted | [7 empty] | MIB
661 | Balachander | Annex D | T | Y | Medium sensing histograms as specified in the 11k draft is too complicated. | Remove it and any references in the MIB to this type of measurement | Accepted | Resolved in 05/0245r2 |  |  |  | Group voted to remove MedSense |  | Gray | MIB
852 | Barber | Annex D | T | Y | The beacon report received elements in the MIB is too short | increase length to 512 minimum | Accepted | Resolved in 05/0245r2 |  |  |  | Increased to 512 |  |  | MIB | Misc
856 | Barber | Annex D | T | Y | dot11PeerStatsTableBSSaging has no default value | suggest 300 | Accepted | Resolved in 05/0245r2 |  |  |  | SF2 - suggested 300 |  |  | Misc
857 | Barber | Annex D | T | Y | dot11PeerStatsTableIBSSaging has no default value | suggest 300 | Accepted | Resolved in 05/0245r2 |  |  |  | SF2 - suggested 300 |  |  | Misc
1077 | Amman | Annex D | T | Y | Page 83, line 49: The text contains the statement "Error! Reference source not found". | Correct the unrecognized reference. | Accepted | Resolved in 05/0245r2 | 1556 |  |  |  |  | Kwak | Periodic
1079 | Amman | Annex D | T | Y | Page 84, line 13: The text contains the statement "Error! Reference source not found". | Correct the unrecognized reference. | Accepted | Resolved in 05/0245r2 | 1556 |  |  |  |  | Kwak | Periodic
1083 | Amman | Annex D | T | Y | Page 93, lines 35-48: The MIB parameter dot11BeaconRprtCFStatus provides information related to the capabilities supported in the AP, however the capabilities field in the Neighbor Report (figure k25) does not have any way to report this information. | Either update the Neighbor Report capabilities field to reflect this information, or remove this MIB parameter. | Accepted | It was removed from the draft | [6 empty] | MIB
1222 | Black | Annex D | T | Y | P81, L10: dot11RRMRqstType is missing Measurement Pause and LCI Request | Add measurement requests that have recently been added. | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB
1223 | Black | Annex D | T | Y | P82, L12: Duration is per request element not frame. | Fix. | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB
1224 | Black | Annex D | T | Y | P82, L59: Request control is per element not frame. | Fix | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB
1225 | Black | Annex D | T | Y | P82, L70: Report control is per element not frame. | Fix. | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB
1227 | Black | Annex D | T | Y | P83, L38 and elsewhere: Remove old periodic measurement related MIB attributes and add new attributes for repeated measurement frames. | Fix. | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB
1228 | Black | Annex D | T | Y | P88, L58 and P89, L66: Noise Histogram now has 9 bins, not 8. | Add new attribute for new bin and fix table. | Accepted | Resolved in 05/0245r2 |  |  |  | Added new sequence and definition |  |  | MIB
1280 | Olson | Annex D | T | Y | dot11RRMRequestTable needs to be updated to handle repeated measurements that have been added at the Measurement Request frame level. This may require some restructuring of how the MIB handles measurement requests. | Fix it. | Accepted | Resolved in 05/0245r2 | 1555 |  |  | Resolved in 438r0 - Joe Kwak |  |  | Periodic
1282 | Olson | Annex D | T | Y | In dot11RRMRequestTable remove the references to the old periodic measurements. | Strike the lines with the following elements: dot11RRMRqstMeasPeriodUnit, dot11RRMRqstMeasurementPeriod, dot11RRMRqstMeasIntervalUnit, and dot11RRMRqstMeasurementInterval. | Accepted | Resolved in 05/0245r2 | 1556 | [5 empty] | Periodic
1285 | Olson | Annex D | T | Y | dot11RRMRequestTable is missing entries for the new Measurement Pause. | Add the following entries: dot11RRMPauseTimeUnits and dot11RRMPauseTime. | Accepted | Resolved in 05/0245r2 | 1555 | [5 empty] | Periodic
1286 | Olson | Annex D | T | Y | dot11RRMRqstType is missing type for the LCI Request and the Measurement Pause. | Add the following entries: lciRequest(10) and measurementPause(11). | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB
1291 | Olson | Annex D p83 l38 | T | Y | No more periodic measurements so remove dot11RRMRqstMeasPeriodUnit. | Remove section. | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB
1292 | Olson | Annex D p83 l53 | T | Y | No more periodic measurements so remove dot11RRMRqstMeasurementPeriod. | Remove section. | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB
1293 | Olson | Annex D p84 l2 | T | Y | No more periodic measurements so remove dot11RRMRqstMeasIntervalUnit. | Remove section. | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB
1294 | Olson | Annex D p84 l17 | T | Y | No more periodic measurements so remove dot11RRMRqstMeasurementInterval. | Remove section. | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB
1295 | Olson | Annex D p84 l60 | T | Y | In dot11RRMRqstThresholdOffset the INTEGER range is -127 to 127. | Make change. | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB
1297 | Olson | Annex D | T | Y | After the entry for dot11LCIRqstOctet there needs to be entries for dot11RRMPauseTimeUnits and dot11RRMPauseTime. | Add entries. | Accepted | [6 empty] | Kwak | Periodic
1298 | Olson | Annex D | T | Y | In the dot11RRMReport section there is no way to report the mode bits returned in measurement reports (late bit, incapable bit, and refused bit). | Add a field to handle these bits in all measurement report tables. | Accepted | Add the following to each report: dot11XXXXXXXXXXXRptMeasurementMode 0,1,2 bits |  |  |  | Comment resolved in the Seattle 3 Ad Hoc on 9/14/05 |  | Gray | MIB
1306 | Olson | Annex D p108 l16 | T | Y | There is no longer a need for dot11RRMNeighborReportTimestampReference. | Remove dot11RRMNeighborReportTimestampReference. | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB
1310 | Olson | Annex D p109 l69 | T | Y | dot11RRMNeighborReportPhyOptions does not handle the optional TBTT information. | Update this entry to support the option TBTT info. | Accepted | Add a new object to the dot11RRMNeighborReport entry that will be called dot11NeighborReportTSFOffsetFlag. The object will be a truth value where true means the TSFOffset is included in the Neighbor Report entry. | [6 empty] | MIB
1311 | Olson | Annex D p110 l2 | T | Y | No more need for dot11RRMNeighborReportTimestampReference. | Remove dot11RRMNeighborReportTimestampReference. | Accepted | Resolved in 05/0245r2 | [6 empty] | MIB
1428 | Soomro | Annex D | T | Y | While MIBs are included for measurement of statistics for TCs, similar MIBS are not added for traffic streams. | Add similar statistics for traffic streams. See doc:11-05-0164 | Accepted | Resolved when 1637r4 was merged into MIB | [6 empty] | MIB
1429 | Soomro | Annex D | T | Y | Delay is an important parameter to measure QoS service being achieved in a QBSS. There is no MIB in the protocol which measures and keeps track of this parameter. | Add MIB parameter for a QSTA to keep track of delays encountered by a TC or a TS in a QSTA. See doc:11-05-0164 | Accepted | The issue is addressed by 05/1635r4. Instruct the editor to incorporate normative text in 05/1635r4. | 467 |  |  | No such document |  |  | QoS
1556 | Kwak | Annex D | T | N | RRMRqstMeasPeriod and RRMRqstMeasInterval are no longer needed in the MIB. Delete them and fix item numbering. | Details to be provided by Joe Kwak at May meeting. | Accepted | Resolved in 05/0245r2 | 1556 | [5 empty] | Periodic
183 | Hansen | 7.3.2.26 | T | Y | I think that I am just missing something in the syntax of the MIB, but how is an entry made to the dot11APChannelReportTable when it and all sub-parts of it are marked as MAX-ACCESS "not accessible"? Does this mean that the entire table is not readable or writeable by any entity? If so, then what good is it? | Educate me. | Counter | "not accessible" is correct for the table, entry, and index. The remaining elements should be defined as "read-write". |  | 183 |  |  |  |  | MIB
226 | Liang | 7.3.2.26 | T | Y | I think that I am just missing something in the syntax of the MIB, but how is an entry made to the dot11APChannelReportTable when it and all sub-parts of it are marked as MAX-ACCESS "not accessible"? Does this mean that the entire table is not readable or writeable by any entity? If so, then what good is it? | Educate me. | Counter | "not accessible" is correct for the table, entry, and index. The remaining elements should be defined as "read-write". |  | 183 |  |  |  |  | MIB
545 | Fischer | 7.3.2.26 | T | Y | I think that I am just missing something in the syntax of the MIB, but how is an entry made to the dot11APChannelReportTable when it and all sub-parts of it are marked as MAX-ACCESS "not accessible"? Does this mean that the entire table is not readable or writeable by any entity? If so, then what good is it? | Educate me. | Counter | "not accessible" is correct for the table, entry, and index. The remaining elements should be defined as "read-write". |  | 183 |  |  |  |  | MIB
718 | Karaoguz | 7.3.2.26 | T | Y | I think that I am just missing something in the syntax of the MIB, but how is an entry made to the dot11APChannelReportTable when it and all sub-parts of it are marked as MAX-ACCESS "not accessible"? Does this mean that the entire table is not readable or writeable by any entity? If so, then what good is it? | Educate me. | Counter | "not accessible" is correct for the table, entry, and index. The remaining elements should be defined as "read-write". |  | 183 |  |  |  |  | MIB
1080 | Amman | Annex D | T | Y | Page 84, line 18: The defined range for "dot11RRMRqstMeasurementInterval" appears excessive in this commenters opinion. | Provide justification for the range of this value, or change the range of possible values to a timeframe that would make the information more useful given changing RF conditions. | Counter | dot11RRMRqstMeasurementInterval was removed from draft | [6 empty] | MIB
1091 | Karcz | Annex D | T | Y | page 77, line 10, what is the default value for dot11RadioMeasurementProbeDelay | define a default value | Counter | P53L18 Replace dot11RadioMeasurementProbeDelay with ProbeDelay. P75L35, P77L4-11 Remove all references to dot11RadioMeasurementProbeDelay. |  |  |  | Comment reassigned to MIB in the Seattle 3 Ad Hoc on 9/14/05 - There is nothing in the text |  | Gray | MIB
1229 | Black | Annex D | T | Y | P91, L34: Why return only selected capability information here? | Fix. | Counter | dot11BeaconRprtCFStatus was removed from draft and 948r0 provides additional information | [6 empty] | MIB
1307 | Olson | Annex D | T | Y | dot11RRMNeighborReportEntry is missing an entry for the capabilities unkown bit. | Add an entry. | Counter | Capabilities unknown bit was removed. | [6 empty] | MIB
1309 | Olson | Annex D p108 | T | T | dot11RRMNeighborReportEntry is missing an entry for the capabilities unkown bit. | After dot11RRMNeighborReportRSN add an entry for the capabilities unkown bit. | Counter | Capabilities unknown bit was removed. | [6 empty] | MIB
92 | Estrada | Annex D | T | Y | The MIB uses a different approach in defining the request table versus the report tables. A single request table contains all parameters required for any request type. But multiple report tables are defined, one for each report type. Wouldn't it be more consistent and cleaner if the MIB used the same approach in defining both tables? As is, I believe the request table must be filled in differently for each request type. Therefore, the originator and the processor of the request must have detailed knowledge of the request attributes. If the request table was arranged like the report tables, with one table defined for each request type, the tasks of originating and processing requests would be cleaner and have fewer bugs. | Define multiple request tables, one for each request type. Each table would contain only those attributes necessary for the associated request type. Delete the currently defined all-in-one request table. | Declined | The group has decided to take the single request table approach because multiple request elements of different types may be simultaneously requested to produce a single request frame. Additional complexity relating to common dialog and measurement tokens across multiple request table types, adds no value, was considered, and not adopted. |  |  |  |  | CC/SF2-GG2/05 |  | MIB
346 | Malinen | Annex D | T | Y | dot11RRMNeighborReportCapQoS and dot11RRMNeigborReportCapBlackAck refer to features that are not yet in approved IEEE 802.11 standard. Deferred in LB71; ok if waiting for IEEE 802.11e. | Wait for IEEE 802.11e to get completed or remove these references on pages 97 and 98 and in the text clauses describing neighbor report. | Declined | TGe has been approved since LB71 | [6 empty] | QoS
660 | Balachander | Annex D | T | Y | Support for Location measurements and reporting is not a requirement for 802.11 Phy or MAC measurements | Remove references in MIB | Declined | Group voted to remove LCI and it did not pass | 312 | [5 empty] | Location | Annex D
957 | O'Hara | Annex D | T | Y | The creation of MIB attributes that hold soley dynamic information, such as last associated station address, are of very limited usefulness. | delete dot11AssociateStation MacAddress, dot11AssociateID INTEGER, dot11AssociateFailStation MacAddress, dot11AssociateFailStatus INTEGER, dot11ReassociateStation MacAddress, dot11ReassociateID INTEGER, dot11ReassociateFailStation MacAddress, dot11ReassociateFailStatus INTEGER | Declined | We are following precedence on adding notifications in the standard 802.11 MIB. This static information works in conjunction with the notifications provided by TGk. | [6 empty] | MIB
958 | O'Hara | Annex D | T | Y | The duplication in the MIB of a mechanism to cause measurements to be conducted is unnecessary. The service primitives are sufficient to cause the peer to peer communication necessary for RRM. | delete the mechanism of using the dot11RadioResourceManagement object to cuase measurments to be conducted. Use this table only fro reporting on measurements initiated by the service primitives. | Declined | The TGk PAR requires standardization of an interface to upper layers and that is ASN.1. The service primitives only represent a logical interface. | [6 empty] | MIB
959 | O'Hara | Annex D | T | Y | keeping information for dubious reports and measurements is not ncessary | delete all attributes from the dot11RadioResourceManagement table that have to do with the Beacon, frame, channel load, noise histogram, hidden station, medium sensing time histogram, and STA statistics measurement requests and reports. | Declined | The TGk PAR requires standardization of an interface to upper layers and that is ASN.1. The service primitives only represent a logical interface. | [6 empty] | MIB
1075 | Amman | Annex D | T | Y | There are several MIB parameters that have been defined, but do not appear to be referenced in the text, and therefore their usage is unclear. | Add corresponding text in the draft to relate each of the new MIB parameters to some behavior in the draft, or remove the MIB parameter if text cannot be provided. | Declined | Comment without reference. | [6 empty] | MIB
1076 | Amman | Annex D | T | Y | Page 75, line 43: The description of "dot11AssociateStation" states "This attribute holds the MAC address from the Address 1 field of the most recently transmitting association response frame…". Tracking this information does not seem useful as it seems like it would change far too frequently to be useful. | Remove any MIB parameters that cannot be directly tied to normative behavior in the text. | Declined | We are following precedence on adding notifications in the standard 802.11 MIB. This static information works in conjunction with the notifications provided by TGk. | [6 empty] | MIB
1230 | Black | Annex D | T | Y | P101, L19 and elsewhere: Should these stats report entries not be unsigned32 and not counter32. They are used to hold a reported value - MIB counters just increment with no reset capability. | Make all reported values unsigned32. | Declined |  |  |  |  | These are based off of dot11Counters which are defined as Counter32. |  |  | MIB
1232 | Black | Annex D | T | Y | Conformance entries probably need to include a new SMTbase group to cover additions to dot11StationConfigEntry with the previous group deprecated? | Add conformance group for new config items. | Declined | Please provide normative text. | [6 empty] | MIB
1555 | Kwak | Annex D | T | N | RRMRequest Table is out of sync with draft text: 1. Token in MIB should actually be Dialog Token, Measurement Token is missing from MIB. 2. Need to add Number of Repetitions, Pause Time, Pause Unit. | Details to be provided by Joe Kwak at May meeting. | Declined | 438r0 fix most of the issues. Joe might submit paper with more details. | 1555 |  |  | I think most of this is addressed. |  |  | Periodic
848 | Barber | Annex D | T | Y | The MIB does not include traps on all changes in the association state machine | Add traps for every state change. Make them optional, controlled by a MIB variable | Deferred | Submitter is welcome to submit normative text. |  |  |  | If time allows we could add text |  |  | MIB
849 | Barber | Annex D | T | Y | The MIB does not include counters on 11k operations | add counters on operations of interest | Deferred | Submitter is welcome to submit normative text. |  |  |  | If time allows we could add text |  |  | MIB
850 | Barber | Annex D | T | Y | The MIB does not include counters and traps on RSN operations | Add traps for every state change. Make them optional, controlled by a MIB variable | Deferred | Submitter is welcome to submit normative text. |  |  |  | If time allows we could add text |  |  | MIB
854 | Barber | Annex D | T | Y | dot11RRMNeighborReportNextIndex has no way to distinguish between table full and not configurable |  | Deferred | The commenter didn't provide recommended changes. | [6 empty] | Neighbor
855 | Barber | Annex D | T | Y | Making measurements by SNMP requires polling for results | Send a TRAP on results being available - especially useful for conditional measurements | Deferred | Submitter is welcome to submit normative text. |  |  |  | If time allows we could add text |  | Olson | Misc
858 | Barber | Annex D | T | Y | the MIB peer stats table reports on all conversations between this STA and a peer. There is no table to collect stats on conversations between other neighboring STA. | Convert the peer stats table into a conversations table, indexed by TA and RA. This table does not need to be completely filled in if the STA cannot observe details of external conversations - but this form allow STAs that can to do so | Deferred | Submitter is welcome to submit normative text. | [6 empty] | MIB
1231 | Black | Annex D | T | Y | P108, L16 and elsewhere: Update Neighbor report table to match recent changes to neighbor report | Update of MIB required. | Deferred |  |  |  |  | Find Motorola documents. |  | Gray | MIB
1312 | Olson | General | T | Y | There is currently no measurement that allows client location tracking by measuring the RSSI from frames transmitted from a client station. | Commenter will make a submission. | Deferred |  |  |  |  | Did Tim Make a submission? | Olson |  | MIB
1557 | Kwak | Annex D general | T | N | Our MIB text descriptions are still out of sync with the draft text. Once the draft text stabilizes for good, someone needs to carefully review each MIB variable name and text description in the MIB and align it with descriptions in the latest text. | Place holder comment. Should be assigned to person or to a team at very end of LB process and before SB begins. | Deferred |  |  |  |  | Joe did you make a presentation. |  |  | MIB
Note on I1: Actual Comment Resolution
Note on J1: This must be a comment number - without text
Note on K1: This column contains notes related to Functional Group (Not Editor and Not Chair) - Free form