## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-05/1024r6
Venue Date: | November 2005
First Author: | Charles Wright, Azimuth Systems, Inc.
Subject: | Task Group T Issues List
Full Date: | 2005-09-20
Author(s): | Name(s) | Charles Wright
| Company | Azimuth Systems
| Address | 31 Nagog Park, Acton, MA 01720
| Phone: | 978-263-6610
| Fax: | 978-264-5352
| email: | charles_wright@azimuthsystems.com
Abstract:
This document is the issues list for TGT. As issues with the current draft are identified, they are appended to the list. It is intended to serve as a focal point for sparking contributions on current serious issues in the draft. Members should examine this list periodically to get an idea of what work needs to be done. Nothing preventing any subset of TG members from picking up an issue and starting a discussion on it, or bringing in a contribution that attempts to resolve the issue. The intent is for this issues list to be rolled into an initial list of comments when the TGT internal review begins.
This document began life as the combined comments submitted for the informal D0.3 review conducted in August/September of 2005.
Notice: This document has been prepared to assist IEEE 802.11. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor grants a free, irrevocable license to the IEEE to incorporate material contained in this contribution, and any modifications thereof, in the creation of an IEEE Standards publication; to copyright in the IEEE’s name any IEEE Standards publication even though it may include portions of this contribution; and at the IEEE’s sole discretion to permit others to reproduce in whole or in part the resulting IEEE Standards publication. The contributor also acknowledges and accepts that this contribution may be made public by IEEE 802.11.
Patent Policy and Procedures: The contributor is familiar with the IEEE 802 Patent Policy and Procedures <http:// ieee802.org/guides/bylaws/sb-bylaws.pdf>, including the statement "IEEE standards may include the known use of patent(s), including patent applications, provided the IEEE receives assurance from the patent holder or applicant with respect to patents essential for compliance with both mandatory and optional portions of the standard." Early disclosure to the Working Group of patent information that might be relevant to the standard is essential to reduce the possibility for delays in the development process and increase the likelihood that the draft publication will be approved for publication. Please notify the Chair <stuart.kerry@philips.com> as early as possible, in written or electronic form, if patented technology (or technology under patent application) might be incorporated into a draft standard being developed within the IEEE 802.11 Working Group. If you have questions, contact the IEEE Patent Committee Administrator at <patcom@ieee.org>.

## Master
ID | Commenter | Clause | T or E | Comment | Suggested Remedy | Resolution | Draft Version
1 | C. Wright | 3.2.9 | E | Appears to be a word missing -> "...the effect one metric on other metrics…" | Change it to say "...the effect one metric has on other metrics…" | 3/23/06, comment accepted by original text author; motion to be brought in next 802.11 meeting requesting approval of change | D0.2
2 | C. Wright | 3.2.9 | T | I don't understand the point of this definition or why it is needed. | Remove definition | 3/23/06 telecon: Some agreement to change the names; some volunteers for the task of writing some background in the framework. | D0.2
3 | C. Wright | 3.2.10 | T | This is not a meaningful definition of "Data Traffic" because the term "data" is overloaded with "data frames" and "non-QoS data" might refer to 802.11 data frames that do not have the 802.11e QoS header. It's perfectly legitimate to send ftp data using 802.11e QoS Data frames. | The definition should be rewritten to reflect the usage model, which is something to the effect of traffic that is "throughput and loss sensitive, but not delay or jitter sensitive". | 3/23/06, comment accepted by original text author; motion to be brought in next 802.11 meeting requesting approval of change | D0.2
4 | C. Wright | 3.2.11 | T | I don't understand the point of the 3.2.10 definition in the context of this one. | Please clarify during the comment resolution process. | 3/23/06 telecon: Resolved by accepting comment to #3 | D0.2
5 | C. Wright | 3.2.12 | T | Do we really need this definition when "test environment" is defined? | Delete this definition | 3/23/06 telecon: proposed solution: remove it and no damage is done, if it's needed it can be added later. | D0.2
6 | C. Wright | 3.2.13 | T | We can and should make a value judgement about "extraneous signals" | How about this as a definition: "Any signal whose source is external to the test setup and whose introduction into the test setup is considered undesirable" | 3/23/06, comment accepted by original text author; motion to be brought in next 802.11 meeting requesting approval of change | D0.2
7 | D. Ward | 4.2 |  | In the Aug 25 Call, we agreed to change 4.1 (a) to environment | Change methodology to environment |  | D0.2
8 | C. Wright | 4.2.2.1 | E | "Characterized transmit/receive antennas" refers to which antennas? DUT antennas or test antennas? | Clarify intent. I'm assuming you mean the reference and test antennas - antennas that are part of the test setup. |  | D0.2
9 | C. Wright | 4.2.2.1 | T | Suggest that "lasers" isn't descriptive enough - user may select a device that is unsuitable for intended purpose. | Replace "lasers" with "laser pointing and alignment device" or some other similar appropriately descriptive term. Note that "lasers" appears in several places. |  | D0.2
10 | D. Ward | 4.2.2.1 | T | There should be an explicit reference to the physical location of the traffic generator. These devices produce extensive radiated emissions and FCC Part 15 approval is insufficient to insure a noise free environment during testing. | The traffic generator should be placed outside the shielded enclosure and the data / traffic provided to the SUT / WLCP via an isolated interface that meet or exceed the isolation requiremetns for the enclosure. |  | D0.2
11 | D. Ward | 4.2.2.1 | T | In the Aug 25 Call, we agreed to add the text "reference" before antennas. In addition, what is considered a high degree of accuracy? Does this imply that vendor data sheets are accurate, or that independent measurements are to be made on the reference antennas | Suggest defining in more explicit detail the intention of high degree of accuracy for antenna characteristics. Provide guidance if a data sheet is sufficient, or if independent range measurements are required. |  | D0.2
12 | D. Ward | 4.2.2.1 | T | More detail should be provided to insure that the equipment used meets minimum standards, without providing any vendor name or model. Providing minimum standards insures more accurate data amongst test locations | Provide minimum analyzer specifications - frequency, bandwidth, noise figure, etc.. |  | D0.2
13 | D. Ward | 4.2.2.1 |  | Agree with Editors recommendation | Suggest placing the Channel characteristic requirement under section 4.2.3.2 and better defining the test conditions. |  | D0.2
14 | D. Ward | 4.2.2.2 |  | Agree with Editors recommendation | Remove clause |  | D0.2
15 | D. Ward | 4.2.2.3 |  | Agree with Editors recommendation | Remove clause |  | D0.2
16 | D. Ward | 4.2.3.1 |  | As discussed in Aug 25 call - this clause did not make sense and suggest a reword to better convey the author's intent in the clause | Reword |  | D0.2
17 | D. Ward | 4.2.3.1 | T | Suggest specific equipment requirements be outlined in this clause rather than general references. This provides minimum standards and simplifies the standard, such that specific equipment requirement are in one location as it applies to a particular test procedure. | Recommend clarifying requirements for power meters to be of type that measure average packet power, and not average continious carrier average power as well as forward power instead of reflected power. Recommend adding specific chamber isolation requirements. Recommend including isolation requirements for equipment and cabling that traverse the chamber boundry. Recommend including any other specifics deemed necessary by the TG. |  | D0.2
18 | D. Ward | 4.2.3.1.2 | T | A baseline must be established first before introducing any modifier. I'm unable to comment further until 4.2.3.1 is reworded. I believe a consistent baseline configuration should be defined to allow comparison of various systems across at least one "standard" test set up. | Recommendation to be provided upon agreeement of 4.2.3.1 |  | D0.2
19 | C. Wright | 4.2.3.2 | T | Agree with editor's note, but would further clarify | Instead of "in the band used for the test", say "in the band or bands used for the test" |  | D0.2
20 | D. Ward | 4.2.3.2 | T | This clause is a double standard. The first sentence states no test conditions, and the second states that channel ripple is a condition | Recommend defining the conditions for the test environment |  | D0.2
21 | D. Ward | 4.2.3.2 | T | Given the discussion at the Aug 25 Call, this may be unresolved - However, since chamber isolation is a requirement and there's discussion on that - should there be a test condition regarding environemnt noise and in-band signals? It's possible, but unlikely that a 20dbm transmitter may be outside the chamber - this case could skew test results | Recommend adding isolation and/or extranious noise / signal measurement in the chamber. Perhaps taken from the reference receive antenna? |  | D0.2
22 | D. Ward | 4.2.3.3.1 | T | Item a) In light of comments above, this can be simplified to insure that the test condition is implied with. However, the antenna type on the spectrum analyzer, and what exactly is measured should be better defined. | Recommend using the receive reference antenna as the point of measurement with the Spectrum Analyzer - it is consistent with the test set up. Further recommend that specific Span, Resolution BW, Video BW, and type of measuremennt - Peak Power, Band Power, over a specified time frame with peak hold be incorporated to verify the environment. |  | D0.2
23 | D. Ward | 4.2.3.3.1 | T | Item b) a minimum distance should be a requirement. Individuals testing and those receiving results may not know the difference or implications of near versus far field. | Recommend requirement for minimum distance. If the minimum distance is expressed in wavelengths, then the method for calculating that distance should also be included - ie: 10* 300 / F (MHz) using the lowest frequency under test in the band. |  | D0.2
24 | D. Ward | 4.2.3.3.1 | T | Item c) The RF Quiet Zone has not been previously defined | Recommend that either or both: The RF Quiet Zone be clearly defined, or reword such that the SUT can be placed in the isolated environment / chamber. This comment applies to subsequent clauses that reference quite zone. |  | D0.2
25 | C. Wright | 4.2.3.3.2 | T | What is meant by "…are within +/- 1 dB of desired metric"? What if the metric is not measured in dB? Is +/- 1 dB the right tolerance in all cases? | I can only guess on a recommended change, since I don't understand what this means. |  | D0.2
26 | D. Ward | 4.2.3.3.2 | T | Item b) Shouldn't the "precise" location of the transmit and the receive antenna be known since a system is under test and not a device? Since WLAN is bi-directional, should the wording be considered different since both antennas in a system are used for transmitting and receiving? | Precisely note the location of both antennas in the system. Please see comments below regarding path loss / channel characterization. |  | D0.2
27 | D. Ward | 4.2.3.3.2 | T | Remaining Items: Not having been involved in early discussions, perhaps this has been previously addressed? Wouldn't it be more accurate and consistent to measure the path loss with the antennas under test, instead of replacing one antenna with a "calibrated" or reference antenna? Does this statement imply replacing both antennas in the Wireless system with a reference since the sysetm was removed? Per previoius comments how does one perform a correlation between the test and "calibrated" antennas - what data is used and how does it map to the environment under test to insure consistency across platforms? In addition to previous comments regarding Network Analzyer specs, additional information should be provided to insure accurate data - At what point in the chain are the analyzers calibrated - at the connection point of the antenna feedline? What output should be provided in the report - Smith Chart, log / lin, etc.. same for scales. Defining these variables will place all SUTs at the same level and allow users to better interpret and compare data. | Recommend measuring path loss with the antennas under test. Recommend defining both end-point antennas and more clearly defining the meaning of transmit and receive antenna. Recommend more clearly defining at what point(s) in the system the path loss and channel characteristics are to be measured and recorded. Recommend defining a consistent presentation of the data. |  | D0.2
28 | D. Ward | 4.2.3.3.3 | T | Since a system is under test, isn't there more than one antenna and one device being replaced? If the comments above are considered, this entire step could be removed? In the case of integral antennas, and units needed to be replaced would it simplify the test to provide accurate location markings? If not, what type of tolerance are you allowing for placement in the XYZ plane - As engineers measurements are never precise and it makes sense to allow for a tolerance band. | Recommend clarification if one or more devices in the system have been removed, characterized,and replaced. Recommend allowance for a small tolerance such as less than 1/4 wavelength be considered. If not, there's no accounting for measurement equipment tolerances and these should be specified. |  | D0.2
29 | D. Ward | 4.2.3.3.4 | T | This section is worded as a suggestion and not a requirement. If this section is not a requirement, there's no guarantee that testers will actually follow the proceedure so therefore is this clause actually necessary? | If there are items that the authors / TG believe are imperative to the performance test, these should become requirements and not suggestions by using the word shall instead of should. There's no way to insure consistency across tests, vendors, or test locations. |  | D0.2
30 | D. Ward | 4.2.3.3.4 | T | Item a) The purpose of outlining the test and calibration proceedure is to use a known environment. Using the calibrated path loss measured during the calibration proceedure of 4.2.3.3.2 must be a requirement and not a suggestions | Recommend changing the statement requiring that the test use the calibrated test environment / path loss. |  | D0.2
31 | D. Ward | 4.2.3.3.4 | T | Item c) Modiifiers are allowed under clause 4.2.3.1.2 - Shouldn't Clause 4.2.3.1.2 explicilty state that calibration is required prior to changing bands, orientation or other factors? This section seems to contradict clause 4.2.3.1.2 | Recommend removing item c, and including requirements / steps in clause 4.2.3.1.2 |  | D0.2
32 | D. Ward | 4.2.3.4 | T | If more strict equipment set up and test parameters are specified in previous clauses, it may not be necessary to suggest a RBW < 100kHz. In addition, if discussing RBW - what results other than path-loss, noise, and isolation are reported in a frequency domain format? See my comment on line 20 above. | Recommned more precisely defining measurement standards / set up and adding clarification to what data should be reported in the frequency domain. |  | D0.2
33 | C. Wright | 4.3 | E | In definition 3.2.5, we refer to "conducted" test environment, yet here, we are using the word "conductive" | We should be consisitent. My preference is "conducted". Replace all instances of "conductive" with "conducted" | 3/23/06, comment accepted by original text author; motion to be brought in next 802.11 meeting requesting approval of change | D0.2
34 | C. Wright | 4.3.1 | E | Reference to "this standard", when in fact we are writing a "recommended practice" | Replace "standard" with "recommended practice" | 3/23/06, comment accepted by original text author; motion to be brought in next 802.11 meeting requesting approval of change | D0.2
35 | C. Wright | 4.3.1 | E | In bullet 4, do we really need the word "guaranteed"? This would seem to be a bit over-reaching, reeks of hyperbole and adds nothing to the statement about high repeatability. What or whom is providing the guarantee? | Remove the word "Guaranteed" | 3/23/06, comment accepted by original text author; motion to be brought in next 802.11 meeting requesting approval of change | D0.2
36 | C. Wright | 4.3.1, D0.6-5.3.1 | T | Statement about modeling real life is inconsistent with "LOS environment" definition in 3.2.22. A Rician channel has a random component associated with the random phase and amplitude of signals received in addition to the LOS component. Perhaps it is true it is Rician if the K factor is extremely large, but this is contrived. The environment does model a smple WGN channel very well, since there are no channel-induced amplitude variations. | Suggest a rewording of this item, something to the effect of modeling an AWGN scenario, useful for baseline performance benchmarking. | 3/23/06 telecon: will resubmit comment as comment on definition 3.2.22 | D0.2
37 | D. Ward | 4.3.1 | T | From a practical perspective, I disagree with the last statement. Theoretically the statement is true. However, the conducted environment does not account and in fact masks hardware design issues such as self intereference due to radiated emissions. I note that this has been a real-world problem with NIC's without mentioning vendors. I have many other real design experiences with other RF products with integral antennas where this has also been the case. | Recommend clarifying the last statement to completely clarify that the conducted test is a near approximation and does not account for system variations due to self interference and antenna proximity / design. | 3/23/06, comment accepted by original text author; motion to be brought in next 802.11 meeting requesting approval of change | D0.2
38 | C. Wright | 4.3.2.1 | T | I dispute the opening statement. The listed equipment is not necessary for all tests in this environment. Various pieces of it may be necessary for each test. For instance, a test may not require the use of a wired traffic analyzer. Why mandate it in this section? | Break the list into two - one with the required components (e.g., shielded enclosures, etc) and the "useful for some tests" list. | 3/23/06, comment accepted by original text author; motion to be brought in next 802.11 meeting requesting approval of change | D0.2
39 | C. Wright | 4.3.2.2 | E | Use of word "conductive" again. In reference to cables, this is redundant anyway. Are you intending to rule out waveguide, if someone wanted to use that instead of cable? Does WG count as conducted? | Remove "conductive" | 3/23/06, comment accepted by original text author; motion to be brought in next 802.11 meeting requesting approval of change | D0.2
40 | C. Wright | 4.3.2.2 | T | Figure 1 - no need to show test controller if methodology describes functions performed in the test set in an abstract manner. The controller will be implied by the functionality described, and when present in the diagram, clutters it as well as mandates it. | Remove controller block and associated signal wires from Figure 1. Remove "A Test Controller" from list in 4.3.2.1 | 3/23/06 telecon: started discussion, 4/6/06 telecon: further discussion on the diagram, no agreement | D0.2
41 | C. Wright | 4.3.2.2 | T | Final paragraph about test controller - as stated in previous comment, the functionality of the controller should be defined in an abstract way. The "ability" items in the list should be specified only in specific test methodologies. As stated here, they are irrelevant to the test setup. We are not standardizing a piece of test equipment with specific capabilities. We want to standardize the abstract functional requirements of the test. | Delete this last paragraph | 4/6/06 telecon: comment is linked with #40 and should be resolved with it | D0.2
42 | C. Wright | 4.3.2.2 | T | Connection of wired LAN cables does not ensure traffic will pass through the wireless link. If the traffic generator sends a frame to the traffic analyser, what guarantees that it won't simply follow the wired path instead of the wireless path? | The connection between the TG and TA must be broken. | 4/6/06 telecon: Charles proposed some diagram changes, accepted in principle, pending Charles sends diagram to Sasha. | D0.2
43 | C. Wright | 4.3.2.2 | T | Figure 1 shows RF junctions as dots. This is misleading, as all RF junctions must be made through some sort of splitting device, whether it be a resistive splitter, reactive splitter, directional coupler or circulator. | Be clear in the diagram as to which sort of splitting device is required at each junction. | 4/6/06 telecon: not resolved but Charles will send some symbols along with diagram suggested in 42, and people are free to try to find other sources for standard symbols. | D0.2
44 | D. Ward | 4.3.2.2 | T | A combiner and splitter are two different passive devices | Recommend removing the statement: (splitter) after combiner. | 4/6/06 telecon: editorial change to "2-way splitter/combiner" | D0.2
45 | D. Ward | 4.3.2.2 | T | One-way couplers are more commonly known as unidirectional couplers | Recommend rewording to unidirectional | 3/23/06, comment accepted by original text author; motion to be brought in next 802.11 meeting requesting approval of change | D0.2
46 | C. Wright | 4.3.3.1 | T | Final sentence of this clause is vague. What level should the "external interference and other unwanted signals" be relative to the desired signals? | Suggest something to the effect of "Ensure that external interference and other unwanted signals are better than 10 dB (e.g.) below the sensitivity of any receiver in the test system" | 3/23/06, comment accepted by original text author; motion to be brought in next 802.11 meeting requesting approval of change | D0.2
47 | D. Ward | 4.3.3.1 | T | Per comments above, specific isolation requirements should be outlined in 4.3.2.1 with minimum standards. | Recommend providing more explicit direction - As an example: The DUT's / SUT shall be configured as outlined in Figure X. Remove the second sentence. | 4/6/06 telecon: original text author agrees with intent of improving text and welcomes specific proposals for its enhancement along these lines. | D0.2
48 | D. Ward | 4.3.3.2 | T | Shouldn't the losses be measured rather than inferred? What about the addiditive effects of insertsion losses? The stack up from data sheet tolerances could be larger than the nominal insertion loss. Same for insertion losses of the unidirectional couplers and measured power tolerances? The measured losses and equipment tolerances must be known and recorded. Otherwise more explicit requirements should be placed on the type(s) of equipment used. | Recommend requiring loss measurements, documenting equipment tolerances, and explicity stating that test equipment such as power meters have a valid NIST traceable validation certificate. If self-calibration is used for other equpment, those calibration steps / proceedures should be documented and submitted with any test report data. | 4/20/06 telecon: Add a section after 4, "Common Test Practices" | D0.2
49 | D. Ward | 4.3.4 | T | Multipath tests / simulations are not trivial. If it is intended to be a modifier suggest providing specific guidance for the multi-path test set up. | Recommend providing more specific guidance for a suggested multi-path test environment such as fraction wavelength cables that include velocity factor of the cable / all coaxial cable shall have the same velocity factor. The phase and magnitude affects of additional elements must also be factored. Recommend stipulating that measured data phase and amplitude parameters of each path be included in the test report | 4/20/06 telecon: change sentence to say "Equipment can be inserted in place of or along with the attenuator to simulate multipath effects" Note: It would be helpful to add text to address the need to make sure calibration and signal levels are maintain with any modifiers to the baseline (specifically, with other equipment replacing baseline components). This probably applies across all environments and should be put in a more general section. | D0.2
50 | D. Ward | 4.3.5 | T | Variations to the baseline as outlined in Figure 1 must be explicity documented in any test report, especially in the case where multiple cables, attenuators, etc. are in use as identified in the previous comment | Recommend adding the requirement that any variation from the baseline set up per Figure X be documenting with an explanation of the purpose of the test variation and what function / feature is under test. | Comment is resolved by resolution of comment 49 | D0.2
51 | C. Wright | 4.4.1 | E | "Multi-path" is a single word - no hyphen | "multi-path" -> "multipath" | 3/23/06, comment accepted by original text author; motion to be brought in next 802.11 meeting requesting approval of change | D0.2
52 | C. Wright | 4.4.2.1 | T | Item d of outdoor range requirements is vague. What level should the "external interference and other unwanted signals" be relative to the desired signals? | Suggest something to the effect of "Ensure that external interference and other unwanted signals are better than 10 dB (e.g.) below the sensitivity of any receiver in the test system" |  | D0.2
53 | C. Wright | 4.4.2.1 | T | There is no specification as to the type of material composing or conductivity of the ground. Is this damp or dry grass? Is astroturf acceptable? What about material under the astroturf? | Please specify in the outdoor range requirements, or justify why this should not be in the requirements. |  | D0.2
54 | D. Ward | 4.4.2.1 | T | If noise measurements are a requirement and a spectrum analyzer is referenced as the measurement tool, shouldn't then the spectrum analyzer be a required piece of equipment? | Recommend requiring a spectrum analyzer, and as in previous comments above provide some minimum specifications including a NIST traceable calibration certificate. |  | D0.2
55 | D. Ward | 4.4.2.1 | T | In addition to editor's comment - Should test equipment radiated emissions be considered? Part 15 compliance may not insure an interference free environment, although there is a measurement requirement later in the test environment specification. | Recommend specifying that there shall be no active RF devices in the band / bands under test. |  | D0.2
56 | C. Wright | 4.4.2.3 | E | Table 1, item 1 and others - refers to "floor", yet test is specified to be conducted outside. | "floor" -> "ground" |  | D0.2
57 | C. Wright | 4.4.2.3 | T | Table 1, item 2 - the requirement addresses only client devices. Are there specific recommendations for APs? | Clarify the requirement. |  | D0.2
58 | C. Wright | 4.4.2.3 | T | Table 1, item 4. Are there any further requirements on the length of a specific run, relative to the rate of spinning the DUT? I.e., if a 60 sec run is long enough for a 10 RPM spin rate, should the run be 600 sec for a 1 RPM spin rate? | Clarify the requirement. |  | D0.2
59 | C. Wright | 4.4.2.3 | T | Table 1, item 10. Does this item intend to have a single person push the test station cart? | Clarify the requirement. |  | D0.2
60 | D. Ward | 4.4.2.3 | T | Item 1) Should the height of the DUT actually be the height of the platform that the DUT sits on with no modifications to the DUT? | Recommend clarifying height parameter for consistency and better ease of measurement / construction. The figure should better clarify the intention or the words in the requirement better clarify the reference points |  | D0.2
61 | D. Ward | 4.4.2.3 | T | Item 2) Measuring an LCD Screen is not easy. Should the measurement / reference points be more clearly defined such as the center line of the horizontal surface or the top / bottom? Same for the screen or is the angle between the top surface and the front surface of the screen be the measurment parameters? Is a 1 degree tolerance too difficult to maintain? | Recommend providing more precise reference points / locations / surfaces on the DUT to provide for consistent measurement across DUT platforms / devices. The figure should provide more clarification, or the statement should be more precise. |  | D0.2
62 | D. Ward | 4.4.2.3 | T | Item 5) Should a restriction be placed such that theWLCP can only be of a type with integral antennas? This is inferred but not specified. Would it simplify the statement to say that the antennas must be verticaly polarzied? What about cases where the WLCP has antennas integrated in the device and not | Recommend modifying the WLCP only be of a type with integral antennas / or antenna type. If using an external antenna with an RF cable minor clarifications can be made to the requirement to insure accurate antenna placement as oppossed to DUT placement. |  | D0.2
63 | D. Ward | 4.4.2.3 | T | Item 7) How is -100dbm defined? Over what bandwidth (note at room temp -174dbm in a 1 Hz BW is the thermal noise floor in a 16MHz Channel it is ~ -102dbm)? What settings are used on the Spec An - Span, RBW, VBW, peak power, band power, continous scan or peak hold for X time period? What type of antenna is to be used, along with associated cable / connector losses? Maximum / Minimum Antenna gain? Where is the measurement taken on the rang WRT to the WLCP and / or DUT? Without more specific requirements on the test set up end-users will never be able to decipher data from different sources. | Recommend adding more specific detail wrt to measurements, equipment, and location of measurements on the range. |  | D0.2
64 | C. Wright | 4.5.2.1 | T | Indoor NLOS range requriements - why is home situation specified as "combination of metal framing and window glass"? This sounds like an office building to me | Was this chosen based on the dominant construction methods for homes? Please explain rationale or change requirement to something more like a wood frame house. |  | D0.2
65 | C. Wright | 4.5.2.1 | T | Item d of range requirements is vague. What level should the "extraneous signals" be relative to the desired signals? | Suggest something to the effect of "Ensure that extraneous signals are better than 10 dB (e.g.) below the sensitivity of any receiver in the test system" |  | D0.2
66 | D. Ward | 4.5.2.1 | T | I have the same comments for this clause as 4.4.2.1 | Same recommendations as 4.4.2.1 |  | D0.2
67 | C. Wright | 4.5.2.3 | T | Table 2 - item 5, is the 2.75 meter height intended to be appropriate for the home situation as well as enterprise? | Please justify this choice. |  | D0.2
68 | D. Ward | 4.5.2.3 | T | I have the same comments for this clause as 4.4.2.3 | Same recommendations as 4.4.2.3 |  | D0.2
69 | D. Ward | 4.5.5.5 | T | Unless the testers report the type of environment under test this environment is highly subjective. | Recommend providing detailed & scaled drawings of the test site to include wall materials and thicknesses, floor/ Ceiling materials, heights, thickness etc. Other obstructions such as cubicle walls, book shelves large plants, cabinets, etc. Location of WLCP and DUT, antenna type (manufacturer model # at minimum) and antenna orientation. |  | D0.2
70 | C. Wright | 4.6.2.1 | T | There is no specification as to the type of material composing or conductivity of the ground. Is this concrete and linoleum? Will rebar matter? | Please specify in the range requirements, or justify why this should not be in the requirements. |  | D0.2
71 | D. Ward | 4.6.2.1 | T | I have the same comments for this clause as 4.4.2.1 | Same recommendations as 4.4.2.1 |  | D0.2
72 | D. Ward | 4.6.2.1 | T | Item a) Is the intention to remove obstacles due to multipath? Even indoors, that can't be avoided. Or is the intention to remove obstacles such that it doesn't impair the direct wave? Ie: No first Fresnel Zone obstructions. It appears the latter is the case. Note: At some distance there may be an obstruction from the floor due to the height of the devices and typically the Fresnel Zone is not considered for indoor environments. | Recommend specifying no obstructions within the first Fresnel Zone between the WLCP and the DUT. This can be explicitly calcuated for the frequency under test and the linear distance between the devices. This provides for an unambiguios meaning in the standard regarding vicinity. |  | D0.2
73 | D. Ward | 4.6.2.3 | T | I have the same comments for this clause as 4.4.2.1 | Same recommendations as 4.4.2.1 |  | D0.2
74 | D. Ward | 4.7.2.1 | T | I have the same comments for this clause as 4.4.2.1 and 4.2.3.2 - specifically in regards to items a and b. | Same recommendations as 4.4.2.1 and 4.2.3.2 |  | D0.2
75 | D. Ward | 4.7.2.3 | T | I have the same comments for this clause as 4.4.2.3 | Same recommendations as 4.4.2.3 |  | D0.2
76 | D. Ward | 4.7.3.2 | T | I have the same comments for this clause as 4.2.3.3.2 | Same recommendations as 4.2.3.3.2 |  | D0.2
77 | D. Ward | 5.2.3.2 | T | Suggestt a minimum and maximum test run time for consistency. | Recommend specifying a minimum test time of 1 minute and a maximum test time of 3, 4, or 5 minutes. | 3/23/06, comment accepted by original text author; motion to be brought in next 802.11 meeting requesting approval of change | D0.2
78 | D. Ward | 5.2.3.3 | E | References to 2.3.X | Correct references |  | D0.2
79 | D. Ward | 5.2.3.3 | T | Item b) The type of traffic should be specified as separate tests. Suggest TCP and UDP as baselines. In all cases the TCP traffic should be tested first to determine the available channel bandwidth under steady state conditions for each attenuation level. | Recommend that a TCP throughput test be run to determine the steadystate available bandwidth, then a UDP test be run afterwards under the same conditions utilizing a bandwidth of 90 to 95% of the steady state TCP bandwidth. | 3/23/06, comment accepted by original text author; motion to be brought in next 802.11 meeting requesting approval of change | D0.2
80 | D. Ward | 5.2.3.3 | T | Based on above, traffic type should be included in the order recommended. | Recommend measurements should be reported for TCP traffic and error rate for UDP traffic at recorded / configured bandwidth. | 3/23/06, comment accepted by original text author; motion to be brought in next 802.11 meeting requesting approval of change | D0.2
81 | D. Ward | 5.2.3.4 | T | Again for consistency, especially for end users, the reporting requirement should stipulate the minimum amount of data using the word shall. | Recommend developing a table of minimum values and allow optional modifiers at the testers discretion. Throughput shold be expanded based on traffic type - ie: either steady state or in reported intervals such as 5 seconds such as TCP throughput and bandwidth. Same for UDP error rate. Also recommend that unidirectional and bidirectional traffic be reported in the table with the originator and the receiver clearly identified for unidirectional traffic. | 45/4/06, believed to be covered by resolutions to comments in 79-80? Suggestion: IETF has solved this by saying that the device (in this case AP) should be set up according to the manufacturer's recommended defaults (handles other obscure 802.111 configuration differences). | D0.2
82 | D. Ward | 5.3.2.1 | T | As in previous comments, suggestion providing more details wrt to test equipment such as power meters. Further suggest that losses be measured rather than inferred including losses from the unidirectional coupler to the power meter. Combiners are typically not calibrated devices, but their insertion loss can be measured. | Recommend adding more specific detail wrt to test equipment and measurement of actual losses in the RF path. |  | D0.2
83 | D. Ward | 5.3.2.1 | T | This clause stipulates 85 db of isolation instead of all previous clauses that require 95 db of isolation. As with previous comments, concern over nearby WAP's and ISM Band devices at higher power levels. In addition, isolation of cables and equipment (Conducted noise) should be specified. | Recommend consistent isolation specifications, isloation of equipemnt due to conducted noise, and futher stipulation on nearby devices capable of producing and RF signal, especially in-band. | 3/23/06, comment accepted by original text author; motion to be brought in next 802.11 meeting requesting approval of change | D0.2
84 | D. Ward | 5.3.3.3.1 | T | Throughput is generically specified. Suggest more formal definition of the traffic type such as TCP. | Recommend clarifying traffic type - If UDP is allowed / specified further recommend same steps as above for determining UDP bandwidth and using the UDP error rate in calculating the average efficiency. | 3/23/06, comment accepted by original text author; motion to be brought in next 802.11 meeting requesting approval of change | D0.2
85 | D. Ward | 5.3.3.4 | T | Again for consistency, especially for end users, the reporting requirement should stipulate the minimum amount of data using the word shall. | Recommend developing a table of minimum values and allow optional modifiers at the testers discretion. Throughput shold be expanded based on traffic type |  | D0.2
86 | D. Ward | 5.4.2.1 | T | I have the same comments for this clause as 5.3.2.1 | Same recommendations as 5.3.2.1 |  | D0.2
87 | D. Ward | 5.4.2.1 | T | I have the same comments regarding isolation as 5.3.2.1 | Same recommendation regarding isolation as 5.3.2.1 |  | D0.2
88 | D. Ward | 5.4.2.4 | T | Calibration or equipment used for self calibration should be NIST traceable. | Recommend adding requirement for NIST tracebility |  | D0.2
89 | D. Ward | 5.4.3.2 | T | Throughput is generically specified. Suggest more formal definition of the traffic type such as TCP. | Recommend clarifying traffic type | 3/23/06, comment accepted by original text author; motion to be brought in next 802.11 meeting requesting approval of change | D0.2
90 | D. Ward | 5.4.3.2 | T | Suggest specifying a ramp during the transition time - ie: db/ sec for each dwell time or some other parameter for consistency | Recommend specifying consistent attenuation rate during the transition time. This should include step size(s) allowed during the attenuation ramp up / down. | 3/23/06, comment accepted by original text author; motion to be brought in next 802.11 meeting requesting approval of change | D0.2
91 | D. Ward | 5.4.3.2 | T | Depending on the traffic type a dwell time of 10 seconds may not be sufficient for steady state to occur | Recommend removing 10 seconds as a valid dwell time if the desire is to transition after reaching a steady state condition. |  | D0.2
92 | D. Ward | 5.4.3.4 | T | Again for consistency, especially for end users, the reporting requirement should stipulate the minimum amount of data using the word shall. | Recommend developing a table of minimum values and allow optional modifiers at the testers discretion. Throughput shold be expanded based on traffic type |  | D0.2
93 | D. Ward | 5.5.3.2 | T | The turn table requirement is ambigiuos | Recommend specifying the clause - 4.7.2.3 test parameter 4 - that stipulates turn table spin rates |  | D0.2
94 | D. Ward | 5.5.3.3 | T | Same comments regarding minimum and maximum times of throughput testing and traffic types. | Same recommendations related to test duration and traffic types as previous comments |  | D0.2
95 | D. Ward | 5.5.3.4 | T | Again for consistency, especially for end users, the reporting requirement should stipulate the minimum amount of data using the word shall. | Recommend developing a table of minimum values and allow optional modifiers at the testers discretion. Throughput shold be expanded based on traffic type |  | D0.2
96 | D. Ward | 5.6.2.1 |  | Why are there multiple references? | Recommend providing a single reference instead of a reference to a reference within the standard. |  | D0.2
97 | D. Ward | 5.6.3.2 | T | Same comments regarding minimum and maximum times of throughput testing and traffic types. | Same recommendations related to test duration and traffic types as previous comments |  | D0.2
98 | D. Ward | 5.6.3.4 | T | Again for consistency, especially for end users, the reporting requirement should stipulate the minimum amount of data using the word shall. | Recommend developing a table of minimum values and allow optional modifiers at the testers discretion. Throughput shold be expanded based on traffic type |  | D0.2
99 | D. Ward | General | T | There should be a section in the draft that describes e.g., minimum test equipment capability, calibration or measurement techniques, generic standard specifications for test equipment, subjects such as guaranteeing chamber isolation, how you guarantee you've met the requirements of the test methodology |  | Potential dissent on the idea, but group to discuss offlne and come up with a decision and potentially candidate draft text. | D0.2
100 | F. Pirzada | General | T | There should be an introductory section that provides an introduction and explanation of the use cases addressed by the draft |  | Group generally agrees; Fahd to head a tiger team to produce candidate draft text | D0.2
101 | D. Ward | 5.7.2.3 / 5.7.3.3.1 | T | Figures 22 & 23 are confusing and its difficult to discern the baseline test set up. | Although the authors intend to show a superset test, a figure for the baseline would clarify the intent of receiver ACI. It is only really necessary, and much easier to collect results if one receiver ACI is tested per test run and not multiple recievers. Provide clear detail / direction for modifiers. |  | D0.4
102 | D. Ward | 5.7.2.3 / 5.7.3.3.1 | T | If portions of the test set up in Figures 22 & 23 are used for a superset with mulitple ports, then unused ports must be clearly shown for that equipment | Allow used of multi-port devices for the baseline, that have ports unused for the baseline, but required for the modifier. The unused ports for any test must be terminated in to a 50 ohm load and shown as such |  | D0.4
103 | D. Ward | 5.7.2.3 / 5.7.3.3.1 | T | A Mux is shown with no details / specifications for the device. | Provide explicit specifications for the depicted MUX. If this is a multi-port combiner, specify as such. All unused ports must be terminated in to a 50 ohm load. |  | D0.4
104 | D. Ward | 5.7.2.3 / 5.7.3.3.1 | T | Circulator shown is actually an Isolator | Correct Figures 22 & 23 - An Isolator is a specific case of a Circulator. |  | D0.4
105 | D. Ward | 5.7.2.3 / 5.7.3.3.1 | T | Jammer at Node C is providing two inputs to MUX. | Clarify Figures 22 & 23. What is the purpose of the varioius inputs from the jammer to the MUX |  | D0.4
106 | D. Ward | 5.7.2.3 / 5.7.3.3.1 | T | Jammer at Node E is providing tow inputs to MUX | Clarify Figures 22 & 23. What is the purpose of the varioius inputs from the jammer to the MUX |  | D0.4
107 | D. Ward | 5.7.2.3 / 5.7.3.3.1 | T | As depicted, with minimum attenuation, some WLCP receiver front ends will be overloaded and could be damaged | Guidance should be provided to set attenuators at levels that come near the desired levels necessary to conform with the requirement for the desired and interfering channel receiver input levels for the DUT. |  | D0.4
108 | D. Ward | 5.7.3.1.2.f | T | ACI should only be performed in a conducted environment. | In order to derive consistent results across platforms the most repeatable test is a conducted environment. There is little guidance provided in the test for other than a conducted test, and as such results and methodologies will be open to much interpretation. |  | D0.4
109 | D. Ward | 5.7.2.3 / 5.7.3.3.1 | T | It's good RF practice to use combiners / splitters instead of direct connections to isolate the circuits. Direct connections are only used in very specific circumstances with specific feedline lengths - typically with antenna phasing / feedlines. | As depicted there could be any number of unpredictable reflections and impedance mismatches that will certainly skew the results. Hybrid combiners are by far the best practice and provide the most stability to the test environment. Simple magnitude S21 measurements provide insufficeint detail regarding the test environment. |  | D0.4
110 | D. Ward | 5.7.3.3.2 | T | The prescribed procedure is vague | The actual steps, including the formulas / calculations referenced to the diagrams must be shown and followed for each test / path when using such a complex diagram. |  | D0.4
111 | D. Ward | 5.7.2.4 | T | How was the margin of error +/- 1 db derived? | Equipment parameters dictate margin of error, as such to achieve +/- 1db exact test equipment parameters / dependencies must be specified. |  | D0.4
112 | D. Ward | 5.7.3.4 | T | Reported results are worded as a suggestion, not a requirement | should be a minimum reporting requirement |  | D0.4
113 | D. Ward | 5.7.3.3.2 | T | Tom is correct, how is PER being measured? | There should be limitations / specifications around this. Do the MAC processors have this capability and is it limited in use / availability? Does this then require unique data files / training sequences at the data generation side? |  | D0.4
114 | D. Ward | 5.7.3.2 | E | Table 5 is inconsistent | Designators should be all Upper or Lower case |  | D0.4
115 | D. Ward | 5.7.3.2 | T | Rate Dependent data | Rate dependent sensitivity standard and clause should be referenced |  | D0.4
116 | D. Ward | 5.7 - All | T | In & Out of "Band" Signals | Signals are charcterized / defined as "in-band" or "out-of-band." Should be worded as desired and interfering channel. They are all in the same band. |  | D0.4
117 | D. Ward | 5.7.3.3.2.f | T | Allows Multiple measurement methods | Be specific and consistent so all results are tested in an identical manner. If two methods are desired, then require a report for each method, even though guidance is given for +/- 5db different receivers may behave differently and having each set of data for the type of test is important and honest. |  | D0.4
118 | D. Ward | 5.6.3.2 | T | How are the WLCP Jammers configured? | Simply Beacon / Management frames, data frames to a STA, etc.. At Layer 1, the test is only valid when both the desired and the interfering devices are transmitting simultaneously. A possible suggestions is to configure the Jammer to use multicast to some client as that traffic does not require an ACK? |  | D0.4
119 | D. Ward | 5.7.3.1.1.e | E | There are no further references below | A placeholder? |  | D0.4
120 | Fanny Mlinarsky | Entire document | E | "Conductive" and "conducted" are used interchangeably thorughout the document. | Change all occurances of "Conductive" to "Conducted"
121 | Fanny Mlinarsky | 5.7 | E | "Adjacent channel interference test methodology" inconsistent title | Change to "Adjacent channel interference"
122 | D. Ward | 5.5.2.1 | T |  | Table 4, Item 5 & other like tables in Section 5. I thought there was a motion to change the the requirement to 1 RPM +/- 1RPM and not 1 - 10 RPM +/- 10 % ? | Can we investigate if this is correct, as it was a motion that should have been recorded in the minutes for the July 2005 Plenary session | D0.6
123 | D. Ward | 5.5.2.1 | T |  | Table 4, Item 8: How is -100dbm defined? Over what bandwidth (note at room temp -174dbm in a 1 Hz BW is the thermal noise floor in a 16MHz Channel it is ~ -102dbm)? What settings are used on the Spec An - Span, RBW, VBW, peak power, band power, continous scan or peak hold for X time period? What type of antenna is to be used, along with associated cable / connector losses? Maximum / Minimum Antenna gain? Where is the measurement taken on the range WRT to the WLCP and / or DUT? Without more specific requirements on the test set up end-users will never be able to decipher data from different sources. | Recommend adding more specific detail wrt to measurements, equipment, and location of measurements on the range. | D0.6
124 | D. Ward | 6.10 | T |  | Generic References are made in this test methodology to "IEEE Std 802.11" Each reference should be explicit and clear for the desired methodology / metric under test | Revise 6.10 to provide specific references - Standard, Amemdment, Clause, Sub-Clause as applicable. This will also eliminate the need for editorial notes. | D0.6
125 | D. Ward | 6.10.1 | T |  | Agree with editor comments regarding "real life environment." | Remove real life environment and replace with environmental references from within the recommended practice. | D0.6
126 | D. Ward | 6.10.2.1 | T |  | 85db of chamber isolation is required, but there still lacks any metric with which to test / verify the actual isolation of the test environment | The recommended practice should provide either a methodology, or a specific normative reference for validating appropriate isolation of test environments. | D0.6
127 | D. Ward | 6.10.2.5 | E |  | Suggest rewording tolerance of temperature measuring apparatus | The phrase is poorly written. The intent is to provide for a specific amount of accuracy of the measurement apparatus. Suggest: "Temperature measurements shall have an accuracy of +/- 2 C across the temperature range of -40 to +85 C." | D0.6
128 | D. Ward | 6.10.3.3.2 | T |  | Proceedure (d) should specify a minimum & maximum number of data packets and/or minimum & maximum test duration to insure greater consistency across test platforms. | A test duration min / max would insure greater consistency across devices and platforms as well. Suggest 15 - 30 Seconds. Suggest a commensurate # of packets within that time frame for the conditions of the test (OFDM w/ protection, CCK, OFDM, etc..). | D0.6
129 | D. Ward | 6.10.3.4 | T |  | Figure 40 should be more specific regarding misc. losses in the test sytem due to interconnects, combiners, splitters, cable, etc.. | Add a note in the table with Attenuation that clearly states it is the summation of all losses including fixed attenuation, or add a new column to account for additional losses. | D0.6
130 | D. Ward | 6.16 | T |  | Although an informative and useful test, I don't believe that this test belongs in a network standard that relates to performance at Layer 1 and Layer 2 of the OSI model. | Suggest removing the entire test methodology as it does not conform to the scope of IEEE 802 standards. | D0.6
131 | D. Ward | 6.16.1 | T |  | A DSO is not the only method to measure power consumption from a DUT. This test should not restrict measurments to only a DSO | Allow the use of a Data Acquistion System with comparable measurement accuracy. | D0.6
132 | D. Ward | 6.16.2.1 | T |  | The DSO must measure average Voltage and Current - not just average Current | Add the requirement for average voltage. | D0.6
133 | D. Ward | 6.16.2.4 | E |  | Figure 55 does not exist - incorrect reference | Should reference Figure 54 | D0.6
134 | D. Ward | 6.16.2.6 | T |  | There is no accuracy given in regard to "Zeroing" of a Hall Effect Sensor. The sensor must be calibrated - zeroed prior to the start of any measurement. How is this factored in to the current measurement accuracy? | More detail should be provided that stipulates that if a Hall Effect probe is used for current measurements that the accuracy also includes any offset affects of the probe, and that the probe must be "zeroed" prior to use. | D0.6
135 | D. Ward | 6.16.2.6 | T |  | Accuracy is generally a value above and below a reference level. The accuracy should be stipulated as +/- 10mV & +/- 0.5mA. As written it infers only error in one direction | Add +/- to the measurement accuracy. | D0.6
136 | D. Ward | 6.16.2.6 | T |  | Notes a) and b) - How do these correlate to the previous fixed accuracy requirements? The measurement accuracy consider all the test cases to accurate equipment and calculations in all situations | Remove these statements and refine, if necessary, the measurement accuracy of Voltage and Current to provide for ample power measurement accuracy. In this case the Power accuracy is +/- 5uW. | D0.6
137 | D. Ward | 6.16.3.1.1 | T |  | Baseline temperature should have some value of error associated with it / accuracy of temp measurement as in Clause 6.10 | Suggest Temp accuracy of +/- 2 C | D0.6
138 | D. Ward | 6.16.3.3.1 | T |  | A DSO is not the only method to measure power consumption from a DUT. This test should not restrict measurments to only a DSO | Allow the use of a Data Acquistion System with comparable measurement accuracy. | D0.6
139 | D. Ward | 6.16.3.3.1 | T |  | The DSO must measure average Voltage and Current - not just average Current | Add the requirement for average voltage. | D0.6
140 | D. Ward | 6.16.3.3.1 | T |  | The measurement sample rate is not specified / recommended. | A mimium sample rate should be specified to allow accruate and consistent measurements across test platforms. | D0.6
141 | C. Warren | 5.2 |  | Why is there not figure for this environment? Should there be? It may be helpful to have some kind of block diagram | Supply appropriate figure |  | D0.7
142 | C. Warren | 5.3.3.1 Preparation of the test setup |  | As seen from Figure 2, the wired and RF interfaces of the DUT are connected to traffic generators and analyzers capable of generating and gathering 802.11 traffic at the desired attenuation. The whole system should be properly isolated from external interference and other unwanted signals. | Is the wording actually good to have a statement saying you need generators and analyzers to gather data at the desired attn? Would it be better to mention sensitivity of the modulation schemes and bands? I know we have some issues that cards do well at 12 and 6 but do not have good sensitivity at 9mbps and miss packets no matter what. So if I was to use this setup to test fixed rates, this may not matter the path loss. Also, the clause to mention properly isolated from interference and unwanted signals. This is too generic perhaps we should recommend something to isolate Xdb from freq A to Z taking into account bands being tested...saying 95 across the board may not work ...since some shielding may not be that great at A band frequencies nor is it needed. Again should it be driven by the sensitivity of the device? Xdb below the recommended sensitivity of band B/G and A? |  | D0.7
143 | C. Warren | Table 1—Outdoor LOS test parameters for PC external antenna model item 3 |  | The DUT should be placed in test locations such that its positioning is repeatable run-to-run/day-to-day within an area represented by a circle centered at the intended test point, and with a radius of 1.5cm (for 2.4 GHz testing) and 0.75cm (for 5 GHz testing), as measured from a consistent reference point on the DUT base (e.g., back left hand corner of the DUT). This requirement is intended to keep the DUT positioned within less than ¼ wave length run-to-run/day-to-day as one of the factors necessary in presenting a consistent multipath condition to the device. Location marking, fixturing, or some other robust method should be utilized to ensure adherence to this requirement. | This is difficult to achieve to get an accurate position doing outside testing. The land "dirt what have you" is likely to change as days of rain and vegetation occurs. So the ground bounce "multipath parasitics" is hard to make repeatible. If the test area is cement or some kind of level non-erouding anacohic material that would be best. but to get 1.5cm Az and elev for 2.5 and .75 is almost impossible to achieve. I dont have any other suggestions here for this... |  | D0.7
144 | C. Warren | Table 1—Outdoor LOS test parameters for PC external antenna model item 5 |  | APs used for performance testing should be placed such that their antennas are pointing up (straight) and perpendicular to the ground, with the base of the antennas at a fixed height (e.g. 150cm ± 2 cm) above the ground. This requirement is intended to define a consistent antenna orientation, and to adhere to the WLCP manufacturers recommendation to mount the WLCP as high as possible. Fixturing is recommended to provide consistent WLCP placement | This seems to have a simular requirement as item 3 does. By the representiting figure. It seems that the same imposed position requirements should be imposed on the WLCP as well. And the same difficulty will be present in this configuration as well. |  | D0.7
145 | C. Warren | Table 1—Outdoor LOS test parameters for PC external antenna model item 10 |  | During testing, people on the test range shall be kept to a minimum, and no person should be located within 50 meters of the line of sight between the DUT and the WLCP | remove the Line Of Sight from this wording |  | D0.7
146 | C. Warren | Figure 7—WLCP height and orientation test parameter |  | Figure of WLCP | Should a 3 dimensional figure be done here to ensure that the AP isnt tilted forward or sideways? |  | D0.7
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862

## References
References:
IEEE 802.11-05/868r0, now obsolete