## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-06/0153r4
Venue Date: | January 2006
First Author: | Clint Chaplin, TGr Chair
Subject: | Letter Ballot 79 Comment Resolution To-Do List
Full Date: | 2006-01-17
Author(s): | Clint Chaplin
Symbol Technologies
6480 Via Del Oro, San Jose, CA 95119-1208
+1-408-528-2766
clint.chaplin@gmail.com
Abstract:
Letter Ballot 79 Comment Resolution To-Do List
Notice: This document has been prepared to assist IEEE 802.11. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor grants a free, irrevocable license to the IEEE to incorporate material contained in this contribution, and any modifications thereof, in the creation of an IEEE Standards publication; to copyright in the IEEE’s name any IEEE Standards publication even though it may include portions of this contribution; and at the IEEE’s sole discretion to permit others to reproduce in whole or in part the resulting IEEE Standards publication. The contributor also acknowledges and accepts that this contribution may be made public by IEEE 802.11.
Patent Policy and Procedures: The contributor is familiar with the IEEE 802 Patent Policy and Procedures <http:// ieee802.org/guides/bylaws/sb-bylaws.pdf>, including the statement "IEEE standards may include the known use of patent(s), including patent applications, provided the IEEE receives assurance from the patent holder or applicant with respect to patents essential for compliance with both mandatory and optional portions of the standard." Early disclosure to the Working Group of patent information that might be relevant to the standard is essential to reduce the possibility for delays in the development process and increase the likelihood that the draft publication will be approved for publication. Please notify the Chair <stuart.kerry@philips.com> as early as possible, in written or electronic form, if patented technology (or technology under patent application) might be incorporated into a draft standard being developed within the IEEE 802.11 Working Group. If you have questions, contact the IEEE Patent Committee Administrator at <patcom@ieee.org>.

## To-Do List
Line | CID | Volunteer | Technical Issue # | Description | Status
353 | 57 | Michael Montemurro | 4 | Policy Management Server
371 | 63 | Michael Montemurro | 4 | Policy Management Server
372 | 75 | Michael Montemurro | 4 | Policy Management Server
367 | 420 | Michael Montemurro | 4 | Policy Management Server
373 | 609 | Michael Montemurro | 4 | Policy Management Server
374 | 677 | Michael Montemurro | 4 | Policy Management Server
375 | 816 | Michael Montemurro | 4 | Policy Management Server
380 | 928 | Michael Montemurro | 4 | Policy Management Server
376 | 958 | Michael Montemurro | 4 | Policy Management Server
377 | 965 | Michael Montemurro | 4 | Policy Management Server
378 | 1241 | Michael Montemurro | 4 | Policy Management Server
467 | 79 |  | 7 | MIC Issue
524 | 80 |  | 7 | MIC Issue
546 | 82 |  | 7 | MIC Issue
19 | 298 |  | 12 | Fast Transition without RSN
716 | 322 |  | 12 | Fast Transition without RSN
729 | 323 |  | 12 | Fast Transition without RSN
877 | 329 |  | 12 | Fast Transition without RSN
900 | 332 |  | 12 | Fast Transition without RSN
907 | 333 |  | 12 | Fast Transition without RSN
1181 | 508 |  | 12 | Fast Transition without RSN
1182 | 1190 |  | 12 | Fast Transition without RSN
696 | 939 | Various | 15 | Action Frame MIC | Combined proposal needed
697 | 940 | Various | 15 | Action Frame MIC | Combined proposal needed
710 | 941 | Various | 15 | Action Frame MIC | Combined proposal needed
718 | 942 | Various | 15 | Action Frame MIC | Combined proposal needed
731 | 943 | Various | 15 | Action Frame MIC | Combined proposal needed
692 | 994 | Various | 15 | Action Frame MIC | Combined proposal needed
737 | 1271 | Various | 15 | Action Frame MIC | Combined proposal needed
1040 | 108 |  | 16 | PMK-R1 PMK SA
316 | 120 | Michael Montemurro | 17 |  | To be addressed in updates to Section 5
13 | 151 | Jon Edney | 21 | Roam back to current AP
439 | 636 | Frank/Kapil | 22 | Beacon Bloat
532 | 647 | Frank/Kapil | 22 | Beacon Bloat
440 | 747 | Frank/Kapil | 22 | Beacon Bloat
596 | 842 | Frank/Kapil | 22 | Beacon Bloat
600 | 990 | Frank/Kapil | 22 | Beacon Bloat
822 | 1048 | Frank/Kapil | 22 | Beacon Bloat
838 | 1050 | Frank/Kapil | 22 | Beacon Bloat
736 | 705 | Various | 36 | Included with Issue 15
735 | 921 | Various | 36 | Included with Issue 15
740 | 578 | Various | 37 | Included with Issue 15
742 | 735 | Various | 37 | Included with Issue 15
744 | 805 | Various | 37 | Included with Issue 15
745 | 822 | Various | 37 | Included with Issue 15
746 | 832 | Various | 37 | Included with Issue 15
747 | 1147 | Various | 37 | Included with Issue 15
1145 | 733 | Michael Montemurro | 46 | Figure 121H
1146 | 1000 | Michael Montemurro | 46 | Figure 121H
1147 | 1196 | Michael Montemurro | 46 | Figure 121H
1170 | 118 | Michael Montemurro | 47 | RRB Error Handling
1172 | 507 | Michael Montemurro | 47 | RRB Error Handling
1178 | 694 | Michael Montemurro | 47 | RRB Error Handling
1173 | 1064 | Michael Montemurro | 47 | RRB Error Handling
1174 | 1150 | Michael Montemurro | 47 | RRB Error Handling
1188 | 350 |  | 48 | RIC
1209 | 354 |  | 48 | RIC
1215 | 356 |  | 48 | RIC
985 | 105 | Bill Marshall
10 | 148
14 | 152
430 | 190
16 | 295
924 | 334
157 | 373 | Clint Chaplin |  |  | Bill already resolved. Need to accept
317 | 491 | Clint Chaplin |  |  | Rejected in principle
32 | 514
369 | 523
36 | 587 | Clint Chaplin |  |  | Accepted with Bill's proposal
928 | 594
41 | 595 | Clint Chaplin
905 | 606
584 | 655
634 | 659 | Bill Marshall
1123 | 674 | Clint Chaplin |  |  | Key Transfer Protocol issue
811 | 685
926 | 729
234 | 742
54 | 794
927 | 818
858 | 838
1016 | 858
60 | 983
1262 | 999
1100 | 1015
365 | 1025 | Bill Marshall
65 | 1109 | Frank Ciotti
663 | 1171 | Bill Marshall
923 | 1248
74 | 1255 | Steve Emeott
75 | 1259 | Steve Emeott
306 | 1261
819 | 1274

## References
References: