## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-06/0153r9
Venue Date: | January 2006
First Author: | Clint Chaplin, TGr Chair
Subject: | Letter Ballot 79 Comment Resolution To-Do List
Full Date: | 2006-01-17
Author(s): | Clint Chaplin
Symbol Technologies
6480 Via Del Oro, San Jose, CA 95119-1208
+1-408-528-2766
clint.chaplin@gmail.com
Abstract:
Letter Ballot 79 Comment Resolution To-Do List
Notice: This document has been prepared to assist IEEE 802.11. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor grants a free, irrevocable license to the IEEE to incorporate material contained in this contribution, and any modifications thereof, in the creation of an IEEE Standards publication; to copyright in the IEEE’s name any IEEE Standards publication even though it may include portions of this contribution; and at the IEEE’s sole discretion to permit others to reproduce in whole or in part the resulting IEEE Standards publication. The contributor also acknowledges and accepts that this contribution may be made public by IEEE 802.11.
Patent Policy and Procedures: The contributor is familiar with the IEEE 802 Patent Policy and Procedures <http:// ieee802.org/guides/bylaws/sb-bylaws.pdf>, including the statement "IEEE standards may include the known use of patent(s), including patent applications, provided the IEEE receives assurance from the patent holder or applicant with respect to patents essential for compliance with both mandatory and optional portions of the standard." Early disclosure to the Working Group of patent information that might be relevant to the standard is essential to reduce the possibility for delays in the development process and increase the likelihood that the draft publication will be approved for publication. Please notify the Chair <stuart.kerry@philips.com> as early as possible, in written or electronic form, if patented technology (or technology under patent application) might be incorporated into a draft standard being developed within the IEEE 802.11 Working Group. If you have questions, contact the IEEE Patent Committee Administrator at <patcom@ieee.org>.

## To-Do List
Line | CID | Volunteer | Tech Issue # | Description | Controversial Topic # | Status
353 | 57 | Michael Montemurro | 4 | Policy Management Server |  | 11-06-0240
371 | 63 | Michael Montemurro | 4 | Policy Management Server |  | 11-06-0240
372 | 75 | Michael Montemurro | 4 | Policy Management Server |  | 11-06-0240
367 | 420 | Michael Montemurro | 4 | Policy Management Server |  | 11-06-0240
373 | 609 | Michael Montemurro | 4 | Policy Management Server |  | 11-06-0240
374 | 677 | Michael Montemurro | 4 | Policy Management Server |  | 11-06-0240
375 | 816 | Michael Montemurro | 4 | Policy Management Server |  | 11-06-0240
380 | 928 | Michael Montemurro | 4 | Policy Management Server |  | 11-06-0240
376 | 958 | Michael Montemurro | 4 | Policy Management Server |  | 11-06-0240
377 | 965 | Michael Montemurro | 4 | Policy Management Server |  | 11-06-0240
378 | 1241 | Michael Montemurro | 4 | Policy Management Server |  | 11-06-0240
467 | 79 | Kapil/Henry/Nancy/Jesse/Jon | 7 | MIC Issue Protect Vendor Specific IEs? Other IEs? | 4a | Not protecting Vendor Specific IEs.
524 | 80 | Kapil/Henry/Nancy/Jesse/Jon | 7 | MIC Issue Protect Vendor Specific IEs? Other IEs? | 4a | Not protecting Vendor Specific IEs.
546 | 82 | Kapil/Henry/Nancy/Jesse/Jon | 7 | MIC Issue Protect Vendor Specific IEs? Other IEs? | 4a | Not protecting Vendor Specific IEs.
19 | 298 |  | 12 | Fast Transition without RSN | 1 | 11-06-0251-01-000r; need PICS updates
716 | 322 |  | 12 | Fast Transition without RSN | 1 | 11-06-0251-01-000r; need PICS updates
729 | 323 |  | 12 | Fast Transition without RSN | 1 | 11-06-0251-01-000r; need PICS updates
877 | 329 |  | 12 | Fast Transition without RSN | 1 | 11-06-0251-01-000r; need PICS updates
900 | 332 |  | 12 | Fast Transition without RSN | 1 | 11-06-0251-01-000r; need PICS updates
907 | 333 |  | 12 | Fast Transition without RSN | 1 | 11-06-0251-01-000r; need PICS updates
1181 | 508 |  | 12 | Fast Transition without RSN | 1 | 11-06-0251-01-000r; need PICS updates
1182 | 1190 |  | 12 | Fast Transition without RSN | 1 | 11-06-0251-01-000r; need PICS updates
696 | 939 | Various | 15 | Action Frame MIC | 4 | Combined proposal needed Possible it will be solved with proposal for Tech issue #4
697 | 940 | Various | 15 | Action Frame MIC | 4 | Combined proposal needed Possible it will be solved with proposal for Tech issue #4
710 | 941 | Various | 15 | Action Frame MIC | 4 | Combined proposal needed Possible it will be solved with proposal for Tech issue #4
718 | 942 | Various | 15 | Action Frame MIC | 4 | Combined proposal needed Possible it will be solved with proposal for Tech issue #4
731 | 943 | Various | 15 | Action Frame MIC | 4 | Combined proposal needed Possible it will be solved with proposal for Tech issue #4
692 | 994 | Various | 15 | Action Frame MIC | 4 | Combined proposal needed Possible it will be solved with proposal for Tech issue #4
737 | 1271 | Various | 15 | Action Frame MIC | 4 | Combined proposal needed Possible it will be solved with proposal for Tech issue #4
1040 | 108 | Bill Marshall? | 16 | PMK-R1 PMK SA contains: PMK-R1 PMKR1Name R1KH-ID R0KH-ID PMKR0Name SPA |  | email sent 1/25 Seems to be sufficient
316 | 120 | Michael Montemurro | 17 |  |  | To be addressed in updates to Section 5 7A updates show this
13 | 151 | Jon Edney | 21 | Roam back to current AP | 6 | discussed at ad-hoc; Jon to write up something soon.
439 | 636 | Frank/Kapil | 22 | Beacon Bloat | 3 | Feedback to slide presentation; policy bit in MDIE? Present updated text later this week. Text based on 11-06-0214-00
532 | 647 | Frank/Kapil | 22 | Beacon Bloat | 3 | Feedback to slide presentation; policy bit in MDIE? Present updated text later this week. Text based on 11-06-0214-00
440 | 747 | Frank/Kapil | 22 | Beacon Bloat | 3 | Feedback to slide presentation; policy bit in MDIE? Present updated text later this week. Text based on 11-06-0214-00
596 | 842 | Frank/Kapil | 22 | Beacon Bloat | 3 | Feedback to slide presentation; policy bit in MDIE? Present updated text later this week. Text based on 11-06-0214-00
600 | 990 | Frank/Kapil | 22 | Beacon Bloat | 3 | Feedback to slide presentation; policy bit in MDIE? Present updated text later this week. Text based on 11-06-0214-00
822 | 1048 | Frank/Kapil | 22 | Beacon Bloat | 3 | Feedback to slide presentation; policy bit in MDIE? Present updated text later this week. Text based on 11-06-0214-00
838 | 1050 | Frank/Kapil | 22 | Beacon Bloat | 3 | Feedback to slide presentation; policy bit in MDIE? Present updated text later this week. Text based on 11-06-0214-00
736 | 705 | Various | 36 | Included with Issue 15 | 4 | Combined proposal needed Possible it will be solved with proposal for Tech issue #4
735 | 921 | Various | 36 | Included with Issue 15 | 4 | Combined proposal needed Possible it will be solved with proposal for Tech issue #4
740 | 578 | Various | 37 | Included with Issue 15 | 4 | Combined proposal needed Possible it will be solved with proposal for Tech issue #4
742 | 735 | Various | 37 | Included with Issue 15 | 4 | Combined proposal needed Possible it will be solved with proposal for Tech issue #4
744 | 805 | Various | 37 | Included with Issue 15 | 4 | Combined proposal needed Possible it will be solved with proposal for Tech issue #4
745 | 822 | Various | 37 | Included with Issue 15 | 4 | Combined proposal needed Possible it will be solved with proposal for Tech issue #4
746 | 832 | Various | 37 | Included with Issue 15 | 4 | Combined proposal needed Possible it will be solved with proposal for Tech issue #4
747 | 1147 | Various | 37 | Included with Issue 15 | 4 | Combined proposal needed Possible it will be solved with proposal for Tech issue #4
1145 | 733 | Michael Montemurro | 46 | Figure 121H |  | Updated. Will submit.
1146 | 1000 | Michael Montemurro | 46 | Figure 121H |  | Updated. Will submit.
1147 | 1196 | Michael Montemurro | 46 | Figure 121H |  | Updated. Will submit.
1170 | 118 | Michael Montemurro | 47 | RRB Error Handling |  | Submisson created based on discussion.
1172 | 507 | Michael Montemurro | 47 | RRB Error Handling |  | Submisson created based on discussion.
1178 | 694 | Michael Montemurro | 47 | RRB Error Handling |  | Submisson created based on discussion.
1173 | 1064 | Michael Montemurro | 47 | RRB Error Handling |  | Submisson created based on discussion.
1174 | 1150 | Michael Montemurro | 47 | RRB Error Handling |  | Submisson created based on discussion.
1188 | 350 | Jon/Kapil | 48 | Can a station make a QoS request during pre-reservation, and request a different QoS request during association? |  | Nancy will accept.
1209 | 354 | Jon/Kapil | 48 | Can a station make a QoS request during pre-reservation, and request a different QoS request during association? |  | Nancy will accept.
1215 | 356 | Jon/Kapil | 48 | Can a station make a QoS request during pre-reservation, and request a different QoS request during association? |  | Nancy will accept.
985 | 105 | Michael Montemurro |  |  | 5 | Action frames vs. Authentication Frames
10 | 148 | Frank/Kapil |  |  |  | Accept Bill's comment resolution
14 | 152 | Henry Ptasinski |  | What is an "Authenticator"? |  | "Authenticator" to be reserved for 802.1X authenticator only. Use "IEEE 802.1X Authenticator" Refer to lower entities as "R0 Key Holder" and "R1 Key Holder" and "PTK Holder" Need to go through draft and identify uses of "Authenticator" and note which new name to use.
430 | 190 |  |  |  |  | Should RRB appear in Figure 11? Email sent 1/25 Proposed resolution text
16 | 295 | Bill Marshall |  |  |  | Beacon Bloat? Comment Resolution for 336 might be sufficient.
157 | 373 | Clint Chaplin |  |  |  | Need to rewrite the comment resolution as "Accept", and vote it in.
317 | 491 | Clint Chaplin |  |  |  | Rejected in principle
32 | 514 | Michael Montemurro |  |  |  | Restructuring to put RRB in annex? Mike needs to put together a resolution.
369 | 523 | Bill Marshall |  | Over-reserve reservations? |  | One of the major discussion points
36 | 587 | Clint Chaplin |  |  |  | Accepted with Bill's proposal
41 | 595 | Clint Chaplin
905 | 606 | Bill Marshall |  |  |  | Accept, Bill to make change
584 | 655 |  |  |  |  | Write Comment Resolution text defending Mobility Domain. Email sent 1/25 Proposed text in comment resolution spreadsheet
634 | 659 | Bill Marshall |  | Timeout Interval |  | IANA motion took care of this Bill will update the comment resolution
1123 | 674 | Clint Chaplin |  |  |  | RRB issue. AP to AP communication mentioned in 11i. Email sent 1/25 Resolution text on reflector. Rename section to "Remote Request Broker Communication", with corresponding changes in text.
811 | 685 |  |  | Use of second 256 bits of MSK. |  | Ask Jesse/Nancy. Email sent 1/25 Jessie OK with this. Kapil to write text for the comment resolution. "The next 256 bits of the MSK is not currently used in 802.11."
54 | 794 | Michael Montemurro |  |  |  | Part of cleanup of 5.4
858 | 838 | Bill Marshall |  |  |  | Propose to reject Reject with proposed text in comment resolution spreadsheet.
1016 | 858 | Michael Montemurro |  | 8.5A: two different mechanisms for handling 802.1X port | 10 | It really isn't an "802.1X" port; it's a 802.11 port. Discussed, and Jon to write something up.
60 | 983 | Michael Montemurro |  | MDID == lowest BSSID? |  | "Accepted in principle. We recommend that MDID be set to the MAC address of the Mobility Domain Controller."
1262 | 999 |  |  |  |  | Remove paragraph? I have a counter to this one. Fifth paragraph of 11.4 mentions how the SME of the HC decides whether to admit or refuse the TSPEC for an ADDTS. We want to affect the behavior of "the SME of the HC" in this case. It gets rid of the offending ill-defined terms of "Resource Manager" and "Scheduler". So this one is for the list in Phoenix.
1100 | 1015 | Bill Marshall |  | Get Rid of Pre-Reservation? | 7
65 | 1109 | Frank Ciotti |  | First Contact |  | FT Initial Association
663 | 1171 | Bill Marshall |  | Responses to TSPEC requests? |  | Needs to be rewritten; Bill will do so.
74 | 1255 | Steve Emeott |  | Resource Query |  | 06/245r0
75 | 1259 | Steve Emeott |  | Resource Query |  | 06/245r0
306 | 1261 |  |  | HCCA? |  | Reject.
819 | 1274 | Bill Marshall |  | Include SSID In PMK-R0

## References
References: