## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-06/0153r14
Venue Date: | January 2006
First Author: | Clint Chaplin, TGr Chair
Subject: | Letter Ballot 79 Comment Resolution To-Do List
Full Date: | 2006-03-05
Author(s): | Clint Chaplin
Symbol Technologies
6480 Via Del Oro, San Jose, CA 95119-1208
+1-408-528-2766
clint.chaplin@gmail.com
Abstract:
Letter Ballot 79 Comment Resolution To-Do List
Notice: This document has been prepared to assist IEEE 802.11. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor grants a free, irrevocable license to the IEEE to incorporate material contained in this contribution, and any modifications thereof, in the creation of an IEEE Standards publication; to copyright in the IEEE’s name any IEEE Standards publication even though it may include portions of this contribution; and at the IEEE’s sole discretion to permit others to reproduce in whole or in part the resulting IEEE Standards publication. The contributor also acknowledges and accepts that this contribution may be made public by IEEE 802.11.
Patent Policy and Procedures: The contributor is familiar with the IEEE 802 Patent Policy and Procedures <http:// ieee802.org/guides/bylaws/sb-bylaws.pdf>, including the statement "IEEE standards may include the known use of patent(s), including patent applications, provided the IEEE receives assurance from the patent holder or applicant with respect to patents essential for compliance with both mandatory and optional portions of the standard." Early disclosure to the Working Group of patent information that might be relevant to the standard is essential to reduce the possibility for delays in the development process and increase the likelihood that the draft publication will be approved for publication. Please notify the Chair <stuart.kerry@philips.com> as early as possible, in written or electronic form, if patented technology (or technology under patent application) might be incorporated into a draft standard being developed within the IEEE 802.11 Working Group. If you have questions, contact the IEEE Patent Committee Administrator at <patcom@ieee.org>.

## To-Do List
Tech Issue # | Controversial Topic # | Line | CID | Volunteer | Description | Status
4 |  | 353 371 372 367 373 374 375 380 376 377 378 | 57 63 75 420 609 677 816 928 958 965 1241 | Michael Montemurro | Policy Management Server | 11-06-0240
7 | 4a | 467 524 546 | 79 80 82 | Kapil/Henry/Nancy/Jesse/Jon | MIC Issue Protect Vendor Specific IEs? Other IEs? | We will not protect Vendor Specific IEs.
12 | 1 | 19 716 729 877 900 907 1181 1182 | 298 322 323 329 332 333 508 1190 |  | Fast Transition without RSN | 11-06-0251-05-000r-fast-bss-transition-in-non-rsn.doc with PICs now on reflector Mike to take a look. | Will discuss proposed resolution at March meeting.
15 | 4 | 696 697 710 718 731 692 737 | 939 940 941 942 943 994 1271 |  | Action Frame MIC | 11-06-0165-01-000r-mic-calculation.doc accepted at the ad-hoc. 11-06-0165-02-000r-mic-calculation.doc now available on the reflector | Will discuss proposed resolution in March meeting.
16 |  | 1040 | 108 | Bill Marshall? | PMK-R1 PMK SA contains: PMK-R1 PMKR1Name R1KH-ID R0KH-ID PMKR0Name SPA | email sent 1/25 Seems to be sufficient
17 |  | 316 | 120 | Michael Montemurro |  | To be addressed in updates to Section 5 7A updates show this
21 | 6 | 13 | 151 | Jon Edney | Roam back to current AP | 11-06-0325-01-000r-fixing-problems-with-ptksa-generation-and-deletion.doc | Discuss in teleconference.
22 | 3 | 439 532 440 596 600 822 838 | 636 647 747 842 990 1048 1050 | Frank/Kapil | Beacon Bloat | 11-06-0235-00-000r-addressing-beacon-bloat.doc posted. Revised 11-06-0235-02-000r-addressing-beacon-bloat.doc posted, addressing Bill's comments. | Will discuss proposed resolution in March meeting.
36 | 4 | 746 747 | 832 1147 |  | MIC Calculation | 11-06-0165-01-000r-mic-calculation.doc accepted at the ad-hoc. 11-06-0165-02-000r-mic-calculation.doc now available on the reflector | Will discuss proposed resolution in March meeting.
37 | 4 | 740 742 744 745 746 747 | 578 735 805 822 832 1147 |  | Definition of "muted". Problem solved by not including header into MIC calculation. | 11-06-0165-01-000r-mic-calculation.doc accepted at the ad-hoc. 11-06-0165-02-000r-mic-calculation.doc now available on the reflector | Will discuss proposed resolution in March meeting.
46 |  | 1145 1146 1147 | 733 1000 1196 | Michael Montemurro | Figure 121H | 11-06-0270-00-000r-updates-to-figure-121h-tgr-draft.doc | Incorporate into comment resolution spreadsheet
47 |  | 1170 1172 1178 1173 1174 | 118 507 694 1064 1150 | Michael Montemurro | RRB Error Handling | 11-06-0308-03-000r-remote-request-broker-error-handling.doc | Will discuss proposed resolution in March meeting
48 |  | 1188 1209 1215 | 350 354 356 | Jon/Rajneesh | Can a station make a QoS request during pre-reservation, and request a different QoS request during association? | 11-06-0336-00-000r-no-change-after-reservation.doc | Will discuss proposed resolution in March meeting
| 5 | 985 | 105 | Michael/Bill | Action frames vs. Authentication Frames | In resolution spreadsheet | Will discussed proposed resolution in March meeting
|  | 10 | 148 | Frank/Kapil |  | Accept Bill's comment resolution
|  | 14 | 152 | Henry Ptasinski | What is an "Authenticator"? | 11-06-0323-00-000r-authenticator-clarifications.doc | Incorporate into comment resolution spreadsheet. Discuss in teleconference.
|  | 430 | 190 |  |  | Should RRB appear in Figure 11? Email sent 1/25 Proposed resolution text
|  | 16 | 295 | Bill Marshall |  | Beacon Bloat? Comment Resolution for 336 might be sufficient.
|  | 157 | 373 | Clint Chaplin |  | Need to rewrite the comment resolution as "Accept", and vote it in.
|  | 317 | 491 | Clint Chaplin |  | Rejected in principle
|  | 32 | 514 | Michael Montemurro |  | Resolution text given to Bill. | Incorporate into comment resolution spreadsheet
|  | 369 | 523 | Bill Marshall | Over-reserve reservations? | One of the major discussion points
|  | 36 | 587 | Clint Chaplin |  | Accepted with Bill's proposal
|  | 41 | 595 | Clint Chaplin
|  | 905 | 606 | Bill Marshall |  | Accept, Bill to make change
|  | 584 | 655 |  |  | Write Comment Resolution text defending Mobility Domain. Email sent 1/25 Proposed text in comment resolution spreadsheet
|  | 634 | 659 | Bill Marshall | Timeout Interval | IANA motion took care of this Bill will update the comment resolution
|  | 1123 | 674 | Clint Chaplin |  | RRB issue. AP to AP communication mentioned in 11i. Email sent 1/25 Resolution text on reflector. Rename section to "Remote Request Broker Communication", with corresponding changes in text.
|  | 811 | 685 |  | Use of second 256 bits of MSK. | Ask Jesse/Nancy. Email sent 1/25 Jessie OK with this. Kapil to write text for the comment resolution. "The next 256 bits of the MSK is not currently used in 802.11."
|  | 54 | 794 | Michael Montemurro |  | Part of cleanup of 5.4
|  | 858 | 838 | Bill Marshall |  | Propose to reject Reject with proposed text in comment resolution spreadsheet.
| 10 | 1016 | 858 | Michael Montemurro | 8.5A: two different mechanisms for handling 802.1X port | Comment resolution text proposed by Michael. Might need to pass by Henry | Incorporate into comment resolution spreadsheet
|  | 60 | 983 | Michael Montemurro | MDID == lowest BSSID? | "Accepted in principle. We recommend that MDID be set to the MAC address of the Mobility Domain Controller."
|  | 1262 | 999 |  |  | Remove paragraph? I have a counter to this one. Fifth paragraph of 11.4 mentions how the SME of the HC decides whether to admit or refuse the TSPEC for an ADDTS. We want to affect the behavior of "the SME of the HC" in this case. It gets rid of the offending ill-defined terms of "Resource Manager" and "Scheduler". So this one is for the list in Phoenix.
| 7 | 1100 | 1015 | Bill Marshall | Get Rid of Pre-Reservation? | Comment resolution in spreadsheet. | Will discussed proposed resolution in March meeting
|  | 65 | 1109 | Frank Ciotti | First Contact | FT Initial Association
|  | 663 | 1171 | Bill Marshall | Responses to TSPEC requests? | Needs to be rewritten; Bill will do so.
|  | 74 | 1255 | Steve Emeott | Resource Query | 11-06-0245-00-000r-simple-qos-resource-query.doc | Need to discuss proposed text in March meeting
|  | 75 | 1259 | Steve Emeott | Resource Query | 11-06-0245-00-000r-simple-qos-resource-query.doc | Need to discuss proposed text in March meeting
|  | 306 | 1261 |  | HCCA? | Reject.
|  | 819 | 1274 | Bill Marshall | Include SSID In PMK-R0

## References
References: