## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-06/0578r10
Venue Date: | July 2006
First Author: | Clint Chaplin
Subject: | Letter Ballot 82 Comment Resolution To-Do List
Full Date: | 2006-07-21
Author(s): | Clint Chaplin
Symbol Technologies
6480 Via Del Oro, San Jose, CA 95119-1208
+1 408 528 2766
clint.chaplin@gmail.com
Abstract:
Letter Ballot 82 Comment Resolution To-Do List
Notice: This document has been prepared to assist IEEE 802.11. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor grants a free, irrevocable license to the IEEE to incorporate material contained in this contribution, and any modifications thereof, in the creation of an IEEE Standards publication; to copyright in the IEEE’s name any IEEE Standards publication even though it may include portions of this contribution; and at the IEEE’s sole discretion to permit others to reproduce in whole or in part the resulting IEEE Standards publication. The contributor also acknowledges and accepts that this contribution may be made public by IEEE 802.11.
Patent Policy and Procedures: The contributor is familiar with the IEEE 802 Patent Policy and Procedures <http:// ieee802.org/guides/bylaws/sb-bylaws.pdf>, including the statement "IEEE standards may include the known use of patent(s), including patent applications, provided the IEEE receives assurance from the patent holder or applicant with respect to patents essential for compliance with both mandatory and optional portions of the standard." Early disclosure to the Working Group of patent information that might be relevant to the standard is essential to reduce the possibility for delays in the development process and increase the likelihood that the draft publication will be approved for publication. Please notify the Chair <stuart.kerry@philips.com> as early as possible, in written or electronic form, if patented technology (or technology under patent application) might be incorporated into a draft standard being developed within the IEEE 802.11 Working Group. If you have questions, contact the IEEE Patent Committee Administrator at <patcom@ieee.org>.

## To-Do List
Tech Issue # | Controversial Topic # | Line | CID | Volunteer | Description | Status | Further Actions
1 |  |  | 191 205 636 638 641 643 1052 1056 1095 1100 1103 1117 1122 1141 1158 | Bill Marshall | Reassociation vs (Re)association | Bill will present proposals in Jacksonville. 11-06-0554-00 changes the usage of FT to be Reassociation frames 11-06-0555-00 changes the usage of FT Initial Association to be Association frames | 11-06-0554 passed in JAX 11-06-0555 failed in JAX
2 |  |  | 363 364 366 371 372 373 374 376 377 378 379 380 381 382 383 388 389 400 401 | Bill Marshall | Changing (Re)Association Request/Response to class 1 frames (i.e. how to handle state 2) (1) (as we have been) Continue to fight the battle that "Authenticated" means something in State 2, and hope that future amendments and revisions will continue this tradition; (2) (give in) Admit that State 2 only means that an exchange of frames named "Authentication" has happened, not that the STA is Authenticated. Leave clause 5.6 untouched. Go to state 2 after exchange of the FT Request/Response; (3) (go further) Deprecate State 2 completely, and combine everything currently in state 2 in state 1. This would fix the base draft so that "Authenticated" doesn't appear in this figure. (4) (go even further) Fix the procedures for RSN so that State 2 is entered part way through the 4-way handshake. Thus (Re)associate would be allowed in State 1 (since the STA completes its association before authenticating), and some data frames are allowed in State 1 (those through the 802.1X uncontrolled port) and the term "Authenticated" means something in the figure in 5.6. | Two submissions (558r0 for alternative 3, 559r0 for alternative 2). Group voted 9-0-1 to present 559r0 in Jacksonville. | 11-06-0559 passed in JAX
3 |  |  | 820 | Kapil Sood | RRB Remote Request error action frame MIC'd by current AP | Eliminate error message from local RRB to STA. dot11FTReservationLimit needs to be modified to be enforced by the target (remote) RRB. Change the dot11FTRemoteRequestTimeout to apply to the STA instead of the AP. Waiting for text from Kapil. | 11-06-0620-00 passed in JAX
4 |  |  | 735 736 737 738 | Bill Marshall | Should the count of Auxiliary IEs be in the RDIE? | 11-06-0560 Refer to solution for #33 and #36. Present in Jacksonville. | 11-06-0560 passed in JAX
5 |  |  | 84 86 1165 1166 | Bill Marshall | FT Initial Association in non-RSN, and fix definition of FT Initial Association | Rename "initial association" to "initial MD association" Add a section/text in 8A.2 describing FT Initial Association for non-RSN. Document 11-06-0603 | 11-06-0603 passed in JAX
6 |  |  | 476 522 780 1090 1092 1101 1116 1135 1137 1138 1152 1154 1155 1216 1273 1274 1283 1292 | Henry Ptasinski: 1101 Bill Marshall: others | Timeout interval (Reassociation Deadline and Key Lifetime) in msg w/o MIC. Add MIC or move to msg#4 | Get rid of reassociation deadline and key lifetime for message #2 How is timeout defined? Henry to come up with solution. | 11-06-0605-01 passed in JAX
7 |  |  | 680 881 882 885 886 887 905 1298 1326 1327 | Bill Marshall: lifetime calculation and distribution Keven Hayes: AP initiating re-key | Whether local policy at the R0KH can decrease the key lifetime of the PTKSA to be less than that of the MSK | R0KH key lifetime can be less than MSK lifetime, and subordinate keys have same lifetime. Accept Kevin Hayes offer to provide a mechanism for the AP to tell the STA to initiate a re-keying. | 11-06-0605-01 passed in JAX
8 |  |  | 47 320 324 831 873 891 892 913 915 929 931 954 978 980 987 988 1009 1019 1049 1058 1096 1131 1147 1181 1182 1285 1464 1466 1468 | Kapil Sood Nancy Cam-Winget Rajneesh Kumar Dorothy Stanley Michael Montemurro | Define how the R0KH retrieves the MSK from the AS. Specify the security protocol and authorization mechanism in place to have the 802.1X to give up the key to another entity. | Discussion of concepts on security architecture socialized at the ad-hoc. 11-06-0566-01-000r-tgr-security-architecture.ppt presented in JAX | Waiting for additional info/normative text June/July
9 |  |  | 1268 | Dorothy Stanley Henry Ptasinski | Add STA and Target AP addresses to Authentication frames to make them independent of transport | Write text to address these issues. Encapsulate the FT in EAPOL key messages (see 12, 13) | Resolutions ready to vote on at San Diego
10 |  |  | 767 |  | Whether the "STA Address" field in the Action frames identifies the "STA's MAC address" ot the "STA's Supplicant's MAC address" | Comment accepted. | Accepted in JAX
11 |  |  | 600 601 607to612 615to627 630 632to637 639 642 1490 | Bill Marshall Dorothy Stanley Henry Ptasinski | Explanation of policy bits in MDIE | Comment 600 has proposed text. Dorothy and Henry to look it over. | Accepted in JAX
12 |  |  | 428 429 432 434 425 466 467 468 488 489 490 513 514 515 542 543 544 586 757 | Dorothy Stanley Henry Ptasinski | Remove MIC Extent from messages | Write text to address these issues. Encapsulate the FT in EAPOL key messages (see 10, 13) | Accepted comments
13 |  |  | 1265 | Kapil Sood | Is a version number needed for the FT Authentication sequence? | Write text to address these issues. Encapsulate the FT in EAPOL key messages (see 10, 12) | Resolved as reject; awaiting vote in July
14 |  |  | 564 683 691 701 710 711 712 1423 | Bill Marshall | Add more examples of RICs, and more text regarding Confirmation RIC | 11-06-0561 for all but #564 11-06-0562 for #564 | 11-06-0561 passed 11-06-0562 failed
15 |  |  | 237 238 829 830 831 832 833 919 920 1010 1011 1021 1022 1023 1024 | Bill Marshall | Clarify inactive/active PTK | Bill to propose text | Accepted in JAX
16 |  |  | 1403 1414 | Kapil Sood Michael Montemurro Bill Marshall | Explain the semantics of "suggested" resource IE | Proposed resolutions in comments Kapil to document corner case situation. | Accepted in JAX
17 |  |  | 579 580 581 582 1070 | Bill Marshall | Text for Neighbor Report IE. Refer to 11-06-0282 | Figure out delta between 11k and what we want. | Accepted in JAX
18 | [5 empty] | Done
19 | [5 empty] | Done
20 | [5 empty] | Done
21 |  |  | 953 967 968 1178 |  | Provide detailed specification for picking names of R0KH-ID and R1KH-ID Dependent on tech issue 28 | No additional text needed. | Accepted in JAX
22 |  |  | 1253 1254 | Kapil Sood | Evaluate possible security hole with Authentication frames used for over-the-air reservations No concensus at ad-hoc that this issue needs to be examined. | Seems to be a possible attack. | Need to somehow differentate message 3 in a resv from message 3 from base. Change sequence numbers. Awaiting vote in July.
23 |  |  | 1262 | Kapil Sood | Evaluate possible security hole with Action frames used for over-the-DS reservations | Proposed text will be provided by Kapil Proposed comment resolutions need to be examined | Accepted comment
24 |  |  | 862 976 989 |  | Take out Key Hierarchy, as out of scope of 11r; let IETF define it and key distribution. | Next step is to wait for presentation on state machine (Nancy Cam-Winget, Kapil Sood, doc. 11-06/566) to address 976 and 989. | Accepted in JAX
25 |  |  | 834 902 903 | Nancy Cam-Winget | Define protocol to revoke keys | Proposed text will be provided. | Waiting for additional info/normative text June/July
26 |  |  | 865 910 927 |  | Take out three-level key hierarchy | Proposed comment resolution is "reject" | Accepted in JAX
27 |  |  | 570 872 879 | Henry Ptasinski Kapil Sood | Take out PSK support | Issue accepted in principle, text to be written to address the security requirements for the use of PSK in 802.11r. | Waiting for additional info/normative text June/July
28 |  |  | 273 275 277 295 990 991 996 997 998 999 1000 1001 | Michael Montemurro | Take out Mobility Domain Controller | Clause 5.3 and 5.4 deleted. Mike to revise 8.5A.6. | 11-06-0173-02 to be voted on in July
31 |  |  | 197 229 239 231 |  | Take out TSPEC negotiation | Clause 5.3 and 5.4 deleted. | Accepted in JAX
32 |  |  | 258 347 602 603 604 1079 1120 1238 1252 |  | Take out ability to make multiple reservations, and mechanism to limit multiple reservations | Ad-hoc agreed to remove reservation limit, but keep ability to make multiple reservations. | Accepted in JAX
33 |  |  | 705 | Bill Marshall | Take out Auxiliary IEs in RIC | Accepted. Refer to document 11-06-0560, where Auxiliary IEs become superfluos due to the combining under Resource IEs and the definition of type Resource IEs. | 11-06-0560 passed
34 |  |  | 725 726 728 731 1392 1393 1394 1397 1398 | Rajneesh Kumar | Take out mandatory/optional designation of RDIEs | Provide text on a proposal for resolution. | 791, 792 available for a vote
35 |  |  | 38 259 260 391 1066 1121 1123 1124 1125 1149 1236 1368 1382 1422 1454 1483 1484 |  | Take out ability to make reservations | Discussed to death. | Accepted resolutions
36 |  |  | 151 158 232 337 341 552 703 799 810 1085 1104 1390 | Bill Marshall | Limit Resource reservations to QoS, or identify all possible resources by name | Document 11-06-0560 specifies that only QoS is supported for Resource IE. Defining the specific type of resources in clause 5 is not appropriate. | 11-06-0560 passed
41 |  |  | 208 213 214 404 407 1431 1432 1440 1441 1442 | Rajneesh Kumar | Take out "More Data" bit | Provide material supporting comments. | 11-06-0730-00-000r-overloading-more-bit.ppt rejected.
42 |  |  | 331 |  | Specification of method to switch channel back and forth |  | Accepted in JAX
43 |  |  | 362 867 | Kapil Sood Jesse Walker | Provide details of possible AP architectures and Network Topologies |  | Resolved
44 |  |  | 1041 | Dorothy Stanley Kapil Sood | Provide measurements of the FT mechanisms to show that they actually work | Dorothy has a paragraph to add to the introduction | Motion in July to add paragraph.
45 |  |  | 1063 1266 | Kapil Sood Jesse Walker | Same as #22 |  | Need to somehow differentate message 3 in a resv from message 3 from base. Change sequence numbers. Awaiting vote in July.
46 |  |  | 1064 |  | Take out multiple protocol options (base, reservation, air, DS, RSN, non-RSN) |  | Commentor to develop specific criteria for satisfying the comment by July
47 |  |  | 1202 1203 |  | Take out over-the-DS procedures |  | Accepted reject resolutions.
48 |  |  | 1334 1335 1363 |  | Take out ability of RRB to limit or block resource requests |  | 11-06-0620-00 passed in JAX
49 |  |  | 1339 1340 |  | Provide justification of default values of the RRB configuration |  | 11-06-0620-00 passed in JAX
50 |  |  | 1349 1350 1351 |  | Take out RRB request/response message definitions |  | Accepted resolutions
51 |  |  | 1364 |  | Specify mechanisms to secure over-the-DS communication |  | Rendered moot
52 |  |  | 677 |  | Provide empirical-based guidelines for setting Timeout intervals |  | Accepted resolutions
53 |  |  | 141 |  | Introduce a scheme to minimize packet loss |  | Accepted in JAX
54 |  |  | 437 441 454 457 491 493 501 504 |  | Complaints about complexity of criteria for including IEs in frames | Put out on Reflector. No response yet. Decided to go with it as is; final decision in JAX. | Accepted comments
55 |  |  | 652 | Dan Harkins | Alternate Beacon Bloat proposal | 11-06-0637-00-000r-secure-key-distribution-and-authorization-protocol.doc, 11-06-0695-00-000r-secure-three-party-protocol-preso.ppt presented in JAX | Voted on proposal; 4-4-8 was result.
56 |  |  | 839 | Dorothy Stanley | Modifications to Clause 8.4.6.1. | 11-06-0832-00-000r-preauthentication.doc | Vote on text in July
57 |  |  | 1109 1132 1148 |  | Unavoidable race condition with final message of sequence | Put out on Reflector. No response yet. | Accepted resolutions
58 |  |  | 1139 1140 1156 1157 |  | Reassociation Deadline timer definition | Put out on Reflector. | Accepted in JAX
59 |  |  | 1194 |  | Replay Counter Initialization | Email posted to reflector; no response Comment provisionally accepted during teleconference | Accepted in JAX
60 |  |  | 1261 1264 1385 | Michael Montemurro Kapil Sood Rajneesh Kumar | Resource reservation: provisional or reserved? | Previously discussed by TG: resolution at that time was pre-reservation == reservation Sentement in JAX is to be as silent as TGe in this area. | Submission and motion in July
61 |  |  | 1407 1497 | Michael Montemurro Kapil Sood | AP processing of RIC RDIEs after a reservation failure | Volunteers to discuss and come back with recommendations and normative text. | Accepted resolutions
62 |  |  | 875 | Dan Harkins | Secure 3-party protocol alternative for 8.5A.6 | 11-06-0637-00-000r-secure-key-distribution-and-authorization-protocol.doc, 11-06-0695-00-000r-secure-three-party-protocol-preso.ppt presented in JAX | Vote 4-4-8
63 |  |  | 1050 1054 |  | Whether/how to restrict reassociations after the FT Initial Association Should reassociations after a FT Association be restricted to FT reassociations only? How to enforce any limitations? | debate during teleconference | Comment Resolutions accepted at JAX
64 |  |  | 1087 1110 1111 1118 1133 1150 | Bill Marshall | How to show the Data transfer capabilities with the Current AP in the 8A.1.2 figures. Of the alternatives proposed, Frank's suggestion seems to be the best; we'll go with it. | Use Frank's proposal | Accepted in JAX
65 |  |  | 925 934 935 936 960 1015 1016 | Nancy Cam-Winget | Crypto questions | Nothing available during JAX | Vote on comment resolutions in July
|  |  | 33 | Clint Chaplin | Make Before Break
|  |  | 1195 1237 | Steve Emeott | Resource Query

## Comment To-Do
33 | Make before Break | Clint
47 | 8
208 | 41
213 | 41
404 | 41
407 | 41
570 | 27 | Henry
652 | 55
834 | 25 | Nancy
839 | 56
872 | 27 | Henry
873 | 8
875 | 62
879 | 27 | Henry
891 | 8
892 | 8
902 | 25 | Nancy
903 | 25 | Nancy
913 | 8
915 | 8
925 | 65
929 | 8
931 | 8
934 | 65
935 | 65
936 | 65
954 | 8
960 | 65
977 |  | Mike
978 | 8
980 | 8
987 | 8
988 | 8
990 | 28
991 | 28
992 |  | Mike
993 |  | Mike
994 |  | Mike
996 | 28
997 | 28
998 | 28
999 | 28
1000 | 28
1001 | 28
1005 |  | Mike
1006 |  | Mike
1008 |  | Mike
1009 | 8
1015 | 65
1016 | 65
1019 | 8
1041 | 44
1049 | 8 | Kapil
1050 | 63
1058 | 8
1063 | 45
1064 | 46 | Kapil
1096 | 8
1131 | 8
1147 | 8
1149 | Digital cash | Kapil
1181 | 8
1182 | 8
1195 |  | Steve
1237 |  | Steve
1253 | 22
1254 | 22
1261 | 60
1264 | 60
1265 | 13
1266 | 45
1268 | 9
1285 | 8
1385 | 60
1431 | 41
1432 | 41
1440 | 41
1441 | 41
1442 | 41
1464 | 8
1466 | 8
1468 | 8

## References
References: