495 | Choudhury, Abhijit | 7.4A1 | 78 | 3 | T | Y | 78 | 3 | Aggregated MPDU format (A-MPDU) | 7.4A.1 | ST |  | R |  |  | 71 | Does the A-MPDU maximum length of 64K bytes include only the sum of the MPDU lengths, sub-frame lengths, pad bytes or it also includes the minimum seperation bytes calculated from the MPDU density, PHY-bit-rate given in the HT Capability element(page 45)? The aggregation parsing algorithm does not mention this minimum seperation at all. |  | reject. In reply to the commenter: 1. the maximum length of the A-MPDU is the maximum length of the structure called the A-MPDU shown in the figure just above this statement, rather that the maximum length of some subset of fields within it. No other interpretation is possible, and no further clarification is required. 2. The parsing algorithm does not need to be modified. The MPDU density may be achieved in multiple ways, but the most obvious one is to include delimiters with a length field set to zero. This is explicitly called out as legal. Parsing of these delimiters is identical to those with a length field that is non-zero, and no accomodation is required in the parsing algorithm. |  | A-MPDU | Frame Format |  | 16
2369 | Ji, Lusheng | 7.4A.1 | 78 | 11 | T | Y | 78 | 11 | Aggregated MPDU format (A-MPDU) | 7.4A.1 | DT |  | R |  |  | 71 | B0-B1 need to be distinguished so that the MAC can properly handle the A-MPDU. | B0-B1 shall be "01" | reject. The MAC "properly handles" the A-MPDU on the basis of the RXVECTOR AGGREGATION paramter. No additional signalling is necessary within the MAC. |  | A-MPDU | Frame Format |  | 303
8145 | Van Nee, Richard | 7.4A.1 |  |  | T | Y | 78 |  | Aggregated MPDU format (A-MPDU) | 7.4A.1 | ST |  | R |  |  | 71 | It is not mentioned in what MSB/LSB order the fields like Length and Unique Pattern are transmitted | Mention for each field whether LSB is first or last | reject. This is unambiguously defined by subclause 7.1 in the baseline. |  | A-MPDU | Frame Format |  | 324
4756 | McCann, Stephen | 7.4A.1 | 79 | 0 | T | Y | 79 | 0 |  | 7.4A.1 | T |  | R |  |  | 70 | Why is the unique pattern ASCII value N? | Clarification required for this chosen constant | Propose reject. The amendment is not required to justify itself. However, in reply to the commenter, it was necessary to choose some value, and lacking any reason to prefer one 8-bit value over another, the proposal chose this value. |  | A-MPDU | Frame Format |  | 391 |  | Frame Format | 1 | 4756
8118 | Tsoulogiannis, Tom | 7.4A.2 | 80 | 28-29 | T | Y | 80 | 28 | A-MPDU Contents | 7.4A.2 | DT |  | R |  |  | 71 | The 2nd and 3rd statements in this clause do not use the word "shall". | Change wording as follows: "All the MPDUs within an A-MPDU shall be addressed to the same receiver address." "The Duration fields in the MAC Headers of all MPDUs in an A-MPDU shall carry the same value." | reject. There's a move to clean clause 7 of shalls. Statements describing the contents of structures use "is" and then appeal to the statement at the top of clause 7: "A STA shall be able properly to construct a subset of the frames specified in this clause for transmission" where "properly construct" is taken to mean according to the various "is" statements. |  | A-MPDU | Frame Format |  | 139
2377 | Ji, Lusheng | 7.4A.2 | 80 | 30 | T | Y | 80 | 30 | A-MPDU Contents | 7.4A.2 | T |  | R |  |  | 71 | Why are the possible MPDUs in an aggregate limited? | Please clarify, or remove this restriction. | reject. The amendment is not required to justify itself internally. However, in reply to the commenter, it simplifies both the implementation and the protocol when these constraints are present. |  | A-MPDU | Frame Format |  | 544
1749 | Inoue, Yasuhiko | 9.2.5.4.1 | 84 |  | T | Y | 84 |  |  | 9.2.5.4.1 | ST |  | R |  |  | 65 | The order of CTS1 and CTS2 should be reversed. |  | Rejected: there is a logical reason for CTS1 preceeding CTS2 |  | Protection Mechanisms | Coexistence
10025 | Xhafa, Ariton | 9.9.4 | 91 |  | T | Y | 91 |  | PSMP NAV operation | 9.9.4 | T |  | R |  |  | 45 | Lines 22 is not clear. First, a PSMP sequence may start with a CTS-2-Self frame, followed by a PSMP frame PIFS times later. CTS-2-Self frame shall protect PSMP phase. | Include CTS-2-Self transmission for NAV operation during PSMP | Reject - Transmitting CTS-2-Self is a recommended practice - U |  | PSMP | PSMP
2492 | Ji, Lusheng | 9.12 | 97 | 6 | T | Y | 97 | 6 | Frame exchange sequences | 9.12 | T |  | R | Adrian |  | 41 | There is no reason why EBNF is not sufficient to define these frame sequences.delete any extensions. | Change to "are defined using the EBNF format" | reject. It is common practice to define extensions to EBNF where appropriate. The extensions defined here simplify the expression of the 802.11 frame format semantics. |  | MAC Operation | MAC
9995 | Xhafa, Ariton | 9.12 | 97 |  | T | Y | 97 |  | Frame exchange sequences | 9.12 | ST |  | R | Adrian |  | 41 | Need to add the PCO frame exchange to this section. |  | reject. The scope of the frame exchange sequence are frames separated by at most a PIFS. PCO operates outside this framework. |  | MAC Operation | MAC
12261 | Montemurro, Michael | 9.12 | 98 | 5 | T | Y | 98 | 5 | Frame exchange sequences | 9.12 | ST |  | R | Adrian |  | 41 | The frame exchange sequence definitions are impossible to read. | Use timing diagrams or some other appropriate mechanism to explain the allowable frame exchanges. | reject. Timing diagrams cannot express the possible sequences adequately - they can only show examples. The definitions are necessarily complex because the sequences generated by the MAC contain this complexity. The HSMC diagrams are being removed from the baseline 9.12 because they are impossible to maintain. |  | MAC Operation | MAC
1293 | Fischer, Matthew | 9.12 | 98 | 7 | T | Y | 98 | 7 | Frame exchange sequences | 9.12 | T |  | R | Adrian |  | 41 | missing exchange - is CTS+PIFS - Mgmt+bcast not allowed? | allow PIFS after CTS preceding BCAST frame | Reject. The quoted exchange is already included as part of hcf-sequence. |  | MAC Operation | MAC
4555 | Lojko, Peter | 9.12 | 98 |  | T | Y | 98 |  | Frame exchange sequences | 9.12 | ST |  | R | Adrian |  | 41 | Attributes are not defined for Link Adaptation frames | Define attributes MCS-req, MCS-feedback | reject. Merely defining attributes, without using them to express exchange sequence syntax is meaningless. |  | MAC Operation | MAC
4556 | Lojko, Peter | 9.12 | 98 |  | T | Y | 98 |  | Frame exchange sequences | 9.12 | ST |  | R | Adrian |  | 41 | Attributes are not defined for Implicit TxBF | TRQ- Sounding request frame; CALstart - A frame with HT control field in which Calibration Postion is '01' and TRQ = '1'; Cal-sounding-response- A frame in which HT control field is present and Calibration Position is set to '10'; Cal-sounding-complete-A frame in which HT control field is present and Calibration Position field is set to '11'; | reject. Merely defining attributes, without using them to express exchange sequence syntax is meaningless. |  | MAC Operation | MAC
2510 | Ji, Lusheng | 9.12 | 99 | 16 | T | Y | 99 | 16 | Frame exchange sequences | 9.12 | T |  | R | Adrian |  | 41 | possibly missing [RTS CTS] here | ?? | reject. cf-ack-piggybacked-qos-poll-sequence delivers an initial CF-Ack. RTS/CTS/Data+CF-Ack is not a valid sequence. |  | MAC Operation | MAC
2513 | Ji, Lusheng | 9.12 | 100 | 11 | T | Y | 100 | 11 | Frame exchange sequences | 9.12 | T |  | R | Adrian |  | 41 | notation. Use EBNF notation | 1*{txop-sequence} | reject. This changes the meaning to exactly one occurrance. |  | MAC Operation | MAC
2520 | Ji, Lusheng | 9.12 | 101 | 13 | T | Y | 101 | 13 | Frame exchange sequences | 9.12 | T |  | R | Adrian |  | 41 | notation. Use EBNF notation | 1*{initiator-sequence} | reject. This changes the meaning to exactly one occurrance. |  | MAC Operation | MAC
5151 | Meylan, Arnaud | 9.12 | 101 | 20 | T | Y | 101 | 20 | Frame exchange sequences | 9.12 | T |  | R | Adrian |  | 41 | Single ended L-sig protection is not allowed | remove line 20 and 21 | reject. This changes the meaning to exactly one occurrance. |  | MAC Operation | MAC
2522 | Ji, Lusheng | 9.12 | 101 | 43 | T | Y | 101 | 43 | Frame exchange sequences | 9.12 | T |  | R | Adrian |  | 41 | BA is undefined, either as a frame name or as a non-terminal | define it | reject: The "design" is the result of a selection process that incorporated some features and excluded others from proposals submitted to TGn. The set of features present has received broad support from TGn members. |  | MAC Operation | MAC
2529 | Ji, Lusheng | 9.12 | 102 | 21 | T | Y | 102 | 21 | Frame exchange sequences | 9.12 | T |  | R | Adrian |  | 41 | "burst" defined as one or more PPDU-not-requiring-response, then used most places as "[burst]" | Change "[burst]" to "{PPDU-not-requiring-response}" wherever it appears | reject. This changes the meaning to exactly one occurrance. |  | MAC Operation | MAC
2531 | Ji, Lusheng | 9.12 | 102 | 46 | T | Y | 102 | 46 | Frame exchange sequences | 9.12 | T |  | R | Adrian |  | 41 | ampdu is an attribute | Match other attributes. This would be italic if my previous comment is rejected. | reject. This changes the meaning to exactly one occurrance. |  | MAC Operation | MAC
2536 | Ji, Lusheng | 9.12 | 103 | 35 | T | Y | 103 | 35 | Frame exchange sequences | 9.12 | T |  | R | Adrian |  | 41 | (BlockAck¦BlockAck) !! | Replace with just BlockAck, or perhaps "(BlockAck¦BlockAckReq)" | reject. Changes being discussed in other ad-hocs limit the order of what goes into an A-MPDU so that any response frame occurs first. |  | MAC Operation | MAC
7888 | Takagi, Masahiro | 9.12 | 103 | 46 | T | Y | 103 | 46 | Frame exchange sequences | 9.12 | DT |  | R | Adrian |  | 41 | 9.10.7.7 says "All frames within an A-MPDU aggregate shall have the same ack policy setting.". This is good to deliver BAR in a robust manner. The definition of PPDU-RD-BAR seems to be inconsistent with this. | Remove Data+QoS+RD+ampdu and "[" and "]" enclosing "implicit-bar". | reject. D1.02 says: "The RDG/More PPDU field shall be set to the same value in all HT Control fields present in a PPDU" |  | MAC Operation | MAC
4557 | Lojko, Peter | 9.12 | 104 |  | T | Y | 104 |  | Frame exchange sequences | 9.12 | ST |  | R | Adrian |  | 41 | Frame exchange sequence for Implicit TxBF are not defined | Define frame exchange sequences based on section 9.20.2 | reject. Changes being discussed in other ad-hocs limit the order of what goes into an A-MPDU so that any response frame occurs first. |  | MAC Operation | MAC
4560 | Lojko, Peter | 9.12 | 104 |  | T | Y | 104 |  | Frame exchange sequences | 9.12 | ST |  | R | Adrian |  | 41 | Frame exchange sequence for PCO operation are not defined | Define frame exchange sequences for PCO operation | reject. These sequences do not attempt to illustrate MLME operation. |  | MAC Operation | MAC
4561 | Lojko, Peter | 9.12 | 104 |  | T | Y | 104 |  | Frame exchange sequences | 9.12 | ST |  | R | Adrian |  | 41 | Frame exchange sequence for ZLF are not defined | Define frame exchange sequence based on 9.22 | Reject. See CID 9995. |  | MAC Operation | MAC
2552 | Ji, Lusheng | 9.14.1 | 105 | 4 |  | Y | 105 | 4 | RIFS Protection | 9.14.1 | ST |  | R | Matthew F |  | 41 | In addition to stating that RIFS sequences shall be protected, the text needs to state how this is done. | State how RIFS sequences are protected, or provide a cross reference to the clause where this is specified. | reject. This is already generated by ht-TXOP-sequence from nav-protected-sequence, from nav-set |  | RIFS | MAC
2551 | Ji, Lusheng | 9.14.1 | 105 | 4 | E | N | 105 | 4 |  | 9.14.1 | T |  | R |  |  | 39 | If 9.14 is not combined with 9.13, then the notion of "protection" needs some clarification | Add text defining the notion of "protection" at the start of 9.14 | reject. 9.13 now includes 9.14, and the introductory text in 9.13 suffices: "9.13.1 Introduction These protection mechanisms ensure that a STA defers transmission for a period of time. These mechanisms are used to insure that non-ERP STAs do not interfere with ERP-frame exchanges between ERP STAs and that non-HT STA do not interfere with HT-frame exchanges between HT STAs. Thereby, allowing non-ERP and/or non-HT STAs to coexist with ERP and/or HT STAs." |  | RIFS | MAC
9996 | Xhafa, Ariton | 9.15 | 105 | 31 | T | Y | 105 | 31 |  | 9.15 | T |  | R |  |  | 65 | "Under L-SIG TXOP Protection operation, the L-SIG field with a Mixed Mode PHY header shall contain a duration value equivalent (except in the case of RTS as described below) to the MAC duration included in the MAC header." As it stands, for EIFS cancellation, CF-End is used, which could be in error. The proposed approach is not prone of CF-End errors. | Change to "Under L-SIG TXOP Protection operation, the L-SIG field with a Mixed Mode PHY header shall contain a duration value till the end of TxOP, while the MAC duration shall contain a duration value till the end of TxOP+(EIFS-DIFS). " | Rejected: CID7308 was accepted and is more approriate for the condition. |  | Protection Mechanisms | Coexistence
9998 | Xhafa, Ariton | 9.15.1 | 106 | 21 | T | Y | 106 | 21 |  | 9.15.1 | T |  | R |  |  | 65 | "… contain an L-SIG Duration up to the endpoint of the MAC duration." This is part of the proposed approach for canceling EIFS when L-SIG protection is used. | Change to "contain an L-SIG duration up to the endpoint of the MAC duration + (EIFS-DIFS)." | Rejected: contradicts CID 7308 and similar to rejected CID 9996 |  | Protection Mechanisms | Coexistence
10000 | Xhafa, Ariton | 9.15.2 | 106 | 30 | T | Y | 106 | 30 |  | 9.15.2 | T |  | R |  |  | 65 | "shall contain an L-SIG Duration up to the endpoint of the MAC duration." Need to change to accommodate the proposed approach for L-SIG protection. | Change to "shall contain an L-SIG duration up to the endpoint of the MAC duration - (EIFS-DIFS)." | Rejected: see CID9996 |  | Protection Mechanisms | Coexistence
10001 | Xhafa, Ariton | 9.15.3 | 106 | 36 | T | Y | 106 | 36 |  | 9.15.3 | T |  | R |  |  | 65 | "to L-SIG duration - HT-SIG duration." This also needs change to accommodate the proposed approach. | Change to "to L-SIG duration + (EIFS+DIFS)." | Rejected: see CID9996 & CID10000 |  | Protection Mechanisms | Coexistence
783 | Durand, Roger | 9.16.2 | 107 | 22 | T | Y | 107 | 22 |  | 9.16.2 | ST |  | R |  |  | 65 | What priority is training feedback? How is it scheduled? | "the adpatation of transmit parameters by training feedback " should not be allowed during a txop without justification. | Rejected: priority of duration not relevant here. Comment does not apply to this section. |  | Protection Mechanisms | Coexistence
7325 | Miller, Robert | 19.16.3 | 108 | 5 | T | Y | 108 | 5 |  | 9.16.3 | T |  | R |  |  | 65 | A QSTA may not send a CF end, as this may be interpreted by HCCA-operating QSTAs as the end of a CFP, possibly disrupting CFP polling operations (particularly in adjacent cells) | Use a different frame type to signal completion of EDCA transmission in a TXOP. | Rejected: CF-end is required because it is the only frame that resets the NAV in legacy STAs. Furthermore, in HCCA there is a BSS ID check on the CF-end for resetting the NAV. |  | Protection Mechanisms | Coexistence
11566 | Marshall, Bill | 9.16.3 | 108 | 8 | T | Y | 108 | 8 |  | 9.16.3 | T |  | R |  |  | 65 | A QSTA can't send a CF end, as this may be interpreted in adjacent cells by HCCA-operating QSTAs as the end of a CFP, disrupting CFP polling operations | Use a different frame type to signal completion of EDCA transmission in a TXOP. | Rejected: See CID7325 |  | Protection Mechanisms | Coexistence
2603 | Ji, Lusheng | 9.18 | 111 | 14 | T | Y | 111 | 14 | PSMP | 9.18 | DT |  | R |  |  | 45 | PSMP may conflict with CFP/CP partition in PCF/HCCA. | Either specify that PSMP only applies to EDCA BSSs or provide specifcation text for how PSMP should not violate PCF/HCCA CFP/CP boundries. | Reject - The AP is the one that initiates the PSMP and hence, there is no problem with overlapping with CFP/CP, .... periods as mentioned in the comment - U |  | PSMP | PSMP
6848 | Myles, Andrew | 9.18 |  |  | T | Y | 111 |  | PSMP | 9.18 | DT |  | R |  |  | 45 | It appears that PSMP that was created to overcome some of the overheads of regular EDCA However, it is replaces a relatively simple but overhead laden system with massve complexity and its own overheads. The complexity is related the specificaton and implemenation of the infrastructure required and the scheduler required. The overheads ae related to new management frames, new protocol and inefficiencies from poor schedulers. 802.11 suceeded where Hyperlan2 failed because it was simple and worked! Why are we redesigning 802.11 to be a new Hyperlan2? | Either prove the efficiency and usefulness of PSMP in a working implemenation or remove it from the specification. I suspect similar comments apply to other parts of the specification, but I have rn out of time to review the rest. | Reject - The idea is not just to address EDCA overheads but at the same time address the issue of Power Efficiency. This would mean adding new mechanisms which might require intelligent implementations - U |  | PSMP | PSMP
4772 | McCann, Stephen | 9.18.1.1 | 111 | 17 | T | Y | 111 | 17 | PSMP sequence | 9.18.1.1 | DT |  | R | Naveen K |  | 45 | I think it should be remembered that an AP is also an STA (see my comment 43 above). Hence I think that this sections requires some re-writing | Clarify when an AP differs from an STA. | Reject: Other areas of the standard talk about setting up a traffic stream do not find it necessary to make this distinction as it is clearly established else where that only a non-AP STA can establish a TSPEC - U |  | PSMP | PSMP
7626 | Stephens, Adrian | 9.18.1.1 |  |  | T | Y | 111 |  | PSMP sequence | 9.18.1.1 | ST |  | R |  |  | 45 | The Min DLT2ULT parameter needs to be a read-only parameter of the MIB. It should also include some measure of propagation time and thinking time. | Recommend that this parameter is replaced with SIFS+ a new MAC read-only MIB parameter with value 16us of name PSMP_MinDLT2ULT | Reject - Fix the value to 32us (Vote 6 - 1) |  | PSMP | PSMP
1355 | Fischer, Matthew | 9.18.1.1 | 112 | 9 | T | Y | 112 | 9 | PSMP sequence | 9.18.1.1 | T |  | R |  |  | 45 | missing word | change "basic" to "BSS Basic" | Reject - Because the change can cause problem in OBSS scenario - U |  | PSMP | PSMP
3860 | Kandala, Srinivas | 9.18.1.1 | 112 | 10 | T | Y | 112 | 10 | PSMP sequence | 9.18.1.1 | DT |  | R |  |  | 45 | Is there any reason why Minimal DLT2ULT Delay should be 32 microseconds? Why isnt a SIFS duration sufficient. | Set the Minimal DLT2ULT Delay value to 16 microseconds. | Reject - SIFS may be sufficient if data is sent from one queue. With PSMP it is possible that data might have to be sent from multiple queues. Hence, SIFS is not sufficient - U |  | PSMP | PSMP
1770 | Jang, KyungHun | 9.18.1.1.2 | 113 |  | T | Y | 113 |  | Up Link Transmission | 9.18.1.1.2 | T |  | R |  |  | 45 | When nothing is transmitted by QSTA during its scheduled Uplink transmission time, there is no way for an QAP to determine whether QSTA does not have anything to transmit or QSTA did not receive PSMP frame correctly. | Provide more detailed behaviors of STA and AP when STA does not have any frames to be transmitted during its ULT. QSTA should transmit NULL frame when it does not have anything to transmit. If AP receives the NULL frame from the STA, it may schedule a 'reverse-direction' traffic to STA as far as the remaining ULT for the corresponding STA allows. On the other hand, if AP senses the medium idle for the duration of a NULL frame, it resends the PSMP frame based on the interpretation that the initial PSMP delivery was not successful. | Reject - Knowledge about the reason why the ULT is not used can help to use ULT. However, the ULT can only be used by STAs that are not part of PSMP and they are awake. 5 - 1 (Reject) |  | PSMP | PSMP
1371 | Fischer, Matthew | 9.18.1.1.2 | 114 | 1 | T | Y | 114 | 1 | Up Link Transmission | 9.18.1.1.2 | T |  | R |  |  | 45 | missing word | change "TSID field" to "TSID set field" | Reject - Use resolution from CID 6922 |  | PSMP | PSMP
10005 | Xhafa, Ariton | 9.18.1.1.2 | 114 | 7 | T | Y | 114 | 7 | Up Link Transmission | 9.18.1.1.2 | DT |  | R |  |  | 45 | "The AP may transmit a PSMP-recovery frame if the currently scheduled ULT duration is longer than the total time of PSMP recovery frame plus PIFS." Sending the PSMP recovery frame should not be the only option and could result in un-necessary increase in complexity. CTS-2-Self should also be an option to recover unused ULTs. | Change to "The AP may transmit a PSMP-recovery frame or non-HT CTS-2-Self frame (with its MAC duration protecting till the end of PSMP phase) if the currently scheduled ULT duration is longer than the total time of PSMP recovery frame or CTS-2-Self frame plus PIFS." | Defer - 2, Reject 4. The suggestion from the group indicates that CTS-2self can be sent in the remaining ULT. It is not required to add the text to explicitly indicate that. |  | PSMP | PSMP
786 | Durand, Roger | 9.18.1.1.2.1 | 114 | 20 | T | Y | 114 | 20 | Scheduling of Up Link Transmissions | 9.18.1.1.2.1 | ST |  | R |  |  | 45 | confusion | across diferent stations some HT some not is the 1US always a SIFS? If yes then please clearly state this | Reject - Line 22, 23 address this confusion - U |  | PSMP | PSMP
7136 | Perahia, Eldad | 9.18.2 | 114 | 33 | T | N | 114 | 33 | Multi-phase PSMP | 9.18.2 | DT |  | R |  |  | 45 | In order to allocate the minimum amount of time to each STA, the AP should use the Peak Data Rate not the Minimum Data Rate. | in line 33, change Minimum Data Rate to Peak Data Rate | Reject - U The text related to the parameter Minimum Data Rate,.. Is an informative note. - U |  | PSMP | PSMP
1772 | Jang, KyungHun | 9.18.2 | 114 |  | T | Y | 114 |  | Multi-phase PSMP | 9.18.2 | T |  | R |  |  | 45 | In 802.11e amendment, the resource request using Quese Size Field or the TXOP Duration Request field of QoS Control Field is optional. But in PSMP, resource request mechanism based on these parameters is crucial to the effectiveness of multi-phase PSMP operation in its power saving capability. The usage of these QoS parameters in the resource request being optional within the PSMP exchange would keep the participating STA's from saving its power to the fullest potential that PSMP mechanism provides. | Resource Request using Quese Size Field or the TXOP Duration Request field of QoS Control Field in multi-phase PSMP shall be mandatory when PSMP is used. | Reject - The comment and the resolution seem to suggest that the AP should allocate the requested resources by the STA (conveyed by the QoS control field). This cannot be guaranteed. - U |  | PSMP | PSMP |  |  |  | PSMP | 0 | 1772
7266 | Raissinia, Ali | 9.18.2.1 | 116 | 8 | T | Y | 116 | 8 | PSMP Power management | 9.18.2.1 | DT |  | R |  |  | 45 | Remove the CF-End as a means to end PSMP sequence. This adds unnecessary complexity to the receiver since the use of CF-End is to reset the NAV. Having only one scheme i.e. use of "more PSMP" bit would be sufficient and thus reduces interoperability issues. | Fix it. | Reject - Even with the use of More PSMP bit, you need CF End to reset the NAV because the PSMP sequence length is dynamic - U |  | PSMP | PSMP
1403 | Fischer, Matthew | 9.18.3.1 | 116 | 35 | T | Y | 116 | 35 | ULT payload retransmission | 9.18.3.1 | DT |  | R |  |  | 45 | allow STA to determine its scheduling - this is what the next paragraph is doing anyway | add "or during the contention period between PSMP sequences." to the end of the paragraph | Reject - Following section adds the required clarification - U |  | PSMP | PSMP
11616 | Shao, Huai-Rong | 9.18.3.1 | 116 | 36 | T | N | 116 | 36 | ULT payload retransmission | 9.18.3.1 | DT |  | R | Hakirath, Naveen |  | 45 | A STA that cannot complete retransmissions in the last Sub-PSMP of the current Service Interval may transmit the data outside the PSMP sequence. However, frames transmitted outside the scheduled SP under EDCA are subject to the AC prioritization. | Since PSMP-enabled STAs can use MTBA within the PSMP sequence, the PSMP-enabled STAs should be allowed to retransmit data outside the scheduled PSMP using MTBA. This helps in further improving | Reject : Use of MTBA outside PSMP is not allowed. - U Defer - Need a submission to address the issues raised - U |  | PSMP | PSMP
4081 | Kerry, Stuart | 9.18.4 | 117 | 5-7 | T | Y | 117 | 5 | Unscheduled PSMP | 9.18.4 | DT |  | R |  |  | 45 | When the trigger frame is sent by the non_AP_QSTA, and the STA supports both APSD and PSMP, how is it decided whether a PSMP duration will be started or a U-APSD. | It may be necessary to indicate that the non_AP_QSTA that sent the trigger frame preferrs to use the U-APSD, and cannot tolerate the latency involved in the PSMP setup. Hence we may need a dynamic method to switch the access policy between U-APSD and U-PSMP, without having to do a TSPEC negotiation. | Reject - The benefit of the proposed mechanism is not clear - U |  | PSMP | PSMP
1407 | Fischer, Matthew | 9.18.4 | 117 | 6 | T | Y | 117 | 6 | Unscheduled PSMP | 9.18.4 | ST |  | R |  |  | 45 | do not like the wording regarding the PS-Poll frame as a trigger frame -just not "specky" enough - also, there is a problem in that the PS-Poll frame does not have a QOS Control field/TID, so for which AC/TID is it a trigger? Also, distinguish legacy vs HT STA sending a PS-Poll and even then, HT with and without PSMP advertised. | make an explicit statement regarding just exactly how a PS-POLL frame can be used as a trigger frame - how does the AP react with respect to TID/AC? Suggest: AP can send frames from an TID/AC. And presumably, this only works if the STA sending the PS-Poll has also advertised itself as PSMP, but not for legacy STA. Write it as such. | Reject - U |  | PSMP | PSMP
6931 | Nanda, Sanjiv | 9.18.4 | 117 | 31 | T | Y | 117 | 31 | Unscheduled PSMP | 9.18.4 | DT |  | R |  |  | 45 | Use of delayed BA with MTBA. Does this require and ACK? | Complex rule. Disallow this use of MTBA with delayed BA | Reject : Adding the additional constraint of delaying the BA, to be sent only outside PSMP is complex as well - U |  | PSMP | PSMP
1419 | Fischer, Matthew | 9.19.4 |  |  | T | Y | 119 |  | Fast Link Adaptation using explicit feedback | 9.19.4 | ST |  | R | Gal |  | 63 | If there is a combination of channel feedback information and MFB (MCS feedback) returned by a device as feedback information, then what is the transmitter supposed to do or allowed to do? | Define the rules of precedence when a device receives both CSI and MCS feedback information within a single frame: explicitly state that the transmitter is free to do whatever it wishes with both MCS feedback and CSI feedback (i.e. use, ignore, modify) | Rejected because: Nowhere within the draft is it defined what the requester does with the MFB. Therefore there is no need to specifcally say it can do whatever it wants |  | Link Adaptation | Beamforming & Adaptation |  | 3989
2657 | Ji, Lusheng | 9.2 | 119 | 23 | T | Y | 119 | 23 |  | 9.2 | DT |  | R |  |  | 39 | Beam forming should only be used for unicast frames. | Specify what frames may use beam forming. | reject. 9.20.1 states: "In order for a transmitting STA to calculate an appropriate steering matrix for transmit spatial processing when transmitting to a specific receiving STA, the transmitting STA needs to have an accurate estimate of the channel that it is transmitting over." However, if an implementation found some way of using the mechanisms described here to determine the channel accurately for all STA in its BSS, and could find a way to use those channels to determine a beamsteering matrix that improved reception at those STA, why should the standard seek to prohibit that? |  | MAC Operation
2658 | Ji, Lusheng | 9.2 | 119 | 23 | T | Y | 119 | 23 |  | 9.2 | DT |  | R |  |  | 39 | It is not clear how to invoke Mac protection for transmissions using beam forming. MAC protections such as RTS/CTS and beacon initiated CFP all designed for omni-directional data transmissions since the protection frames are broadcast. With beam forming, area covered by MAC protection mechanism is no longer the same as data transmission, hence no longer effective. | Either take beam forming out of this specification, or provide a reasonable solution such as directional MAC to solve this problem. | reject. The purpose of beamforming is not to extend range (which is limited by omidirectional RTS/CTS and signal field transmission), but to increase rate at range. The range of the BSS is limited by the omnidirectional transmissions, and this is not changed by the existence of beamforming. Current systems successfully cope with a disparity of protection range (RTS/CTS) and data range. |  | MAC Operation
12009 | Basson, Gal | 9.21.2 Fig n46, n47 | 127 | 10, 12 | T | N | 127 | 10 | Procedure | 9.21.2 | DT |  | R | solomon | 06/886 | 62 | Allow only one ZLF per announcement | Remove "or ZLFs" | Rejected on the grounds that we need multiple ZLFs to support antenna selection. |  | Antenna Selection | Beamforming & Adaptation | Suggested resolution(Tomoya); Change "D" to "R" at column 'Resn Status'. Change 'Resolution' column; Rejected. Series of ZLFs would be allowed in Antenna Selection. In other cases, one ZLF per announcement, as described in 06/0886.
294 | Benveniste, Mathilde | 9.23 | 129-130 |  | T | Y | 129 |  |  | 9.23 | DT |  | R |  |  | 65 | When a 20 MHz station is transmitting or receiving on the control channel, none of the other channels can be used for other transmissions in the BSS. It is possible, however, to increase the BSS throughput even beyond what is achievable by a 40 MHz channel if the MAC included the option for multichannel use, while respecting use of the same channels by OBSSs. | Provide a way for other channel(s) to be used simultaneously with the control channel in a BSS, while observing CCA and virtual carrier sense on all channels. The CCC MAC makes this possible. | Rejected: the CCC reduces throughput in 2.4MHz band |  | Coexistence | Coexistence
7899 | Takagi, Masahiro | 9.23.6 | 130 |  | T | Y | 130 |  |  | 9.23.6 | ST |  | R |  |  | 65 | A 40MHz capable HT STA shall be able to distinguish between reception of 40MHz PPDU and reception of 20MHz PPDU. | Add text to reflect the comment. | Rejected: because there is no defined way to differentiate between non-HT duplcate and legacy transmission on the control channel. |  | Coexistence | Coexistence
2745 | Ji, Lusheng | 9.23.7 | 131 | 1 | T | Y | 131 | 1 |  | 9.23.7 | ST |  | R |  |  | 65 | Allowing STA sending CF-END is dangerous as it may stop CFP established by PCF/HCCA APs. | Define a new frame for terminating unused portion of TXOPs. | Rejected: See CID7325 |  | Coexistence | Coexistence
2746 | Ji, Lusheng | 9.23.8 | 131 | 3 | T | Y | 131 | 3 |  | 9.23.8 | T |  | R |  |  | 65 | This text belongs in the same clause as normal protection measures | Make change indicated in comment | Rejected: this clause is primarily to describe 20/40MHz operation, not protection. |  | Coexistence | Coexistence
11742 | Marshall, Bill | 9.23.8 | 131 | 3 | T | Y | 131 | 3 |  | 9.23.8 | T |  | R |  |  | 65 | This text belongs in the same clause as normal protection measures | as in comment | Rejected: this clause is primarily to describe 20/40MHz operation, not protection. |  | Coexistence | Coexistence
2747 | Ji, Lusheng | 9.23.9 | 131 | 11 | T | Y | 131 | 11 |  | 9.23.9 | T |  | R |  |  | 65 | This text belongs in 9.6 with other multi-rate procedures | Integrate this text into 9.6 | Rejected: this clause is primarily to describe channel width switching rather than rate selection. |  | Coexistence | Coexistence
438 | Chaplin, Clint | 10.3.7.3.2 | 136 | 12 | T | Y | 136 | 12 |  | 10.3.7.3.2 | T |  | R |  |  | 39 | "The parameter may be present only if the MIB attribute dot11HTCapabilityImplemented is true." | "The parameter shall be present only if the MIB attribute dot11HTCapabilityImplemented is true." | reject. This parameter will be absent when associating with a non-HT AP. |  | MLME
10343 | Engwer, Darwin | 11 |  |  | T | Y | 142 |  |  | 11 | T |  | R |  |  | 39 | After combination of the base standard (802.11ma), subsequent ammendments and more focused individual changes, there remain unresolved inconsistencies between the text in this clause and other clauses. This applies to this clause and all subclauses thereof. | Resolve the inconsistencies. | reject. The commenter does not provide sufficient information to determine either the problem or a remedy that would suffice. |  | MAC Management
4013 | Kerry, Stuart | 11.1.2.1.1 | 142 | 17-21 | T |  | 142 | 17 |  | 11.1.2.1.1 | DT |  | R |  |  | 39 | How does the transmission of the secondary beacon reconcile to the PSMP Service Interval schedules that have already been established as stated in 11.4.4(page 147, lines 11-14); the transmission time of the secondary beacon, may co-incide with the scheduled service interval of an STA. | Once an STBC capable QSTA is admitted into the BSS,does it include a recycling of the TSPEC's that have already been established. This would be a very high overhead. | reject. The commenter proposes no change. In reply to the commenter - the service period is not necessarily tied to the beacon interval, or any multiple or submultiple of it - although it may be. An AP may position a service period so that it doesn't collide with either beacon or secondary beacon - i.e. by using the same period as the beacon and a start offset that is not half a beacon period. |  | MAC Management
1007 | Fischer, Matthew | 11.14.1 | 151 | 27 | T | Y | 151 | 27 | PSDU Length Limit Rules | 11.14.1 | T |  | R |  |  | 71 | make normative | change "declares" to "shall declare" | reject. There is already a normative requirement for the HT STA to include this element. The referenced text is intended to be descriptive. |  | A-MPDU | Frame Format |  | 246
1009 | Fischer, Matthew | 11.14.1 | 152 | 13 | T | Y | 152 | 13 | PSDU Length Limit Rules | 11.14.1 | T |  | R |  |  | 71 | extra words | remove "NOTE -" | reject. This is the correct form for including informative text according to IEEE-SA style guide rules. |  | A-MPDU | Frame Format |  | 250
7686 | Stephens, Adrian | A4.15.1 |  |  | T | N | 265 |  | MAC Enhancements for Higher Throughput | A4.15.1 | DT |  | R |  |  | 45 | HTM10.2.1 probably needs to be mandatory based on HTM10.2 | Add HTM10.2:M dependency. | Reject - U |  | PICS | PSMP
10314 | Kwak, Joe | Annex A | 266 | HTM5.4 | T | Y | 266 | 0 |  | Annex A | DT |  | R |  |  | 39 | Capability should be mandatory for HT-APs, optional otherwise. | Modify Status column accordingly. | reject. The PICS correctly represents the requirements of the preceding clauses in which support for HT-delayed BA is implicit if you support delayed BA and you are an HT STA. |  | PICS | MAC
10317 | Kwak, Joe | Annex A | 267 | HTM9 | T | Y | 267 | 0 |  | Annex A | DT |  | R |  |  | 39 | Capability should be mandatory for HT-APs, optional otherwise. | Modify Status column accordingly. | reject. The PICS correctly represents the functionality of the preceding clauses in which a STA never has to offer an RD grant, and a STA that is offered an RD grant can completely ignore this. |  | PICS | MAC
11910 | Ketchum, John | A4.15.1 | 268 |  | T | Y | 268 |  |  | A4.15.1 | T |  | R |  |  | 39 | HTM11: No reference to link adaptation with implicit feedback | Add HTM11.3: Protocol capability: Link adaptation using implicit feedback; References 7.1.3.8, 7.2.2.2, 9.19.5 (proposed new section), 9.20.2; Status: CF15:O | reject. This PICS entry relates to MCS feedback. There is nothing we need to say about implicit MCS feedback, because there is no associated signaling or normative behaviour. Implicit TxBF feedback does have associated signalling and behaviour, and this is included in item HTM12. |  | PICS | MAC
10321 | Kwak, Joe | Annex A | 268 | HTM11.1 | T | Y | 268 | 0 |  | Annex A | DT |  | R |  |  | 39 | Capability should be mandatory for HT-APs, optional only in STAs which implement HTM11.2. | Modify Status column accordingly. | reject. The PICS correctly represents the functionality of the preceding clauses in which a STA need never generate a +HTC frame, and a STA need never generate a response that is modified in any way by the existence +HTC frame. |  | PICS | MAC
10322 | Kwak, Joe | Annex A | 268 | HTM11.2 | T | Y | 268 | 0 |  | Annex A | DT |  | R |  |  | 39 | Capability should be mandatory for HT-APs, optional only in STAs which implement HTM11.1. | Modify Status column accordingly. | reject. The PICS correctly represents the functionality of the preceding clauses in which a STA need never generate a +HTC frame, and a STA need never generate a response that is modified in any way by the existence +HTC frame. |  | PICS | MAC
10323 | Kwak, Joe | Annex A | 269 | HTM12.1 | T | Y | 269 | 0 | PICS | Annex A | DT |  | R |  |  | 62 | Capability should be mandatory for HT-APs, optional otherwise. | Modify Status column accordingly. | Mandatory or optional status of a feature is not determined by PICS. No support in Beamforming ad hoc for making transmission of TxBF frames by APs mandatory. |  | PICS | Beamforming & Adaptation |  | 10323, 10324, 10325 would be resolved at once.
10324 | Kwak, Joe | Annex A | 269 | HTM12.2 | T | Y | 269 | 0 | PICS | Annex A | DT |  | R |  |  | 62 | Capability should be mandatory for all STAs.. | Modify Status column accordingly. | Mandatory or optional status of a feature is not determined by PICS. No support in Beamforming ad hoc for making reception of TxBF frames by STAs mandatory. |  | PICS | Beamforming & Adaptation |  | 10323, 10324, 10325 would be resolved at once.
10325 | Kwak, Joe | Annex A | 269 | HTM12.7 | T | Y | 269 | 0 | PICS | Annex A | DT |  | R |  |  | 62 | Capability should be mandatory for HT-APs, optional otherwise. | Modify Status column accordingly. | Mandatory or optional status of a feature is not determined by PICS. No support in Beamforming ad hoc for making support of calibration procedure byAPs mandatory. |  | PICS | Beamforming & Adaptation |  | 10323, 10324, 10325 would be resolved at once. |  |  | NO
10327 | Kwak, Joe | Annex A | 269 | HTM14 | T | Y | 269 | 0 | PICS | Annex A | DT |  | R |  |  | 62 | Capability should be mandatory for all STAs.. | Modify Status column accordingly. | Rejected on the grounds that: ZLFs are defined as optional in the text, so optionality in the PICS is fully consistent with the text. Also, ZLFs should not be mandatory because they are only used for optional features and protection is provided for STAs that do not support them. |  | PICS | Beamforming
10326 | Kwak, Joe | Annex A | 269 | HTM13 | T | Y | 269 | 0 | PICS | Annex A | DT |  | R |  |  | 71 | Capability should be mandatory for all STAs.. | Modify Status column accordingly. | reject. Antenna selection is clearly optional as there are HT capability bits that describe support for it. |  | PICS | Frame Format |  | 211
10328 | Kwak, Joe | Annex A | 270 | HTM15.1 | T | Y | 270 | 0 |  | Annex A | DT |  | R |  |  | 39 | Capability should be mandatory for HT-APs, optional otherwise. | Modify Status column accordingly. | reject. The PICS correctly represents the functionality of the preceding clauses in which support for STBC is optional for both non-AP STAs and APs. |  | PICS | MAC
10329 | Kwak, Joe | Annex A | 270 | HTM15.2 | T | Y | 270 | 0 |  | Annex A | DT |  | R |  |  | 39 | Capability should be mandatory for HT-APs, optional otherwise. | Modify Status column accordingly. | reject. The PICS correctly represents the functionality of the preceding clauses in which support for STBC is optional for both non-AP STAs and APs. |  | PICS | MAC
10330 | Kwak, Joe | Annex A | 271 | HTP1.3 | T | Y | 271 | 0 | PICS | Annex A | DT |  | R |  |  | 71 | Capability should be mandatory for all STAs.. | Modify Status column accordingly. | reject. Greenfield mode is clearly optional as there are HT capability bits that describe support for it. |  | PICS | Frame Format |  | 225
11871 | Tsien, Chih | Annex C | 271 |  | T | Y | 271 |  |  | Annex C | DT |  | R |  |  | 39 | Nss=1 (incl. STA to STA) should benefit from other HT enhancements over 11a and 11g, such as ABF, Short-GI and LDPC | HTP2.3.2 optional, not mandatory | Note, the comment wrongly refers to Annex C. reject. This entry in the PICS states that Nss=2 is mandatory for an AP, but not a non-AP STA. There is nothing preventing support of only Nss=1 between STAs, which is what the commenter appears to want. |  | MAC SDL
108 | Audeh, Malik | Annex C | 275 | 3 | T | Y | 275 | 3 |  | Annex C | T |  | R |  |  | 39 | This section looks a little vague and non-specific. | Eliminate it, or fill it in with the relevant changes. | reject. The changes help the reader of Annex C to determine its scope more accurately. See CID 3152. |  | MAC SDL
1557 | Hartman, Chris | Annex C | 275 | 3 | T | N | 275 | 3 |  | Annex C | T |  | R |  |  | 39 | No changes to this section at all? | The draft seems to specify quite a number of changes | reject. The commenter does not provide a recommended change. However, in response to the commenter, please see response to CID 3152. |  | MAC SDL
804 | Durand, Roger | annex c |  |  | T | Y | 275 |  |  | annex c | ST |  | R |  |  | 39 | missing section | formal description of MAC operation, empty. | reject. 802.11e established the precident of not maintaining Annex C. It is not feasible for TGn to maintain Annex C as it is dependent on 802.11e behaviour. |  | MAC SDL
10364 | Engwer, Darwin | C |  |  | T | Y | 275 |  |  | Annex C | T |  | R |  |  | 39 | After combination of the base standard (802.11ma), subsequent ammendments and more focused individual changes, there remain unresolved inconsistencies between the text in this clause and other clauses. This applies to this clause and all subclauses thereof. | Resolve the inconsistencies. | reject. It is hard to understand how the additional statement that something is not described is inconsistent. |  | MAC SDL
12025 | Basson, Gal | General |  |  | T | N |  |  | General | General | DT |  | R |  |  | 36 | The number and complexity of the PHY features should be reduced. |  | GenAdHoc: The commenter did not state which features to consider for elimination, and the features that are currently included have been selected by an 802 process. |  | General | General | 8105

## Headings
HID | Clause | Title | Page | Topic
| 0 | General | 0 | General
1 | 1 | Overview | 2 | General
318 | 10 | Layer management | 131 | Interfaces
319 | 10.1 | Overview of management model | 131 | Interfaces
320 | 10.2 | Generic management primitives | 131 | Interfaces
321 | 10.3 | MLME SAP interface | 131 | MLME
343 | 10.3.10 | Start | 136 | MLME
344 | 10.3.10.1 | MLME-START.request | 136 | MLME
345 | 10.3.10.1.2 | Semantics of the service primitive | 136 | MLME
346 | 10.3.15 | Channel switch | 137 | MLME
347 | 10.3.15.1 | MLME-CHANNELSWITCH.request | 137 | MLME
348 | 10.3.15.1.2 | Semantics of the service primitive | 137 | MLME
349 | 10.3.15.1.3 | When generated | 138 | MLME
350 | 10.3.15.3 | MLME-CHANNELSWITCH.indication | 138 | MLME
351 | 10.3.15.3.1 | Function | 138 | MLME
352 | 10.3.15.4 | MLME-CHANNELSWITCH.response | 139 | MLME
353 | 10.3.15.4.2 | Semantics of the service primitive | 139 | MLME
322 | 10.3.2 | Scan | 132 | MLME
323 | 10.3.2.2 | MLME-SCAN.confirm | 132 | MLME
324 | 10.3.2.2.2 | Semantics of the service primitive | 132 | MLME
325 | 10.3.6 | Associate | 132 | MLME
326 | 10.3.6.1 | MLME-ASSOCIATE.request | 132 | MLME
327 | 10.3.6.1.2 | Semantics of the service primitive | 132 | MLME
328 | 10.3.6.2 | MLME-ASSOCIATE.confirm | 133 | MLME
329 | 10.3.6.2.2 | Semantics of the service primitive | 133 | MLME
330 | 10.3.6.3 | MLME-ASSOCIATE.indication | 133 | MLME
331 | 10.3.6.3.2 | Semantics of the service primitive | 133 | MLME
332 | 10.3.6.4 | MLME-ASSOCIATE.response | 134 | MLME
333 | 10.3.6.4.2 | Semantics of the service primitive | 134 | MLME
334 | 10.3.7 | Reassociate | 134 | MLME
335 | 10.3.7.1 | MLME-REASSOCIATE.request | 134 | MLME
336 | 10.3.7.1.2 | Semantics of the service primitive | 134 | MLME
337 | 10.3.7.2 | MLME-REASSOCIATE.confirm | 135 | MLME
338 | 10.3.7.2.2 | Semantics of the service primitive | 135 | MLME
339 | 10.3.7.3 | MLME-REASSOCIATE.indication | 135 | MLME
340 | 10.3.7.3.2 | Semantics of the service primitive | 135 | MLME
341 | 10.3.7.4 | MLME-REASSOCIATE.response | 136 | MLME
342 | 10.3.7.4.2 | Semantics of the service primitive | 136 | MLME
354 | 10.4 | PLME SAP interface | 140 | PLME
355 | 10.4.3 | PLME-CHARACTERISTICS.confirm | 140 | PLME
356 | 10.4.3.2 | Semantics of the service primitive | 140 | PLME
357 | 11 | MLME | 142 | MAC Management
358 | 11.1 | Synchronization | 142 | MAC Management
403 | 11.1 | Radio Measurement Procedures | 150 | MAC Management
359 | 11.1.1 | Basic Approach | 142 | MAC Management
360 | 11.1.2 | Maintaining Synchronization | 142 | MAC Management
361 | 11.1.2.1 | Beacon generation in infrastructure networks | 142 | MAC Management
362 | 11.1.2.1.1 | Secondary Beacon Transmission | 142 | MAC Management
363 | 11.1.3 | Acquiring synchronization, scanning | 142 | MAC Management
364 | 11.1.3.1 | Passive scanning | 142 | MAC Management
365 | 11.1.3.2 | Active scanning | 143 | MAC Management
366 | 11.1.3.2.1 | Sending a probe response | 143 | MAC Management
367 | 11.1.3.2.2 | Active Scanning Procedure | 143 | MAC Management
404 | 11.11 | Usage of the Neighbor Report | 150 | MAC Management
405 | 11.12 | Link Measurement | 150 | MAC Management
406 | 11.13 | Measurement pilot frame generation and usage | 151 | MAC Management
407 | 11.14 | A-MPDU operation | 151 | A-MPDU
408 | 11.14.1 | PSDU Length Limit Rules | 151 | A-MPDU
409 | 11.14.2 | MPDU density | 151 | A-MPDU
410 | 11.15 | 40/20 MHz Operation | 151 | Coexistence
411 | 11.15.1 | Basic functionality in BSS 40/20Mhz mode | 151 | Coexistence
412 | 11.15.2 | Operating Modes (Informative) | 152 | Coexistence
413 | 11.15.3 | STA Capabilities (Informative) | 155 | Coexistence
414 | 11.16 | Phased Coexistence Operation | 156 | PCO
415 | 11.16.1 | Rules for Operation at PCO AP | 157 | PCO
416 | 11.16.2 | Rules for Operation at the PCO non-AP STA | 158 | PCO
368 | 11.2 | Power management | 143 | Power Management
369 | 11.2.1 | Power management in an infrastructure network | 143 | Power Management
370 | 11.2.1.1 | Receive operation for non-AP QSTAs using APSD | 143 | Power Management
371 | 11.2.1.3 | TIM types | 143 | Power Management
372 | 11.2.1.5 | AP operation during the CP | 143 | Power Management
373 | 11.2.1.6 | AP operation during the CFP | 144 | Power Management
374 | 11.2.1.7 | STA operation during the CP | 144 | Power Management
375 | 11.2.1.8 | STA operation during the CFP | 145 | Power Management
376 | 11.2.2 | Power management in an IBSS | 145 | Power Management
377 | 11.2.3 | MIMO Power Save Features | 145 | Power Management
378 | 11.2.3.1 | MIMO Power Save support | 145 | Power Management
379 | 11.2.3.2 | Reduced MIMO capability | 145 | Power Management
380 | 11.3 | Authentication and deauthentication | 146 | Security
381 | 11.4 | TS operation | 146 | TSPEC
382 | 11.4.1 | Introduction | 146 | TSPEC
383 | 11.4.2 | TSPEC construction | 146 | TSPEC
384 | 11.4.3 | TS lifecycle | 146 | TSPEC
385 | 11.4.4 | TS Setup | 146 | TSPEC
386 | 11.4.4A | Management of Scheduled PSMP | 146 | PSMP
387 | 11.4.4A.1 | Introduction (Informative) | 146 | PSMP
388 | 11.4.4A.2 | Join PSMP | 147 | PSMP
389 | 11.4.4B | Management of Unscheduled PSMP | 148 | PSMP
390 | 11.5 | Block Ack operation | 149 | Block Ack
391 | 11.5.2 | Multi-TID Block Ack | 149 | Block Ack
392 | 11.5.2.1 | Multiple TID Block Ack management under scheduled PSMP | 149 | PSMP
393 | 11.5.2.2 | Multiple TID Block Ack management under unscheduled PSMP | 149 | PSMP
394 | 11.6 | Higher layer timer synchronization | 149 | Synchronization
395 | 11.7 | DLS operation | 149 | DLS
396 | 11.8 | TPC | 149 | Coexistence
397 | 11.9 | DFS | 149 | Coexistence
398 | 11.9.4 | Selecting and advertising a new channel | 149 | Coexistence
399 | 11.9.5 | Channel Selection Methods for 20/40 MHz Operation | 149 | Coexistence
400 | 11.9.5.1 | Introduction | 149 | Coexistence
401 | 11.9.5.2 | Rules | 150 | Coexistence
402 | 11.9.5.3 | Channel Management at the AP | 150 | Coexistence
417 | 12 | PHY service specification | 158 | PHY Interface
418 | 12.3.4.4 | Vector descriptions | 158 | PHY Interface
419 | 13 | PHY management | 158 | PHY Management
| 17 | OFDM PHY Spec for 5GHz |  | PHY General
2 | 19 | ERP Specification | 0 | PHY General
420 | 2 | Normative references | 2 | General
421 | 20 | High Throughput PHY specification | 159 | PHY General
422 | 20.1 | Introduction | 159 | PHY General
423 | 20.1.1 | Scope | 159 | PHY General
424 | 20.1.2 | High Throughput PHY functions | 160 | PHY General
425 | 20.1.2.1 | High Throughput PLCP sublayer | 160 | PHY General
426 | 20.1.2.2 | High Throughput PMD sublayer | 160 | PHY General
427 | 20.1.2.3 | PHY management entity (PLME) | 160 | PHY General
428 | 20.1.2.4 | Service specification method | 160 | PHY General
429 | 20.1.3 | Operating Mode | 160 | PHY General
430 | 20.2 | High Throughput PHY specific service parameter list | 161 | PHY Interface
431 | 20.2.1 | Introduction | 161 | PHY Interface
432 | 20.2.2 | TXVECTOR parameters | 161 | PHY Interface
441 | 20.2.2.1 | TXVECTOR L_LENGTH | 162 | PHY Interface
442 | 20.2.2.10 | TXVECTOR SMOOTHING | 164 | PHY Interface
443 | 20.2.2.11 | TXVECTOR NOT_SOUNDING | 164 | PHY Interface
444 | 20.2.2.12 | TXVECTOR AGGREGATION | 164 | PHY Interface
445 | 20.2.2.13 | TXVECTOR STBC | 164 | PHY Interface
446 | 20.2.2.14 | TXVECTOR ADVANCED_CODING | 164 | PHY Interface
447 | 20.2.2.15 | TXVECTOR SHORT_GI | 164 | PHY Interface
448 | 20.2.2.16 | TXVECTOR NUM_EXTEN_SS | 164 | PHY Interface
449 | 20.2.2.17 | TXVECTOR ANTENNA_SET | 164 | PHY Interface
433 | 20.2.2.18 | TXVECTOR EXPANSION_MAT | 165 | PHY Interface
434 | 20.2.2.2 | TXVECTOR L_DATARATE | 163 | PHY Interface
435 | 20.2.2.3 | TXVECTOR SERVICE | 163 | PHY Interface
436 | 20.2.2.4 | TXVECTOR TXPWR_LEVEL | 163 | PHY Interface
437 | 20.2.2.5 | TXVECTOR FORMAT | 163 | PHY Interface
438 | 20.2.2.6 | TXVECTOR MCS | 163 | PHY Interface
439 | 20.2.2.7 | TXVECTOR BW | 163 | PHY Interface
440 | 20.2.2.8 | TXVECTOR CH_OFFSET | 163 | PHY Interface
450 | 20.2.2.9 | TXVECTOR LENGTH | 164 | PHY Interface
451 | 20.2.3 | RXVECTOR parameters | 165 | PHY Interface
460 | 20.2.3.1 | RXVECTOR L_LENGTH | 166 | PHY Interface
461 | 20.2.3.10 | RXVECTOR SMOOTHING | 167 | PHY Interface
462 | 20.2.3.11 | RXVECTOR NOT_SOUNDING | 167 | PHY Interface
463 | 20.2.3.12 | RXVECTOR AGGREGATION | 167 | PHY Interface
464 | 20.2.3.13 | RXVECTOR STBC | 167 | PHY Interface
465 | 20.2.3.14 | RXVECTOR SHORT_GI | 167 | PHY Interface
466 | 20.2.3.15 | RXVECTOR NUM_EXTEN_SS | 167 | PHY Interface
452 | 20.2.3.16 | RXVECTOR CHAN_MAT | 168 | PHY Interface
453 | 20.2.3.2 | RXVECTOR RSSI | 166 | PHY Interface
454 | 20.2.3.3 | RXVECTOR L-DATARATE | 166 | PHY Interface
455 | 20.2.3.4 | RXVECTOR SERVICE | 166 | PHY Interface
456 | 20.2.3.5 | RXVECTOR FORMAT | 166 | PHY Interface
457 | 20.2.3.6 | RXVECTOR MCS | 166 | PHY Interface
458 | 20.2.3.7 | RXVECTOR BW | 166 | PHY Interface
459 | 20.2.3.8 | RXVECTOR CH_OFFSET | 167 | PHY Interface
467 | 20.2.3.9 | RXVECTOR LENGTH | 167 | PHY Interface
468 | 20.3 | High Throughput PLCP sublayer | 168 | PLCP
538 | 20.3.1 | Introduction | 168 | PLCP
539 | 20.3.10 | Transmitter RF delay | 223 | PHY Characteristics
540 | 20.3.11 | Slot time | 223 | PHY Characteristics
541 | 20.3.12 | Transmit and receive port impedance | 223 | PHY Characteristics
542 | 20.3.13 | Transmit and receive operating temperature range | 223 | PHY Characteristics
543 | 20.3.14 | PMD Tx specification | 224 | PHY Characteristics
544 | 20.3.14.1 | Transmit Spectrum Mask | 224 | PHY Characteristics
545 | 20.3.14.2 | Spectral Flatness | 225 | PHY Characteristics
546 | 20.3.14.3 | Transmit Power | 225 | PHY Characteristics
547 | 20.3.14.4 | Transmit center frequency tolerance | 225 | PHY Characteristics
548 | 20.3.14.5 | Packet alignment | 225 | PHY Characteristics
549 | 20.3.14.6 | Reduced Interframe Space (RIFS) | 226 | RIFS
550 | 20.3.14.7 | Symbol clock frequency tolerance | 226 | PHY Characteristics
551 | 20.3.14.8 | Modulation accuracy | 226 | PHY Characteristics
552 | 20.3.14.8.1 | Transmit center frequency leakage | 226 | PHY Characteristics
553 | 20.3.14.8.2 | Transmitter constellation error | 226 | PHY Characteristics
554 | 20.3.14.8.3 | Transmitter modulation accuracy (EVM) test | 227 | PHY Characteristics
555 | 20.3.15 | High Throughput PMD receiver specification | 228 | PHY Characteristics
556 | 20.3.15.1 | Receiver minimum input sensitivity | 228 | PHY Characteristics
557 | 20.3.15.2 | Adjacent channel rejection | 228 | PHY Characteristics
558 | 20.3.15.3 | Non-adjacent channel rejection | 229 | PHY Characteristics
559 | 20.3.15.4 | Receiver maximum input level | 229 | PHY Characteristics
560 | 20.3.15.5 | Clear channel assessment (CCA) sensitivity | 229 | CCA
561 | 20.3.15.6 | Received Channel Power Indicator (RCPI) Measurement | 229 | RCPI
562 | 20.3.16 | PLCP transmit procedure | 230 | PLCP
469 | 20.3.17 | PLCP receive procedure | 233 | PLCP
470 | 20.3.2 | PLCP frame format | 168 | PLCP Frame Format
471 | 20.3.2.1 | Transmitter Block Diagram (informative) | 170 | PLCP
472 | 20.3.2.2 | Overview of the PPDU encoding process | 171 | PLCP
473 | 20.3.2.3 | Modulation and Coding Scheme (MCS) | 174 | PLCP MCS
474 | 20.3.2.4 | Timing related parameters | 174 | PLCP
475 | 20.3.2.5 | Mathematical description of signals | 176 | PLCP
476 | 20.3.2.6 | Transmission in the upper/lower 20MHz of a 40MHz channel | 179 | PLCP
477 | 20.3.3 | High Throughput Preamble | 179 | PLCP Preamble
478 | 20.3.3.1 | Introduction | 179 | PLCP Preamble
479 | 20.3.3.2 | Mixed Mode preamble and header fields | 179 | PLCP Preamble
480 | 20.3.3.2.1 | Non-HT portion of mixed mode preamble | 180 | PLCP Preamble
481 | 20.3.3.2.1.1 | Cyclic shift definition for the non-HT fields. | 180 | PLCP Preamble
482 | 20.3.3.2.1.2 | Non-HT Short Training Field | 181 | PLCP Preamble
483 | 20.3.3.2.1.3 | Non-HT Long Training Field | 182 | PLCP Preamble
484 | 20.3.3.2.1.4 | The Non-HT Signal Field | 183 | PLCP Header
485 | 20.3.3.2.2 | The High Throughput portion of mixed mode preamble | 184 | PLCP Preamble
486 | 20.3.3.2.2.1 | Cyclic shift for the High Throughput portion of Mixed Mode preamble | 184 | PLCP Preamble
487 | 20.3.3.2.2.2 | The High Throughput Signal Field | 185 | PLCP Header
488 | 20.3.3.2.2.2.1 | CRC calculation | 189 | PLCP Header
489 | 20.3.3.2.2.3 | The HT STF training symbol | 190 | PLCP Preamble
490 | 20.3.3.2.2.4 | The HT-LTF long training Field | 191 | PLCP Preamble
491 | 20.3.3.3 | Greenfield preamble and header fields | 195 | PLCP Greenfield
492 | 20.3.3.3.1 | Cyclic shift for the Green Field preamble and header fields | 195 | PLCP Greenfield
493 | 20.3.3.3.2 | Short training field | 195 | PLCP Greenfield
494 | 20.3.3.3.3 | Signal field | 195 | PLCP Header
495 | 20.3.3.3.3.1 | Signal Field for 20 MHz operation | 196 | PLCP Header
496 | 20.3.3.3.3.2 | Signal Field for 40 MHz operation | 196 | PLCP Header
497 | 20.3.3.3.4 | Long training field | 197 | PLCP Preamble
498 | 20.3.4 | The Data Field | 197 | PLCP Data
499 | 20.3.4.1 | The service field | 197 | PLCP Data
500 | 20.3.4.2 | Scrambler | 197 | PLCP Data
501 | 20.3.4.3 | Coding | 198 | PLCP Coding
502 | 20.3.4.3.1 | Encoder Parsing operation | 198 | PLCP Coding
503 | 20.3.4.3.2 | Coding and puncturing | 198 | PLCP Coding
504 | 20.3.4.3.3 | Low density parity check codes (optional ECC) | 199 | PLCP Coding
505 | 20.3.4.3.3.1 | LDPCC Code Rates and Codeword Block Lengths | 199 | PLCP Coding
506 | 20.3.4.3.3.2 | LDPCC Encoder | 200 | PLCP Coding
507 | 20.3.4.3.3.3 | Parity check matrices | 200 | PLCP Coding
508 | 20.3.4.3.3.4 | LDPCC PPDU encoding process | 201 | PLCP Coding
509 | 20.3.4.3.3.5 | LDPC Parser | 203 | PLCP Coding
510 | 20.3.4.4 | Data Interleaver | 203 | PLCP Interleaver
511 | 20.3.4.4.1 | Overview | 203 | PLCP Interleaver
512 | 20.3.4.4.2 | Stream Parser | 204 | PLCP Interleaver
513 | 20.3.4.4.3 | Frequency interleaver | 204 | PLCP Interleaver
514 | 20.3.4.5 | QAM Mapping | 206 | PLCP OFDM
515 | 20.3.4.5.1 | Space-Time-Block-Coding (STBC) | 206 | PLCP STBC
516 | 20.3.4.6 | Pilot Subcarriers | 207 | PLCP OFDM
517 | 20.3.4.7 | OFDM Modulation | 209 | PLCP OFDM
518 | 20.3.4.7.1 | Spatial Mapping | 209 | PLCP OFDM
519 | 20.3.4.7.2 | 20MHz HT transmission | 212 | PLCP OFDM
520 | 20.3.4.7.3 | Transmission in 40MHz HT mode | 213 | PLCP OFDM
521 | 20.3.4.7.4 | Transmission in HT duplicate mode. | 214 | PLCP OFDM
522 | 20.3.4.7.5 | Transmission with a short guard interval | 214 | PLCP OFDM
523 | 20.3.4.8 | Non-HT duplicate transmission | 214 | Coexistence
524 | 20.3.5 | Beamforming | 215 | PHY Beamforming
525 | 20.3.5.1 | Implicit Beamforming | 216 | PHY Beamforming
526 | 20.3.5.2 | Explicit Beamforming | 216 | PHY Beamforming
527 | 20.3.5.2.1 | CSI Matrices Feedback | 216 | PHY Beamforming
528 | 20.3.5.2.2 | Non Compressed Steering Matrix Feedback | 217 | PHY Beamforming
529 | 20.3.5.2.3 | Compressed Steering Matrix Feedback | 217 | PHY Beamforming
530 | 20.3.6 | High Throughput Preamble Format for Sounding PPDUs | 220 | PHY Sounding
531 | 20.3.6.1 | Sounding with a zero length packet | 220 | PHY Sounding
532 | 20.3.6.2 | Sounding PPDU for calibration | 221 | PHY Sounding
533 | 20.3.6.3 | Sounding PPDU for channel quality assessment | 221 | PHY Sounding
534 | 20.3.7 | Regulatory Requirements | 221 | PLCP Regulatory
535 | 20.3.8 | Channel Numbering and Channelization | 221 | PLCP Regulatory
536 | 20.3.8.1 | Channel Allocation in the 5 GHz Band | 222 | PLCP Regulatory
537 | 20.3.8.2 | Channel Allocation in the 2.4 GHz Band | 222 | PLCP Regulatory
563 | 20.3.9 | Transmit and receive in-band and out-of-band spurious transmissions | 223 | PLCP Regulatory
564 | 20.4 | High Throughput PLME | 237 | PLME
565 | 20.4.1 | PLME_SAP sublayer management primitives | 237 | PLME
566 | 20.4.2 | PHY management information base | 238 | PLME
567 | 20.4.3 | TXTIME calculation | 240 | PLME
568 | 20.4.4 | PHY characteristics | 241 | PLME
569 | 20.5 | High Throughput PMD sublayer | 242 | PMD
570 | 20.5.1 | Scope and field of application | 242 | PMD
571 | 20.5.2 | Overview of service | 243 | PMD
572 | 20.5.3 | Overview of interactions | 243 | PMD
573 | 20.5.4 | Basic service and options | 243 | PMD
574 | 20.5.4.1 | PMD_SAP peer-to-peer service primitives | 244 | PMD Interface
575 | 20.5.4.2 | PMD_SAP sublayer-to-sublayer service primitives | 244 | PMD Interface
576 | 20.5.4.3 | PMD_SAP service primitive parameters | 244 | PMD Interface
577 | 20.5.5 | PMD_SAP detailed service specification | 246 | PMD Interface
578 | 20.5.5.1 | PMD_DATA.request | 246 | PMD Interface
579 | 20.5.5.1.1 | Function | 246 | PMD Interface
580 | 20.5.5.1.2 | Semantic of the service primitive | 246 | PMD Interface
581 | 20.5.5.1.3 | When generated | 246 | PMD Interface
622 | 20.5.5.1.4 | Effect of receipt | 246 | PMD Interface
623 | 20.5.5.10 | PMD_EXPANSIONS_MAT.request | 250 | PMD Interface
624 | 20.5.5.10.1 | Function | 251 | PMD Interface
625 | 20.5.5.10.2 | Semantic of the service primitive | 251 | PMD Interface
626 | 20.5.5.10.3 | When generated | 251 | PMD Interface
627 | 20.5.5.10.4 | Effect of receipt | 251 | PMD Interface
628 | 20.5.5.11 | PMD_BW_OFFSET.indicate | 251 | PMD Interface
629 | 20.5.5.11.1 | Function | 251 | PMD Interface
630 | 20.5.5.11.2 | Semantic of the service primitive | 251 | PMD Interface
631 | 20.5.5.11.3 | When generated | 251 | PMD Interface
632 | 20.5.5.11.4 | Effect of receipt | 251 | PMD Interface
633 | 20.5.5.12 | PMD_CHAN_MAT.indicate | 252 | PMD Interface
634 | 20.5.5.12.1 | Function | 252 | PMD Interface
635 | 20.5.5.12.2 | Semantic of the service primitive | 252 | PMD Interface
636 | 20.5.5.12.3 | When generated | 252 | PMD Interface
637 | 20.5.5.12.4 | Effect of receipt | 252 | PMD Interface
638 | 20.5.5.13 | PMD_FORMAT.indicate | 252 | PMD Interface
639 | 20.5.5.13.1 | Function | 252 | PMD Interface
640 | 20.5.5.13.2 | Semantic of the service primitive | 252 | PMD Interface
641 | 20.5.5.13.3 | When generated | 252 | PMD Interface
582 | 20.5.5.13.4 | Effect of receipt | 252 | PMD Interface
583 | 20.5.5.2 | PMD_DATA.indicate | 247 | PMD Interface
584 | 20.5.5.2.1 | Function | 247 | PMD Interface
585 | 20.5.5.2.2 | Semantic of the service primitive | 247 | PMD Interface
586 | 20.5.5.2.3 | When generated | 247 | PMD Interface
587 | 20.5.5.2.4 | Effect of receipt | 247 | PMD Interface
588 | 20.5.5.3 | PMD_TXSTART.request | 247 | PMD Interface
589 | 20.5.5.3.1 | Function | 247 | PMD Interface
590 | 20.5.5.3.2 | Semantic of the service primitive | 247 | PMD Interface
591 | 20.5.5.3.3 | When generated | 247 | PMD Interface
592 | 20.5.5.3.4 | Effect of receipt | 247 | PMD Interface
593 | 20.5.5.4 | PMD_TXEND.request | 247 | PMD Interface
594 | 20.5.5.4.1 | Function | 248 | PMD Interface
595 | 20.5.5.4.2 | Semantic of the service primitive | 248 | PMD Interface
596 | 20.5.5.4.3 | When generated | 248 | PMD Interface
597 | 20.5.5.4.4 | Effect of receipt | 248 | PMD Interface
598 | 20.5.5.5 | PMD_TXPWRLVL.request | 248 | PMD Interface
599 | 20.5.5.5.1 | Function | 248 | PMD Interface
600 | 20.5.5.5.2 | Semantic of the service primitive | 248 | PMD Interface
601 | 20.5.5.5.3 | When generated | 248 | PMD Interface
602 | 20.5.5.5.4 | Effect of receipt | 248 | PMD Interface
603 | 20.5.5.6 | PMD_RATE.request | 248 | PMD Interface
604 | 20.5.5.6.1 | Function | 248 | PMD Interface
605 | 20.5.5.6.2 | Semantic of the service primitive | 249 | PMD Interface
606 | 20.5.5.6.3 | When generated | 249 | PMD Interface
607 | 20.5.5.6.4 | Effect of receipt | 249 | PMD Interface
608 | 20.5.5.7 | PMD_RSSI.indicate | 249 | PMD Interface
609 | 20.5.5.7.1 | Function | 249 | PMD Interface
610 | 20.5.5.7.2 | Semantic of the service primitive | 249 | PMD Interface
611 | 20.5.5.7.3 | When generated | 249 | PMD Interface
612 | 20.5.5.7.4 | Effect of receipt | 249 | PMD Interface
613 | 20.5.5.8 | PMD_RCPI.indicate | 249 | PMD Interface
614 | 20.5.5.8.1 | Function | 250 | PMD Interface
615 | 20.5.5.8.2 | Semantics of the service primitive | 250 | PMD Interface
616 | 20.5.5.8.3 | When generated | 250 | PMD Interface
617 | 20.5.5.8.4 | Effect of receipt | 250 | PMD Interface
618 | 20.5.5.9 | PMD_TX_PARAMETERS.request | 250 | PMD Interface
619 | 20.5.5.9.1 | Function | 250 | PMD Interface
620 | 20.5.5.9.2 | Semantic of the service primitive | 250 | PMD Interface
621 | 20.5.5.9.3 | When generated | 250 | PMD Interface
642 | 20.5.5.9.4 | Effect of receipt | 250 | PMD Interface
643 | 20.6 | Optional Features | 253 | Features
3 | 20.7 | Rate Dependent Parameters for High Throughput Modulation and Coding Schemes (MCS) | 253 | MCS
4 | 3 | Definitions | 2 | General
5 | 4 | Abbreviations and acronyms | 3 | General
6 | 5 | General description | 6 | General
7 | 5.2.7 | HT STA | 6 | Features
8 | 5.2.7.1 | PHY Enhancements Requiring MAC Signaling | 7 | Features
9 | 5.2.7.2 | General description of HT Features | 7 | Features
10 | 5.2.8 | HT STA | 8 | Features
11 | 5.3 | Logical Service Interfaces | 8 | Features
12 | 5.3.1 | SS | 9
13 | 5.3.2 | DSS | 9
14 | 5.4 | Overview of the services | 10 | General
15 | 5.4.9 | Radio link management | 10 | General
16 | 5.4.9.1 | Link adaptation | 10 | Link Adaptation
17 | 5.4.9.2 | Transmit beamforming | 10 | Beamforming
18 | 5.4.9.3 | Antenna selection | 10 | Antenna Selection
19 | 5.6 | Relationship between services | 10 | General
20 | 6 | MAC service definition | 11 | MAC Interface
21 | 6.1 | Overview of MAC services | 11 | MAC Interface
22 | 6.1.1 | Data service | 11 | MAC Interface
23 | 6.1.2 | Security services | 11 | MAC Interface
24 | 6.1.3 | MSDU ordering | 11 | MAC Interface
25 | 6.1.4 | MSDU format | 11 | MAC Interface
26 | 6.1.5 | MAC data service architecture | 11 | MAC Interface
27 | 6.2 | Detailed service specification | 13 | MAC Interface
28 | 6.2.1 | MAC data services | 13 | MAC Interface
29 | 7 | Frame formats | 13 | Frame Formats
30 | 7.1 | MAC frame formats | 14 | Frame Formats
31 | 7.1.1 | Conventions | 14 | Frame Formats
32 | 7.1.2 | General frame format | 14 | Frame Formats
33 | 7.1.3 | Frame fields | 15 | Frame Formats
35 | 7.1.3.1 | Frame Control field | 15 | Frame Formats
34 | 7.1.3.1.10 | Order field | 15 | Frame Formats
36 | 7.1.3.1.2 | Type and Subtype Fields | 0 | Frame Formats
37 | 7.1.3.1.5 | More Fragments field | 15 | Frame Formats
38 | 7.1.3.2 | Duration/ID field | 15 | Frame Formats
39 | 7.1.3.3 | Address Fields | 15 | Frame Formats
40 | 7.1.3.4 | Sequence Control Field | 15 | Frame Formats
41 | 7.1.3.5 | QoS Control Field | 15 | Frame Formats
42 | 7.1.3.5.3 | Ack Policy subfield | 16 | Frame Formats
43 | 7.1.3.5.6 | TXOP Duration Requested subfield | 17 | Frame Formats
44 | 7.1.3.6 | Frame Body field | 17 | Frame Formats
45 | 7.1.3.7 | FCS field | 17 | Frame Formats
46 | 7.1.3.8 | HT Control Field | 17 | Frame Formats
47 | 7.1.4 | Duration/ID field in data and management frames | 21 | Frame Formats
48 | 7.2 | Format of individual frame types | 22 | Frame Formats
49 | 7.2.1 | Control frames | 22 | Frame Formats
50 | 7.2.1.1 | RTS frame format | 22 | Frame Formats
51 | 7.2.1.2 | CTS frame format | 22 | Frame Formats
52 | 7.2.1.3 | ACK frame format | 22 | Frame Formats
53 | 7.2.1.4 | PS-Poll frame format | 22 | Frame Formats
54 | 7.2.1.5 | CF-End frame format | 22 | Frame Formats
55 | 7.2.1.6 | CF-End+CF-Ack frame format | 22 | Frame Formats
56 | 7.2.1.7 | Block Ack Request (BlockAckReq) frame format | 22 | Block Ack
57 | 7.2.1.7.1 | Simple Block Ack Request (Simple BlockAckReq) | 23 | Block Ack
58 | 7.2.1.7.2 | Block Ack Request (BlockAckReq) frame format (compressed) | 24 | Block Ack
59 | 7.2.1.7.3 | Multiple TID Block Acknowledgement Request | 24 | Block Ack
60 | 7.2.1.8 | Block Ack (BlockAck) frame format | 25 | Block Ack
61 | 7.2.1.8.1 | Simple Block Ack (Simple BlockAck) | 27 | Block Ack
62 | 7.2.1.8.2 | Block Ack (BlockAck) frame format (compressed) | 27 | Block Ack
63 | 7.2.1.8.3 | Multiple TID Block Acknowledgement | 28 | Block Ack
64 | 7.2.2 | Data frames | 29 | Frame Formats
65 | 7.2.2.1 | Aggregated MSDU Format (A-MSDU) | 30 | A-MSDU
66 | 7.2.2.2 | QoS Null Embedding of Management Action | 31 | Management Frames
75 | 7.2.3 | Management frames | 32 | Management Frames
76 | 7.2.3.1 | Beacon frame format | 32 | Management Frames
77 | 7.2.3.10 | Authentication frame format | 35 | Management Frames
67 | 7.2.3.11 | Deauthentication | 35 | Management Frames
68 | 7.2.3.12 | Action frame format | 35 | Management Frames
69 | 7.2.3.2 | IBSS ATIM frame format | 32 | Management Frames
70 | 7.2.3.3 | Disassociation frame format | 32 | Management Frames
71 | 7.2.3.4 | Association Request frame format | 32 | Management Frames
72 | 7.2.3.5 | Association Response frame format | 33 | Management Frames
73 | 7.2.3.6 | Reassociation Request frame format | 33 | Management Frames
74 | 7.2.3.7 | Reassociation Response frame format | 34 | Management Frames
78 | 7.2.3.8 | Probe Request frame format | 34 | Management Frames
79 | 7.2.3.9 | Probe Response frame format | 34 | Management Frames
80 | 7.3 | Management frame body components | 35 | Management Frames
89 | 7.3.1 | Fields that are not information elements | 35 | Management Frames
90 | 7.3.1.1 | Authentication Algorithm Number field | 35 | Management Frames
91 | 7.3.1.10 | Timestamp field | 36 | Management Frames
92 | 7.3.1.11 | Action field | 36 | Management Frames
93 | 7.3.1.12 | Dialog Token field | 36 | Management Frames
94 | 7.3.1.13 | DLS Timeout Value field | 36 | Management Frames
95 | 7.3.1.14 | Block Ack Parameter Set field | 36 | Block Ack
96 | 7.3.1.15 | Block Ack Timeout Value field | 37 | Block Ack
81 | 7.3.1.16 | DELBA Parameter Set field | 37 | Block Ack
82 | 7.3.1.17 | QoS Info field | 37 | Management Frames
83 | 7.3.1.2 | Authentication Transaction Sequence Number field | 35 | Management Frames
84 | 7.3.1.3 | Beacon Interval field | 35 | Management Frames
85 | 7.3.1.4 | Capability Information field | 35 | Management Frames
86 | 7.3.1.5 | Current AP Address field | 35 | Management Frames
87 | 7.3.1.6 | Listen Interval field | 35 | Management Frames
88 | 7.3.1.7 | Reason Code field | 35 | Management Frames
97 | 7.3.1.8 | AID field | 36 | Management Frames
98 | 7.3.1.9 | Status Code field | 36 | Management Frames
107 | 7.3.2 | Information elements | 37 | Management Frames
108 | 7.3.2.1 | SSID element | 37 | Management Frames
109 | 7.3.2.10 | Hopping Pattern Parameters information element | 38 | Management Frames
110 | 7.3.2.11 | Hopping Pattern Table information element | 38 | Management Frames
111 | 7.3.2.12 | Request information element | 38 | Management Frames
112 | 7.3.2.13 | ERP Information element | 38 | Management Frames
113 | 7.3.2.14 | Extended Supported Rates element | 38 | Management Frames
114 | 7.3.2.15 | Power Constraint element | 38 | Coexistence
115 | 7.3.2.16 | Power Constraint element | 38 | Coexistence
116 | 7.3.2.17 | TPC Request element | 38 | Coexistence
99 | 7.3.2.18 | TPC Report element | 38 | Coexistence
117 | 7.3.2.19 | Supported Channels element | 38 | Coexistence
118 | 7.3.2.2 | Supported Rates element | 37 | Coexistence
119 | 7.3.2.20 | Channel Switch Announcement element | 38 | Coexistence
120 | 7.3.2.20A | New Extension Channel Offset element | 38 | Coexistence
121 | 7.3.2.21 | Measurement Request element | 39 | Management Frames
122 | 7.3.2.21.1 | Basic request | 39 | Management Frames
123 | 7.3.2.21.2 | CCA request | 39 | Management Frames
124 | 7.3.2.21.3 | RPI histogram request | 39 | Management Frames
125 | 7.3.2.22 | Measurement Report element | 39 | Management Frames
126 | 7.3.2.22.1 | Basic report | 39 | Management Frames
127 | 7.3.2.22.2 | CCA report | 39 | Management Frames
128 | 7.3.2.22.3 | RPI histogram report | 39 | Management Frames
129 | 7.3.2.23 | Quiet element | 39 | Management Frames
130 | 7.3.2.24 | IBSS DFS element | 39 | Management Frames
131 | 7.3.2.25 | RSN information element | 39 | Security
132 | 7.3.2.25.1 | Cipher suites | 39 | Security
133 | 7.3.2.25.2 | AKM suites | 39 | Security
134 | 7.3.2.25.3 | RSN capabilities | 40 | Security
135 | 7.3.2.25.4 | PMKID | 40 | Security
136 | 7.3.2.26 | Vendor Specific information element | 40 | Management Frames
137 | 7.3.2.27 | QBSS Load element | 40 | Management Frames
100 | 7.3.2.28 | EDCA Parameter Set element | 40 | Management Frames
138 | 7.3.2.29 | TSPEC element | 40 | TSPEC
139 | 7.3.2.3 | FH Parameter Set element | 37 | Management Frames
140 | 7.3.2.30 | TCLAS element | 40 | TSPEC
141 | 7.3.2.31 | TS Delay element | 40 | TSPEC
142 | 7.3.2.32 | TCLAS Processing element | 40 | TSPEC
101 | 7.3.2.33 | Schedule element | 40 | TSPEC
143 | 7.3.2.34 | QoS Capability element | 40 | Management Frames
144 | 7.3.2.4 | DS Parameter Set element | 37 | Management Frames
145 | 7.3.2.46 | Fast BSS transition EAPOL-Key information element (EAPKIE) | 40 | Security
146 | 7.3.2.47 | HT Capabilities | 40 | HT Elements
147 | 7.3.2.47.1 | HT Capability element | 41 | HT Elements
148 | 7.3.2.47.2 | HT Capabilities Info field | 41 | HT Elements
149 | 7.3.2.47.3 | MAC HT parameters Info field | 44 | HT Elements
150 | 7.3.2.47.4 | Supported MCS set field | 45 | HT Elements
151 | 7.3.2.47.5 | Extended HT Capabilities Info field | 46 | HT Elements
152 | 7.3.2.47.6 | Transmit Beamforming Capability | 47 | Beamforming
102 | 7.3.2.47.7 | Antenna Selection Capability | 50 | Antenna Selection
103 | 7.3.2.48 | Additional HT Information Elements | 51 | HT Elements
104 | 7.3.2.5 | CF Parameter Set element | 37 | Management Frames
105 | 7.3.2.6 | TIM | 37 | Management Frames
106 | 7.3.2.7 | IBSS Parameter Set element | 37 | Management Frames
153 | 7.3.2.8 | Challenge Text element | 38 | Management Frames
154 | 7.3.2.9 | Country information element | 38 | Management Frames
155 | 7.4 | Action frame format details | 55 | Management Frames
156 | 7.4.1 | Spectrum management action details | 55 | Management Frames
157 | 7.4.1.1 | Measurement Request frame format | 55 | Management Frames
158 | 7.4.1.2 | Measurement Report frame format | 55 | Management Frames
159 | 7.4.1.3 | TPC Request frame format | 55 | Management Frames
160 | 7.4.1.4 | TPC Report frame format | 55 | Management Frames
161 | 7.4.1.5 | Channel Switch Announcement frame format | 55 | Management Frames
162 | 7.4.2 | QoS Action frame details | 55 | Management Frames
163 | 7.4.2.1 | ADDTS Request frame format | 56 | TSPEC
164 | 7.4.2.2 | ADDTS Response frame format | 56 | TSPEC
165 | 7.4.2.3 | DELTS frame format | 56 | TSPEC
166 | 7.4.2.4 | Schedule frame format | 56 | TSPEC
167 | 7.4.3 | DLS Action frame details | 56 | DLS
168 | 7.4.3.1 | DLS Request frame format | 56 | DLS
169 | 7.4.3.2 | DLS Response frame format | 56 | DLS
170 | 7.4.3.3 | DLS Teardown frame format | 56 | DLS
171 | 7.4.4 | Block Ack Action frame details | 56 | Block Ack
172 | 7.4.4.1 | ADDBA Request frame format | 57 | Block Ack
173 | 7.4.4.2 | ADDBA Response frame format | 57 | Block Ack
174 | 7.4.4.3 | DELBA frame format | 57 | Block Ack
175 | 7.4.5 | Radio Measurement action details | 57 | Management Frames
176 | 7.4.6 | Fast BSS transition action details | 57 | Management Frames
185 | 7.4.7 | HT Management Action Frames details | 57 | HT Action Frames
177 | 7.4.7.1 | Recommended Transmission Channel Width Management Action Frame | 57 | Coexistence
178 | 7.4.7.10 | PSMP | 76 | PSMP
179 | 7.4.7.2 | MIMO Power Save Management Action Frame | 58 | Power Management
180 | 7.4.7.3 | PCO Phase Request Management Action Frame | 59 | PCO
181 | 7.4.7.4 | MIMO Channel Measurement frame | 59 | Beamforming
182 | 7.4.7.5 | Reciprocity Correction frame | 62 | Beamforming
183 | 7.4.7.6 | MIMO CSI Matrices frame | 63 | Beamforming
184 | 7.4.7.7 | MIMO Uncompressed Steering Matrices frame | 68 | Beamforming
186 | 7.4.7.8 | Compressed Steering Matrices Feedback frame | 72 | Beamforming
187 | 7.4.7.9 | Antenna Selection Indices Feedback Frame | 75 | Antenna Selection
188 | 7.4A | Aggregated MPDU frames | 78 | A-MPDU
189 | 7.4A.1 | Aggregated MPDU format (A-MPDU) | 78 | A-MPDU
190 | 7.4A.1.1 | CRC | 79 | A-MPDU
191 | 7.4A.1.2 | De-aggregation (Informative) | 79 | A-MPDU
192 | 7.4A.2 | A-MPDU Contents | 80 | A-MPDU
193 | 7.5 | Frame usage | 81 | A-MPDU
194 | 8 | Security | 81 | Security
195 | 8.1 | Framework | 81 | Security
196 | 8.2 | Pre-RSNA security methods | 81 | Security
197 | 8.3 | RSNA data confidentiality protocols | 82 | Security
198 | 8.4 | RSNA security association management | 82 | Security
199 | 8.5 | Keys and key distribution | 82 | Security
200 | 8.6 | Mapping EAPOL keys to IEEE 802.11 keys | 82 | Security
201 | 8.7 | Per-frame pseudo-code | 82 | Security
202 | 8.8 | Security for HT STA | 82 | Security
238 | 9 | MAC sublayer functional description | 82 | MAC Operation
203 | 9.1 | Block Acknowledgment (Block Ack) | 91 | Block Ack
239 | 9.1 | MAC architecture | 82 | MAC Operation
240 | 9.1.5 | Fragmentation/defragmentation overview | 82 | MAC Operation
241 | 9.10.1 | Introduction | 91 | Block Ack
242 | 9.10.2 | Setup and modification of the Block Ack parameters | 91 | Block Ack
243 | 9.10.3 | Data and acknowledgement transfer | 92 | Block Ack
244 | 9.10.4 | Receive Buffer Operation | 92 | Block Ack
245 | 9.10.5 | Teardown of the Block Ack mechanism | 92 | Block Ack
246 | 9.10.6 | Use of Compressed bitmap | 92 | Block Ack
247 | 9.10.7 | N-Immediate BlockAck extensions | 92 | Block Ack
248 | 9.10.7.1 | BlockAck Extension Architecture | 93 | Block Ack
249 | 9.10.7.2 | Rx reordering buffer control | 93 | Block Ack
250 | 9.10.7.3 | Scoreboard context control in full state | 94 | Block Ack
251 | 9.10.7.4 | Scoreboard context control in partial state | 94 | Block Ack
252 | 9.10.7.5 | Scoreboard context control of BlockAck | 95 | Block Ack
253 | 9.10.7.6 | Scoreboard context control of BlockAckReq | 95 | Block Ack
254 | 9.10.7.7 | Originator's behavior | 95 | Block Ack
255 | 9.10.7.8 | Maintaining the BlockAck state at the originator | 95 | Block Ack
256 | 9.10.7.9 | Originator's support of Responder's partial state | 96 | Block Ack
257 | 9.10.8 | N-Delayed BlockAck extensions | 96 | Block Ack
258 | 9.10.8.1 | N-Delayed BlockAck negotiation | 96 | Block Ack
259 | 9.10.8.2 | Operation of N-Delayed BlockAck | 96 | Block Ack
260 | 9.11 | No Acknowledgment (No Ack) | 97 | MAC Operation
261 | 9.12 | Frame exchange sequences | 97 | MAC Operation
262 | 9.13 | Protection mechanism for non-ERP receivers | 104 | Protection Mechanisms
263 | 9.14 | Protection mechanisms for different HT PHY options | 105 | Protection Mechanisms
264 | 9.14.1 | RIFS Protection | 105 | RIFS
265 | 9.14.2 | Green Field Protection | 105 | Protection Mechanisms
266 | 9.15 | L-SIG TXOP Protection | 105 | Protection Mechanisms
267 | 9.15.1 | L-SIG TXOP Protection Rules at the Initiator | 106 | Protection Mechanisms
268 | 9.15.2 | L-SIG TXOP Protection Rules at the Responder | 106 | Protection Mechanisms
269 | 9.15.3 | L-SIG TXOP Protection Rules at Third Party HT | 106 | Protection Mechanisms
270 | 9.16 | Protection mechanisms for Aggregation Exchange Sequences | 107 | Protection Mechanisms
271 | 9.16.1 | Generally | 107 | Protection Mechanisms
272 | 9.16.2 | Long NAV | 107 | Protection Mechanisms
273 | 9.16.3 | Truncation of TXOP | 108 | Protection Mechanisms
274 | 9.17 | Reverse direction | 109 | MAC Operation
275 | 9.17.1 | Reverse direction aggregation exchanges | 109 | MAC Operation
276 | 9.17.2 | Bi-Directional Data Exchange Rules | 110 | MAC Operation
277 | 9.17.3 | Constraints regarding responses | 111 | MAC Operation
278 | 9.18 | PSMP | 111 | PSMP
279 | 9.18.1 | Scheduled PSMP | 111 | PSMP
280 | 9.18.1.1 | PSMP sequence | 111 | PSMP
281 | 9.18.1.1.1 | Down Link Transmission | 113 | PSMP
282 | 9.18.1.1.2 | Up Link Transmission | 113 | PSMP
283 | 9.18.1.1.2.1 | Scheduling of Up Link Transmissions | 114 | PSMP
284 | 9.18.2 | Multi-phase PSMP | 114 | PSMP
285 | 9.18.2.1 | PSMP Power management | 116 | PSMP
286 | 9.18.3 | MTBA rules in scheduled PSMP sequence | 116 | PSMP
287 | 9.18.3.1 | ULT payload retransmission | 116 | PSMP
288 | 9.18.4 | Unscheduled PSMP | 117 | PSMP
289 | 9.19 | Link Adaptation | 117 | Link Adaptation
290 | 9.19.1 | Introduction (informative) | 117 | Link Adaptation
291 | 9.19.2 | Link Adaptation using the HT Control Field | 118 | Link Adaptation
204 | 9.19.3 | Immediate Response Frame Exchange for HT Control | 119 | Link Adaptation
292 | 9.19.4 | Fast Link Adaptation using explicit feedback | 119 | Link Adaptation
206 | 9.2 | DCF | 82 | MAC Operation
207 | 9.2.3 | IFS | 82 | MAC Operation
208 | 9.2.3.1 | SIFS | 83 | MAC Operation
209 | 9.2.3.2 | PIFS | 83 | MAC Operation
210 | 9.2.3.3 | DIFS | 83 | MAC Operation
211 | 9.2.3.4 | AIFS | 83 | MAC Operation
212 | 9.2.3.5 | Extended IFS (EIFS) | 83 | MAC Operation
214 | 9.2.3.6 | RIFS | 83 | RIFS
213 | 9.2.4 | DCF access procedure | 83 | MAC Operation
215 | 9.2.5 | DCF access procedure | 84 | MAC Operation
216 | 9.2.5.4 | Setting and resetting the NAV | 83 | MAC Operation
217 | 9.2.5.4 | Setting and resetting the NAV | 84 | MAC Operation
293 | 9.2.5.4.1 | Dual CTS Protection | 84 | Protection Mechanisms
294 | 9.2.6 | Directed MPDU transfer procedure | 84 | MAC Operation
205 | 9.20 | Transmit Beamforming | 119 | Beamforming
295 | 9.20.1 | Introduction (Informative) | 119 | Beamforming
296 | 9.20.2 | Transmit Beamforming with Implicit Feedback | 120 | Beamforming
297 | 9.20.2.1 | Calibration | 121 | Beamforming
298 | 9.20.2.1.1 | Introduction (Informative) | 121 | Beamforming
299 | 9.20.2.1.2 | Procedure | 122 | Beamforming
300 | 9.20.3 | Explicit feedback beamforming | 123 | Beamforming
301 | 9.20.3.1 | Introduction (informative) | 123 | Beamforming
302 | 9.20.3.2 | Feedback request and response rules | 123 | Beamforming
303 | 9.20.3.3 | Transmit Beamforming with explicit Feedback | 124 | Beamforming
304 | 9.21 | Antenna Selection | 125 | Antenna Selection
305 | 9.21.1 | Introduction (Informative) | 125 | Antenna Selection
306 | 9.21.2 | Procedure | 125 | Antenna Selection
307 | 9.22 | Zero Length Frame as sounding frame | 128 | ZLF
308 | 9.22.1 | Determination of ZLF destination | 128 | ZLF
309 | 9.22.2 | Determination of ZLF source | 129 | ZLF
310 | 9.23 | 40/20 Functional description | 129 | Coexistence
311 | 9.23.1 | Rules for operation in 40/20Mhz BSS | 129 | Coexistence
312 | 9.23.2 | STA CCA sensing 40/20MHz BSS | 129 | Coexistence
313 | 9.23.3 | AP CCA sensing in 40/20Mhz BSS | 130 | Coexistence
314 | 9.23.4 | NAV assertion in 40/20Mhz BSS | 130 | Coexistence
315 | 9.23.5 | Frame transmission in 40/20Mhz BSS | 130 | Coexistence
316 | 9.23.6 | Protection in 40/20MHz BSS | 130 | Coexistence
317 | 9.23.7 | CF-End in duplicated mode | 130 | Coexistence
218 | 9.23.8 | ACK and BlockAck in non-HT duplicated mode | 131 | Coexistence
219 | 9.23.9 | STA switching from 40MHz to 20MHz in 40/20MHz BSS | 131 | Coexistence
220 | 9.3 | PCF | 85 | MAC Operation
221 | 9.3.3 | PCF transfer procedure | 85 | MAC Operation
222 | 9.3.3.3 | CFPMaxDuration limit | 85 | MAC Operation
223 | 9.4 | Fragmentation | 85 | MAC Operation
224 | 9.5 | Defragmentation | 86 | MAC Operation
225 | 9.6 | Multirate support | 87 | MAC Operation
226 | 9.6.1 | Modulation classes | 88 | MAC Operation
227 | 9.6.2 | Non-HT Basic Rate calculation | 88 | Coexistence
228 | 9.7 | MSDU transmission restrictions | 89 | MAC Operation
229 | 9.8 | Operation across regulatory domains | 89 | MAC Operation
230 | 9.9 | HCF | 89 | MAC Operation
231 | 9.9.1 | HCF contention-based channel access (EDCA) | 89 | MAC Operation
232 | 9.9.1.1 | Reference Implementation | 90 | MAC Operation
233 | 9.9.1.2 | EDCA TXOPs | 90 | MAC Operation
234 | 9.9.1.3 | Obtaining an EDCA TXOP | 90 | MAC Operation
235 | 9.9.1.4 | Multiple frame transmission in an EDCA TXOP | 90 | MAC Operation
236 | 9.9.1.6 | Retransmit procedures | 90 | MAC Operation
237 | 9.9.3 | Admission Control at the HC | 90 | MAC Operation
645 | 9.9.3.2 | Controlled-access admission control | 91 | MAC Operation
647 | 9.9.4 | PSMP NAV operation | 91 | PSMP
646 | A.4 | PICS proforma-IEEE Std 802.11, 2006 Edition9 | 265 | PICS
648 | A.4.15 | Enhancements for Higher Throughput | 265 | PICS
649 | A.4.3 | IUT configuration | 265 | PICS
644 | A4.15.1 | MAC Enhancements for Higher Throughput | 265 | PICS
650 | A4.15.2 | PHY Enhancements for Higher Throughput | 271 | PICS
652 | Annex A | PICS | 265 | PICS
653 | Annex C | Formal description of MAC operation | 275 | MAC SDL
651 | Annex D | ASN.1 encoding of the MAC and PHY MIB | 276 | MIB
| Annex P | LDPC Matrix Definitions | 323 | PLCP Coding
| Boilerplate | Boilerplate | 0 | General
| C.3 | State machines for MAC stations | 275 | MAC SDL
| CA DOC | CA Document | 0 | CA DOC
| General | General | 0 | General
| Table of Contents | Table of Contents | 0 | General
| Title | Title | 0 | General

## TopicGroupings
Topic | Grouping
0 | General
A-MPDU | Frame Format
A-MSDU | Frame Format
Antenna Selection | Beamforming & Adaptation
Beamforming | Beamforming & Adaptation
Block Ack | MAC
CA DOC | CA DOC
CCA | Coexistence
Coexistence | Coexistence
DLS | MAC
Duplicate | Duplicate
Features | General
Frame Formats | Frame Format
General | General
HT Action Frames | Frame Format
HT Elements | Frame Format
Interfaces | General
Link Adaptation | Beamforming & Adaptation
MAC Interface | MAC
MAC Management | MAC
MAC Operation | MAC
MAC SDL | MAC
Management Frames | Frame Format
MCS | PHY
MIB | General
MLME | MAC
PCO | Coexistence
PHY Beamforming | Beamforming & Adaptation
PHY Characteristics | PHY
PHY General | PHY
PHY Interface | PHY
PHY Management | PHY
PHY Sounding | Beamforming & Adaptation
PICS | General
PLCP | PHY
PLCP Coding | PHY
PLCP Data | PHY
PLCP Frame Format | PHY
PLCP Greenfield | PHY
PLCP Header | PHY
PLCP Interleaver | PHY
PLCP MCS | PHY
PLCP OFDM | PHY
PLCP Preamble | PHY
PLCP Regulatory | Coexistence
PLCP STBC | PHY
PLME | PHY
PMD | PHY
PMD Interface | PHY
Power Management | MAC
Protection Mechanisms | Coexistence
PSMP | PSMP
RCPI | PHY
RIFS | Coexistence
Security | MAC
Synchronization | MAC
TSPEC | Frame Format
ZLF | Beamforming & Adaptation
General