## Sorted Comments
Color Codes: |  | Closed. Accepted the comment and updated the draft based on the comment resolution
Yet to be reviewed by the group
Reviwed the comment. Needs further work for closure.
Remove at end of March 2007 meeting if no further input
Name | Clause | Page No. | Line No | Comment Type (E or T) | Part of No Vote? (Y or N) | Comment / Explanation | Recommended Change | Comment Review Status
Angelo Centonza | General |  |  | T |  | In document IEEE802.11-06/1039r0 three new features are presented inorder to provide emergency call services. However, only the feature employing expedited bandwidth request seems to be a non-informative part of the actual draft. | the draft shall include the option of having emergency call services not necessarily using expedited bandwidth request, i.e. by using public security credentials or open outentication SSIDs | Commentor to provide the text
Angelo Centonza | General |  |  | T |  | Any reference to IEEE802.21 standard shall only be made to indicate an example of advertisment protocol or informative description of a network selection scenario. | Any reference to the IEEE802.21 standard directly influencing the 802.11u standard shall be removed. | Approved but requires specific text from the commentor
Donghee | General |  |  | T |  | Emergency call number should be obtained from the network before the emergency call setup for the STA to detect the emergency call. In other words, the STA should be able to use the well-known emergency numbers (e.g. 911) as well as the emergency numbers that are valid based on current user’s location in the Visited SSPN. | Adopt the solution proposed in doc 11-07/0033 | Donghee needs to submit a proposal that meets the requested changes
Stephen McCann | Intro | 1 |  | E | N | Copyright year needs changing and version of IEEE 802.11ma | change 2006 to 2007. Refer to P802.11 REV-ma 9.0 | Accepted
Tony Mo | 1.2 | 3 | 26 | E | N | "IEEE 802.11TM compliant" should be "IEEE 802.11™-compliant" | Change IEEE802.11TM to IEEE 802.11™ | Accepted
Stephen McCann | 3 | 4 | 2 | E |  | May want to check IEEE 802.11i definitions of AAA, as we perhaps don't want to go into too much detail about authentication and security here. |  | McCann will follow up with this
Tony Mo | 3 | 4 | 17 | T | N | What's the difference between Destination Network and SSPN? |  | Keep the two definitions. but a volunteer should provide better description of DN (Hong Cheng has volunteered)
Dave Stephenson | 3 | 4 | 19 | T |  | There needs to be a formal definition of the term, "ESSID". | Add the following definition: an ESSID identifies a collection of BSSs wherein the set of reachable networks, defined by their SSIDs, and services provided by those networks available at any one BSS are available at all BSSs. All BSSs identified by an ESSID must also be in the same mobility domain, if one is defined. | Defer it until we get feedback from 802.21 group. D. Stephenson volunteers to provide the text.
Hong Cheng | 3 | 4 | 22 | E | N | The reference number "[2]" should be removed. | Remove "[2]" after "…to the DS" | Accepted
Necati Canpolat | H | 4 | 30 | E |  | MIH definition is missing | Add the folliowing definition: MIH: Media Independent Handover | Accepted
Necati Canpolat | H | 4 | 31 | E |  | ES and CS definitions are missing | Add CS and ES definitions | Accepted
Stephen McCann | 3 | 4 | 44 | E |  | May want to re-consider definition of "Roaming", to avoid it being confused with BSS transistion and traditional handover |  | McCann: Rewrite the definition of roaming
Hong Cheng | 4 | 5 | 13 | E | N | Acronym of Destination Network is not available. | To insert "DN" in above "DS" | Accepted
Dave Stephenson | 5 | 5 | 23 | T |  | Text needs to be added to this section. | Suggest we ask for volunteers at London meeting. | Necati, Hong & Srini will provide text
Necati Canpolat | 5 | 5 | 25 | T |  | Text need do be added for changing this clause to account for new WLAN Interworking with External Networks services | Volunteer is needed. | Necati, Hong & Srini will provide text
Necati Canpolat | 5 | 5 | 28 | T |  | Provide a general description of the Interworking services set with the following diagram. Need to illustrate how each component interacts. In this case, how the SSPN affects the operations | Volunteer is needed. | Duplicate
Necati Canpolat | 5.3 | 6 | 5 | T |  | Change this clause to account for new WLAN Interworking with External Networks services | Volunteer is needed. | Necati, Hong & Srini will provide text
Stephen McCann | 5 | 6 |  | T |  | This section needs to clearly state which part of the architecture (as in Figure u1) is in scope of Tgu standardisation and more specifically which bits are not. |  | Necati, Hong & Srini will provide text
Necati Canpolat | 5.4.7.1 | 7 | 17 | T |  | Describe the interworking architecture using Figure u1 | Volunteer is needed. | Necati, Hong & Srini will provide text
Dave Stephenson | 7.2.3 | 10 | 15 | E |  | Heading number of Beacon frame format is incorrect and consequently the heading numbers describing other management frame types are also incorrect. | Change heading number to 7.2.3.1 and renumber subsequent headings to end of section 7.2.3. | Accepted
Necati Canpolat | 7.2.3 | 10 | 15 | E |  | Beacon frame format header and following headers are incorrect | Change Beacon frame header number to 7.2.3.1 and renumber following headers. | Duplicate
Tony Mo | 7.2.4 | 10 | 15 | E | N | The clause number is wrong | Change 7.2.4 to 7.2.3.1 | Duplicate
Dave Stephenson | 7.2.4 | 10 | 17 | E |  | Table 8 header is not "connected" to table and heading row is not repeated on next page. | Format table. | Accepted
Tony Mo | 7.2.4 | 10 | 17 | E | N | Here should be Generic Advertisement Service Capability. | Change Advertisement Service Capability to Generic Advertisement Service Capability in the second row in Table 8 | Accepted
Tony Mo | 7.2.4.1 | 11 | 1 | E | N | The clause number is wrong | Change 7.2.4.1 to 7.2.3.2 | Accepted
Tony Mo | 7.2.4.2 | 11 | 2 | E | N | The clause number is wrong | Change 7.2.4.2 to 7.2.3.3 | Accepted
Tony Mo | 7.2.4.3 | 11 | 3 | E | N | The clause number is wrong | Change 7.2.4.3 to 7.2.3.4 | Accepted
Tony Mo | 7.2.4.4 | 11 | 6 | E | N | The clause number is wrong | Change 7.2.4.4 to 7.2.3.5 | Accepted
Tony Mo | 7.2.4.5 | 11 | 10 | E | N | The clause number is wrong | Change 7.2.4.5 to 7.2.3.6 | Accepted
Tony Mo | 7.2.4.6 | 12 | 1 | E | N | The clause number is wrong | Change 7.2.4.6 to 7.2.3.7 | Accepted
Tony Mo | 7.2.4.7 | 12 | 5 | E | N | The clause number is wrong | Change 7.2.4.7 to 7.2.3.8 | Accepted
Necati Canpolat | 7.2.4.7 | 12 | 7 | T |  | Table 14 row 2. Default Emergency Services Realm should not be in Probe Request. It is supposed to be in the Probe Response frame. | Move Emergency Services Realm to Probe Response frame. | Accepted by the group
Dave Stephenson | 7.2.4.7 | 12 | 7 | T |  | Default Emergency Services Realm IE is in Probe Request frame, it should be in the Probe Response frame. | Move to Probe Response frame. | Accepted by the group
Tony Mo | 7.2.4.7 | 12 | 7 | T | N | STA can't know the Default Emergency Services Realm when it probes | Delete the second row in Table 14 | Duplicate
Tony Mo | 7.2.4.8 | 12 | 8 | E | N | The clause number is wrong | Change 7.2.4.8 to 7.2.3.9 | Accepted
Tony Mo | 7.2.4.8 | 12 | 10 | E | N | Here should be Generic Advertisement Service Capability. | Change Advertisement Service Capability to Generic Advertisement Service Capability in the second row in Table 15 | Accepted
Peng Mo | 7.2.4.8 | 12 | 10 | T | N | AP should include the Default Emergency Services Realm in its Probe Response frame if it configures | Insert the following row at the end of Table 15: | Duplicate of #40
Tony Mo | 7.2.5 | 13 | 1 | E | N | The clause number is wrong. | Change 7.2.5 to 7.2.4 | Accepted
Tony Mo | 7.3.1.9 | 14 | 4 | T | N | What are the use cases of Status Code 56&57 in Table 23? |  | no action. Resoveld with the discussion on 01/17/07
Tony Mo | 7.3.1.11 | 14 | 8 | E | N | Description is wrong | Change (X+1)--127 to 5--127 | Rejected
Hitoshi Morioka | 7.3.1.18 | 14 | 11 | T |  | The length of GAS Query ID is defined as 1 octet. I suppose it will cause DoS attacks easily. | The length of GAS Query ID should be at least 2 octets. | Declined: Changing the ID length does not provide resilence to DoS attack.
Tony Mo | 7.3.1.18 | 14 | 14 | E | N | Description is wrong | Change Comeback Request to Comeback Request frame | Accepted
Dave Stephenson | 7.3.2.36 | 18 | 3 | T |  | There doesn't need to be a separate interworking capabilities IE | Merge the needed bits into the ESSID IE. | needs further discussison - open Dave withdrew the comment during the adhoc on 2/20/07
Tony Mo | 7.3.2.36 | 18 | 4 | E | N | Description is wrong | Change Figure u13 to Figure u4 | Accepted
Jin Lee | 7.3.2.36 | 18 | 4 | E |  | Wrong figure number | Change figure u13 to figure u4 | Accepted
Dave Stephenson | 7.3.2.36 | 18 | 10 | T |  | Of the bits defined, only the ESO bit is truly needed. The other capabilities {QoS Map and EBR} capabilities should be required when TGu capability is present. | Delete QoS Map bit and EBR bit. | needs further discussison - open Dave withdrew the comment during the adhoc on 2/20/07
Hong Cheng | 7.3.2.36 | 18 | 11 | T | Y | Change the "AP" to "STA" | Make changes as indicated by the comment | Accepted by the group
Angelo Centonza | 7.3.2.36 | 18 | 22 | T |  | If the Expedited Bandwidth Request bit has to be set to 1 there would not be any possibility to have emergency call services without the use of expedited bandwidth request. | Setting of the Expedited Bandwidth Request bit to one shall not be compulsory, but optional. | Commentor to provide the text -- Review during Orlando meeting
Donghee | 7.3.2.36 | 18 | 24 | T |  | 11u D0.02 says “802.11k or 802.11v location information capability is enabled on AP if AP is located in a regulatory domain that requires this” in 7.3.2.36. This means that 11u assumes that 11v or 11k mechanisms would be used to obtain the location of STA for emergency call. However, it is not clear the interaction between emergency call support in 11u and location support in 11v or 11k. What is the whole procedure and dependencies on each TG’s draft? The location of the STA should be obtained before the emergency call setup or during the expedited bandwidth request procedure or after that? | There woud be any informative text to explain the relationship between TGu mechanism to support for emergency call and TGv /TGk to support for positioning the STA. | Dave will provide the text for Annex P. Discussed during the adhoc on 2/20/07. S. McCann willl have folllow up discusiion with TGv folks.
Hong Cheng | 7.3.2.36 | 18 | 24 | E | N | Should not refer to other TG in the draft. | To remove the reference of 802.11k & 802.11v in the text and place it into a Editorial Note. | Stephenson & Hong
Hong Cheng | 7.3.2.36 | 18 | 26 | T | Y | There is no definition of PSAP | To define the PSAP in clause 3 & 4 | Commentor will provide the normative refrence
Angelo Centonza | 7.3.2.36 | 18 | 26 | T |  | Tgu standard shell not impose guaranteed QoS up to the PSAP as this node is outside the .11 network. | QoS shall only be guaranteed within the .11 network. Ouytside the .11 network QoS guarantees shall only be recommended. | Commentor to provide the text for comment 49 Discussed during the adhoc on 2/20/07. S. McCann willl have folllow up with Angelo.
Tony Mo | 7.3.2.36 | 18 | 11,12 | T | N | Description is wrong | The QoS Map Service capability bit set to 1 indicates the STA supports QoS Map Service. The QoS Map Service capability bit set to 0 indicates the STA does not support QoS Map Service. | Accepted
Tony Mo | 7.3.2.36 | 18 | Figure u5 | T | N | Does the STA need to send the SSPN interface capability bit to AP? Otherwise the AP may not know whether the STA can provide the STA's attributions to it. | The SSPN interface capability bit should be added in the Interworking Capabilies IE. | Rejected:SSPN interface is not over the air that's why not included in the Interworking capability.
Tony Mo | 7.3.2.37 | 19 | 12 | T | N | The GAS Capability IE indicates AP's advertisement service capabilities. | The lack of a GAS Capability element shall be interpreted as AP having no advertised GAS Capability. | Accepted the proposed changes.
Necati Canpolat | 7.3.2.38 | 19 | 13 | E |  | "Advertising" Protocol" heading should be "Advertisment Protocol" | Change the heading to "Advertisement Protocol" | Accepted
Dave Stephenson | 7.3.2.38 | 19 | 13 | E |  | Heading calls this the "Advertising" Protocol, but Figure u7 calls it the "Advertisment" protocol. | Change one of the names to match the other. I prefer "advertisement". | Accepted
Tony Mo | 7.3.2.38 | 19 | 13 | E | N | The name of the IE should be identical to the above. | Change Advertising to Advertisement | Duplicate
Tony Mo | 7.3.2.38 | 19 | 14,15 | E | N | The name of the IE should be identical to the above. | Change Advertising to Advertisement | Duplicate
Tony Mo | 7.3.2.37 | 19 | 4,5 | T | N | The GAS Capability IE indicates AP's advertisement service capabilities. | The GAS Capability Information element contains information about the advertisement service capabilities of AP as shown in Figure u6. | Accepted the proposed changes.
Hong Cheng | 7.3.2.38 | 20 | 4 | E | N | Remove "a" after "Table u1" | As indicated in the comment | Accepted
Necati Canpolat | 7.3.2.38 | 20 | 4 | E |  | Fix the reference to table | Remove "a" after "u1" | Duplicate
Tony Mo | 7.3.2.38 | 20 | 4 | E | N | Description is wrong | Changes Table u1a to Table u1 | Duplicate
Tony Mo | 7.3.2.38 | 20 | 8 | E | N | reference to non-existent clause | Change clause 11.11.1 to clause 11.10.1.3 | Accepted
Tony Mo | 7.3.2.38 | 20 | 10 | E | N | reference to non-existent clause | Change clause 11.11.2 to clause 11.10.1.4 | Accepted
Dave Stephenson | 7.3.2.39 | 20 | 24 | E |  | Heading 7.3.2.39 is hanging at the end of the page | Format keep with next to heading stays next to text across page breaks. All headings should be so formatted as there are other instances of this same behavior. | Accepted
Tony Mo | 7.3.2.38 | 20 | 1-4 | E | N | The name of the Protocol ID should be identical to the above. | Change Advertising to Advertisement | Accepted
Tony Mo | 7.3.2.38 | 20 | 10,11 | E | N | If the STA does not support unicast delivery for this Advertisement Protocol IE, Bit 1 should be set to 0. | Bit 1 is set to 1 if the STA supports unicast delivery as described in clause 11.11.2. Bit 1 is set to 0 if the STA does not support unicast delivery for this Advertisement Protocol IE. | Accepted
Tony Mo | 7.3.2.39 | 21 | 3 | E | N | The name of the IE should be identical to the above. | Change Advertisement Request Information element format to GAS Request Information element format | Accepted
Tony Mo | 7.3.2.39 | 21 | 11 | E | N | Description is wrong | The GAS Request element is included in a GAS Initial Request action frame or a GAS Comeback Response frame. | Accepted
Tony Mo | 7.3.2.40 | 21 | 21 | E | N | "GAS response info" should be "Response Info" which is the same with Figure u10 | Change GAS response info to Response Info | Accepted
Tony Mo | 7.3.2.40 | 21 | 24,25 | E | N | Description is ambiguous | GAS Response Element is sent by the AP to the non-AP STA in the GAS Initial Response or GAS Comeback Response frame to provide the information about one or more requested network services. | Accepted
Tony Mo | 7.3.2.41 | 22 | 16 | T |  | Why and how does the STA use the "Time to Suspend" here? |  | Rejected: Current text is satisfactory.
Tony Mo | 7.3.2.41 | 22 | 5-6 | E | N | undefined Query ID | Change Query ID to GAS Query ID in Figure u11. | Accepted
Tony Mo | 7.3.2.41 | 22 | 19-22 | E | N | undefined Query ID | The GAS Query ID(s) field is a variable length field composed of a list of GAS Query ID(s) (cf. clause 7.3.1.18). Inclusion of a GAS Query ID in this list means the AP has scheduled the GAS Comeback Response(s) (cf. clause 7.4.6.4) for transmission subsequent to this GASTIM with the GAS Query ID(s) as indicated in this field. This field can only be present when GASTIM count is zero. | Accepted
Dave Stephenson | 7.3.2.44 | 23 | 21 | E |  | The number of octets in Realm field should be listed a variable. | Change text to "variable" | Accepted
Dave Stephenson | 7.3.2.44 | 23 | 23 | E |  | The text states "… shall be set to N, where N indicates the Realm field." | Text would be more accurate to state: "… shall be set to the length in octets of the Realm field." | Accepted
Dave Stephenson | 7.3.2.45 | 23 | 27 | E |  | The terms QSTA and QAP are use--my understanding is that these terms have been deprecated due to the difficulty of merging amendments with the baseline standard. | Change QSTA -> STA and QAP -> AP. | QoS AP & QoS STA
Tony Mo | 7.3.2.44 | 23 | 24,25 | E | N | The name of NAI(RFC 4282) is wrong | Change RFC-4282 to RFC 4282 | Accepted
Dave Stephenson | 7.3.2.46 | 24 | 9 | E |  | The terms QSTA and QAP are use--my understanding is that these terms have been deprecated due to the difficulty of merging amendments with the baseline standard. | Change QSTA -> STA and QAP -> AP. Now that I've noticed a couple occurances, I would suggest a global replace. | Accepted
Dave Stephenson | 7.3.2.46 | 24 | 12 | E |  | QoS Map Set table heading is hanging without any table cells. | Mark keep with next paragraph. | Accepted
Tony Mo | 7.3.2.45 | 24 | Figure u15 | T |  | Why is a TSID field inclued since the TSID field has already been included in the TSPEC IE in ADDTS? |  | Remove TSID in the Fig u15 and remove the text describing TSID.
Dave Stephenson | 7.3.2.46 | 25 | 9 | E |  | The sentence, "All DSCP values are between 0 and 63 inclusive" is vague. | Change sentence to read, "All DSCP values shall be between 0 and 63 inclusive. | Accepted
Tony Mo | 7.3.2.46 | 25 | 20 | E | N | The name of the IE should be identical to the above. | Change Exception element description to DSCP Exception element description | Accepted
Tony Mo | 7.3.2.46 | 25 | 4-6 | T | N | A UP corresponding an exception value in the QoS Map Set can only override one UP value in the UP n DSCP Range portion of the IE. | Any packet to be transmitted by a QSTA whose DSCP matches any exception value in the QoS Map Set shall use the corresponding UP for transmission; that is, it overrides the UP value provided in the UP n DSCP Range portion of the IE. | Deferred: Needs further info from Tony Adhoc discussed it. Recommeded the comment to be removed. (02/20/2007)
Dave Stephenson | 7.3.2.46 | 26 | 1 | E |  | This sentence is out of place. | Move sentence to page 25, end of line 3. | Accepted
Necati Canpolat | 7.3.2.46 | 26 | 5 | E |  | This is a duplicate sentence as in line 1. | Delete the lines 5 & 6. | Accepted
Dave Stephenson | 7.3.2.46 | 26 | 5 | E |  | The sentence on this line is too repetitive. | Delete sentence. | Accepted
Hong Cheng | 7.3.2.47 | 26 | 7 | T | Y | This section does not belong to clause 7.3, since the information defined here are for the SSPN interface instead of the air interface. | Move contents of the clause 7.3.2.47 to Annex P.3.1.3. Some updated text is available in the attached submission. (06/1799r0) | Stephenson & Hong Dave presented the changes during adhoc (2/20/2007). Dave and Hong will submit a presentation for Orlando meeting.
Dave Stephenson | 7.3.2.47 | 26 | 7 | T |  | SSPN Interface elements should not be an information element since this data is never transmitted over-the-air. | Create MIB in Annex D (normative) and move this information into the MIB in ASN.1 format. | Stephenson & Hong Dave presented the changes during adhoc (2/20/2007). Dave and Hong will submit a presentation for Orlando meeting.
Tony Mo | 7.3.2.47 | 27 | 13 | E | N | edit wrongly | Change intension to intention | Accepted
Necati Canpolat | 7.3.2.47 | 27 | 32 | T |  | Resolution to the stated editorial comment is need. "[Note: It is up to discussion if this is enough for the QoS requirements from the SSPN. It depends whether the SSPN wants the WLAN AN to allocate resource statically or dynamically. For example, other than the static limit indicated by user subscription, there may be different QoS limit set by the SSPN based on the service the STA requested. Do we want/need to support this?]" | Volunteer is needed. | Stephenson & Hong Dave presented the changes during adhoc (2/20/2007). Dave and Hong will submit a presentation for Orlando meeting.
Necati Canpolat | 7.3.2.47 | 28 | 35 | T |  | Resolution to the stated editorial comment is need. "[Note: The new possible Reason Codes are:…" | Volunteer is needed. | Stephenson & Hong Dave presented the changes during adhoc (2/20/2007). Dave and Hong will submit a presentation for Orlando meeting.
Necati Canpolat | 7.3.2.47 | 29 | 32 | T |  | Resolution to the stated editorial comment is need. "Does format of such information needs to be defined? Or, kept it the same as LCI defined in 7.3.2.22.9? What is the requirement of E911 services?" | Volunteer is needed. | Stephenson & Hong Dave presented the changes during adhoc (2/20/2007). Dave and Hong will submit a presentation for Orlando meeting.
Necati Canpolat | 7.3.2.47 | 29 | 49 | T |  | Resolution to the stated editorial comment is need. "There are two aspects in this element, from DS to STA and from STA to DS" | Volunteer is needed. | Stephenson & Hong Dave presented the changes during adhoc (2/20/2007). Dave and Hong will submit a presentation for Orlando meeting.
Tony Mo | 7.3.2.47 | 29 | 19-21 | E | N | solecism | This indicates whether STA is Active or PS Mode. This is necessary because when a STA is in the PS mode it may go to Doze state, and the AP needs to buffer the MSDU, and thus may not meet certain Interworking Service requirements. | Accepted
Tony Mo | 7.4.2.5 | 31 | 16 | E | N | reference to non-existent clause | Change 11.4.y to P.2.1 | Accepted
Hong Cheng | 7.4.2.5 | 31 | 17 | E | N | Change "Table u1" to "Table u3" | As indicated in the comment | Accepted
Tony Mo | 7.4.2.5 | 31 | 17 | E | N | The number of the DSCP Map request frame body table is wrong. | The frame body of the QoS Map Request frame contains the information shown in Table u3. | Accepted
Tony Mo | 7.4.2.5 | 31 | 18 | E | N | Description is wrong | Change DSCP to QoS | Accepted
Tony Mo | 7.4.2.5 | 31 | 22 | E | N | Description is wrong | delete the sentence | Accepted
Tony Mo | 7.4.2.1 | 31 | 10,11 | E | N | The clause number is wrong | There may be one Expedited bandwidth request element which is defined in 7.3.2.45 | Accepted
Tony Mo | 7.4.2.6 | 32 | 3 | E | N | reference to non-existent clause | Change 11.4.y to P.2.1 | Accepted
Hong Cheng | 7.4.2.6 | 32 | 4 | E | N | Change "Table u2" to "Table u4" | As indicated in the comment | Accepted
Tony Mo | 7.4.2.6 | 32 | 4 | E | N | The number of the DSCP Map configure frame body table is wrong. | The frame body of the QoS Map Configure frame contains the information shown in Table u4. | Accepted
Tony Mo | 7.4.2.6 | 32 | 5 | E | N | Description is wrong | Change DSCP to QoS | Accepted
Dave Stephenson | 7.4.6 | 32 | 11 | E |  | Heading would read better if it were "Interworking action frame details. | Change heading per suggestion. | Accepted
Tony Mo | 7.4.6 | 32 | 15-16 | T | N | Description is wrong Not all Action frames use UP = 0 to transmit | All Interworking Action frames shall be transmitted using UP = 0 with the EDCA parameters for AC_BE. | Needs clarification Reviwed during adhoc (2/20/07) and recommending to accept the suggestion.
Tony Mo | 7.4.6.1 | 33 | 1 | E | N | Description is wrong | Change non-AP-STA to non-AP STA | Accepted
Tony Mo | 7.4.6.1 | 33 | 7 | E | N | The number of table is wrong | The Action field shall be set to 0 (representing a GAS Initial Request frame, as specified in Table u5). | Reference to Table u6 is correct
Tony Mo | 7.4.6.1 | 33 | 10 | E | N | The clause number is wrong | GAS request element is defined in 7.3.2.39. There shall be only one element per request. | Accepted
Tony Mo | 7.4.6.2 | 33 | 12 | E | N | Description is wrong | Change non-AP-STA to non-AP STA | Accepted
Tony Mo | 7.4.6.2 | 33 | 18 | E | N | The number of table is wrong | The Action field shall be set to 1 (representing a GAS Initial Response frame, as specified in Table u5). | Accepted
Tony Mo | 7.4.6.2 | 33 | 12,13 | E | N | Description is wrong | The GAS Initial Response frame uses the Action frame body format and is transmitted by an AP to a non-AP-STA. The format of the GAS Initial Response frame body is shown in Table u7. | Accepted
Tony Mo | 7.4.6.2 | 34 | 9 | E | N | The clause number of is wrong | The GAS Response Element is defined in 7.3.2.40. There shall be zero or one element per response. | Accepted
Tony Mo | 7.4.6.3 | 34 | 11 | E | N | Description is wrong | Change non-AP-STA to non-AP STA | Accepted
Tony Mo | 7.4.6.3 | 34 | 12 | E | N | Description is wrong | Change Response to Request, Change 61 to 8 | Accepted
Tony Mo | 7.4.6.4 | 34 | 25 | E | N | Description is wrong | Change non-AP-STA to non-AP STA | Accepted
Tony Mo | 7.4.6.3 | 34 | 11,12 | E | N | Description is wrong The number of the GAS Comeback Response frame body table is wrong. | The GAS Comeback Request frame uses the Action frame format and is transmitted by a non-AP STA to AP. The format of the GAS Comeback Request frame body is shown in Table u8. | Accepted
Tony Mo | 7.4.6.3 | 34 | 19,20 | E | N | The number of table is wrong | The Action field shall be set to the 2 (representing a GAS Comeback Request frame, as specified in Table u5). | Accepted
Tony Mo | 7.4.6.4 | 34 | 24-26 | E | N | Description is wrong. | The Action field shall be set to the 2 (representing a GAS Comeback Request frame, as specified in Table u5). | Accepted
Tony Mo | 7.4.6.4 | 35 | 5 | T | N | In which situation the GAS Query ID value shall be set to 0? |  | Deferred for further discussion. Reviewed during adhoc (2/20/07) and recommending to delete the line 6-7 "The GAS Query ID field shall correspond to the GAS Initial Response action frame exchange. This value shall be set to 0 when there is no outstanding request to process."
Jin Lee | 7.4.6.4 | 35 | 14 | T |  | In the current draft, GAS Request Element is included when either multicast delivery method or unicast is used. In page 61, GAS Request Element could be included optionally even in unicast GAS comeback Response. | For consistency, Either delete the second sentence in line 14 of page 35 or modify line 8-9 of page 61. | Deferred: Necati, Srini and Dave provide new text. Reviewed duiring the adhoc (2/20/07). Recommending to change the text in page 35 line 14 & 15 as such "This information element shall be optional when unicast delivery method is used."
Dave Stephenson | 9.9.3.1 | 36 | 23 | T |  | Text reads, "For a QSTA accessing interworking service, the QAP shall use the priority information sent from the SSPN in the admission control." | This sentence is too vague. Assuming we are moving this section to a MIB, then the "priority" should refer the exact MIB variables desired. | Deferred to re-writing of section 7.3.2.47 Dave presented the changes during adhoc (2/20/2007). Dave and Hong will submit a presentation for Orlando meeting.
Necati Canpolat | 9.9.3.1 | 36 | 25 | E |  | Heading number is wrong. | Change the heading number to 9.9.3.2 and fix the subsequent heading numbers | Accepted
Dave Stephenson | 9.9.3.1 | 36 | 25 | E |  | There are two sections labelled "9.9.3.1". The numbering error is propagated into following subsections. | Fix numbering system. | Accepted
Dave Stephenson | 9.9.3.1b | 36 | 27 | T |  | The text reads, "For QAP supports interworking service, the determination shall be based on authorization information from the SSPN." | This sentence is too vague. Assuming we are moving this section to a MIB, then the "authorization information" should refer the exact MIB variables desired. | Deferred to re-writing of section 7.3.2.47 Dave presented the changes during adhoc (2/20/2007). Dave and Hong will submit a presentation for Orlando meeting.
Dave Stephenson | 9.9.3.2 | 36 | 37 | T |  | The text reads, "For a non-AP QSTA accessing the interworking service, the HC shall admit its request based on authorization information derived from the SSPN of the QSTA." | This sentence is too vague. Assuming we are moving this section to a MIB, then the "authorization information" should refer the exact MIB variables desired. | Deferred to re-writing of section 7.3.2.47 Dave presented the changes during adhoc (2/20/2007). Dave and Hong will submit a presentation for Orlando meeting.
Necati Canpolat | 10.3 | 37 | 2 | T |  | ESO and emrgency service realm primitives are missing. | Define the primitives | Deferred: Dave will provide the text. Reviewed at adhoc (2/20/07) and re-assigned it to Elly & Angelo. It could be handled as part of comment 138 resolution.
Dave Stephenson | 10.3 | 37 | 2 | T |  | There needs to be a set of primitives defined to deliver ESO and emergency services realm IE to STA. | There needs to be a set of primitives defined to deliver ESO and emergency services realm IE to STA. | Duplicate
Dave Stephenson | 10.3.2 | 37 | 4 | T |  | ESSID parameter needs to be added to scan primitives. | Add. | Necati will provide the text.
Jin Lee | 10.3.2.2 | 37 | 5 | T |  | MLME-SCAN.confirm primitive should transport GAS capability information to the the upper layer (eg. MIHF). | Insert 'Generic Advertisement Service Capability' and 'Generic Advertisement Service Traffic Indication Map' as parameters in MLME-SCAN.confirm Relocate the table in line 7 to subsection 10.3.2.2.2 | Elly & Angelo Reviewed a presentation during adhoc (2/20/07). Elll & Angelo will have presentation at Orlendo meeting.
Tony Mo | 10.3.2.2 | 37 | 7 | E | N | modification to wrong place | The amendment should be added in clause 10.3.2.2.2. | Accepted
Necati Canpolat | 10.3.6 | 37 | 14 | T |  | Section 10.3.6 has not been defined in any of the confirmed proposals but needs be included here. This is editorial addition for now. | Volunteer is needed. | Elly & Angelo Reviewed a presentation during adhoc (2/20/07). Elll & Angelo will have presentation at Orlendo meeting.
Tony Mo | 10.3.6.1.2 | 38 | 12 | E | N | Description is wrong | Change InterworkingCapabilities to InterworkingCapability Change dot11InterworkingImplemented to dot11InterworkingEnabled | Accepted
Necati Canpolat | 10.3.7 | 40 | 4 | T |  | Section 10.3.7 has not been defined in any of the confirmed proposals but needs be included here. This is editorial addition for now. | Volunteer is needed. | Elly & Angelo Reviewed a presentation during adhoc (2/20/07). Elll & Angelo will have presentation at Orlendo meeting.
Necati Canpolat | 10.3.25.2.1 | 42 | 17 | T |  | Explanation for REJECTED_LOCAL_WITH_SUGGESTED_CHANGES and REJECTED_HOME_WITH_SUGGESTED_CHANGES items are misssing | Add explanation. | Elly & Angelo Reviewed a presentation during adhoc (2/20/07). Elll & Angelo will have presentation at Orlendo meeting.
Dave Stephenson | 10.3.25.2.1 | 42 | 17 | E |  | Table 73 is in clause 11.4.4 in 802.11ma-d9. It should not have an editorial change made in this section. | Move to clause 11.4.4. | Accepted
Dave Stephenson | 10.3.25.2.1 | 42 | 17 | T |  | Reason code "Rejected with suggested changes" has been changed to "Rejected _locale_ with suggested changes" without providing an explanation of what this means. | Provide explanation. | Duplicate
Dave Stephenson | 10.3.25.2.1 | 42 | 17 | T |  | Reason code "Rejected _home_ with suggested changes" has been added without providing an explanation of what this means. | Provide explanation. | Duplicate
Peng Mo | 10.3.30.1.2 | 43 | 15 | T | N | This primitive is not enough parameter for STA to form the right GAS Initial Request frame. | Insert the following row at the end of the prameter table after Line 15 in page 43: | Reviewed during adhoc (2/20/07). Dave and Elly will have a presentation on GAS comment resolution.
Tony Mo | 10.3.30.1.4 | 43 | 20 | E | N | reference to non-existent clause | Change 11.11.1 to 11.10.1.3 | Accepted
Tony Mo | 10.3.30.1.2 | 43 | 10-14 | T | N | This primitive is not enough parameter for STA to form the right GAS Initial Request frame. | MLME-GAS-Initial-Request.request ( DialogToken , DeliveryMethod, AdvertisementProtocolID, Query ) | Duplicate of 148
Peng Mo | 10.3.30.2.2 | 44 | 9 | T | N | This primitive is not enough parameter for STA to handle the right GAS Initial Response frame. | Insert the following row at the end of the prameter table after Line 9 in page 44: | Reviewed during adhoc (2/22/07). Dave will provide the text for it.
Jin Lee | 10.3.30.2.2 | 44 | 9 | T |  | StatusCode' does not harmonize with the one in 7.3.1.9. | Match 'StatusCode with 7.3.1.9 | Reviewed during adhoc (2/22/07). Dave will provide the text for it.
Tony Mo | 10.3.30.2.4 | 44 | 18 | E | N | reference to non-existent clause | Change 11.y to 11.10.1 | Accepted
Tony Mo | 10.3.30.2.2 | 44 | 1-8 | T | N | This primitive is not enough parameter for STA to handle the right GAS Initial Response frame. | StatusCode, DialogToken, GASQueryID, GASComebackDelay, GASMulticastAddress, DeliveryMethod, AdvertisementProtocolID, ResponseInfo ) | Reviewed during adhoc (2/20/07). Dave and Elly will have a presentation on GAS comment resolution.
Tony Mo | 10.3.30.3.2 | 45 | 8 | T | N | This primitive is not enough parameters for AP to handle the right GAS Initial Request frame. | Insert the following row at the end of the prameter table after Line 8 in page 45: | Reviewed during adhoc (2/22/07). Dave will provide the text for it.
Tony Mo | 10.3.30.3.4 | 45 | 15 | E | N | reference tonon-existent clause | Change 11.11 to 11.10.1 | Accepted
Tony Mo | 10.3.30.3.4 | 45 | 16 | T |  | There is no definition about the dot11GASResponseTimeout | A definition should be added. | reviewed at adhoc and recommeded that Ely to provide MIB for it.
Tony Mo | 10.3.30.4.2 | 45 | 25 | E | N | Description is wrong | Change NonAPSTAAddress to Non-APSTAAdress | Rejected
Tony Mo | 10.3.30.3.2 | 45 | 3-7 | T | N | This primitive is not enough parameters for AP to handle the right GAS Initial Request frame. | MLME-GAS-Initial-Request.indication ( DialogToken , DeliveryMethod, AdvertisementProtocolID, Query, Non-APSTAAddress ) | Reviewed during adhoc (2/22/07). Dave will provide the text for it.
Tony Mo | 10.3.30.4.2 | 45 | 23-31 | T | N | This primitive is not enough parameters for AP to form the right GAS Initial Response frame. | MLME-GAS-Initial-Response.response ( StatusCode, DialogToken , NonAPSTAAddress, GASQueryID, GASComebackDelay, GASMulticastAddress, DeliveryMethod, AdvertisementProtocolID, ResponseInfo ) | Reviewed during adhoc (2/22/07). Dave will provide the text for it.
Tony Mo | 10.3.30.4.2 | 46 | 1 | T | N | This primitive is not enough parameters for AP to form the right GAS Initial Response frame. | Insert the following row at the end of the prameter table after Line 1 in page 46: | Reviewed during adhoc (2/22/07). Dave will provide the text for it.
Jin Lee | 10.3.30.4.2 | 46 | 1 | T |  | StatusCode' does not harmonize with the one in 7.3.1.9. | Match 'StatusCode with 7.3.1.9 | Reviewed during adhoc (2/22/07). Dave will provide the text for it.
Tony Mo | 10.3.30.4.2 | 46 | 2 | E | N | solecism | Change a 802.11 to an 802.11 in the 6th row in the table | Accepted
Tony Mo | 10.3.30.5.2 | 46 | 15-17 | T | N | This primitive is not enough parameter for STA to form the right GAS Comeback Request frame. | MLME-GAS-Comeback-Request.request ( GASQueryID, DialogToken ) | Reviewed during adhoc (2/22/07). Dave will provide the text for it.
Tony Mo | 10.3.30.5.2 | 47 | 1 | T | N | This primitive is not enough parameter for STA to form the right GAS Comeback Request frame. | Insert the following row at the end of the prameter table before Line 1 in page 47: | Reviewed during adhoc (2/22/07). Dave will provide the text for it.
Tony Mo | 10.3.30.5.4 | 47 | 6 | E | N | reference to non-existent clause | Change 11.11 to 11.10.1 | Accepted
Tony Mo | 10.3.30.6.2 | 47 | 21 | T | N | This primitive is not enough parameter for STA to handle the right GAS Comeback Response frame. | Insert the following row at the end of the prameter table after Line 21 in page 47: | Reviewed during adhoc (2/22/07). Dave will provide the text for it.
Jin Lee | 10.3.30.6.2 | 47 | 21 | T |  | 'StatusCode' does not harmonize with the one in 7.3.1.9. | Match 'StatusCode with 7.3.1.9 | Reviewed during adhoc (2/22/07). Dave will provide the text for it.
Tony Mo | 10.3.30.6.2 | 47 | 14-20 | T | N | This primitive is not enough parameter for STA to handle the right GAS Comeback Response frame. | MLME-GAS-Comeback-Response.confirm ( StatusCode, DialogToken , GASQueryID, GASComebackDelay, DeliveryMethod, AdvertisementProtocolID, ResponseInfo ) | Reviewed during adhoc (2/22/07). Dave will provide the text for it.
Tony Mo | 10.3.30.7.2 | 48 | 18 | T | N | This primitive is not enough parameter for STA to handle the right GAS Comeback Request frame. | Insert the following row at the end of the prameter table after Line 18 in page 48: | Reviewed during adhoc (2/22/07). Dave will provide the text for it.
Tony Mo | 10.3.30.7.4 | 48 | 25 | E | N | reference to non-existent clause | Change 11.y to 11.10.1 | Accepted
Tony Mo | 10.3.30.8.1 | 48 | 29 | E | N | solecism | Change a advertisement to an advertisement | Accepted
Tony Mo | 10.3.30.7.2 | 48 | 14-17 | T | N | This primitive is not enough parameters for AP to handle the right GAS Initial Request frame. | MLME-GAS-Comeback-Request.indication ( DialogToken , GASQueryID, Non-APSTAAddress ) | Reviewed during adhoc (2/22/07). Dave will provide the text for it.
Tony Mo | 10.3.30.8.2 | 49 | 9 | T | N | This primitive is not enough parameters for AP to form the right GAS Initial Response frame. | Insert the following row at the end of the prameter table after Line 9 in page 49: | Reviewed during adhoc (2/22/07). Dave will provide the text for it.
Tony Mo | 10.3.30.8.2 | 49 | 9 | E | N | the StatusCode valid range is not equal to the Status Code field definition in Table 23 Page 14 | Status Code 56 and 57 should be added. | Duplicate
Jin Lee | 10.3.30.8.2 | 49 | 9 | T |  | 'StatusCode' does not harmonize with the one in 7.3.1.9. | Match 'StatusCode with 7.3.1.9 | Reviewed during adhoc (2/22/07). Dave will provide the text for it.
Tony Mo | 10.3.30.8.2 | 49 | 1-8 | T | N | This primitive is not enough parameters for AP to form the right GAS Initial Response frame. | MLME-GAS-Comeback-Response.response ( StatusCode, DialogToken , Non-APSTA Address, GASQueryID, GASComebackDelay, DeliveryMethod, AdvertisementProtocolID, ResponseInfo ) | Reviewed during adhoc (2/22/07). Dave will provide the text for it.
Tony Mo | 10.3.30.8.4 | 49 | 15-16 | E | N | Description is wrong | Change GAS Comeback-response to GAS Comeback Request | Accepted
Tony Mo | 10.3.31.2.3 | 51 | 8-10 | E | N | solecism | Change a STA to an STA | Rejected
Tony Mo | 10.3.31.3.2 | 51 | 26-31 | T | N | This parameter can help handover. | MLME-LinkGoingDown.indication ( ReasonCode, MacMobileTerminal, TimeInterval, ConfidenceLevel, UniqueEventIdentifier ) | reviewed at ahoc (2/22/07). Further discussion is needed.
Tony Mo | 10.3.31.3.2 | 52 | 2 | T | N | This parameter can help handover. | Insert the following row at the end of the prameter table before Line 2 in page 52: | reviewed at ahoc (2/22/07). Further discussion is needed.
Dave Stephenson | 10.3.32 | 56 | 6 | T |  | Explantory text on how QoS Map works should be minimized in this clause. | Add detailed explanation of QoS Map set operation to clause 11.4 and abbreviate explanation in clause 10.3.32. | Reviewed at adhoc (2/22/07) - Dave will have presentation at Orlando meeting.
Tony Mo | 10.3.32 | 56 | 12 | E | N | Description is wrong | Change AP to QAP in Table u10 | Accepted
Tony Mo | 10.3.32.1.1 | 56 | 20 | E | N | Description is wrong | Change AP to QAP | Accepted
Tony Mo | 10.3.32.1.4 | 56 | 30 | E | N | reference to non-existent clause | Change 11.y to P.2.1 | Accepted
Tony Mo | 10.3.32 | 56 | 13,14 | E | N | Description is wrong | Change AP to QAP | Accepted
Tony Mo | 10.3.32.2.1 | 57 | 3 | E | N | Description is wrong | Change AP to QAP | Accepted
Tony Mo | 10.3.32.2.3 | 57 | 14 | E | N | Description is wrong | Change an QoS to a QoS | Accepted
Tony Mo | 10.3.32.2.3 | 57 | 15 | E | N | Description is wrong | Change AP to QAP | Accepted
Dave Stephenson | 10.3.32.2.4 | 57 | 21 | E |  | Text makes reference to clause 11.y. | Change reference to proper clause. | Accepted
Tony Mo | 10.3.32.2.4 | 57 | 21 | E | N | reference to non-existent clause | Change 11.y to P.2.1 | Accepted
Necati Canpolat | 10.3.32.2.4 | 57 | 21 | E |  | Incorrect referenc 11.y. | Fix it to correct clause reference | Accepted
Tony Mo | 10.3.32.2.3 | 57 | 24 | E | N | Description is wrong | Change AP to QAP | Accepted
Tony Mo | 10.3.32.3.2 | 57 | 27 | E | N | Here should be an indication primitive | Change MLME-QoSMap.request to MLME-QoSMap.indication | Accepted
Tony Mo | 10.3.32.2.3 | 57 | 17-19 | E | N | edit wrongly | For example, an ADDTS or DELTS procedure should be activated if the QoS Map information indicates a Change in the admission controlled AC. | not clear what needs to be changed
Dave Stephenson | 10.3.32.3.4 | 58 | 5 | E |  | Text makes reference to clause 11.y. | Change reference to proper clause. | Accepted
Necati Canpolat | 10.3.32.3.4 | 58 | 5 | E |  | Incorrect referenc 11.y. | Fix it to correct clause reference | Accepted
Tony Mo | 10.3.32.3.4 | 58 | 5 | E | N | reference to non-existent clause | Change 11.y to P.2.1 | Accepted
Dave Stephenson | 10.3.32.4.1 | 58 | 10 | T |  | The text reads "The specified non-AP QSTA MAC address could be a broadcast or multicast address." How is the broadcast/multicast address requested? There is no way identified to do this. | Delete this sentence. | Reviewed at adhoc (2/22/07) - Recommed that we remove the "or multicast" in the sentence.
Tony Mo | 10.3.32.4.2 | 58 | 13 | E | N | Here should be a response primitive | Change MLME-QoSMap.request to MLME-QoSMap.response | Accepted
Tony Mo | 10.3.32.2.3 | 58 | 20 | E | N | Description is wrong | Change AP to QAP | Accepted
Necati Canpolat | 11.4 | 59 | 3 | T |  | Editoriol Comment: Procedure description should be provided on how each procedure is performed when information elements defined for SSPN interface is used. For example, how the admission control should use the “Authorized Priority” to treat a TS operation (admission control) | Volunteer is needed. | Matthew, Angelo,& Hong Reviewed at adhoc (2/22/07). The text will be provided by volunteers.
Dave Stephenson | 11.4 | 59 | 3 | T |  | Agree with editor's comment. | Suggest we ask for volunteers at London meeting. | Duplicate
Dave Stephenson | 11.4.1 | 59 | 11 | E |  | How do we integrate expeditied bandwidth request element into TGr RIC? | Suggest we discuss at London meeting. | Not editorial
Hong Cheng | 11.7 | 59 | 14 | T | Y | Add text to clause 11.7 DLS operation | Proposed text available in the attached submission (06/1799r0) | reviewed at adhoc (2/22/07). Hong will present the doc 06/1799r0 in Orlando.
Hong Cheng | 11.4.4 | 59 | 14 | T | Y | Add text to the clause 11.4.4 TS Setup procedures | Proposed text available in the attached submission (06/1799r0) | reviewed at adhoc (2/22/07). Hong will present the doc 06/1799r0 in Orlando.
Hong Cheng | 11.4.7 | 59 | 14 | T | Y | Add changes to clause 11.4.7 TS Delete | Proposed change available in the attached submission (06/1799r0) | reviewed at adhoc (2/22/07). Hong will present the doc 06/1799r0 in Orlando.
Hong Cheng | 11.10.1.3 | 59 | 29 | E | N | Correct the title numbering. | Change "11.10.1.3" to "11.10.1.1" | Accepted
Tony Mo | 11.10.1.3 | 59 | 31-33 | E | N | Description is wrong | The non-AP STA can send a GAS-Initial-Request frame with one of the supported protocol ids with specific query to obtain information about the specific interworking service. | Accepted
Hong Cheng | 11.10.1.4 | 60 | 22 | E | N | Correct the title numbering. | Change "11.10.1.4" to "11.10.1.2" | Accepted
Tony Mo | 11.10.1.4 | 61 | 5 | T | N | Description is wrong | Change "for the comeback delay duration" to "untill the expiry of the comeback delay" | reviewed at adhoc (2/22/07) recommed to leave it as is.
Tony Mo | 11.10.1.4 | 61 | 9 | E | N | Description is wrong | delete "and the query results" | Accepted
Tony Mo | 11.10.1.4 | 61 | 19 | E | N | Description is wrong | Change "a new" to "the same or a new" | Accepted
Dave Stephenson | 11.10.2 | 62 | 30 | E |  | The terms ES and CS should be included in the definitions clause of this amendment. | Add to clause 3. | Accepted
Dave Stephenson | 11.10.2.3 | 63 | 5 | E |  | This paragraph states what TGu intends to do and is worded in future tense. | Reword to change to present tense. | Accepted
Dave Stephenson | 11.10.2.3 | 63 | 9 | T |  | The text reads, "Connectivity includes AP is configured with MIH services. Interworking capability element will be used in beacons." This suggests that it is important for STA to know whether a certain capability is in AP." | Change text to indicate that AP provides only logical connectivity information--it should be up to implementation whether a particular service is in AP or somewhere in DS. | reviewed at adhoc (2/22/07). The text implies that AP is an MIH entity which is not the case. AP is MIH aware, which means it can provide MIH transport. capability Change the text to reflect the resolved comment.
Dave Stephenson | 11.10.2.4 | 63 | 13 | E |  | This paragraph is worded as a TGu requirement. I'm not sure what the purpose of this paragraph is--the requirement has been accepted by TGu and this TGu amendment provides what has been done to support it. | Remove paragraph or re-word so the intended meaning is clarified. | Accepted
Dave Stephenson | 11.10.2.5 | 63 | 19 | E |  | This paragraph is worded as a TGu requirement. I'm not sure what the purpose of this paragraph is--the requirement has been accepted by TGu and this TGu amendment provides what has been done to support it. | Remove paragraph or re-word so the intended meaning is clarified. | Accepted
Dave Stephenson | 11.10.2.6 | 63 | 25 | T |  | The text reads, "When GAS Protocol ID of MIH Information Service and/or GAS Protocol ID of MIH Command and Event Services Capability Discovery are/is included in GAS Capability Information element, STA shall use GAS Request/Response action frames in order to query Information Elements of Information Service and/or to discover MIH capabilities of Event Service and/or Command Service." Why is it required for STA to operate this way? | Change "shall" to "may". | adhoc recommeds (2/22/07) that we adopt the resolution.
Hong Cheng | 11.10.3 | 64 | 7 | T | Y | Need to add the text about QoS Map Distribution procedure | Move contents of Annex P.2.2 and P.2.3 to clause 11.10.3 | Reviewed at adhoc (2/22/07). Recommed that Hong and Dave provide solution.
Dave Stephenson | 11.10.3 | 64 | 7 | T |  | The text of this section is stated as a requirement to TGu as well as a problem statement. This is no longer needed. | Add text to section 10.4 to describe desired operation. | reviewed at adhoc (2/22/07) It should be covered by the proposal from Dave & Hong.
Necati Canpolat | Annex A | 65 | 3 | T |  | This section is missing details | Volunteer is needed. | Dave & Necati
Dave Stephenson | Annex A | 65 | 3 | T |  | Annex A is incomplete. | Suggest we ask for volunteers at London meeting. | Duplicate
Dave Stephenson | Annex D | 66 | 1 | T |  | Annex D is incomplete. | Suggest we ask for volunteers at London meeting. | Elly & Necati
Necati Canpolat | Annex D | 66 | 2 | T |  | This section is missing details | Volunteer is needed. | Duplicate
Hong Cheng | Annex D | 66 | 2 | T | Y | Add defintion of the "dot11InterworkingImplemented" | As indicated in the comment | Matthew to present at Orlando meeting
Necati Canpolat | Annex K | 67 | 1 | T |  | This section is missing details | Volunteer is needed. | Duplicate
Dave Stephenson | Annex K | 67 | 1 | T |  | Annex K is incomplete. | Suggest we ask for volunteers at London meeting. | Mathew, Angelo, Srini & Hong
Hong Cheng | Annex K | 67 | 4 | T | Y | Add text about the SSPN information in Admission Control | Proposed text available in the attached submission (06/1799r0) | Mathew, Angelo, Srini & Hong
Dave Stephenson | Annex P | 68 | 1 | E |  | Annex P has already been used in 802.11ma-d9. | Add editorial note that annex letter will be assigned later. | Accepted
Tony Mo | P.1 | 68 | 22 | E | N | reference to non-existent clause | Change 11.15.1.5 to P.1.4 | Accepted
Tony Mo | P.1 | 68 | 24 | E | N | reference to wrong clause | Change P.1.1 to P.1.5 | Accepted
Tony Mo | P.1.2 | 70 | 3 | E | N | reference to wrong clause | Change 1.5 to P.1.4 | Accepted
Tony Mo | P.1.2 | 70 | 11 | E | N | solecism | Change a advertisement to an advertisement | Accepted
Tony Mo | P.1.2 | 70 | 20 | E | N | reference to wrong clause | Change 1.6 to P.1.5 | Accepted
Hong Cheng | Annex P | 71 | 34 | T | N | Update the text from Page 71 Line 34 to Page 72 Line 14 | Proposed text available in the attached submission | Hong to come back with further clarification
Necati Canpolat | Annex P.2.1 | 72 | 17 | E |  | Delete"(As stated in requirement R11N3)" | remove the G23text | Accepted
Hong Cheng | P.2.1 | 72 | 17 | E | N | Remove "(As stated in requirement R11N3)" | As indicated in the comment | Accepted
Tony Mo | P.2.1 | 72 | 18 | T | N | Is virtual AP considered in the User Plane? |  | Need response from commentor
Tony Mo | P.2.1 | 72 | 18 | E | N | Description is wrong | Change Figure 1 to Figure u23 | Accepted
Hong Cheng | P.2.1 | 73 | 2 | E | N | Remove "from the example in previous section" | As indicated in the comment | Accepted
Necati Canpolat | P.2.1 | 73 | 4 | E |  | Change the reference of "Figure 2" to "Figure u24" | Fix the reference | Accepted
Hong Cheng | P.2.1 | 73 | 4 | E | Y | Change "Figure 2" to "Figure u24" | As indicated in the comment | Accepted
Tony Mo | P.2.1 | 73 | 4 | E | N | Description is wrong | Change Figure 2 to Figure u23 | Accepted
Hong Cheng | P.2.2 | 74 | 1 | T | Y | Text here described the normative operation of the QoS Map distribtion procedure. It should be under clause 10. | Move the text to cluase 10.11.3 | Duplicate of #219
Necati Canpolat | P.2.2 | 74 | 5 | T |  | Editorial Comment needs to be addressed "To add in corresponding description of the QoS Map information distribution, e.g. what are the procedures for AP and STA." | Volunteer is needed. | Mathew, Angelo, Srini & Hong
Hong Cheng | P.2.3 | 74 | 24 | T | Y | Add text to refer to the correct clause for the transport |  | reviewed at adhoc (2/22/07) Hong agreed to proposed change
Tony Mo | P.2.3 | 74 | 24 | E | N | Description is wrong | Change section XYZ to P.2 | Accepted
Hong Cheng | P.3 | 75 | 7 | T | Y | Update the text accordingly. | Proposed text available in 06/1799r0 | reviewed at adhoc (2/22/07). Hong will present the doc 06/1799r0 in Orlando.
Tony Mo | P.3 | 76 | 9 | E | N | Description is wrong | Change Figure A to Figure u25 | Accepted
Jin Lee | P.3 | 76 | 9 | E |  | Wrong figure number | Change Figure A to figure u25 | Optional (present if configured)
Tony Mo | 7.3.2.46 P.2.4 | 25 75 | Figure u17 Table P.2 | T | N | Does the QoS based on user level need to be considered when the AP distributes QoS Map in the User Plane proposal? |  | reviewed at adhoc (2/22/07). It seems be optimization issue and nice to have. Commentor should provide the text to resolve it.
Tony Mo | 7.3.2.46,P.2.1 | 25, 73 | 17,18 | T | Y | How to use the Action Frame to configure the QoS Map at the STA without solicitation? Unicast ? Broadcast or Multicast? More importantly, there are still some problems need to be solved when we choose to use each one of them. Please see the document for the detail. | Please see the document | Reviewed at ahoc (2/22/07). It is resolved thru the QoS map presentation from Dave & Hong.
Tony Mo | 7.4.6.4 11.10.1.4 | 35，61 | 14-15 Figure u21 | T | N | Shall the GAS Request Element be needed in the GAS Comeback Response frame which is identified by the GAS Query ID? If so, why? | The GAS Request Element in the GAS Comeback Response frame should be removed. | Duplicate of line 129
Tony Mo | 7.4.6.4 11.10.1.4 | 35，61 | 14-15 Figure u21 | T | N | Shall the GAS Request Element be needed in the GAS Comeback Response frame which is identified by the GAS Query ID? If so, why? | The GAS Request Element in the GAS Comeback Response frame should be removed. | Duplicate of line 129
Tony Mo | 10.3.30.2.2 | 44 46 47 | 9 1 21 | E | N | the StatusCode valid range in the table is not equal to the Status Code field definition in Table 23 Page 14 | Status Code 56 and 57 should be added. | Accepted
Tony Mo | 10.3.31 | 50-56 | 2 | T | N | Why aren't all primitives related to the MIH event indication added in the draft? |  | Reviewed at adhoc (2/22/07). Recommed that the text be updated. Commentor to provide
Hitoshi Morioka |  | iii |  | E |  | The page number starts from iii. | The page number should start from i. | Accepted
Tony Mo | All |  |  | T |  | The word "Advertisement"' in "Generic Advertisement Service (GAS)" will confuse people that the desired network information can only be advertised by an AP in broadcast/multicast deliver method, but actually the STA can also request the network information for the network selection using unicast method. | Maybe we can rename this service name using in network selection. E.g."'Network Discovery Service" | Reviewed at adhoc (2/22/07). Further discussion is needed.
Dave Stephenson | 7.4.6.4 | 35 | 14 | T |  | Adhoc recommends to consider the fragmentation case |  | Dave et al to produce the text

## Stats
Stats at the end of London meeting
Overall Summary | Total | Reviewed | Needs more work | Not reviewed | Closed | % Closed
Total Comments: | 252 | 207 | 58 | 45 | 149 | 59.13%
Editorial Comments: | 144 | 144 | 2 | 0 | 142 | 98.61%
Technical Comments: | 108 | 63 | 56 | 45 | 7 | 6.481%
Tentative stats based on adhoc recommendations which needs to be reviewed at Orlando meeting
Overall Summary | Total | Reviewed | Needs more work | Not reviewed | Closed | % Closed
Total Comments: | 253 | 252 | 83 | 0 | 170 | 67.19%
Editorial Comments: | 144 | 144 | 2 | 0 | 142 | 98.61%
Technical Comments: | 109 | 108 | 81 | 0 | 28 | 25.69%