## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-07/0214r2
Venue Date: | January 2007
First Author: | Clint Chaplin, TGr Chair
Subject: | Issues To-Do List
Full Date: | 2007-01-31
Author(s): | Clint Chaplin
TGr Chair
75 W. Plumeria Dr., San Jose, CA 95134
Phone: 408-544-5815
Fax:
email: clint.chaplin@gmail.com
Abstract:
Issues To-Do List
Notice: This document has been prepared to assist IEEE 802.11. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor grants a free, irrevocable license to the IEEE to incorporate material contained in this contribution, and any modifications thereof, in the creation of an IEEE Standards publication; to copyright in the IEEE’s name any IEEE Standards publication even though it may include portions of this contribution; and at the IEEE’s sole discretion to permit others to reproduce in whole or in part the resulting IEEE Standards publication. The contributor also acknowledges and accepts that this contribution may be made public by IEEE 802.11.
Patent Policy and Procedures: The contributor is familiar with the IEEE 802 Patent Policy and Procedures <http:// ieee802.org/guides/bylaws/sb-bylaws.pdf>, including the statement "IEEE standards may include the known use of patent(s), including patent applications, provided the IEEE receives assurance from the patent holder or applicant with respect to patents essential for compliance with both mandatory and optional portions of the standard." Early disclosure to the Working Group of patent information that might be relevant to the standard is essential to reduce the possibility for delays in the development process and increase the likelihood that the draft publication will be approved for publication. Please notify the Chair <stuart@ok-brit.com> as early as possible, in written or electronic form, if patented technology (or technology under patent application) might be incorporated into a draft standard being developed within the IEEE 802.11 Working Group. If you have questions, contact the IEEE Patent Committee Administrator at <patcom@ieee.org>.

## Sheet1
Issue Number | CID | Issue Description | Solution Consensus | Next Steps | Status
2 | 18 | EAPoL Reauthentication after FT Association needs to be explicitly specified. IEEE 802.11i allows re-authentication without re-association; 802.11r doesn't have an analagous solution. | Needs to be solved; client may want to do EAPoL reauthentication for other reasons than just key lifetime timeout (Network Access Control; OS fix) | Jouni Malinen and Kapil Sood to work on solution
3 | 124 | Clause 5: do we need text here? | Not needed; BSS Transition is already defined in Clause 5
4 | 237 | Do we need a sentence that states that the PMKR0SA is used to calculate a PMKID for FT? | Unsure | Michael Montemurro to decide if there is an issue, and suggest text if there is an issue. Michael to look at draft 4.1 and see if anything is needed.
5 | 265 | Over the DS be optional to implement? | Straw poll shows group is divided on this one. Implementations can be easier if over-the-DS is not implemented, but there are scenarios where over-the-DS is the only solution. Also, off-channel over-the-air is power inefficient, and is slower.
6 | 576 | 802.1X state machines are not defined well enough to be separated across the various entities we are defining in IEEE 802.11r. In fact, IEEE 802.11r doesn't define which functionality of 802.1X should reside in which key holder. |  | Part of the 802.1X that gets the MSK must be part of the R0KH, while the part of the 802.1X that does the controlled port must somehow communicate with the R1KH. 802.1X state machine splits? Informative note? Jouni Malinen to decide if there is an issue.
7 | 601 | What is "key binding"? What is "binding"? It seems that people who use the term know what it means, but there is no official definition that we can point to or quote. | Remove the term "binding" from the draft, replace with a description of what we are really doing. | Dorothy Stanley suggests: p. 30: "The top level FT Key Hierarchy key, PMK-R0 is derived using the key derivation function defined in section 8.5a.3. and p.33: "The R0KH authenticates a potential R1KH using the same R1HK identity as is included in the PMK-R1 derivation.
8 | 667, 706, 712 | AP receives an Association Request that contains an MDIE that doesn't match what it advertises? | This is a problem. | Need a submission describing parameter checking for FT parameters. Bill Marshall to take a look.
9 | 690 | Message 2 and 3 of FT 4-way handshake is described to use modified RSN IE (PMKR1Name in the PMKID list). This would mean that the RSN IE in (Re)AssocReq and Beacon/ProbeResp frames would not match exactly with the ones in these EAPOL frames. IEEE 802.11r is using the base standard description of EAPOL-Key frames from 8.5.2 that requires that the RSN IE in EAPOL-Key messages 2/4 and 3/4 match with the RSN IE “as transmitted” in (Re)AssocReq and Beacon/ProbeResp. 8.5.3.2 and 8.5.3.4 even define that the RSN IE are to be validated with bit-wise comparison and the frames are to be rejected if the RSN IE does not match. TGr would need to change something in 8.5 to allow the RSN IE to be different. How is the comparison carried out? IEEE 802.11i does a bitwise compare, but IEEE 802.11r has scrambled the order of elements so that a bitwise compare will not currently work. | This is a problem. | Change 8.5 to allow PMKID list to be different in EAPOL-Key frames 2/4 and 3/4 when using FT. This includes at least changing message descriptions in 8.5.2 and processing in 8.5.3.2 and 8.5.3.4. Ad-hoc topic?
10 | 727, 755, 903 | Delaying the GTK distribution and Timeout Interval IE until message 4 destroys the 4-Way Handshake property that the GTK is acknowledged. TGr should decide whether this matters. We could argue that the STA will resend the Reassociate Request if the Response is not received, but I do not think we understand whether this makes the protocol less reliable. | If security folks have proof that this is an issue, they need to bring it to the group's attention. | Does it matter? Is this a protocol design issue, or is it a just a security issue?
11 | N/A | Flaws in GTK encapsulation in the FTIE: No RSC, No IV for RC4 encapsulation | Needs to be solved | Jouni Malinen and Nancy Cam-Winget to work on solution 11-07-0180-01-000r-ft-gtk-encapsulation.doc
12 | N/A | TK being set before any MIC validation in FT. The key is configured before the MIC is validated | Implementation issue; incorrect implementation might create a small hole timewise, especially if implementations don't implement 802.1X port. Roam to self.
13 | N/A | Some references to "STA" in the draft should be qualified to "Non-AP STA". |  | Resume discussion at ad-hoc; Jouni's new comments point out places in the draft that might need to be modified.
14 | N/A | Should the client side key hierarchy/state machines be rolled into a single entity? What should it be called? |  | Resume discussion at ad-hoc.
15 | LB87/2009 | Clause 11 includes description of MLME procedure used during authentication (11.3.1) and association (11.3.2). Since IEEE 802.11r is modifying the authentication process (e.g., reservation with authentication frames) and adding new MLME primitives, it would be nice to see these changes described here. Should also apply to 8A.4 and 8A.5 (and probably 8A.8 too). | Needs to be solved | Bill will propose text to be discussed at the ad-hoc.

## References
References: