## TGv Draft 0.10 Review Comments
ID | Reviewer Name | Page | Line | Clause | Type of Comment (CID implementation or technical change) | Related CID(s) | Comment | Proposed Solution (if necessary) | Edit Status | Edit Notes
13 | Bill Marshall | 5 | 13 | 7.2.3.1 | E |  | keep table title and table contents together on a single page | Appears to be resolved in FrameMaker version of amendment | D0.11
31 | Bill Marshall | 8 | 10 | 7.2.3.9 |  |  | keep table title and table contents together on a single page | Appears to be resolved in FrameMaker version of amendment | D0.11
73 | Bill Marshall | 25 | 8 | 7.3.2.49 | E |  | keep table title and table contents together on a single page | Appears to be resolved in FrameMaker version of amendment | D0.11
87 | Bill Marshall | 36 | 8 | 7.3.2.51.1 |  |  | remove underline of period | Appears to be resolved in FrameMaker version of amendment | D0.11
93 | Bill Marshall | 39 | 19 | 7.3.2.52.4 | E |  | keep table title and table contents together on a single page | Appears to be resolved in FrameMaker version of amendment | D0.11
105 | Bill Marshall | 48 | 16 | 7.3.2.52.4.21 | E |  | keep table title and table contents together on a single page | Appears to be resolved in FrameMaker version of amendment | D0.11
107 | Bill Marshall | 49 | 17 | 7.3.2.53 | E |  | keep table title and table contents together on a single page | Appears to be resolved in FrameMaker version of amendment | D0.11
111 | Bill Marshall | 53 | 7 | 7.3.2.54 | E |  | remove underlining in this figure | Appears to be resolved in FrameMaker version of amendment | D0.11
112 | Bill Marshall | 53 | 13 | 7.3.2.54 | E |  | keep table title and table contents together on a single page | Appears to be resolved in FrameMaker version of amendment | D0.11
119 | Bill Marshall | 57 | 3 | 7.3.2.54.4 | E |  | font is different |  | D0.11
122 | Bill Marshall | 58 | 25 | 7.3.2.54.7 | E |  | keep table title and table contents together on a single page | Appears to be resolved in FrameMaker version of amendment | D0.11
123 | Bill Marshall | 59 | 17 | 7.3.2.54.8 | E |  | keep table title and table contents together on a single page | Appears to be resolved in FrameMaker version of amendment | D0.11
124 | Bill Marshall | 60 | 21 | 7.3.2.54.9 | E |  | keep table title and table contents together on a single page | Appears to be resolved in FrameMaker version of amendment | D0.11
125 | Bill Marshall | 62 | 4 | 7.3.2.54.9 | E |  | remove the "5" in the upper right corner of the box containing "Description" | Appears to be resolved in FrameMaker version of amendment | D0.11
134 | Bill Marshall | 69 | 7 | 7.3.2.60 | E |  | Accept probably shoud have the value 0 in this table |  | D0.11
136 | Bill Marshall | 71 | 16 | 7.3.2.63 | E |  | keep table title and table contents together on a single page | Appears to be resolved in FrameMaker version of amendment | D0.11
147 | Bill Marshall | 77 | 30 | 7.4.8.5 | E |  | keep table title and table contents together on a single page | Appears to be resolved in FrameMaker version of amendment | D0.11
150 | Bill Marshall | 78 | 21 | 7.4.8.6 | E |  | keep table title and table contents together on a single page | Appears to be resolved in FrameMaker version of amendment | D0.11
154 | Bill Marshall | 82 | 22 | 7.4.8.10 | E |  | keep figure and figure caption together on single page | Appears to be resolved in FrameMaker version of amendment | D0.11
155 | Bill Marshall | 84 | 16 | 7.4.8.12 | E |  | remove underline of space after the period | Appears to be resolved in FrameMaker version of amendment | D0.11
156 | Bill Marshall | 85 | 28 | 7.4.8.14 | E |  | keep figure and figure caption together on single page | Appears to be resolved in FrameMaker version of amendment | D0.11
157 | Bill Marshall | 86 | 26 | 7.4.8.15 | E |  | keep figure and figure caption together on single page | Appears to be resolved in FrameMaker version of amendment | D0.11
172 | Bill Marshall | 94 | 5 | 10.3.7.11 | E |  | numbering goof. Should be 10.3.7.1 |  | D0.11
180 | Bill Marshall | 99 | 4 | 10.3.36.11 | E |  | numbering botch. Should be 10.3.36.1. This occurs in every subclause up through 10.3.49 on page 135 |  | D0.11
211 | Bill Marshall | 167 | 2 | A.4.16 | E |  | Table lost its vertical separators | Appears to be resolved in FrameMaker version of amendment | D0.11
1 | Bill Marshall | i | 2 | Boilerplate | E |  | Title wrong for document Note the line breaks. Note the capitalization is different on the first line than on subsequent lines. Why do they do this to us? | Draft Standard for Information Technology - <linebreak> Telecommunications and information exchange between systems - <linebreak> Local and metropolitan area networks - <linebreak> Specific requirements <linebreak> Part 11: Wireless LAN Medium Access Control (MAC) and Physical Layer (PHY) specifications <linebreak> Amendment 9: Wireless Network Management | D0.12
3 | Bill Marshall | iv | 1 | Boilerplate | E |  | Document History should not appear in the "clean" version of the draft | Suggestion: Use FrameMaker's "Conditional Text". Define a conditional text tag (I use "EditorInfo") and make this table and the non-TBD-explanation Editorial Notes conditional. Have them appear in the redline version (nobody seems to care about such stuff in the redline version), but not appear in the clean version (where lots of people do care about this stuff appearing). This keeps the info in the same .fm file (and thus easy to search for dependencies on other drafts), but hidden from normal view. | D0.12
4 | Bill Marshall | 1 | 1 | Title | E |  | Title wrong for document Note the line breaks. Note the capitalization is different on the first line than on subsequent lines. Why do they do this to us? | Draft Standard for Information Technology - <linebreak> Telecommunications and information exchange between systems - <linebreak> Local and metropolitan area networks - <linebreak> Specific requirements <linebreak> Part 11: Wireless LAN Medium Access Control (MAC) and Physical Layer (PHY) specifications <linebreak> Amendment 9: Wireless Network Management | D0.12
5 | Bill Marshall | 2 | 1 | Title | E |  | In definition of base document, 802.11-2007, not 2006, 11r D5.0, 11w D2.0. Also need to include: 11y D2.0 (RevCom Mar08), 11n D2.0 (RevCom Sep08), 11u (RevCom Mar09), 11p D2.0 (RevCom Mar09), 11s D1.0 (RevCom Mar09). | Also need to monitor the Official Timeline for changes in the RevCom dates, and adjust the base document accordingly. This is a REAL PAIN. Easiest way I've found is to include copious Editorial Notes everywhere something is dependent on prior amendments (like for numbering, etc), with known strings "11k", "11r", "11n", etc. Make these Editorial Notes conditional text (see above comment, I use tag EditorInfo) so they don't appear in the clean version of the draft. | D0.12
6 | Bill Marshall | 3 | 3 | 2 | E |  | change editor's instructions to say "in alphabetical order" |  | D0.12
7 | Bill Marshall | 3 | 4 | 2 | E |  | alphabetize the new normative references |  | D0.12
8 | Bill Marshall | 3 | 11 | 3 | E |  | Need to assign numbers for the new definitions. Co-located interference should be 3.22a, Configuration profile should be 3.22b, Flexible Broadcase/Multicast Serivce should be 3.56a (or 3.54a, the rule for alphabetizing numbers isn't specified in the IEEE Style Guide), etc. |  | D0.12
9 | Bill Marshall | 3 | 11 | 3 | E |  | Need to word these as definitions. "Interference that is caused by another radio…" |  | D0.12
10 | Bill Marshall | 3 | 17 | 3 | E |  | "A service in which a non-AP STA…" |  | D0.12
14 | Bill Marshall | 6 | 1 | 7.2.3.1 | E |  | numbering | Change note below table to "last entry in 802.11-2007 has order 24. 11k adds 25-29. 11r adds 30. 11y adds 31-32. 11n adds 4 entries (33-36). 11s adds 26-35 (37-46)" I use the (xx-xx) to give the "corrected" values when the other amendments are not yet up to date. | D0.12 | should 47.
15 | Bill Marshall | 6 | 1 | 7.2.3.1 | E |  | numbering | change entries in table to 47-48-49-50-32 | D0.12 | change to 47-48-49-50-51 for now, and waiting for the group response for ECSA issues.
17 | Bill Marshall | 6 | 4 | 7.2.3.4 | E |  | numbering | Change note below table to "last entry in 802.11-2007 has order 9. 11k no changes. 11r adds 10. 11y adds 11. 11n adds 2 entries (12-13). 11s adds 11-16 (14-19)" | D0.12
18 | Bill Marshall | 6 | 4 | 7.2.3.4 | E |  | numbering | change entries in table to 20-21-22-23-11 | D0.12 | change to 20-21-22-23-24 for now, and wait for the group response for ECSA issues.
20 | Bill Marshall | 7 | 2 | 7.2.3.5 | E |  | numbering | Change note below table to "last entry in 802.11-2007 has order 6. 11k adds 7-8. 11r adds 9-10. 11y adds 12-13 (11-12). 11n adds 3 entries (13-15). 11s adds 8-14 (16-22). | D0.12
21 | Bill Marshall | 7 | 2 | 7.2.3.5 | E |  | numbering | change entries in table to 23-24-11 | D0.12 | change to 23-24-25, and wait for the group response for ECSA issues.
23 | Bill Marshall | 7 | 6 | 7.2.3.6 | E |  | numbering | Change note below table to "last entry in 802.11-2007 has order 10. 11k changes 7 but adds none. 11r adds 11-13. 11y adds 14. 11n adds 1 entry (15). 11s adds 12-14 (16-18)." | D0.12
24 | Bill Marshall | 7 | 6 | 7.2.3.6 | E |  | numbering | change entries in table to 19-20-21-22-14 | D0.12 | changed to 19-20-21-22-23, and wait for the group response for ECSA issues.
26 | Bill Marshall | 8 | 2 | 7.2.3.7 | E |  | numbering | Change note below table to "last entry in 802.11-2007 has order 6. 11k adds 7-8. 11r adds 9-12. 11y adds 13-14. 11n adds 2 entries (15-16). 11s adds 8-10 (17-19)." | D0.12
27 | Bill Marshall | 8 | 2 | 7.2.3.7 | E |  | numbering | change entries in table to 20-21-13 | D0.12 | change to 20-21-22 for now, and wait for the group response for ECSA issues.
29 | Bill Marshall | 8 | 6 | 7.2.3.8 | E |  | numbering | Change note below table to "last entry in 802.11-2007 has order 4. 11k adds 5. 11r adds none. 11y adds 6. 11n adds 1 entry (7). 11s adds 6-7 (8-9)." | D0.12
30 | Bill Marshall | 8 | 6 | 7.2.3.8 | E |  | numbering | change entries in table to 10 | D0.12
32 | Bill Marshall | 9 | 1 | 7.2.3.9 | E |  | numbering | Change note below table to "last entry in 802.11-2007 has order 22. 11k adds 23-28. 11r adds 29. 11y adds 30-32. 11n adds 3 entries (33-35). 11s adds 25-31 (36-42)." | D0.12
33 | Bill Marshall | 9 | 1 | 7.2.3.9 | E |  | numbering | change entries in table to 43-44-45-46-31 | D0.12 | change to 43-44-45-46-47 for now, and wait for the group response for ECSA issues.
38 | Bill Marshall | 11 | 12 | 7.3.2.6 | E |  | in the MSWord version, there are no "floor" symbols to be fixed. Probably should be some |  | D0.12 | Remove Editorial note
40 | Some of the changes in this table can't be shown with underlining and strikethrough. | 12 | 2 | 7.3.2.21 | E |  | Some of the changes in this table can't be shown with underlining and strikethrough. An Editorial Note should be added below the table pointing this out. |  | D0.12
41 | Bill Marshall | 13 | 10 | 7.3.2.21.8 | E |  | Figure numbering needs to follow the IEEE Style Guide | This goes beyond the Style Guide, but a reasonable extension would be to call this figure 79e1 (figures inserted between 79e and 79f would be 79e1, 79e2, 79e3, etc). Confirmation from IEEE Staff would be nice | D0.12
42 | Bill Marshall | 13 | 11 | 7.3.2.21.8 | E |  | Capitalization of figure caption | only first word, and proper nouns, should be capitalized. Here I think it should be "Triggered Reporting field for STA counters" | D0.12
43 | Bill Marshall | 13 | 16 | 7.3.2.21.8 | E |  | Figure numbering | Figure 79e2 | D0.12
44 | Bill Marshall | 14 | 1 | 7.3.2.21.8 | E |  | Dash list would normally be introduced by some text, and have multiple dash list items. This looks like a normal paragraph that shouldn't be a dash list item |  | D0.12
45 | Bill Marshall | 15 | 1 | 7.3.2.21.8 | E |  | Figure numbering | Figure 79e3 | D0.12
46 | Bill Marshall | 15 | 1 | 7.3.2.21.8 | E |  | Capitalization of figure caption | Triggered Reporting field for RSNA counters | D0.12
47 | Bill Marshall | 15 | 5 | 7.3.2.21.8 | E |  | Figure numbering | Figure 79e4 | D0.12
48 | Bill Marshall | 15 | 6 | 7.3.2.21.8 | E |  | Dash list item looks like a normal paragraph |  | D0.12
49 | Bill Marshall | 16 | 5 | 7.3.2.21.10 | E |  | "renumbering subsequent clauses" isn't done any more. That's the whole reason for the number/letter scheme for clause/figure/table numbering | delete "renumbering subsequent clauses" | D0.12
50 | Bill Marshall | 16 | 6 | 7.3.2.21.11 | E |  | subclause number should be 7.3.2.21.10a |  | D0.12
51 | Bill Marshall | 16 | 10 | 7.3.2.21.11 | E |  | Figure numbering | Figure 79l1 at line 10, 79l2 at 25, and 79l3 at line 1 of page 17 | D0.12
52 | Bill Marshall | 17 | 2 | 7.3.2.21.11 | E |  | Dash list item looks like a normal paragraph |  | D0.12
53 | Bill Marshall | 18 | 2 | 7.3.2.22 | E |  | Some of the changes in this table can't be shown with underlining and strikethrough. An Editorial Note should be added below the table pointing this out. |  | D0.12
54 | Bill Marshall | 19 | 6 | 7.3.2.22.8 | E |  | figure numbering | Figure 85k1 at line 6, 85k2 at line 12 | D0.12
55 | Bill Marshall | 20 | 1 | 7.3.2.22.8 | E |  | table/figure numbering | Figure 85k3 at line 1, 85o1 at line 7, table 31c1 at line 18 | D0.12
56 | Bill Marshall | 21 | 2 | 7.3.2.22.11 | E |  | figure numbering | Figure 85o2 | D0.12
57 | Bill Marshall | 22 | 5 | 7.3.2.27 | E |  | new text should be underlined | Underline "The Capabilities field is shown in Table xxx." | D0.12
58 | Bill Marshall | 22 | 6 | 7.3.2.27 | E |  | table numbering | Table 35a | D0.12
59 | Bill Marshall | 22 | 6 | 7.3.2.27 | E |  | table title | drop "The" | D0.12
60 | Bill Marshall | 22 | 16 | 7.3.2.37 | E |  | table numbering | Table 43b (lower case "b") | D0.12
62 | Bill Marshall | 23 | 16 | 7.3.2.37.3 | E |  | figure should show the sub-element ID and length |  | D0.12
63 | Bill Marshall | 23 | 17 | 7.3.2.37.3 | E |  | figure numbering | Figure 112g1 | D0.12
64 | Bill Marshall | 23 | 19 | 7.3.2.37.3 | E |  | What is "BSS Transition Candidate List Entries" | I think it should be "Neighbor report element" | D0.12 | it should be BSS Transition Candidate List Entries. TO be clear, change to "BSS Transition Candidate List Entries field in the BSS Transition Management Request frame."
65 | Bill Marshall | 23 | 24 | 7.3.2.37.3 | E |  | table numbering | Table 43b1 | D0.12
66 | Bill Marshall | 24 | 5 | 7.3.2.37.4 | E |  | figure numbering | Figure 112g2 at line 5, Figure 112g3 at line 12, Figure 112g4 at line 19 | D0.12
70 | Bill Marshall | 24 | 22 | 7.3.2.49 | E |  | numbering | Change Note to "802.11-2007 ends with 7.3.2.35. 11k adds 36-44. 11r adds 45-48. 11y adds 49-51. 11n adds 49-52 (52-55). 11w adds 55 (56). 11s adds 64-68 (57-61). | D0.12
71 | Bill Marshall | 24 | 24 | 7.3.2.49 | E |  | Should be 7.3.2.62 |  | D0.12
77 | Bill Marshall | 28 | 20 | 7.3.2.50.1.2 | E |  | figure title should match the entry in table v6, "Source BSSID Transition sub-element format" |  | D0.12
79 | Bill Marshall | 29 | 23 | 7.3.2.50.1.4 | E |  | figure title should only have the first word and proper nouns capitalized, "MatchValue field definitions" |  | D0.12
86 | Bill Marshall | 35 | 14 | 7.3.2.51.1 | E |  | cross ref to Table 23 should be "Table 23 in 7.3.1.9" |  | D0.12
90 | Bill Marshall | 36 | 26 | 7.3.2.51.2 | E |  | cross ref to Table 23 should be "Table 23 in 7.3.1.9" |  | D0.12
91 | Bill Marshall | 36 | 27 | 7.3.2.51.2 | E |  | "RSN Element" should be "RSN information element" |  | D0.12
92 | Bill Marshall | 38 | 17 | 7.3.2.52.1 | E |  | Use of 802.11 and 802.1X should be preceeded with IEEE, as in "IEEE 802.11" and "IEEE 802.1X" | Make this change globally. Many many places needed. | D0.12
97 | Bill Marshall | 41 | 1 | 7.3.2.52.4.1 | E |  | Figure title should be "IEEE 802.1X credentials format" (i.e., not 802.11) |  | D0.12
98 | Bill Marshall | 41 | 9 | 7.3.2.52.4.2 | E |  | cross ref to Table 34 should be "Table 34 in 7.3.2.25.2" |  | D0.12
102 | Bill Marshall | 48 | 6 | 7.3.2.52.4.20 | E |  | Status code is 2 octets |  | D0.12
103 | Bill Marshall | 48 | 8 | 7.3.2.52.4.20 | E |  | cross ref to Table 23 should be "Table 23 in 7.3.1.9" |  | D0.12
114 | Bill Marshall | 54 | 2 | 7.3.2.54 | E |  | awkward wording. Change to "Of the Presence sub-elements listed in Table v30, Table v31 lists the sub-elements that are excluded in the Presence Parameters information element…." |  | D0.12
115 | Bill Marshall | 54 | 6 | 7.3.2.54 | E |  | In table title, change "Exclusion" to "excluded", and change "Frames" to "frames" |  | D0.12
116 | Bill Marshall | 55 | 1 | 7.3.2.54.1 | E |  | Element ID(1), Length(8) -- should instead follow the style used throughout 802.11 standard. Element-ID, Length, and a sentence below the figure stating that the Element ID contains the value 1, and the length contains the value 8. | This change should be made to all of 7.3.2.54 sub-clauses | D0.12
117 | Bill Marshall | 55 | 1 | 7.3.2.54.1 | E |  | Figure title should be "Presence Indication Parameters sub-element" |  | D0.12
126 | Bill Marshall | 63 | 10 | 7.3.2.54.11 | E |  | instead of "should set", say that it "sets". Keep normative language out of clause 7 |  | D0.12
128 | Bill Marshall | 64 | 28 | 7.3.2.55 | E |  | keep table title and table contents together on a single page | Appears to be resolved in FrameMaker version of amendment | D0.12
130 | Bill Marshall | 65 | 0 | 7.3.2.55 | E |  | "QBSS Load" was changed in 11ma to "BSS Load" |  | D0.12
133 | Bill Marshall | 67 | 17 | 7.3.2.58 | E |  | don't need a cross reference to the definition. Delete "as defined in 3.v.2" |  | D0.12
138 | Bill Marshall | 74 | 10 | 7.4.8 | E |  | numbering | Change note to "802.11-2007 ends with 7.4.5. 11k adds 6. 11r adds 7. 11y adds none 11n adds 9 (8). 11w adds none. 11p adds 8 (9). 11s adds 6 (10). | D0.12
139 | Bill Marshall | 74 | 11 | 7.4.8 | E |  | change to "7.4.11" |  | D0.12
149 | Bill Marshall | 78 | 16 | 7.4.8.6 | E |  | grammar, "indicates that the STA stop sending presence request frames." ??? |  | D0.12
158 | Bill Marshall | 88 | 4 | 9.2.7 | E |  | bad style of cross reference. Delete "section" |  | D0.12
161 | Bill Marshall | 88 | 18 | 9.2.7.1.1 | E |  | IEEE uses "shall" instead of "must" |  | D0.12
162 | Bill Marshall | 88 | 19 | 9.2.7.1.1 | E |  | IEEE uses "shall" instead of "must" |  | D0.12
169 | Bill Marshall | 91 | 16 | 10.3.6.2.2 | E |  | 11r changes missing; Vendor Specific missing; 11y added SupportedRegulatoryClasses, so drop underlining |  | D0.12
170 | Bill Marshall | 92 | 18 | 10.3.6.3.2 | E |  | 11r changes missing. VendorSpecific missing. Presence Parameters should be underlined. SupportedRegulatoryClasses added by 11y and should not be underlined |  | D0.12
171 | Bill Marshall | 93 | 16 | 10.3.6.4.2 | E |  | 11r changes missing. Vendor Specific missing. SupportedRegulatoryClasses added by 11y and should not be underlined |  | D0.12
173 | Bill Marshall | 94 | 22 | 10.3.7.11.2 | E |  | VendorSpecific missing. PresenceParameters should be underlined. SupportedRegulatoryClasses already added by 11y and should not be underlined |  | D0.12
174 | Bill Marshall | 95 | 15 | 10.3.7.12.2 | E |  | VendorSpecific missing. SupportedRegulatoryClasses already added by 11y and should not be underlined |  | D0.12
175 | Bill Marshall | 96 | 19 | 10.3.7.13.2 | E |  | VendorSpecific missing. PresenceParameters should be underlined. SupportedRegulatoryClasses already added by 11y and should not be underlined |  | D0.12
176 | Bill Marshall | 97 | 15 | 10.3.7.14.2 | E |  | VendorSpecific missing. SupportedRegulatoryClasses already added by 11y and should not be underlined |  | D0.12
177 | Bill Marshall | 98 | 3 | 10.3.36 | E |  | "Add" is not a valid editor instruction. Change to "Insert" |  | D0.12
178 | Bill Marshall | 98 | 4 | 10.3.36 | E |  | numbering | Change note to "802.11-2007 ends with 10.3.29. 11k adds 30-33. 11r adds 34-35. 11y adds 36 11n adds 38 (dup of 11y). 11w adds none. 11p adds 36-37 (37-38). 11s adds 30-34 (39-43). | D0.12
179 | Bill Marshall | 98 | 6 | 10.3.36 | E |  | clause should be 10.3.44 |  | D0.12
182 | Bill Marshall | 148 | 1 | 11 | E |  | title wrong. Should be "11. MLME" |  | D0.12
184 | Bill Marshall | 148 | 5 | 11.2.1.5 | E |  | should be 11.2.1.4a |  | D0.12
185 | Bill Marshall | 148 | 15 | 11.2.1.6 | E |  | should be 11.2.1.4b |  | D0.12
186 | Bill Marshall | 148 | 24 | 11.2.1.7 | E |  | should be 11.2.1.5 (unchanged) |  | D0.12
187 | Bill Marshall | 148 | 25 | 11.2.1.7 | E |  | subclause should still be 11.2.1.5. Change 11.2.1.6 in the instructions to 11.2.1.5. Delete "(11.2.1.5 before the renumbering)" |  | D0.12
188 | Bill Marshall | 148 | 31 | 11.2.1.7 | E |  | subclause should still be 11.2.1.5. Change 11.2.1.6 in the instructions to 11.2.1.5. Delete "(11.2.1.5 before the renumbering)" |  | D0.12
189 | Bill Marshall | 149 | 13 | 11.2.1.8 | E |  | should be 11.2.1.6 (unchanged) |  | D0.12
190 | Bill Marshall | 149 | 13 | 11.2.1.8 | E |  | title should be "AP operation during the CFP" |  | D0.12
191 | Bill Marshall | 149 | 14 | 11.2.1.8 | E |  | subclause should still be 11.2.1.6. Change 11.2.1.7 in the instructions to 11.2.1.6. Delete "(11.2.1.6 before the renumbering)" |  | D0.12
192 | Bill Marshall | 149 | 29 | 11.2.1.9 | E |  | should be 11.2.1.7 (unchanged) |  | D0.12
193 | Bill Marshall | 149 | 30 | 11.2.1.9 | E |  | subclause should still be 11.2.1.7. Change 11.2.1.8 in the instructions to 11.2.1.7. Delete "(11.2.1.7 before the renumbering)" |  | D0.12
194 | Bill Marshall | 149 | 39 | 11.3 | E |  | This doesn't match 11ma D9.0 at all. Title should be "STA Authentication and Association" |  | D0.12
197 | Bill Marshall | 152 | 10 | 11.15 | E |  | numbering | Add an Editorial Note here. 802.11-2007 ends with 11.9. 11k adds 11.10-13. 11r adds none. 11y adds 14. 11n adds 15-17. 11w adds 18. 11p adds 14 (19). 11s adds none. | D0.12
198 | Bill Marshall | 152 | 10 | 11.15 | E |  | change editor's instructions to say "Insert the following after 11.19" |  | D0.12
199 | Bill Marshall | 152 | 11 | 11.15 | E |  | should be 11.20 |  | D0.12
202 | Bill Marshall | 154 | 11 | 11.15.2 | E |  | numbering | Add an Editorial Note here. 802.11-2007 ends with Table 79. 11k adds a. 11r adds none. 11y adds none. 11n adds n53 (b). 11w adds none. 11p adds none. 11s adds none. | D0.12
203 | Bill Marshall | 154 | 11 | 11.15.2 | E |  | Table 79c |  | D0.12
205 | Bill Marshall | 156 | 21 | 11.15.3 | E |  | Table 79d |  | D0.12
207 | Bill Marshall | 157 | 15 | 11.15.3.5 | E |  | 802.11 should be IEEE 802.11. both in title of subclause, and twice in first two lines of text |  | D0.12
209 | Bill Marshall | 157 | 39 | 11.15.3.7 | E |  | 802.1X should be IEEE 802.1X |  | D0.12
210 | Bill Marshall | 158 | 20 | 11.15.4.1 | E |  | information element should be lower case |  | D0.12
231 | Yongho Seok | 10 | 2 | 7.3.2 | E |  | In Table 26, Event Log Request and Event Log Report shall be changed to Event Request and Event Report, respectively. |  | D0.12
235 | Yongho Seok | 85 | 24 | 7.4.8.14 | E |  | Change the index from 7.4.6 to 7.4.8. |  | D0.12 | changed to 7.4.11
238 | Yongho Seok | 164 | 14 | 11.15.9 | E |  | Change "Automatic Response bit" to "Automatic Response Enabled bit". |  | D0.12
239 | Yongho Seok | 87 | 3 | 7.4.8.15 | E |  | Change the index from 11.15.8 to 11.15.9. |  | D0.12
240 | Yongho Seok | 87 | 11 | 7.4.8.15 | E |  | Change the index from 11.15.8 to 11.15.9. |  | D0.12
242 | Yongho Seok | 145 | 5 | 10.3.51.3.4 | E |  | Change the index from 11.15.8 to 11.15.9. |  | D0.12
250 | Yongho Seok | 31 | 13 | 7.3.2.50.2.2 | E |  | It seems that the value of the Leghth field is 4. |  | D0.12
251 | Yongho Seok | 68 | 1 | 7.3.2.59 | E |  | It seems that the value of the Leghth field is 2+n instead of 1+n. |  | D0.12
252 | Yongho Seok | 68 | 25 | 7.3.2.60 | E |  | It seems that the value of the Leghth field is 1+n instead of n, where n is the total length of all FBMS Status Sub-elements. |  | D0.12
254 | Yongho Seok | 39 | 1 | 7.3.2.52.4 | E |  | In Table v16, the range of the identifier shall be from 0 to 255 because the size of Diagnositic Information Sub-element ID is 1 byte. |  | D0.12
269 | Yongho Seok | 24 | 19 | 7.3.2.37.6 | E |  | The size of AC Station Count Element is from 3 byte to 11 byte. Please check Figure v86. |  | D0.12
271 | Yongho Seok | 163 | 2 | 11.15.7.2 | E |  | The following sentence has incorrect. "The preference value is only before Validity Interval is expired." |  | D0.12 | Changed to "The preference value is only valid before Validity Interval is expired".
275 | Yongho Seok | 37 | 7 | 7.3.2.51.3 | E |  | Please correct "averange transmit power" and explicitly specify the notation of the transmit power like Figure v67. |  | D0.12
276 | Yongho Seok | 115,118, 121, 123, 144, 146 |  |  | E |  | SCCESS of Result code should be corrected. |  | D0.12
165 | Bill Marshall | 90 | 22 | 10.3.6.1.2 | E |  | 11r changes to this MLME primitive missing |  | D0.12
167 | Bill Marshall | 91 | 2 | 10.3.6.1.2 | E |  | Vendor Specific is missing fro the parameter list |  | D0.12
200 | Bill Marshall | 152 | 12 | 11.15 | E |  | This line/paragraph is a hanging paragraph. See Style Guide 11.1. |  | D0.12 | Removed the sentence.
236 | Yongho Seok | 86 | 21 | 7.4.8.15 | E |  | Change the index from 7.4.6 to 7.4.8. |  | D0.12 | changed to 7.4.11
108 | Bill Marshall | 50 | 2 | 7.3.2.53 | E |  | cross ref for Status Code should be to Table 23 of 7.3.1.9. |  | reject, | Deferred to the group.EN: this status is not status code defined in Table 23. Perhaps it should be rename to something else.
106 | Bill Marshall | 49 | 9 | 7.3.2.53 | E |  | Status code is 2 octets |  | reject. | Deferred to the group.EN: this status is not status code defined in Table 23. Perhaps it should be rename to something else.
2 | Bill Marshall | ii | 8 | Intro | E |  | probably need some kind of introduction |  |  | General. Dorothy will draft text for this.
11 | Bill Marshall | 4 | 3 | 5.4.3.7 | T |  | Proper editing instruction here is "Change", for a paragraph that already exists in the base standard that you want to add something to. The change is properly shown with underlining (and strikethrough if something is to be deleted). | Remove 5.4.3.7. |  | General. Deferred to the Group:
12 | Bill Marshall | 4 | 3 | 5.4.3.7 | T |  | This text doesn't appear in 11w D2.0 | Remove 5.4.3.7. |  | General.. Deferred to the Group:
16 | Bill Marshall | 6 | 1 | 7.2.3.1 | T |  | Extended Channel Switch Announcement is already in the table from 11y. Order number is 32 (according to Note below table); the "Notes" column needs to be "Changed" for this one. | Change the editing instructions above table to "Change order 32 entry as follows, and insert order 47-50 entries in Table 8". Show the "Notes" column for Extended Channel Switch Announcement as "The Extended Channel Switch Announcement element may be present only if dot11Extended ChannelSwitchImplemented is true <underline>or if dot11WirelessmanagementImplemented is true<end-underline>." |  | ECSA issue: Deferred to the Group:
19 | Bill Marshall | 6 | 4 | 7.2.3.4 | T |  | Extended Channel Switch Announcement is already in the table from 11y. Order number is 11 (according to Note below table); the "Notes" column needs to be "Changed" for this one. | Similar change as for Table 8 above |  | ECSA issue: Deferred to the Group:
22 | Bill Marshall | 7 | 2 | 7.2.3.5 | T |  | Supported Regulatory Classes is already in table from 11y. Order number is 11; the "Notes" column needs to be "Changed" for this one | Similar change as for Table 8 above |  | ECSA issue: Deferred to the Group:
25 | Bill Marshall | 7 | 6 | 7.2.3.6 | E |  | Supported Regulatory Classes is already in table from 11y. Order number is 14; the "Notes" column needs to be "Changed" for this one | Similar change as for Table 8 above |  | ECSA issue: Deferred to the Group:
28 | Bill Marshall | 8 | 2 | 7.2.3.7 | E |  | Supported Regulatory Classes is already in table from 11y. Order number is 13; the "Notes" column needs to be "Changed" for this one | Similar change as for Table 8 above |  | ECSA issue: Deferred to the Group:
34 | Bill Marshall | 9 | 1 | 7.2.3.9 | T |  | Extended Channel Switch Announcement is already in table from 11y. Order number is 31 | Similar change as for Table 8 above |  | ECSA issue: Deferred to the Group:
35 | Bill Marshall | 10 | 2 | 7.3.2 | E |  | This a lot of new information elements, and a small space from which to allocate them. Consider various ways to reduce the number | Event Log Request, Event Log Report, Diagnostic Request, and Diagnostic Report only appear in Action frames, and can be defined with the corresponding Action frame. FMS Request and Response can probably be combined into a single IE. Similarly Multiple BSSID and Multiple BSSID-Index. Others? |  | IE issues: Deferred to the Group.
36 | Bill Marshall | 10 | 2 | 7.3.2 | T |  | Extended Channel Switch Announcement and Supported Regulatory Classes are both defined in 11y, and should not be in this table |  |  | ECSA issue: Deferred to the Group:
37 | Bill Marshall | 11 | 1 | 7.3.2.6 and 7.3.1.8 | T |  | I think 7.3.1.8 and 7.3.2.6 are confused about 2**n and n. Its clear that you want to reserve n bits in the virtual bitmap if you have n BSSIDs. You don't want to reserve 2**n bits. | The virtual bitmap is only ~2000 bits in length. If an AP supports 12 BSSIDs, did that just destroy its ability to allocate AIDs? Hope not, since AID values 13-2000 would still be OK. |  | Virtual AP.
39 | Bill Marshall | 11 | 12 | 7.2.3.6 | T |  | Need some text that qualifies the existing paragraph in 7.3.2.6 that starts "The partial virtual bitmap field…" so that text covers the legacy STAs |  |  | Virtual AP
61 | Bill Marshall | 22 | 18 | 7.3.2.37 | E |  | Insertion of 7.3.2.37.1 here generates a "hanging paragraph", which are not allowed by the IEEE Style Guide 11.1. | Insert a new heading "7.3.2.37.1 General" (or some such intro title) immediately after the 7.3.2.37 heading, and make this 7.3.2.37.2 |  | BSS Transition Managemnet. Not clear how to do it, TGv editor will consult the commenter.
67 | Bill Marshall | 24 | 7 | 7.3.2.37.4 | E |  | this text doesn't specify whether the element ID and length are included in the 6-30 octets of data in this sub-element. | There is no need for element ID and length being specified twice. But mainly, be consistent. |  | BSS Transition Managemnet
68 | Bill Marshall | 24 | 13 | 7.3.2.37.5 | E |  | BSS Load Element seems to contain the element ID and length in the sub-element | Be consistent on this |  | BSS Transition Managemnet
69 | Bill Marshall | 24 | 20 | 7.3.2.37.6 | E |  | AC Station Count Element seems to not contain the element ID and length in the sub-element | Be consistent on this |  | BSS Transition Managemnet
72 | Bill Marshall | 25 | 1 | 7.3.2.49 | E |  | table/figure numbering | Figures: 802.11-2007 ends with 112. 11k adds a-o. 11r adds p-x. 11y adds y-ab. 11n adds n29-n40 (ac-an). 11w adds 1 figure (ao). 11s adds s12-s67 (ap-cs). Figure 112ct on line 1. Tables: 802.11-2007 ends with 43. 11k adds a-c. 11r adds d-e. 11y adds none. 11n adds n24-n30 (f-k). 11w adds none. 11s adds s2-s24 (l-x). Table 43y on line 8. |  | General. Deferred to the editor meeting
74 | Bill Marshall | 27 | 7 | 7.3.2.50 | T |  | Table title should be "Event Type definition" |  |  | Event
75 | Bill Marshall | 27 | 7 | 7.3.2.50 | T |  | I would say that the proper nouns in Table v5 are "Transition", "RSNA", "Peer-to-Peer", and "System Log". I'd drop "Event Request" or "Request" from the entries. The sub-clause titles that follow would then be "Transition event request" (note the lower case "e" and "r", since those words aren't proper nouns), "RSNA event request", etc. |  |  | Event
76 | Bill Marshall | 28 | 6 | 7.3.2.50.1.1 | E |  | IEEE Style Guide says 5-level headings are as deep as we can go. See 11.1. Need to re-structure the document to avoid 6-level headings. | I suggest this IE be defined in 7.4.8.1, not as an IE, but as an element in the Action frame. It solves the 6-level heading problem, and reduces the number of IEs needed for ANA. |  | General. Too manany IEs: Deferred to the Group.
78 | Bill Marshall | 29 | 11 | 7.3.2.50.1.3 | T |  | Somewhere needs to specify how the transition time is calculated. 11.15.2.1 would be the right place for normative statements; some declarative statements here would be helpful |  |  | Event
80 | Bill Marshall | 30 | 12 | 7.3.2.50.1.5 | T |  | Units need to be specified for this time interval. The normative procedures can call it just a "time interval", but clause 7 needs to state how it is stored, and that requires units to be specified. |  |  | Event
81 | Bill Marshall | 31 | 14 | 7.3.2.50.2.2 | T |  | bad xref. Authentication Types are described in Table 34 of 7.3.2.25.2 |  |  | Event. Suggest changing to "The Authentication Type field contains one of the AKM suite selectors defined in Table 34"
82 | Bill Marshall | 34 | 7 | 7.3.2.51 | T |  | table title should have only first word and proper nouns capitalized, "Event Type definitions for event report". See comment on 7.3.2.50 about what the proper nouns are in the table entries |  |  | Event. this table should be removed and use table v5 (Event Type definition).
83 | Bill Marshall | 34 | 8 | 7.3.2.51 | T |  | The terms "Status" and "Status Code" are used throughout 802.11 and always refer to Table 23 in 7.3.1.9. If you want to call this a Status value, then refer to that table for the values, otherwise call it something other than "Status" (e.g., "Result Code", which is used throughout clause 10 for a similar enumerated list of possibilities) |  |  | Event
84 | Bill Marshall | 35 | 1 | 7.3.2.51.1 | T |  | If the entry in Table v9 is "Transition", then this figure should be titled "Event Report format for Transition event". But if the entry in Table v9 is "Transition Event Report", then the figure title should be "Event Report format for Transition Event Report". My preference is the former. |  |  | Event
85 | Bill Marshall | 35 | 8 | 7.3.2.51.1 | T |  | How is the transition time calculated when the BlockAck policy is set to "no ack"? |  |  | Event
88 | Bill Marshall | 36 | 22 | 7.3.2.51.2 | T |  | If the EAP Method field is only present with certain Authentication Type values, then it should be shown as "(optional)" in Figure v34. Much easier if the octet was always present, and only "valid" when the Authentication Type of 00-0F-AC:1 | Change "present" to "valid" |  | Event
89 | Bill Marshall | 36 | 22 | 7.3.2.51.2 | T |  | EAP Method field would also be valid if the Authentication Type os 00-0F-AC:3 (11r's AKM) |  |  | Event
94 | Bill Marshall | 40 | 0 | 7.3.2.52.4 | T |  | There is no sub-clause with a definition of STA Rport Group Type, nor with a definition of SSID. |  |  | Diagnostics. Deferred to the group. EN: STA Rport Group Type should be removed since the subclause was removed by one of interval review comment solution. SSID need to be defined.
95 | Bill Marshall | 40 | 1 | 7.3.2.52.4.1 | T |  | 6-level heading, need to reorganize this part to keep within 5 levels |  |  | Diagnostics. Or General
96 | Bill Marshall | 41 | 1 | 7.3.2.52.4.1 | T or E |  | Figures in all of these subclauses 7.3.2.52.4.1 through 7.3.2.52.4.21 should all show the Sub-element ID and length, in addition to the data contents |  |  | Diagnostics. Deferred to the group.
99 | Bill Marshall | 46 | 9 | 7.3.2.52.4.15 | T |  | TGn has defined another Power Save mode, PSMP. It needs a value in this table |  |  | Diagnostics.
100 | Bill Marshall | 47 | 13 | 7.3.2.52.4.18 | T |  | Reason codes are defined in Table 22 in 7.3.1.7. Either refer to that table here, or call this value something else (like "Result Code") |  |  | Diagnostics.
101 | Bill Marshall | 48 | 3.5 | 7.3.2.52.4.19a | T |  | STA Report Group Type sub-element |  |  | Diagnostics.
104 | Bill Marshall | 48 | 9.5 | 7.3.2.52.4.20a | T |  | SSID sub-element |  |  | Diagnostics.
109 | Bill Marshall | 50 | 11 | 7.3.2.53.1 | E |  | include a cross reference to the definition of these sub-elements, 7.3.2.52.4 |  |  | Diagnostics.Deferred to the group.EN: I am not sure we should add. There is no reference in Table 8, 9, 10, …
110 | Bill Marshall | 51 | 4 | 7.3.2.53.2 | E |  | include a cross reference to the definition of these sub-elements, 7.3.2.52.4. Also in all of the follow sub-clauses of 7.3.2.53 |  |  | Diagnostics.Deferred to the group.EN: I am not sure we should add. There is no reference in Table 8, 9, 10, …
113 | Bill Marshall | 54 | 0 | 7.3.2.54 | T |  | Vendor Specific uses the value 221 consistently throughout 802.11 | 12-220: reserved; 221 Vendor Specific; 222-255: reserved |  | Presence
118 | Bill Marshall | 55 | 5 | 7.3.2.54.1 | T |  | put the report interval units in order, from smallest to largest. You might consider "seconds" in the middle of the range, with reserved values on both ends. |  |  | Presence
120 | Bill Marshall | 58 | 6 | 7.3.2.54.6 | E |  | bad cross ref (EDCA Parameter Set???). Not sure what it should be |  |  | Presence. comment is not clear to me.
121 | Bill Marshall | 58 | 23 | 7.3.2.54.7 | T |  | This seems an overly complex way to specify a floating point number. Why not just call it a 32-bit floating point number? |  |  | Presence
127 | Bill Marshall | 63 | 21 | 7.3.2.54.12 | T |  | Vendor Specific uses the value 221 consistently throughout 802.11 |  |  | Presence
129 | Bill Marshall | 65 | 0 | 7.3.2.55 | T |  | "Capability" is marked as optional. Since this is a fixed size field, and not an information element, how is it optionally present? This should just say "Included" |  |  | Virtual AP
131 | Bill Marshall | 65 | 0 | 7.3.2.55 | T |  | Other IEs have been added by other amendments, TGk, TGr, Tgy, TGn, TGs… Those IEs should be listed in this table too |  |  | Virtual AP
132 | Bill Marshall | 66 | 3 | 7.3.2.56 | T |  | SSID is a variable length ascii string. How are multiple strings combined into this one IE? Multiple {length, SSID} pairs? Why not just include multiple (single)SSID IEs? |  |  | Virtual AP
135 | Bill Marshall | 70 | 7 | 7.3.2.61 | T |  | Believe the Official Timeline. Tgy is ahead of TGv. If that changes in the Official Timeline, then this text could be restored. In the meantime, it is going through ballots with Tgy and being updated by Tgy. For TGv, delete all of 7.3.2.61 and 7.3.2.62. |  |  | ECSA issue: Deferred to the Group:
137 | Bill Marshall | 73 | 19 | 7.4.1 | T |  | This text apepars in 11y, and should not be repeated here |  |  | ECSA issue: Deferred to the Group:
140 | Bill Marshall | 74 | 15 | 7.4.8 | E |  | table/figure numbering | Table: 802.11-2007 ends with 57. 11k adds a. 11r adds b-f. 11y adds none. 11n adds n31-n40 (g-p). 11w adds none. 11p adds p3 (q). 11s adds s25-s26 (r-s). Next is 57t. Figures: 802.11-2007 ends with 118. 11k adds a-f. 11r adds g-j. 11y adds none. 11n adds n40 (k). 11w adds none. 11p adds p2 (l). 11s ads s68-s82 (m-aa). Next is 118ab. |  | General. Deferred to the Recir LB or before go to the SB.
141 | Bill Marshall | 74 | 15 | 7.4.8 | E |  | table numbering | Table 57t |  | General. Deferred to the Recir LB or before go to the SB.
142 | Bill Marshall | 75 | 5 | 7.4.8.1 | E |  | figure numbering | Figure 118ab |  | General.Deferred to the Recir LB or before go to the SB.
143 | Bill Marshall | 76 | 3.5 | 7.4.8.1 | T |  | since this is the only use of the Event Request IE, move its definition here and remove the element ID. |  |  | General-IE issues: Deferred to the Group.
144 | Bill Marshall | 76 | 17.5 | 7.4.8.2 | T |  | since this is the only use of the Event Report IE, move its definition here and remove the element ID. |  |  | General-IE issues: Deferred to the Group.
145 | Bill Marshall | 76 | 31 | 7.4.8.3 | T |  | since this is the only use of the Diagnostic Request IE, move its definition here and remove the element ID. |  |  | General-IE issues: Deferred to the Group.
146 | Bill Marshall | 77 | 11.5 | 7.4.8.4 | T |  | since this is the only use of the Diagnostic Report IE, move its definition here and remove the element ID. |  |  | General-IE issues: Deferred to the Group.
148 | Bill Marshall | 78 | 0 | 7.4.8.5 | T |  | Vendor Specific uses the value 221 consistently throughout 802.11 |  |  | General-Vendor Specific
151 | Bill Marshall | 79 | 0 | 7.4.8.6 | T |  | Vendor Specific uses the value 221 consistently throughout 802.11 |  |  | General-Vendor Specific
152 | Bill Marshall | 80 | 5 | 7.4.8.7 | T |  | Vendor Specific uses the value 221 consistently throughout 802.11 |  |  | General-Vendor Specific
153 | Bill Marshall | 81 | 9 | 7.4.8.8 | T |  | Vendor Specific uses the value 221 consistently throughout 802.11 |  |  | General-Vendor Specific
159 | Bill Marshall | 88 | 5 | 9.2.7.1 | T |  | 9.2.7.1 creates a hanging paragraph. See IEEE Style Guide 11.1. Add Add "9.2.7.1 non-FBMS" (or similar title) at beginning of 9.2.7, and 9.2.7.2 here | Remove section headers 9.2.7.1 and 9.2.7.1.1 and insert remaining paragraphs into 9.2.7 after the last paragraph. |  | FBMS.
160 | Bill Marshall | 88 | 9 | 9.2.7.1.1 | T |  | this creates another hanging paragraph. Also, this is a .1 without a .2. Both are not allowed. See IEEE Style Guide 11.1. Drop this heading line | Duplicate resolution to CID 159 |  | FBMS.
163 | Bill Marshall | 88 | 29 | 9.2.7.1.1 | T |  | Normative statements are needed in this paragraph about the generation of the AID 0 Descriptor | REJECT, Reason: Paragraph starting on L29 describes this. |  | FBMS.
164 | Bill Marshall | 89 | 14 | 9.8.3 | T |  | this is already in 11y. Drop it |  |  | ECSA issue: Deferred to the Group:
166 | Bill Marshall | 91 | 1 | 10.3.6.1.2 | T |  | Supported Regulatory Classes is already added by TGy. Remove underlining |  |  | ECSA issue: Deferred to the Group:
168 | Bill Marshall | 91 | 3 | 10.3.6.1.2 | E |  | table entry for SupportedRegulatoryClasses should be "changed" not "inserted", based on the 11y text |  |  | ECSA issue: Deferred to the Group:
181 | Bill Marshall | 138 | 13 | 10.3.50 | E |  | this is already in 11y. Drop it |  |  | ECSA issue: Deferred to the Group:
183 | Bill Marshall | 148 | 4 | 11.2.1 | E |  | Renumbering isn't done any more. See Style Guide 21.2. A new subclause inserted after 11.2.1.4 should be numbered 11.2.1.4a. | Change the editing instruction to "Insert the following after 11.2.1.4" |  | General
195 | Bill Marshall | 150 | 3 | 11.3 | T |  | Rest of the Wireless Network Management Action frames need to be listed in c)2)i) |  |  | General
196 | Bill Marshall | 150 | 4 | 11.9 | E |  | this is already in 11y. Drop it |  |  | ECSA issue: Deferred to the Group:
201 | Bill Marshall | 152 | 23 | 11.15.1.1 | T |  | .1 here without a .2. See Style Guide 11.1. Delete this heading, or change it to 11.15.2. |  |  | General
204 | Bill Marshall | 154 | 13 | 11.15.2.1 | T |  | This creates a hanging paragraph. See Style Guide 11.1. |  |  | General
206 | Bill Marshall | 156 | 24 | 11.15.3.1 | T |  | This creates a hanging paragraph. See Style Guide 11.1. |  |  | General
208 | Bill Marshall | 157 | 25 | 11.15.3.5 | T |  | Performing this test shouldn't make the current association go away. It only goes away if the STA follows through with a Reassociation Request to the specified target AP, which it doesn't do. Change "go back to the requesting AP and 802.11 authenticate....so that it can respond" with "respond to the requesting AP" |  |  | Diagnostics
212 | Bill Marshall | 169 | 0 | A.4.16 | T |  | RME10, RME10.1, RME10.2, and RME10.3 are already in 11y. Drop them |  |  | ECSA issue: Deferred to the Group:
213 | Bill Marshall | 170 | 19 | D | T |  | Can't have a TBD in the MIB |  |  | Annex
214 | Bill Marshall | 170 | 24 | D | T |  | Can't have a TBD in the MIB |  |  | Annex
215 | Bill Marshall | 171 | 16 | D | T |  | Can't have a TBD in the MIB |  |  | Annex
216 | Bill Marshall | 172 | 55 | D | T |  | Missing from MIB: entries for Presence information: Location data and encoding information |  |  | Annex
217 | Bill Marshall | 172 | 55 | D | T |  | Missing from MIB: Compliance entries |  |  | Annex
218 | Bill Marshall | 172 | 55 | D | T |  | Missing from MIB: entries for the extensions to the Neighbors Report element |  |  | Annex
219 | Bill Marshall | 172 | 55 | D | T |  | Missing from MIB: Multiple BSSIDs require lots of additional entries for each of the possible BSSIDs. Not sure what the best way is to do that. |  |  | Annex
220 | Bill Marshall | 172 | 55 | D | T |  | Missing from MIB: Table for event entries |  |  | Annex
221 | Bill Marshall | 172 | 55 | D | T |  | Missing from MIB: Table for syslog entries |  |  | Annex
222 | Jiyoung Huh | 141 | 37 | 11.15.1.1 | T |  | "The Multicast MAC Address and trigger conditions for diagnostic reporting shall be specified in the request" - Multicast MAC Address shall be originally included in the request even though the request is not triggered multicast diagnositc and the trigger conditions shall be included only if the request is triggered multicast diagnostic |  |  | Diagnostics
223 | Jiyoung Huh | 29 | 19 | 7.3.2.50.2.1 | T |  | The function of Target BSS RSNA sub-element is equal to Target BSSID Transition sub-element's |  |  | Event
224 | Jiyoung Huh | 142 | 18 | 11.15.2 | T |  | "However, if STA moves to a different ESS, all outstanding Event Requests shall be cancelled" - Only a single Event Request frame shall be outstanding at a given STA, and upon a BSS transition within the same ESS, the outstanding Event Requests shall be cancelled at the STA. There is no differentiation between transition within the same ESS and transition within a different ESS |  |  | Event
225 | Jiyoung Huh | 142 | 21~27 | 11.15.2 | T |  | The status value "fail" is not described in this paragraph. And in the sentence"If the STA is unable to process the request at that time, a value of Refused shall be returned", Fail seems to be better than Refused. |  |  | Event
226 | Jiyoung Huh | 142 | 52~53 | 11.15.2 | T |  | "A STA sends an Event Request frame containing one or more Event Request elements including one or more sub-elements." - No sub-element may be included in the request. |  |  | Event
227 | Yongho Seok | 20 | 7 | 7.3.2.22.11 | T |  | The Measurement Start Time field in the multicast diagnostic report frame is set to the value of the STA TSF timer. So, this field should uses 8 bytes instead of 4 bytes. |  |  | Diagnostics
228 | Yongho Seok | 152 | 29,30 | 11.15.1.1 | T |  | When the number of received MSDUs is zero, it seems that the multicast diagnositc report for the performance measurement should not be issued. If the multicast diagnositc mechanism is used in the power saving mode, a number of useless multicast diagnostic reports can be transmitted during the AP does not transmit any multicast frame. |  |  | Multicast Diagnostics
229 | Yongho Seok | 89 | 8,9 | 9.2.7.1.1 | T |  | For the unsolicited FBMS response delivery, the AID 0 information element in DTIM beacon shall include the corresponding FBMSID to remain awake. If there is no buffered multicst frame for the corresponding FBMSID, the multicast receivers will go to sleep mode after receiving DTIM beacon. Consequently, the multicast receives can not receive the unsolicited FBMS response for updating the delivery interval. | Insert new paragraph add the end of 9.2.7.1.1 " The AP may send an unsolicited FBMS Response whenever it changes the delivery interval for a FBMSID. The FBMS Response will be transmitted as a unicast frame to all non-STAs that are subscribed to that FBMSID. For any non-AP STA that is asleep, normal power-save transmission rules will apply where the TIM bit will be set for each sleeping non-AP STA and the non-AP STA will retrieve the queued frames during the next PS-POLL exchange. |  | FBMS.
230 | Yongho Seok | 58 | 21,22 | 7.3.2.54.7 | T |  | To support the location service, the exact timing meausrement point is required. However, it is not explicitly specified whenever the PHY-TXSTART.confirm primitive is issued. Recommand to change the PHY-TXSTART.confirm to PHY-TXEND.confirm because PHY-TXEND.confirm is more explicitly specified in the PHY layer. |  |  | Presence
232 | Yongho Seok | 153 | 5 | 11.15.1.1 | T |  | It seems that "Multicast Diagnostic reporting" should be changed to "Triggered Multicast Diagnostic reporting". |  |  | Multicast Diagnostics
233 | Yongho Seok | 10 | 2 | 7.3.2 | T |  | The almost legnth values in Table 26 is not correct. |  |  | General
234 | Yongho Seok | 152 | 27 | 11.15.1.1 | T |  | "An AP may send a Multicast Diagnostic Request frame to a non-AP STA that has indicated support for the multicast diagnositic capability." It seems that the Multicast Diagnostic Request frame can not be transmitted to the multicast group address. Please change this sentence as the following: "An AP may send a Multicast Diagnostic Request frame to either a non-AP STAs or non-AP multicast receivers that have indicated support for the multicast diagnositic capability." |  |  | Multicast Diagnostics
237 | Yongho Seok | 86 | 25 | 7.4.8.15 | T |  | It seems that the Co-located Interference Response frame has 8 Response Info fields. |  |  | Interference
241 | Yongho Seok | 87 | 15,18 | 7.4.8.15 | T |  | What is the mening of "the interference is non-periodic"? When the interval between two successive periods of interference is variable, it seems that it also corresponds to a non-periodic case. |  |  | Interference
243 | Yongho Seok | 87 | 8, 13, 16, 19, 24, 27 | 7.4.8.15 | T |  | If no co-located interfernece is present, which values are set to Response Info filelds, e.g, interference interval, interference burst length, interference start time ? |  |  | Interference
244 | Yongho Seok | 87 | 2 | 7.4.8.15 | T |  | It seems that the Report Period should be determinded by the Co-located Interference Request frame. |  |  | Interference
245 | Yongho Seok | 87 | 22 | 7.4.8.15 | T |  | In the calculation of an average duty cycle, it is bettter to use the (65535-1) instead of using (232-1). Is there a special reason about using (232-1)? |  |  | Interference
246 | Yongho Seok | 21 | 20 | 7.3.2.22.11 | T |  | Is it possible to report the multicast rate that is not in the basic rate set? If it is possible, please mention that the MSB of the multicast rate field is set to 0. | Change to "The Multicast Rate field specifies the highest data rate at which the STA can reliably receive multicast frames. The Multicast Rate field is encoded with the MSB set to 1 to indicate that the data rate is in the basic rate set, and set to 0 to indicate that the data rate is not in the basic rate set. The remaining 15 bit value is multiplied by 0.5 Mbit/s to indicate the data rate. If no value is provided by the STA, the Multicast Rate field is set to 0" |  | FBMS.
247 | Yongho Seok | 68 | 18,19 | 7.3.2.59 | T |  | What is the unit of the multicast rate ? And, is there a constraint that the multicast rate shall be in the BSS Basic Rate set? Otherwise, it is necessary to change the Section 9.6, "All frames with multicast and broadcast in the Address 1 field that have a UP of zero shall be transmitted at one of the rates included in the BSSBasicRateSet parameter." | Change the sentence starting L18 from "The Multicast Rate field specifies the highest data rate at which..." to "The Multicast Rate field specifies the highest data rate, in 500 kb/s units, at which…" |  | FBMS.
248 | Yongho Seok | 70 | 1,2 | 7.3.2.60 | T |  | What is the unit of the multicast rate ? Why don't you reuse a multicast rate field of the multicast diagnositic report? | Change the sentence starting L1 from "The Multicast Rate field specifies the data rate to be used for the multicast service" to "The Multicast Rate field specifies the data rate in units of 500 kb/s to be used for the multicast service" |  | FBMS.
249 | Yongho Seok | 158 | 19, 20 | 11.15.4.1 | T |  | What does the following sentence mean? Is it typos? A STA in a BSS may send Presence Request frames as indicated in the Beacon or Probe Response frame Presence Parameters Information element. |  |  | Presence
253 | Yongho Seok | 30 | 11,12 | 7.3.2.50.1.5 | T |  | What is the unit of the Time Interval ? |  |  | Event
255 | Yongho Seok | 46 | 9 | 7.3.2.52.4.15 | T |  | In the Table v19, what is the difference between two Normal Power Save modes? |  |  | Diagnostics
256 | Yongho Seok | 58 | 6 | 7.3.2.54.6 | T |  | What is the Antenna ID? Do you mean the Antenna ID in the Antenna Information element (7.3.2.40 in TGK D7.0). |  |  | Presence
257 | Yongho Seok | 13 | 4,5,6 | 7.3.2.21.8 | T |  | Dot11RetryCount, dot11MultipleRetryCount, dot11FrameDuplicateCount, dot11RTSFailureCount and dot11ACKFailureCount correspond to the group identity of 1. But, dot11FailedCount and dot11FCSErrorCount correspond to the group indentity of 0. If Triggered Reporting has consist of dot11FailedCount Threshold and dot 11RetryCount Threshold, which value is set to the group identity? It seems that STA Counters Trigger in Figure v1 should be divided into two categories according to the Group Identity. |  |  | Measurement
258 | Yongho Seok | 13 | 16 | 7.3.2.21.8 | T |  | It seems that the size of STA Counter Trigger Condition field should be 1 byte, when I compare the Reporting Reason field in Figure v9. |  |  | Measurement
259 | Yongho Seok | 15 | 5 | 7.3.2.21.8 | T |  | Please change the size of RSNA Trigger Condition field to 1 byte. |  |  | Measurement
260 | Yongho Seok | 15 | 11,15,18,21 | 7.3.2.21.8 | T |  | As the dot11RSNAStatesTKIPHdrErros is modified in the TGW (11-06-1729-23-000w-lb88-comment-resolution), please also exchange it to dot11RSNAStatsRobustMgmtCCMPReplays. Also, please include the dot11RSNATKIPICVErrors, dot11RSNAStatsCCMPDecryptErrors, dot11RSNAStatsCCMPReplays, dot11RSNSStatsTKIPReplays. |  |  | Measurement
261 | Yongho Seok | 20 | 1 | 7.3.2.22.8 | T |  | Please the size of Reporting Reason field for RSNA Counters change from 2 bytes to 1 bytes. |  |  | Measurement
262 | Yongho Seok | 18 | 7 | 7.3.2.22.8 | T |  | Please the size of Reporting Reason field change from variable to 1 bytes. |  |  | Measurement
263 | Yongho Seok | 12 | 3 | 7.3.2.21.8 | T |  | It seems that Triggered Statistic Request/Report should also support the QoS STA Counters. |  |  | Measurement
264 | Yongho Seok | 23 | 17 | 7.3.2.37.3 | T |  | It seems that the field format of Figure v13 should be changed to a frame format that includes the Sub-element ID and Length field like Figure v14. |  |  | BSS Transition Management
265 | Yongho Seok | 71 | 5 | 7.3.2.62 | T |  | Is it sure that the length of the Supported Regulatory Classes element is should be between 1 and 32 octets? If it is true, please change the Figure v84. |  |  | ECSA
266 | Yongho Seok | 73 | 6,7 | 7.3.2.64 | T |  | Please change from STAs to QSTAs and from BSS to QBSS. |  |  | Traffic Generation
267 | Yongho Seok | 56 | 1 | 7.3.2.54.2 | T |  | It seems that the length field should be changed from 2xnumber of channels + 1 to 2xnumber of channels. |  |  | Presence
268 | Yongho Seok | 82 | 19 | 7.4.8.10 | T |  | It seems that the BSS Transition Management Request frame should be transmitted from AP. Please change STA to AP. |  |  | BSS Transition Management
270 | Yongho Seok | 73 | 6,7 | 7.3.2.64 | T |  | What is the meanig of "the number of STAs that are currently associated with the BSS for the corresponding AC traffic"? It seems that the STA should be associated with AP for each AC. When the STA only sent one frame with AC 0 before long times ago, is it also considered as the STA associated with AC 0? |  |  | Traffic Generation
272 | Yongho Seok | 163 | 11 | 11.15.7.2 | T |  | In the BSS Transition Management Request frame, where is the expiration time? Please add an expirtation time field. |  |  | BSS Transition Management
273 | Yongho Seok | 163 | 23,24 | 11.15.7.3 | T |  | It seems that the result of the BSS transition decision should be included in the Status code field instead of the Target BSSID field. |  |  | BSS Transition Management
274 | Yongho Seok | 27 | 7 | 7.3.2.50 | T |  | It seems that the name of Table v5 should be changed from Event Request Type Definitions to Event Type Definitions. And, please combine Table v5 and Table v9 into one Table. |  |  | Event
277 | Yongho Seok | 60 | 7 | 7.3.2.54.9 | T |  | Why do you specify the location information formats such as CIVIC and GEO? It seems that it is not necessary to specify the detailed location information format since the goal of RFC 4119 is to defines an object that is suitable both for identifying and encapsulating preexisting location information formats. If we don't explicitly specify the CIVIC and GEO in the Location Descriptor, any other preexisiting location information formats including CIVIC and GEO can be supported in TGV. Please combine CIVIC and GEO into "XML-based Presence Information Data Format". |  |  | Presence
278 | Dorothy Stanley | 66 | 20 | 7.3.2.58 | t |  | “AID 0” is not the only AID value that indicates Broadcast/Multicast - With the Multiple BSSID (Virtual AP) proposal, the first 2^n AIDs are allocated to indicate MC/BC. | Change from “AID 0 Descriptor” to “FBMS Descriptor” throughout |  | FBMS.
279 | Emily Qi | 22 | 17 | 7.3.2.37 | E |  | Change editorial instructure from " Insert the following titles and text …" to "insert the following titles … ". Aka, Remove "and text". |  |  | General
280 | Emily Qi | 23 | 8 | 7.3.2.37.2 | E |  | The text is not consistent with 802.11k D7.0 draft |  |  | General
281 | Emily Qi | iv | 27 |  | E |  | Add a list of contributors |  |  | General
Note on F1: Adrian Stephens: T - technical error E - editorial error

## TGv Draft 0.11 Review Comments
Reviewer Name | Page | Line | Clause | Type of Comment (CID implementation or technical change) | Related CID(s) | Comment | Proposed Solution (if necessary) | Edit Status | Edit Notes
| v | 0 |  | E |  | Document History was dropped from the FrameMaker version. | Suggestion: Use FrameMaker's "Conditional Text". Define a conditional text tag (I use "EditorInfo") and make this table and the non-TBD-explanation Editorial Notes conditional. Have them appear in the redline version (nobody seems to care about such stuff in the redline version), but not appear in the clean version (where lots of people do care about this stuff appearing). This keeps the info in the same .fm file (and thus easy to search for dependencies on other drafts), but hidden from normal view. | D0.12
| 2 | 0 |  | E |  | Why the blank page? I don't think the Style Guide requires one here |  | D0.12
Bill Marshall | 3 | 1 | 1 | E |  | Extraneous title | Delete "1 Overview" | D0.12
Note on E1: Adrian Stephens: T - technical error E - editorial error