## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-07/1952r18
Venue Date: | July 2011
First Author: | Clint Chaplin, SISA
Subject: | IEEE 802.11 Non-Procedural Letter Ballot Results
Full Date: | 2011-06-27
Author(s): | Name(s) | Clint Chaplin
| Company | SISA
| Address | 75 W. Plumeria Dr., San Jose, CA 95134
| Phone: | 408-544-2740
Fax:
| email: | firstname dot lastname at gmail dot com
Abstract:
Results of IEEE 802.11 non-procedural Letter Ballots
Notice: This document has been prepared to assist IEEE 802.11. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor grants a free, irrevocable license to the IEEE to incorporate material contained in this contribution, and any modifications thereof, in the creation of an IEEE Standards publication; to copyright in the IEEE’s name any IEEE Standards publication even though it may include portions of this contribution; and at the IEEE’s sole discretion to permit others to reproduce in whole or in part the resulting IEEE Standards publication. The contributor also acknowledges and accepts that this contribution may be made public by IEEE 802.11.
Patent Policy and Procedures: The contributor is familiar with the IEEE 802 Patent Policy and Procedures <http:// ieee802.org/guides/bylaws/sb-bylaws.pdf>, including the statement "IEEE standards may include the known use of patent(s), including patent applications, provided the IEEE receives assurance from the patent holder or applicant with respect to patents essential for compliance with both mandatory and optional portions of the standard." Early disclosure to the Working Group of patent information that might be relevant to the standard is essential to reduce the possibility for delays in the development process and increase the likelihood that the draft publication will be approved for publication. Please notify the Chair <stuart@ok-brit.com> as early as possible, in written or electronic form, if patented technology (or technology under patent application) might be incorporated into a draft standard being developed within the IEEE 802.11 Working Group. If you have questions, contact the IEEE Patent Committee Administrator at <patcom@ieee.org>.

## Sheet1
Document | PAR Approved | Initial WG Ballots (failed) | [22 empty] | Initial WG Ballot (passed) | [7 empty] | Ballots and drafts to gain 75% WG | Months between start of first Initial Letter Ballot and end of letter ballot gaining 75% WG | Recirc voting pool | Recirculation WG Ballots | [47 empty] | Final Approval % | Ballots during WG recirc. | Ballots at WG level | Months between start of first WG recirc Letter Ballot and end of last WG recirc ballot | Months between start of first Initial WG Letter Ballot and end of last WG recirc ballot | Initial Sponsor Ballot | [6 empty] | Recirculation Sponsor Ballots | [61 empty] | Final Approval % | Ballots at Sponsor level | Total number of ballots | Months between start of first Sponsor ballot and end of last Sponsor recirc ballot | Voter Pool | REVCOM/Standards Board Approval | IEEE Publish | Days between start of first letter ballot and REVCOM / Standards Board Approval | Months between start of first letter ballot and REVCOM / Standards Board Approval | Years between start of first letter ballot and REVCOM / Standards Board Approval | Days between start of first sponsor ballot and REVCOM / Standards Board Approval | Months between start of first sponsor ballot and REVCOM / Standards Board Approval | Years between start of first sponsor ballot and REVCOM / Standards Board Approval | Days between PAR approval and REVCOM / Standards Board Approval | Months between PAR approval and REVCOM / Standards Board Approval | Years between PAR approval and REVCOM / Standards Board Approval
[6 empty] | y | n | a | [5 empty] | y | n | a | [12 empty] | y | n | a | [8 empty] | y | n | a | [5 empty] | y | n | a | [5 empty] | y | n | a | [5 empty] | y | n | a | [5 empty] | y | n | a | [5 empty] | y | n | a | [9 empty] | y | n | a |  |  |  |  | y | n | a |  |  |  |  | y | n | a |  |  |  |  | y | n | a |  |  |  |  | y | n | a |  |  |  |  | y | n | a |  |  |  |  | y | n | a | [10 empty] | y | n | a |  |  |  |  | y | n | a
IEEE 802.11
IEEE 802.11a | 1997-09-16
IEEE 802.11b | 1997-12-09
IEEE 802.11c | 1997-12-09
IEEE 802.11d | 1999-06-26 | [23 empty] | D1.0 | [7 empty] | 1 |  |  | D1.6 | LB21 | 2000-03-27 | 2000-04-04 |  |  |  |  | D1.9 | LB22 | 2000-06-12 | 2000-06-26 | [37 empty] | 2 | 3 | 2.9918 |  | D2.0 | 2001-01-31 | 2001-03-01 | 38 | 3 |  | 92.68% | D3.0 | 2001-04-03 | 2001-04-13 | 42 | 0 |  | 100% | [55 empty] | 100% | 2 | 5 | 2.3671 | 55
IEEE 802.11e | 2000-03-30 | D1.0 | LB27 | 2001-04-05 | 2001-05-15 |  |  |  |  | D2.0 | LB30 | 2001-12-05 | 2002-01-16 | 101 | 84 |  | 54.59% | D3.0 | LB39 | 2002-05-23 | 2002-07-02 | 106 | 110 | 49.07% | D4.0 | LB51 | 2002-11-28 | 2003-01-08 | 228 | 47 |  | 82.91% | 4 | 21.1397 | 321 | D5.0 | LB59 | 2003-08-01 | 2003-08-22 | 240 | 34 |  | 87.59% | D6.0 | LB63 | 2003-12-04 | 2003-12-20 | 248 | 30 |  | 89.21% | D7.0 | LB65 | 2004-01-31 | 2004-02-15 | 258 | 19 |  | 93.14% | D8.0 | LB67 | 2004-02-24 | 2004-03-10 | 262 | 16 |  | 94.24% | [16 empty] | 94.24% | 4 | 8 | 7.2986 | 35.1781 | D8.0 | 2004-04-07 | 2004-05-30 | 91 | 16 |  | 85.05% | D9.0 | 2004-08-06 | 2004-08-31 | 95 | 14 |  | 87.16% | D10.0 | 2004-09-23 | 2004-10-08 | 100 | 9 |  | 91.74% | D11.0 | 2004-10-27 | 2004-11-11 | 106 | 5 |  | 95.5% | D12.0 | 2004-12-08 | 2004-12-23 | 107 | 5 |  | 95.54% | D13.0 | 2005-02-03 | 2005-02-18 | 109 | 4 |  | 96.46% | D13.0 | 2005-04-01 | 2005-04-16 | 113 | 1 |  | 99.12% | [20 empty] | 99.12% | 7 | 15 | 12.2959 | 161 | 2005-09-22 | 2005-11-11 | 1631 | 53.6219 | 4.4685 | 533 | 17.5233 | 1.4603 | 2002 | 65.8192 | 5.4849
IEEE 802.11F | 2000-03-30 | D1.1 | LB26 | 2001-04-05 | 2001-05-15 |  |  |  |  | D2.0 | LB28 | 2001-07-25 | 2001-09-03 | [11 empty] | D3.0 | LB32 | 2002-01-29 | 2002-03-10 | 139 | 37 |  | 78.98% | 3 | 11.1452 | 290 | D3.1 | LB38 | 2002-05-08 | 2002-06-16 | 142 | 37 |  | 79.33% | [40 empty] | 79.33% | 1 | 4 | 1.2822 | 14.3671 | D4.0 | 2002-09-18 | 2002-10-28 | 50 | 7 |  | 87.72% | D4.1 | 2002-12-04 | 2002-12-19 | 56 | 3 |  | 94.92% | D5.0 | 2003-02-07 | 2003-02-17 | 57 | 2 |  | 96.61% | D6.0 | 2003-03-25 | 2003-04-08 | 61 | 1 |  | 98.39% | [41 empty] | 98.39% | 4 | 8 | 6.6411 | 73 | 2003-06-12 | 2003-07-14 | 798 | 26.2356 | 2.1863 | 267 | 8.7781 | 0.73151 | 1169 | 38.4329 | 3.2027
IEEE 802.11g | 2000-09-21 | D2.1 | LB33 | 2002-01-31 | 2002-03-11 | 86 | 104 |  | 45.26% | [15 empty] | D3.0 | LB41 | 2002-07-23 | 2002-09-01 | 176 | 44 |  | 80% | 2 | 7.0027 | 382 | D4.0 | LB49 | 2002-10-17 | 2002-11-01 | 217 | 33 |  | 86.8% | D5.0 | LB50 | 2002-11-27 | 2003-01-08 | 256 | 34 |  | 88.28% | D6.1 | LB54 | 2003-01-20 | 2003-02-04 | 285 | 7 |  | 97.6% | [24 empty] | 97.6% | 3 | 5 | 3.6164 | 12.1315 | D6.2 | 2003-02-06 | 2003-03-09 | 54 | 10 |  | 84.38% | D7.1 | 2003-03-25 | 2003-04-08 | 58 | 10 |  | 85.29% | D8.2 | 2003-04-29 | 2003-05-14 | 64 | 3 |  | 95.52% | [48 empty] | 95.52% | 3 | 8 | 3.189 | 96 | 2003-06-12 | 2003-06-27 | 497 | 16.3397 | 1.3616 | 126 | 4.1425 | 0.34521 | 994 | 32.6795 | 2.7233
IEEE 802.11h | 2000-12-07 | D1.0 | LB29 | 2001-07-25 | 2001-09-03 | [19 empty] | D2.0 | LB36 | 2002-03-26 | 2002-05-05 | 165 | 52 |  | 76.04% | 2 | 9.337 | 330 | D2.1 | LB42 | 2002-07-23 | 2002-09-01 | 208 | 24 |  | 89.66% | D2.2 | LB48 | 2002-10-17 | 2002-11-01 | 220 | 13 |  | 94.42% | [32 empty] | 94.42% | 2 | 4 | 3.3205 | 15.2548 | D3.0 | 2002-12-12 | 2003-02-06 | 48 | 4 |  | 92.31% | D3.6 | 2003-04-15 | 2003-04-30 | 53 | 2 |  | 96.36% | D3.11 | 2003-06-10 | 2003-06-26 | 56 | 1 |  | 98.25% | [48 empty] | 98.25% | 3 | 7 | 6.4438 | 75 | 2003-09-11 | 2003-10-14 | 778 | 25.5781 | 2.1315 | 273 | 8.9753 | 0.74795 | 1008 | 33.1397 | 2.7616
IEEE 802.11i | 2000-03-30 | D1.0 | LB25 | 2001-04-05 | 2001-05-15 |  |  |  |  | D2.0 | LB35 | 2002-03-25 | 2002-05-04 | 92 | 115 |  | 44.44% | [7 empty] | D3.0 | LB52 | 2002-12-02 | 2003-01-12 | 209 | 65 |  | 76.28% | 3 | 21.2712 | 321 | D4.0 | LB57 | 2003-05-22 | 2003-06-06 | 218 | 61 |  | 78.14% | D5.0 | LB60 | 2003-08-04 | 2003-08-19 | 243 | 36 |  | 87.1% | D6.0 | LB61 | 2003-09-24 | 2003-10-09 | 257 | 21 |  | 92.45% | D7.0 | LB62 | 2003-10-20 | 2003-11-04 | 264 | 14 |  | 94.96% | [16 empty] | 94.96% | 4 | 7 | 5.4575 | 31.0027 | D7.0 | 2003-11-20 | 2003-12-20 | 117 | 15 |  | 88.64% | D8.0 | 2004-02-26 | 2004-03-12 | 122 | 11 |  | 91.73% | D9.0 | 2004-03-26 | 2004-04-10 | 131 | 3 |  | 97.76% | D10.0 | 2004-04-23 | 2004-05-08 | 130 | 3 |  | 97.74% | [41 empty] | 97.74% | 4 | 11 | 5.589 | 163 | 2004-06-24 | 2004-07-24 | 1176 | 38.663 | 3.2219 | 217 | 7.1342 | 0.59452 | 1547 | 50.8603 | 4.2384
IEEE 802.11j | 2002-12-11 | D1.0 | LB56 | 2003-01-01 | 2003-05-12 | 172 | 45 |  | 79.26% | [15 empty] | D1.2 | LB64 | 2003-12-05 | 2004-01-14 | 212 | 27 |  | 88.7% | 2 | 12.4274 | 463 | D1.3 | LB66 | 2004-02-04 | 2004-03-11 | 258 | 17 |  | 93.82% | D1.4 | LB68 | 2004-04-05 | 2004-04-20 | 273 | 13 |  | 95.45% | [32 empty] | 95.45% | 2 | 4 | 2.4986 | 15.6164 | D1.5 | 2004-06-02 | 2004-07-02 | 66 | 9 |  | 88% | D1.6 | 2004-07-30 | 2004-08-14 | 74 | 3 |  | 96.1% | [55 empty] | 96.1% | 2 | 6 | 2.4 | 93 | 2004-09-23 | 2004-10-29 | 631 | 20.7452 | 1.7288 | 113 | 3.7151 | 0.30959 | 652 | 21.4356 | 1.7863
IEEE 802.11k | 2002-12-11 | D1.0 | LB71 | 2004-08-02 | 2004-09-11 | 211 | 74 |  | 74.04% | D2.0 | LB73 | 2005-02-03 | 2005-03-15 | 217 | 86 |  | 71.62% | [7 empty] | D3.0 | LB78 | 2005-10-03 | 2005-11-12 | 295 | 75 |  | 79.73% | 3 | 15.3534 | 514 | D4.0 | LB83 | 2006-03-16 | 2006-03-31 | 308 | 73 |  | 80.84% | D5.0 | LB86 | 2006-09-01 | 2006-09-16 | 325 | 59 |  | 84.64% | D6.0 | LB90 | 2006-11-01 | 2006-11-15 | 354 | 36 |  | 90.77% | D7.0 | LB96 | 2007-01-29 | 2007-02-15 | 361 | 30 |  | 92.33% | D7.0 | LB103 | 2007-04-18 | 2007-05-05 | 363 | 29 |  | 92.6% | [8 empty] | 92.6% | 5 | 8 | 13.6438 | 33.074 | D8.0 | 2007-07-11 | 2007-08-10 | 89 | 10 |  | 89.9% | D9.0 | 2007-09-24 | 2007-10-04 | 91 | 11 |  | 89.22% | D10.0 | 2007-11-28 | 2007-12-08 | 94 | 9 |  | 91.26% | D11.0 | 2008-01-07 | 2008-01-17 | 103 | 5 |  | 95.37% | D12.0 | 2008-01-22 | 2008-02-01 | 105 | 5 |  | 95.45% | D12.0 | 2008-02-04 | 2008-02-14 | 105 | 5 |  | 95.45% | D13.0 | 2008-03-03 | 2008-03-18 | 106 | 3 |  | 97.25% | [20 empty] | 97.25% | 7 | 15 | 8.2521 | 135 | 2008-05-09 | 2008-06-12 | 949 | 31.2 | 2.6 | 303 | 9.9616 | 0.83014 | 1976 | 64.9644 | 5.4137
IEEE 802.11ma | 2003-03-20 | [23 empty] | D1.0 | LB74 | 2005-03-29 | 2005-05-08 | 348 | 36 |  | 90.62% | 1 | 1.3151 | 542 | D2.0 | LB75 | 2005-07-07 | 2005-07-17 | 387 | 26 |  | 93.7% | D3.0 | LB76 | 2005-08-08 | 2005-08-19 | 397 | 20 |  | 95.2% | D4.0 | LB77 | 2005-09-09 | 2005-09-19 | 411 | 15 |  | 96.48% | [24 empty] | 96.48% | 3 | 4 | 2.4329 | 5.7205 | D5.0 | 2005-10-21 | 2005-11-20 | 86 | 14 |  | 86% | D6.0 | 2006-04-10 | 2006-05-10 | 95 | 10 |  | 90.48% | D7.0 | 2006-06-21 | 2006-07-11 | 99 | 10 |  | 90.83% | D8.0 | 2006-08-25 | 2006-09-09 | 111 | 5 |  | 95.69% | D9.0 | 2006-10-23 | 2006-11-07 | 111 | 5 |  | 95.69% | [34 empty] | 95.69% | 5 | 9 | 12.5589 | 145 | 2007-03-08 | 2007-06-12 | 709 | 23.3096 | 1.9425 | 503 | 16.537 | 1.3781 | 1449 | 47.6384 | 3.9699
IEEE 802.11n | 2003-09-11 | D1.0 | LB84 | 2006-03-19 | 2006-04-29 | 149 | 171 |  | 46.56% | [15 empty] | D2.0 | LB97 | 2007-02-07 | 2007-03-09 | 231 | 46 |  | 83.39% | 2 | 11.6712 | 325 | D3.0 | LB115 | 2007-10-07 | 2007-10-27 | 240 | 43 |  | 84.81% | D4.0 | LB124 | 2008-03-28 | 2008-04-12 | 253 | 34 |  | 88.15% | D5.0 | LB129 | 2008-05-23 | 2008-06-12 | 261 | 29 |  | 90% | D6.0 | LB134 | 2008-07-21 | 2008-08-05 | 266 | 27 |  | 90.78% | D7.0 | LB136 | 2008-09-15 | 2008-09-30 | 276 | 17 |  | 94.2% | D7.0 | LB138 | 2008-11-17 | 2008-12-02 | 281 | 14 |  | 95.25% | 95.25% | 6 | 8 | 13.874 | 32.5151 | D7.0 | 2008-12-11 | 2009-01-10 | 158 | 45 |  | 77.83% | D8.0 | 2009-02-19 | 2009-03-06 | 169 | 42 |  | 80.09% | D9.0 | 2009-03-20 | 2009-04-04 | 171 | 41 |  | 80.66% | D10.0 | 2009-05-15 | 2009-05-30 | 190 | 26 |  | 87.96% | D11.0 | 2009-06-05 | 2009-06-20 | 195 | 22 |  | 89.86% | D11.0 | 2009-06-23 | 2009-07-03 | 198 | 20 |  | 90.83% | [27 empty] | 90.83% | 6 | 14 | 6.7068 | 277 | 2009-09-11 | 2009-10-29 | 947 | 31.1342 | 2.5945 | 274 | 9.0082 | 0.75068 | 2192 | 72.0658 | 6.0055
IEEE 802.11p | 2004-09-23 | D1.0 | LB81 | 2006-03-02 | 2006-04-11 | 167 | 117 |  | 58.8% | D2.0 | LB92 | 2006-12-06 | 2007-01-05 | 166 | 83 |  | 66.67% | D3.0 | LB110 | 2007-08-13 | 2007-09-12 | 143 | 50 | 74.09% | D4.0 | LB125 | 2008-04-03 | 2008-05-03 | 136 | 37 |  | 78.61% | 4 | 26.0712 | 234 | D5.0 | LB141 | 2008-11-20 | 2008-12-05 | 149 | 26 |  | 85.14% | D6.0 | LB144 | 2009-03-16 | 2009-03-31 | 161 | 20 | 29 | 88.95% | D7.0 | LB151 | 2009-05-29 | 2009-06-13 | 158 | 27 | 26 | 85.41% | D8.0 | LB154 | 2009-07-21 | 2009-08-05 | 163 | 20 | 28 | 89.07% | D9.0 | LB158 | 2009-09-25 | 2009-10-10 | 171 | 12 | 29 | 93.44% | [8 empty] | 93.44% | 5 | 9 | 10.6521 | 43.3315 | D9.0 | 2009-10-23 | 2009-11-22 | 114 | 8 |  | 93.44% | D10.0 | 2010-02-01 | 2010-02-16 | 120 | 5 |  | 96% | D11.0 | 2010-03-23 | 2010-04-07 | 131 | 1 |  | 99.24% | [48 empty] | 99.24% | 3 | 12 | 5.4575 | 164 | 2010-06-17 | 2010-07-15 | 805 | 26.4658 | 2.2055 | 237 | 7.7918 | 0.64932 | 2093 | 68.811 | 5.7342
IEEE 802.11r | 2004-05-13 | [23 empty] | D1.0 | LB79 | 2005-11-25 | 2006-01-04 | 268 | 64 |  | 80.72% | 1 | 1.3151 | 518 | D2.0 | LB82 | 2006-03-15 | 2006-04-04 | 316 | 44 |  | 87.78% | D3.0 | LB87 | 2006-09-29 | 2006-10-14 | 318 | 50 |  | 86.41% | D4.0 | LB91 | 2006-11-20 | 2006-12-04 | 335 | 30 |  | 91.78% | D5.0 | LB98 | 2007-03-20 | 2007-04-04 | 350 | 19 |  | 94.85% | D6.0 | LB105 | 2007-05-28 | 2007-06-13 | 360 | 11 |  | 97.04% | [8 empty] | 97.04% | 5 | 6 | 14.9589 | 18.5753 | D7.0 | 2007-07-31 | 2007-08-30 | 79 | 13 |  | 85.87% | D8.0 | 2007-09-27 | 2007-10-07 | 86 | 10 |  | 89.58% | D9.0 | 2008-01-07 | 2008-01-17 | 95 | 4 |  | 95.96% | D9.0 | 2008-01-22 | 2008-02-01 | 100 | 3 |  | 97.09% | [41 empty] | 97.09% | 4 | 10 | 6.0822 | 130 | 2008-05-09 | 2008-07-15 | 896 | 29.4575 | 2.4548 | 283 | 9.3041 | 0.77534 | 1457 | 47.9014 | 3.9918
IEEE 802.11s | 2004-05-13 | D1.0 | LB93 | 2006-12-07 | 2007-01-06 | 128 | 138 |  | 48.12% | D2.0 | LB126 | 2008-04-03 | 2008-05-03 | 103 | 67 |  | 60.59% | [7 empty] | D3.0 | LB147 | 2009-04-04 | 2009-05-04 | 132 | 35 | 34 | 79.04% | 3 | 28.8986 | 248 | D4.0 | LB159 | 2009-12-09 | 2010-01-08 | 150 | 27 | 33 | 84.75% | D5.0 | LB161 | 2010-03-31 | 2010-04-15 | 159 | 19 | 32 | 89.33% | D6.0 | LB165 | 2010-06-13 | 2010-06-28 | 157 | 20 | 33 | 88.7% | D7.0 | LB166 | 2010-07-29 | 2010-08-13 | 167 | 9 | 34 | 94.89% | [16 empty] | 94.89% | 4 | 7 | 8.1205 | 44.2192 | D7.0 | 2010-10-02 | 2010-11-01 | 123 | 6 |  | 95.35% | D8.0 | 2010-12-20 | 2011-01-10 | 131 | 6 | 11 | 95.62% | D9.0 | 2011-02-18 | 2011-03-05 | 134 | 7 | 9 | 95.04% | D10.0 | 2011-03-25 | 2011-04-09 | 140 | 5 | 9 | 96.55% | D11.0 | 2011-04-22 | 2011-05-07 | 140 | 5 | 9 | 96.55% | D12.0 | 2011-05-20 | 2011-06-04 | 141 | 4 | 9 | 97.24% | [27 empty] | 97.24% | 6 | 13 | 8.0548 | 184 | 2011-09-10 | 2011-09-10 | 1738 | 57.1397 | 4.7616 | 343 | 11.2767 | 0.93973 | 2676 | 87.9781 | 7.3315
IEEE 802.11.2 | 2004-08-12 | [23 empty] | D1.0 | LB101 | 2007-04-16 | 2007-05-16 | 163 | 52 |  | 75.81% | 1 | 0.9863 | 307
IEEE 802.11u | 2004-12-08 | D1.0 | LB107 | 2007-06-08 | 2007-07-08 | 111 | 62 |  | 64.16% | D2.0 | LB122 | 2008-02-14 | 2008-03-15 | 125 | 53 |  | 70.22% | [7 empty] | D3.0 | LB132 | 2008-06-12 | 2008-07-12 | 113 | 34 |  | 76.87% | 3 | 13.1507 | 213 | D4.0 | LB137 | 2008-09-23 | 2008-10-08 | 118 | 34 |  | 77.63% | D5.0 | LB142 | 2009-02-05 | 2009-02-20 | 125 | 27 | 39 | 82.24% | D6.0 | LB148 | 2009-04-09 | 2009-04-24 | 142 | 15 | 35 | 90.45% | D7.0 | LB152 | 2009-06-04 | 2009-06-19 | 142 | 19 | 33 | 88.2% | D8.0 | LB156 | 2009-07-31 | 2009-08-18 | 148 | 11 | 35 | 93.08% | [8 empty] | 93.08% | 5 | 8 | 10.8164 | 26.3671 | D8.0 | 2009-10-08 | 2009-11-07 | 106 | 12 |  | 89.83% | D9.0 | 2010-04-08 | 2010-04-23 | 115 | 10 |  | 92% | D10.0 | 2010-06-23 | 2010-07-08 | 120 | 7 |  | 94.49% | D11.0 | 2010-08-03 | 2010-08-13 | 124 | 5 |  | 96.12% | D12.0 | 2010-09-02 | 2010-09-12 | 127 | 2 |  | 98.45% | D13.0 | 2010-11-11 | 2010-11-21 | 128 | 1 | 14 | 99.22% | [27 empty] | 99.22% | 6 | 14 | 13.4466 | 154 | 2011-02-02 | 2011-02-25 | 965 | 31.726 | 2.6438 | 482 | 15.8466 | 1.3205 | 2247 | 73.874 | 6.1562
IEEE 802.11v | 2004-12-08 | D1.0 | LB108 | 2007-07-31 | 2007-08-30 | 132 | 77 |  | 63.16% | D2.0 | LB123 | 2008-02-14 | 2008-03-15 | 126 | 62 |  | 67.02% | D3.0 | LB133 | 2008-06-13 | 2008-07-13 | 106 | 47 | 69.28% | D4.0 | LB140 | 2008-11-19 | 2008-12-19 | 149 | 36 |  | 80.54% | 4 | 16.6685 | 254 | D5.0 | LB146 | 2009-03-20 | 2009-04-04 | 155 | 32 | 41 | 82.89% | D6.0 | LB150 | 2009-05-28 | 2009-06-12 | 172 | 20 | 38 | 89.58% | D7.0 | LB155 | 2009-07-23 | 2009-08-07 | 176 | 16 | 38 | 91.67% | [24 empty] | 91.67% | 3 | 7 | 4.6027 | 24.263 | D7.0 | 2009-10-08 | 2009-11-07 | 105 | 25 |  | 80.77% | D8.0 | 2010-01-29 | 2010-02-17 | 112 | 22 |  | 83.58% | D10.0 | 2010-03-29 | 2010-04-13 | 122 | 18 |  | 87.14% | D11.0 | 2010-05-26 | 2010-06-10 | 130 | 11 |  | 92.2% | D12.0 | 2010-06-22 | 2010-07-07 | 133 | 8 |  | 94.33% | D13.0 | 2010-07-18 | 2010-07-28 | 138 | 3 |  | 97.87% | D14.0 | 2010-08-10 | 2010-08-25 | 140 | 3 |  | 97.9% | D15.0 | 2010-09-15 | 2010-09-30 | 140 | 3 | 97.9% | D15.0 | 2010-10-08 | 2010-10-18 | 141 | 3 | 7 | 97.92% | D16.0 | 2010-11-05 | 2010-11-15 | 141 | 3 | 7 | 97.92% | 97.92% | 10 | 17 | 13.2493 | 161 | 2011-02-02 | 2011-02-09 | 805 | 26.4658 | 2.2055 | 482 | 15.8466 | 1.3205 | 2247 | 73.874 | 6.1562
IEEE 802.11w | 2005-03-20 | [23 empty] | D1.0 | LB88 | 2006-10-10 | 2006-11-19 | 202 | 34 |  | 85.59% | 1 | 1.3151 | 427 | D2.0 | LB102 | 2007-04-17 | 2007-05-02 | 227 | 29 |  | 88.67% | D3.0 | LB114 | 2007-10-04 | 2007-10-19 | 245 | 21 |  | 92.11% | D4.0 | LB117 | 2007-12-12 | 2008-01-05 | 245 | 21 |  | 92.11% | D5.0 | LB121 | 2008-02-05 | 2008-02-20 | 259 | 14 |  | 94.87% | D6.0 | LB128 | 2008-04-03 | 2008-04-18 | 266 | 8 |  | 97.08% | [8 empty] | 97.08% | 5 | 6 | 12.0658 | 18.2795 | D6.0 | 2008-08-22 | 2008-09-21 | 92 | 15 |  | 85.98% | D7.0 | 2009-01-08 | 2009-01-18 | 99 | 13 |  | 88.39% | D9.0 | 2009-05-09 | 2009-05-23 | 104 | 9 |  | 92.04% | D10.0 | 2009-05-31 | 2009-06-14 | 107 | 8 |  | 93.04% | D11.0 | 2009-06-18 | 2009-06-28 | 110 | 6 |  | 94.83% | [34 empty] | 94.83% | 5 | 11 | 10.1918 | 148 | 2009-09-11 | 2009-09-30 | 1067 | 35.0795 | 2.9233 | 385 | 12.6575 | 1.0548 | 1636 | 53.7863 | 4.4822
IEEE 802.11y | 2006-03-16 | [23 empty] | D1.0 | LB94 | 2006-12-08 | 2007-01-07 | 182 | 59 |  | 75.52% | 1 | 0.9863 | 347 | D2.0 | LB104 | 2007-04-19 | 2007-05-05 | 221 | 41 |  | 84.35% | D3.0 | LB106 | 2007-06-05 | 2007-06-20 | 242 | 24 |  | 90.98% | D4.0 | LB109 | 2007-08-06 | 2007-08-21 | 250 | 17 |  | 93.63% | D5.0 | LB112 | 2007-09-28 | 2007-10-13 | 257 | 11 |  | 95.9% | D6.0 | LB116 | 2007-11-23 | 2007-12-08 | 271 | 2 |  | 99.27% | [8 empty] | 99.27% | 5 | 6 | 7.6603 | 12 | D7.0 | 2007-12-21 | 2008-01-30 | 87 | 7 |  | 92.55% | D8.0 | 2008-02-27 | 2008-03-08 | 91 | 5 |  | 94.79% | D9.0 | 2008-03-12 | 2008-03-27 | 95 | 4 |  | 95.96% | D10.0 | 2008-04-03 | 2008-04-18 | 98 | 3 |  | 97.03% | D11.0 | 2008-06-05 | 2008-06-20 | 100 | 3 |  | 97.09% | [34 empty] | 97.09% | 5 | 11 | 5.9836 | 128 | 2008-09-26 | 2008-11-06 | 658 | 21.6329 | 1.8027 | 280 | 9.2055 | 0.76712 | 925 | 30.411 | 2.5342
IEEE 802.11z | 2007-08-22 | D1.0 | LB127 | 2008-04-03 | 2008-05-03 | 103 | 59 |  | 63.58% | D2.0 | LB135 | 2008-07-21 | 2008-08-20 | 99 | 51 |  | 66% | [7 empty] | D3.0 | LB139 | 2008-11-18 | 2008-12-18 | 155 | 29 |  | 84.24% | 3 | 8.5151 | 254 | D4.0 | LB143 | 2009-02-18 | 2009-03-05 | 170 | 23 | 37 | 88.08% | D5.0 | LB153 | 2009-06-08 | 2009-06-23 | 183 | 15 | 34 | 92.42% | D6.0 | LB157 | 2009-08-11 | 2009-08-26 | 187 | 8 | 38 | 95.9% | [24 empty] | 95.9% | 3 | 6 | 6.2137 | 16.7671 | D6.0 | 2009-10-07 | 2009-11-06 | 103 | 15 |  | 87.29% | D7.0 | 2010-02-12 | 2020-02-27 | 105 | 16 |  | 86.78% | D8.0 | 2010-04-19 | 2010-05-04 | 121 | 8 |  | 93.8% | D9.0 | 2010-05-26 | 2010-06-10 | 123 | 6 |  | 95.35% | D11.0 | 2010-07-19 | 2010-08-04 | 123 | 6 |  | 95.35% | D12.0 | 2010-08-06 | 2010-08-16 | 124 | 5 |  | 96.12% | D13.0 | 2010-08-19 | 2010-08-29 | 126 | 3 |  | 97.67% | [20 empty] | 97.67% | 7 | 13 | 10.7178 | 144 | 2010-09-30 | 2010-10-14 | 681 | 22.389 | 1.8658 | 358 | 11.7699 | 0.98082 | 1135 | 37.3151 | 3.1096
IEEE 802.11mb | 2007-03-22 | [23 empty] | D1.0 | LB149 | 2009-05-18 | 2009-06-27 | 155 | 23 | 29 | 87.08% | 1 | 1.3151 | 246 | D2.0 | LB160 | 2009-12-11 | 2010-01-08 | 166 | 20 | 25 | 89.25% | D3.0 | LB162 | 2010-03-31 | 2010-04-25 | 167 | 20 | 25 | 89.3% | D4.0 | LB163 | 2010-06-10 | 2010-06-25 | 164 | 20 | 28 | 89.13% | D5.0 | LB167 | 2010-08-04 | 2010-08-19 | 172 | 15 | 25 | 91.98% | [16 empty] | 91.98% | 4 | 5 | 8.2521 | 15.0575 | D6.0 | 2010-09-21 | 2010-11-05 | 122 | 18 | 9 | 87.14% | D7.0 | 2011-02-03 | 2011-02-18 | 132 | 14 | 9 | 90.41% | D8.0 | 2011-03-25 | 2011-04-15 | 136 | 12 | 10 | 91.89% | D9.0 | 2011-06-02 | 2011-06-22 | 139 | 11 | 10 | 92.67% | D10.0 | 2011-08-18 | 2011-09-07 | 142 | 13 | 9 | 91.61% | D11.0 | 2011-10-07 | 2011-10-22 | 147 | 9 | 8 | 94.23% | D12.0 | 2011-11-03 | 2011-11-13 | 150 | 5 | 9 | 96.77% | [24 empty] | 186
IEEE 802.11aa | 2008-03-27 | [23 empty] | D1.0 | LB164 | 2010-06-10 | 2010-07-10 | 112 | 31 | 37 | 78.32% | 1 | 0.9863 | 257 | D2.0 | LB170 | 2010-11-23 | 2010-12-08 | 117 | 32 | 36 | 78.52% | D3.0 | LB173 | 2011-02-09 | 2011-02-24 | 127 | 30 | 37 | 80.89% | D4.0 | LB175 | 2011-03-25 | 2011-04-09 | 135 | 23 | 37 | 85.44% | D5.0 | LB179 | 2011-06-02 | 2011-06-17 | 142 | 15 | 39 | 90.45% | D6.0 | LB182 | 2011-07-25 | 2011-08-09 | 149 | 9 | 38 | 94.3% | D6.0 | LB184 | 2011-08-16 | 2011-08-31 | 151 | 8 | 38 | 94.97% | 94.97% | 6 | 7 | 9.2384 | 14.6959 | D6.0 | 2011-09-12 | 2011-10-12 | 106 | 8 | 9 | 92.98% | D7.0 | 2011-11-11 | 2011-11-26 | 113 | 5 | 9 | 95.76% | D8.0 | 2011-12-12 | 2012-01-02 | 119 | 1 | 11 | 99.17% | [52 empty] | 156
IEEE 802.11ac | 2008-09-26 | D1.0 | LB178 | 2011-05-26 | 2011-06-25 | 148 | 52 | 16 | 74%
IEEE 802.11ad | 2008-12-10 | [23 empty] | D1.0 | LB168 | 2010-09-24 | 2010-10-24 | 163 | 24 | 26 | 87.17% | 1 | 0.9863 | 278 | D2.0 | LB174 | 2011-03-21 | 2011-04-05 | 175 | 25 | 25 | 87.5% | D3.0 | LB177 | 2011-05-17 | 2011-06-01 | 188 | 16 | 24 | 92.16% | D4.0 | LB183 | 2011-07-25 | 2011-08-09 | 195 | 11 | 22 | 94.66% | D5.0 | LB185 | 2011-09-21 | 2011-10-06 | 196 | 13 | 19 | 93.78% | D5.0 | LB186 | 2011-11-09 | 2011-11-24 | 197 | 11 | 21 | 94.71% | [8 empty] | 94.71% | 5 | 6 | 8.1534 | 14.0055 | D5.0 | 2011-12-06 | 2012-01-05 | 141 | 23 | 11 | 85.98% | [66 empty] | 214
IEEE 802.11ae | 2009-12-09 | [23 empty] | D1.0 | LB169 | 2010-09-27 | 2010-10-27 | 134 | 32 | 40 | 80.72% | 1 | 0.9863 | 278 | D2.0 | LB172 | 2011-02-03 | 2011-02-18 | 155 | 26 | 38 | 85.64% | D3.0 | LB176 | 2011-04-11 | 2011-04-26 | 163 | 21 | 37 | 88.59% | D4.0 | LB180 | 2011-06-03 | 2011-06-18 | 180 | 8 | 35 | 95.74% | D5.0 | LB181 | 2011-07-20 | 2011-08-04 | 182 | 7 | 35 | 96.3% | [16 empty] | 96.3% | 4 | 5 | 5.9836 | 10.2247 | D5.0 | 2011-08-10 | 2011-09-09 | 110 | 6 | 7 | 94.83% | D6.0 | 2011-10-14 | 2011-10-29 | 115 | 5 | 7 | 95.83% | D8.0 | 2011-12-15 | 2012-01-04 | 126 | 0 | 9 | 100%
IEEE 802.11af | 2009-12-09 | D1.0 | LB171 | 2011-01-25 | 2011-02-24 | 125 | 76 | 35 | 62.19%
IEEE 802.11ah | 2010-09-30
IEEE 802.11ai

## References
References: