## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-07/2701r5
Venue Date: | November 2007
First Author: | John Ketchum /Qualcomm Incorporated
Subject: | TGN LB115 Beam Ad Hoc Comments
Full Date: | 2007-11-01
Author(s): | John Ketchum
Qualcomm Incorporated
9 Damonmill Square Suite 2A, Concord MA 01742 USA
Phone: +1 781-276-0915
Joonsuk Kim
Broadcom Corporation
190 Mathilda Place, Sunnyvale, CA 94086 USA
Phone: +1 408-543-3455
| email: johnk@qualcomm.com | email: joonsuk@broadcom.com
Abstract:
This document contains the consolidation of comments submitted by voters for LB97.
This information is PROVISIONAL awaiting validation.

## Revision History
Revision | Date | Description
1 | 2007-11-06 | Updated assignees and added transferred comments
2 | 2007-11-12 | Updated submissions
3 | 2007-11-13 | Updated submissions
4 | 2007-11-13 | Resolutions from 1st beam ad hoc
5 | 2007-11-15 | Resolutions from 2nd November beam ad hoc + Motion #1
6 | 2008-01-11 | Resolution from adhoc meeting with 1 comment transferred in from General
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## TxBF
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
5054 | Chan, Douglas | 115 | 3 | 20.3.11 |  |  | T | Y | 290.31 | 31 | 20.3.11 |  | R | John Ketchum |  |  | Like the vectors are bolded in this subclause, all matrices of >1 rows or col'ns should be bolded in typeface. | Like the vectors are bolded in this subclause, all matrices of >1 rows or col'ns should be bolded in typeface. | BEAM: 2008-01-11 07:34:38Z Reject - agreed for the resolution proposed in 08/008r0 with following reason Discussion: The use of boldface type to represent vectors and matrices is a common stylistic choice in mathematical texts that involve matrices and vectors, in order to clearly distinguish between vector and scalar quantities. However, in this document these distinctions are made clear in the text, and it is unnecessary to take the additional step of bolding matrices and vectors throughout the document. Also, limitations of the Framemaker equation editor may make it difficult to set matrix and vector variables in bold in a consistant manner. | BEAM | TxBF | [5 empty] | 2008-01-11 07:36 | BEAM
5057 | Chan, Douglas | 115 | 3 | 20.3.11 | 291 | 4-20 | T | Y | 291.04 | 4 | 20.3.11 |  | C | John Ketchum |  |  | In Fig 20-14, what is the meaning of the ";" between A_TX and A_RX, etc. | Clarify or replace them with ellipses. | BEAM: 2008-01-11 07:35:57Z Counter - agreed for the resolution proposed in 08/008r0 | BEAM | TxBF | [5 empty] | 2008-01-11 07:36 | BEAM
5056 | Chan, Douglas | 115 | 3 | 20.3.11 | 291 | 4-20 | T | Y | 291.04 | 4 | 20.3.11 |  | C | John Ketchum |  |  | There should be eillipses b/w the antennas to illustrate multiple number of them in Fig 20-14. Otherwise, say in the caption that this is only an example. | There should be eillipses b/w the antennas to illustrate multiple number of them in Fig 20-14. Otherwise, say in the caption that this is only an example. | BEAM: 2008-01-11 07:36:17Z Counter - agreed for the resolution proposed in 08/008r0 | BEAM | TxBF | [5 empty] | 2008-01-11 07:36 | BEAM
5059 | Chan, Douglas | 115 | 3 | 20.3.11.2 |  |  | T | Y | 293.35 | 35 | 20.3.11.2 |  | R | John Ketchum |  |  | Sometimes the subscript "k" is used to denote the kth element of a vector/matrix, but sometimes (k) is used. Should we unify the notation? | Should we unify the notation? | BEAM: 2008-01-11 07:36:28Z Reject - agreed for the resolution proposed in 08/008r0 with following reason Discussion: Subscripts are used consistently throughout the text to indicate position in a matrix or vector, as well as to index subcarriers, with the exception that in cases where there are multiple indices involved, such as in 20.3.11.2.1, where both superscripts and subscripts are used for other indices or quantities, and it is necessary to use parenthetical notation to accommodate an additional index. There is no obvious alternative to this approach. | BEAM | TxBF | [5 empty] | 2008-01-11 07:37 | BEAM
5528 | Scarpa, Vincenzo | 115 | 3 | Annex A | 349 | 49 | T | Y | 349.49 | 49 | A.4.19.1 |  |  | Bjorn |  |  | Transmission of sounding PPDUs should be OPTIONAL when Link Adaptation is supported. The reason is that a station can decide to support Link Adaptation only in Rx (i.e. providing MCS feedback only, which I guess doesn't require sounding format). | As in the comment. |  | BEAM | TxBF |  | GEN: 2008-01-10 07:35:09Z - more discussion on the use and fields of the sounding PPDU. Sounding and Link Adaptation are tied together in clause 9.16, but not sure how they relate to the comment or in the PICs. Transfer to Beam AdHoc for further discussion. GEN: 2007-10-29 14:58:22Z Check - discuss |  |  |  | 2008-01-11 07:28 | BEAM

## NDP
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
5487 | Petranovich, James | 115 | 3 | 9.19.2 | 172 | 45 | T | Y | 172.45 | 45 | 9.19.2 |  |  | John Ketchum | 11-07-2739-00-000n-proposed-resolutions-to-NDP-CIDs.doc |  | The requirement that an NDP must have at least 2 SS is limiting and unnecessary. There are cases where an NDP with 1 SS is useful. bemaformed | Allow NDP to consist of 1 SS. |  | BEAM | NDP |  | BEAM: 2007-11-15 14:26:13Z - Deferred-- Hongyuan & Vinko will respond |  |  |  | 2007-11-15 14:27 | BEAM

## Explicit TxBF
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
5075 | Chan, Douglas | 115 | 3 | 7.3.1.30 | 48 | 54 | T | Y | 48.54 | 54 | 7.3.1.30 |  |  | Joonsuk Kim |  |  | When carrier grouping is used, it is not clear whether the values to be sent back are smoothed across tones, or sampled individual tones. Although CID 1645 did not mention how exactly, but there exists ways to may effect the way the beamformer interprets the data. (So rejection of CID 1645 is unsatisfactory.) | Either specify that the channel estimates should be smoothed or not smoothed, or provide an extra bit to indicate whether smoothing was used. |  | BEAM | Explicit TxBF | [5 empty] | 2007-11-01 14:51 | BEAM
5269 | Erceg, Vinko | 115 | 3 | 7.3.1.30 | 49 | 28 | T | Y | 49.28 | 28 | 7.3.1.30 |  |  | Joonsuk Kim |  |  | In table 7-25d, it is better to have frequency index symmetric. | For 20Mhz Ng=2, change it to -28,-26,...-4, -2, -1, 1,2,4,...26,28 |  | BEAM | Explicit TxBF | [5 empty] | 2007-11-01 14:51 | BEAM
5272 | Erceg, Vinko | 115 | 3 | 7.3.1.30 | 49 | 29 | T | Y | 49.29 | 29 | 7.3.1.30 |  |  | Joonsuk Kim |  |  | Seems like that the choice of tones should have the HT-short training tones as an intersection of all grouping (in Table 7-25d) | Change to: For 20 MHz, Ng=4, [-28 -24,-20,-16,...-8,-4 ,4, 8,....,16, 20,24, 28] and for 40 MHz, Ng=4, [-58 -56,-52,-48,-44,-40,-36, -34, -30 ,-28,-24, -20, ...-12,-8 ,-4, -2, 2, 4, 8, 12,...20,28, 30 ,34 36,40,44,48, 52, 56 58] |  | BEAM | Explicit TxBF | [5 empty] | 2007-11-01 14:51 | BEAM
5484 | Petranovich, James | 115 | 3 | 7.3.1.31 | 50 | 36 | T | Y | 50.36 | 36 | 7.3.1.31 |  |  | Joonsuk Kim |  |  | It is nowhere defined what the rows and columns of the V matrix represent, they are just N_c and N_r. There is a tradition in the literature to construct the matrices a specific way, but this is a standard and we should be clear and not rely on well-known but unreferenced convention. My impression is that this vagueness was a compromise to avoid arguments, but in a standard we must try for clarity sufficient to enable interoperability and not leave important details unspecified. | Clarify that the rows corrspond to active transmit chains and the columns correspond to space-time streams (unless I got that backwards). |  | BEAM | Explicit TxBF | [5 empty] | 2007-11-01 14:51 | BEAM
5482 | Petranovich, James | 115 | 3 | 7.3.1.31 | 50 | 36 | T | Y | 50.36 | 36 | 7.3.1.31 |  |  | Joonsuk Kim |  |  | There are several references to "V matrix" or "Matrix V" in this section. V matrix is never really defined. More importantly, the use of the term implies that SVD is used to determine the matrix. This is not required in the draft, nor is it necessary that the matrix even be unitary (and they may be good reasons for it to possibly not be unitary). | Change the term from "V matrix" to "Non compressed beamforming matrix" or if a shorter term is required "NCB matrix". Explictly define the term in the definitions, and make it clear that this matrix need not be unitary |  | BEAM | Explicit TxBF | [5 empty] | 2007-11-01 14:51 | BEAM
5483 | Petranovich, James | 115 | 3 | 7.3.1.32 | 52 | 26 | T | Y | 52.26 | 26 | 7.3.1.32 |  |  | Joonsuk Kim |  |  | There are several references to "V matrix" or "Matrix V" in this section. V matrix is never really defined. More importantly, the use of the term implies that SVD is used to determine the matrix. This is not required in the draft. Unlike the non-compressed section, this matrix must be unitary for the Givens rotaiton to work properly. | Change the term from "V matrix" to "compressed beamforming matrix" or if a shorter term is required "CB matrix". Explicitly define the term in the definitions and make it clear that this matrix is unitary. |  | BEAM | Explicit TxBF | [5 empty] | 2007-11-01 14:51 | BEAM
5270 | Erceg, Vinko | 115 | 3 | 7.3.1.32 | 53 | 7 | T | Y | 53.07 | 7 | 7.3.1.32 |  |  | Joonsuk Kim |  |  | The dynamic range for both angles may be reduced for V matrix update. | We may need to indicate the dynamic range for the feedback. |  | BEAM | Explicit TxBF | [5 empty] | 2007-11-01 14:51 | BEAM
5076 | Chan, Douglas | 115 | 3 | 7.3.1.32 | 55 |  | T | Y | 55 |  | 7.3.1.32 |  |  | Joonsuk Kim |  |  | When carrier grouping is used, it is not clear whether the values to be sent back are smoothed across tones, or sampled individual tones. Although CID 1649 did not mention how exactly, but there exists ways to may effect the way the beamformer interprets the data. (So rejection of CID 1649 is unsatisfactory.) | Either specify that the channel estimates should be smoothed or not smoothed, or provide an extra bit to indicate whether smoothing was used. |  | BEAM | Explicit TxBF | [5 empty] | 2007-11-01 14:51 | BEAM
5662 | Stephens, Adrian | 115 | 3 | 9.16.2 | 156 | 41 | T | N | 156.41 | 41 | 9.16.2 |  |  | Vinko Erceg |  |  | "If the beamformer decides to employ Compressed Beamforming or Non-compressed Beamforming," What does this mean? Relate to the TXVECTOR parameters. | Replace with: "If the beamformer transmits a PPDU with the TXVECTOR EXPANSION_MAT_TYPE set to either COMPRESSED_SV or NON_COMPRESSED_SV," |  | BEAM | Explicit TxBF |  | BEAM: 2007-11-06 18:16:59Z - Submission in January. |  |  |  | 2007-11-06 18:17 | BEAM
5678 | Stephens, Adrian | 115 | 3 | 9.17.3 | 165 | 41 | T | N | 165.41 | 41 | 9.17.3 |  |  | Vinko Erceg |  |  | "dot11MaxCSIFeedbackDelay" is a particularly useless concept. This MIB variable is read-only and has no default value. At least setting a default value would communicate expectations about the time available for this calculation to other STA. All this currently says is "if you don't send the response quickly enough (but we won't tell you what that is), it may be ignored). | Set a default value for this mib variable or be honest - remove it and change this sentence to say "an implementation may ignore feedback if it is too old, or out of fashion, or the phase of the moon is wrong, or according to other implementation-defined criteria". |  | BEAM | Explicit TxBF |  | BEAM: 2007-11-06 18:16:59Z - Submission in January. |  |  |  | 2007-11-06 18:17 | BEAM
5171 | Chu, Liwen | 115 | 3 | 9.17.3 | 165 | 43 | T | Y | 165.43 | 43 | 9.17.3 |  |  | Vinko Erceg |  |  | According to this sentence, explicit feedback beamforming can not be used for direct link which is wrong. | Add DLS support here. |  | BEAM | Explicit TxBF |  | BEAM: 2007-11-06 18:16:59Z - Submission in January. |  |  |  | 2007-11-06 18:17 | BEAM
5679 | Stephens, Adrian | 115 | 3 | 9.17.3 | 165 | 54 | T | Y | 165.54 | 54 | 9.17.3 |  |  | Vinko Erceg |  |  | This section is aparently undecided whether immediate means "after SIFS" or "within the current TXOP". in a) - it clearly means either. But bullet b) implies it is just the former | change "Delayed: the beamformee is not capable of sending the feedback response a SIFS time after receiving a sounding PPDU" to: "Delayed: the beamformee is not capable of sending the feedback response within the beamformer's TXOP" (which also implies it can't send it after a SIFS). |  | BEAM | Explicit TxBF |  | BEAM: 2007-11-06 18:16:59Z - Submission in January. |  |  |  | 2007-11-06 18:17 | BEAM
5680 | Stephens, Adrian | 115 | 3 | 9.17.3 | 165 | 55 | T | Y | 165.55 | 55 | 9.17.3 |  |  | Vinko Erceg |  |  | "and shall not send the feedback response a SIFS time after receiving a sounding PPDU," Having just indicated we're incapable of doing this thing, is there any need for a prohibition? Also, I would rather not have a normative requirement in what appears to be definitions of three terms. | Delete the quoted sentence or move it somewhere later in the same subclause. |  | BEAM | Explicit TxBF |  | BEAM: 2007-11-06 18:16:59Z - Submission in January. |  |  |  | 2007-11-06 18:17 | BEAM
5681 | Stephens, Adrian | 115 | 3 | 9.17.3 | 165 | 63 | T | Y | 165.63 | 63 | 9.17.3 |  |  | Vinko Erceg |  |  | "The sounding frame types supported by the beamformee, staggered and/or NDP, shall be advertised the HT Capabilities element in frames that are transmitted by the beamformee." We're missing an article here. Regardless of grammar "shall be advertised" is a rather meaningless requirement. Clause 7 alread says how to set the fields of the HT Capabilities element, and it seems to me it allows no leaway that needs to be addressed by a normative behavioural statement here. | Either delete this sentence or change "shall be" to "are". |  | BEAM | Explicit TxBF |  | BEAM: 2007-11-06 18:16:59Z - Submission in January. |  |  |  | 2007-11-06 18:17 | BEAM
5682 | Stephens, Adrian | 115 | 3 | 9.17.3 | 166 | 27 | T | Y | 166.27 | 27 | 9.17.3 |  |  | Vinko Erceg |  |  | "that transmits a frame in response to a sounding PPDU or an NDP" Two problems: 1. "frame in response" suggests a MAC protocol such as RTS/CTS 2. An NDP is a sounding PPDU | Replace cited text with: "transmits a feedback frame in response to a sounding PPDU" |  | BEAM | Explicit TxBF |  | BEAM: 2007-11-06 18:16:59Z - Submission in January. |  |  |  | 2007-11-06 18:17 | BEAM
5683 | Stephens, Adrian | 115 | 3 | 9.17.3 | 166 | 27 | T | N | 166.27 | 27 | 9.17.3 |  |  | Vinko Erceg |  |  | This para should be moved down two (i.e. after the para reading: "A +HTC MPDU that contains a non-zero value of the CSI/Steering field and that has the NDP Announcement field set to 1 is a request for feedback based on the NDP that follows.") because it relates to beamformee behaviour and reads awkwardly in the current position. | Move para down 2 paras. |  | BEAM | Explicit TxBF |  | BEAM: 2007-11-06 18:16:59Z - Submission in January. |  |  |  | 2007-11-06 18:17 | BEAM
5684 | Stephens, Adrian | 115 | 3 | 9.17.3 | 166 | 47 | T | Y | 166.47 | 47 | 9.17.3 |  |  | Vinko Erceg |  |  | The response rules are confusing and inconsistent. It is not clear exactly what is a response to what. You have MPDU-level responses, you have the sounding PPDU/feedback response, you have the +HTC with CSI/Steering non-zero / feedback response too. And the "otherwise" on line 52 is an inscrutable gem. I think a precondition to all of these is "reception of a sounding PPDU", but that is not stated, and inconsistent with the "otherwise" clause which talks about delaying the response until after the NDP, so perhaps the "kickoff" event is intended to be reception of the +HTC with CSI/Steering set to a non-zero value. Also the rules, as written appear to disallow: RTS(NDP announce)/cts/NDP/feedback; which might be a really useful sequence. I think the rules would be simpler if it talks about reception of a sounding PPDU with an associated CSI/Steering value > 0 (where associated is defined as "in the current PPDU" for non-NDP, and "in the NDP Announcement" for NDP). | Rewrite with focus on the event (or combination of events) and the response |  | BEAM | Explicit TxBF |  | BEAM: 2007-11-06 18:16:59Z - Submission in January. |  |  |  | 2007-11-06 18:17 | BEAM
5685 | Stephens, Adrian | 115 | 3 | 9.17.3 | 166 | 58 | T | Y | 166.58 | 58 | 9.17.3 |  |  | Vinko Erceg |  |  | "If the immediate feedback capable beamformee cannot transmit an aggregated or immediate CSI/ Steering response in a SIFS time after the end of the received sounding packet, it may transmit the feedback response in an aggregate with an ACK or BA in the same TXOP" This is too broad. For example, this is true, even if the beamformee would not otherwise be transmitting an Ack or BA. | Constrain so that the feedback is aggregated with an Ack/BA only if an Ack/BA response frame is required. |  | BEAM | Explicit TxBF |  | BEAM: 2007-11-06 18:16:59Z - Submission in January. |  |  |  | 2007-11-06 18:17 | BEAM
5686 | Stephens, Adrian | 115 | 3 | 9.17.3 | 167 | 9 | T | Y | 167.09 | 9 | 9.17.3 |  |  | Vinko Erceg |  |  | "A beamformee transmitting delayed feedback response shall use an Action frame to send this information within a separate TXOP that is obtained using the highest priority AC (see 9.1.3.1)." This is either redundant with the rules for channel access for management frames (which is the case) or it contradicts those rules. | Change to informative language as this is redundant with the rules in 9.1.3.1. |  | BEAM | Explicit TxBF |  | BEAM: 2007-11-06 18:16:59Z - Submission in January. |  |  |  | 2007-11-06 18:17 | BEAM

## Explicit Quant
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
5273 | Erceg, Vinko | 115 | 3 | 20.3.11.2.2 | 295 | 50 | T | Y | 295.5 | 50 | 20.3.11.2.2 |  | W | Eldad Perahia | 11-07-2836-00-000n-beam-explicit-quant.doc |  | How the quantization is done needs to be explicitly stated. | delta = 2^(-Nb+1) if V is not equal to 1 Vq= floor(V/delta)*delta else Vq= 1-delta end | BEAM: 2007-12-20 18:38:16Z - Withdrawn by commenter; email copied below Date: Wed, 19 Dec 2007 15:45:26 -0800 Reply-To: Vinko Erceg <verceg@BROADCOM.COM> Sender: ***** IEEE stds-802-11-tgn List ***** <STDS-802-11-TGN@LISTSERV.IEEE.ORG> From: Vinko Erceg <verceg@BROADCOM.COM> Subject: Re: [802-11TGN] Beam ad hoc conference call 20071219 X-To: "Perahia, Eldad" <eldad.perahia@INTEL.COM> To: STDS-802-11-TGN@LISTSERV.IEEE.ORG List-Help: <http://listserv.ieee.org/cgi-bin/wa?LIST=STDS-802-11-TGN>, <mailto:LISTSERV@LISTSERV.IEEE.ORG?body=INFO%20STDS-802-11-TGN> List-Unsubscribe: <mailto:STDS-802-11-TGN-unsubscribe-request@LISTSERV.IEEE.ORG> List-Subscribe: <mailto:STDS-802-11-TGN-subscribe-request@LISTSERV.IEEE.ORG> List-Owner: <mailto:STDS-802-11-TGN-request@LISTSERV.IEEE.ORG> X-PMX-Version: 5.3.3.310218, Antispam-Engine: 2.5.2.311128, Antispam-Data: 2007.12.19.153558 X-OriginalArrivalTime: 19 Dec 2007 23:53:29.0259 (UTC) FILETIME=[5A9B67B0:01C8429A] --- This message came from the IEEE 802.11 Task Group N Technical Reflector --- Hi All, I withdraw my CID 5273 which is a part of the LB 115 Beamforming comment resolution process. Thanks and regards, Vinko.. | BEAM | Explicit Quant |  | BEAM: 2007-11-15 13:11:16Z - Defer until January BEAM: 2007-11-13 20:06:10Z - Defer until Thursday BEAM: 2007-11-06 18:17:40Z - Submission in January. |  |  |  | 2007-12-20 18:39 | BEAM

## Channel Sounding
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
5390 | Loc, Peter | 115 | 3 | 7.3.2.52.6 | 76 | 24-50 | T | N | 76.24 | 24 | 7.3.2.52.6 |  |  | Bjorn Bjerke | 11-07-2900-01-000n-channel-sounding-cid-5390.doc |  | The channel estimation capability definition for a device with both NDP and staggered receiving capabilities is vague. For example, if a 2-antenna device (not supporing STBC) can receive NDP with Nsts=3, but can only receive data carried in up to 2 spatial streams, setting this field equal to 2 implies that (3,0) or (3,1) can also be received, which is beyond the capability of the 2-antenna device. | Add a note saying that when staggered sounding is upported, this field should be explained by combining with Supported MCS Field and Rx STBC field. |  | BEAM | Channel Sounding | pre-motion | BEAM: 2007-11-15 13:54:49Z - Defer until telecon or Taipei BEAM: 2007-11-13 19:15:38Z - Defer to Thursday -- Hongyuan will provide text BEAM: 2007-11-06 15:51:18Z - Submission in November. |  |  |  | 2007-11-15 13:55 | BEAM
5393 | Loc, Peter | 115 | 3 | 9.17.2.4.3 | 163 | 21-26 | T | N | 163.21 | 21 | 9.17.2.4.3 |  |  | John Ketchum |  |  | This paragraph gives the restriction for maximum number of sounded dimensions during calibration exchange, when extensive Ht_LTFs is not supported by the recipient. The same requirement should also be added for sounding packets used for link adaptation, implicit TxBF exchange, explicit TxBF exchange, and antenna selection. | Add similar paragraphs in link adaptation, implicit TxBF exchange, explicit TxBF exchange, and antenna selection. |  | BEAM | Channel Sounding | [5 empty] | 2008-01-11 07:15 | BEAM

## Calibration
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
5392 | Loc, Peter | 115 | 3 | 9.17.2.4.2 | 161 | 51-54 | T | N | 161.51 | 51 | 9.17.2.4.2 |  |  | Yuichi Morioka |  |  | The requirements in this paragraph is only for calibration initiator, not for calibration responder. | modify as "A STA that claims as a calibration initiator (the Calibration subfield of the Transmit Beamforming Capabilities field is set to 3) …." |  | BEAM | Calibration |  | BEAM: 2007-11-06 14:56:35Z - Submission in January. |  |  |  | 2007-11-06 14:57 | BEAM
5846 | Yamaura, Tomoya | 115 | 3 | 9.17.2.4.2 | 161 | 61 | E | N | 161.61 | 61 | 9.17.2.4.2 |  |  | Yuichi Morioka |  |  | "the Calibration Position subfield of the HT Control field set to 1 or 3," This means misleading. It may meant that as a response to the frames that has Cal Position 1 or 3. But CSI request =1 with Cal position=3. | Remove "1" in the quoted sentence. Or reword it. |  | BEAM | Calibration |  | BEAM: 2007-11-06 21:15:50Z - Submission in January EDITOR: 2007-11-01 12:35:18Z - this looks like a technical change. Transferring to BEAM. |  |  |  | 2007-11-06 21:20 | BEAM
5847 | Yamaura, Tomoya | 115 | 3 | 9.17.2.4.2 | 162 | 2 | E | N | 162.02 | 2 | 9.17.2.4.2 |  |  | Yuichi Morioka |  |  | "the Calibration Position subfield set to 1 or 3," . It may meant that CSI report as a response to the frames that has Cal Position 1 or 3. But CSI request =1 with Cal position=3. | Remove "1 or" in the quoted sentence. Or reword it. |  | BEAM | Calibration |  | BEAM: 2007-11-06 21:16:28Z - Submission In January EDITOR: 2007-11-01 12:35:18Z - this looks like a technical change. Transferring to BEAM. |  |  |  | 2007-11-06 21:20 | BEAM
5670 | Stephens, Adrian | 115 | 3 | 9.17.2.4.3 | 164 | 11 | T | Y | 164.11 | 11 | 9.17.2.4.3 |  |  | Yuichi Morioka |  |  | "The Duration/ID field in the frame signaling calibration start shall cover the frame that contains the calibration sounding response (if it exists) plus two NDP frames plus the frame that signals calibration sounding complete and its ACK, plus the SIFS intervals that separate these PPDUs." I am concerned about finding a Duration/ID field rule in clause 9 that potentially conflicts with that in clause 7. For example, the rules for RTS say: "-- If the RTS is not part of a dual CTS exchange and if the NAV protection is desired for only the first or sole frame in the TXOP, the duration value is set to the estimated time, in microseconds, required to transmit the pending frame, plus one CTS frame, plus one ACK or BlockAck frame if required, plus any NDPs required, plus explicit feedback if required, plus three the SIFS intervals that precede these PPDUs. -- Otherwise, the duration value is set to the remaining duration of the TXOP." It is hard to read a calibration exchange consisting of 3 mpus and 2ndps as "sole or first" frame protection. So the default is "balance of txop". But this conflicts with the rule above. The only logical conclusion is that a calibration sequence cannot start with an RTS - contrary to figure 9-36. | A separate comment addresses the Duration/ID field value for an RTS frame. If that comment is accepted, review the material in 9.17.2.4.3 for consistency with the updated RTS rules. Otherwise, delete the cited text or find some other way of making it consistent with the RTS rules. |  | BEAM | Calibration |  | BEAM: 2007-11-06 14:56:35Z - Submission in January. |  |  |  | 2007-11-06 14:57 | BEAM
5671 | Stephens, Adrian | 115 | 3 | 9.17.2.4.3 | 164 | 20 | T | Y | 164.2 | 20 | 9.17.2.4.3 |  |  | Yuichi Morioka |  |  | "As determined by NDP rules a) or b) in 9.19.1 (NDP Rules), STA A shall send the first NDP as a sounding PPDU a SIFS after receiving the frame that signals calibration sounding response or a SIFS after transmitting the frame that signals calibration start if a MAC response is not implied by the frame that signals calibration start" As this sentence calls out, this is already determined by the NDP rules, so it is redundant. | Either remove it, or change "shall send" to "sends". |  | BEAM | Calibration |  | BEAM: 2007-11-06 14:56:35Z - Submission in January. |  |  |  | 2007-11-06 14:57 | BEAM
5672 | Stephens, Adrian | 115 | 3 | 9.17.2.4.3 | 164 | 31 | T | Y | 164.31 | 31 | 9.17.2.4.3 |  |  | Yuichi Morioka |  |  | "As determined by NDP rule d), STA B shall transmit a second NDP as a sounding PPDU a SIFS interval after receiving the first NDP." As this sentence calls out, this is already determined by the NDP rules, so it is redundant. | Either remove it, or change "shall transmit" to "transmits". |  | BEAM | Calibration |  | BEAM: 2007-11-06 14:56:35Z - Submission in January. |  |  |  | 2007-11-06 14:57 | BEAM
5673 | Stephens, Adrian | 115 | 3 | 9.17.2.4.4 | 164 | 53 | T | N | 164.53 | 53 | 9.17.2.4.4 |  |  | Yuichi Morioka |  |  | "The calibration initiator should abort the calibration sequence..." The meaning of "abort" needs to be unpacked. | add (i.e., does not transmit any further frames that are part of this calbration sequence) after the cited text. |  | BEAM | Calibration |  | BEAM: 2007-11-06 14:56:35Z - Submission in January. |  |  |  | 2007-11-06 14:57 | BEAM
5674 | Stephens, Adrian | 115 | 3 | 9.17.2.4.4 | 164 | 55 | T | Y | 164.55 | 55 | 9.17.2.4.4 |  |  | Yuichi Morioka |  |  | "is not received correctly within the expected time." Lazy. What is the expected time? How is failure to receive a PPDU detected? Same comment in 164.60. | Relate to some kind of timeout. May need language similar to AckTimeout. |  | BEAM | Calibration |  | BEAM: 2007-11-06 14:56:35Z - Submission in January. |  |  |  | 2007-11-06 14:57 | BEAM
5675 | Stephens, Adrian | 115 | 3 | 9.17.2.4.4 | 164 | 56 | T | N | 164.56 | 56 | 9.17.2.4.4 |  |  | Yuichi Morioka |  |  | "If the calibration initiator aborts the calibration sequence, it may re-start the calibration sequence with a value of the Calibration Sequence in the Calibration Control subfield of the HT Control field which is different from the value used in the aborted sequence." There's nothing to stop it doing this already, because once the sequence is aborted, it no longer exists, and the calibration initiator can always start a sequence. And 164.3 requires any new sequence to have an incremented sequence number - so one could argue that the "may" above is in conflict because it is broader - i.e. "different" vs "increment". | change "may" -> "can" (i.e. makes the text informative). change "different" -> "different (i.e., incremented)" |  | BEAM | Calibration |  | BEAM: 2007-11-06 14:56:35Z - Submission in January. |  |  |  | 2007-11-06 14:57 | BEAM
5170 | Chu, Liwen | 115 | 3 | 9.17.2.4.4 | 164 | 60 | T | Y | 164.6 | 60 | 9.17.2.4.4 |  |  | Yuichi Morioka |  |  | The calibration responder should also abort the calibration the calibration sequence if calibration procedure with NDP is used and the NDP1 is not received from the calibration initiator within expected time. | Change the sentence accordingly. |  | BEAM | Calibration |  | BEAM: 2007-11-06 14:56:35Z - Submission in January. |  |  |  | 2007-11-06 14:57 | BEAM
5676 | Stephens, Adrian | 115 | 3 | 9.17.2.4.4 | 165 | 15 | T | Y | 165.15 | 15 | 9.17.2.4.4 |  |  | Yuichi Morioka |  |  | "may ignore the request." Which request - the original one or the later one? | Disambiguate. |  | BEAM | Calibration |  | BEAM: 2007-11-06 14:56:35Z - Submission in January. |  |  |  | 2007-11-06 14:57 | BEAM

## Beam November Motion #1
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
5153 | Chu, Liwen | 115 | 3 | 7.3.1.29 | 47 | 37 | E | Y | 47.37 | 37 | 7.3.1.29 |  | R | Joonsuk Kim, Hongyuan Zhang | 11-07-2848-00-000n-explicit-txbf-cids-5153-5174-and-5175.doc |  | I guess that set 1 for Nb=2 in Table 7-25a is not correct. | Set 1 for Nb=5 | BEAM: 2007-11-15 13:59:54Z Reject - as in 11-07/2848r0 | BEAM | Beam November Motion #1 |  | EDITOR: 2007-10-29 11:14:22Z - Transferred to PHY as this looks like a technical change. PHY--This is actually a BEAM comment. |  |  |  | 2007-11-15 15:09 | BEAM
5175 | de Courville, Marc | 115 | 3 | 7.3.1.30 | 48 | 48 | T | N | 48.48 | 48 | 7.3.1.30 |  | R | Joonsuk Kim, Hongyuan Zhang | 11-07-2848-00-000n-explicit-txbf-cids-5153-5174-and-5175.doc |  | The following metric is used for PHY performance indicator: "SNR_average is the dB representation of linearly averaged values over the tones". This metric is a poor PHY performance abstraction metric since when deep attenuations occur the strong negative SNR values are predominent in the averaging result and is not representing the throughput achievable on the channel. | Replace the SNR averaging in dB by the standard one in terms of information theory being the effective SNR representing the averaging of Shanon capacity: i.e. 10log10(2^(SUM(log2(1+SNR))/Nb_carriers-1)) in dB. With this one if a strong attenuation occurs it yields a 0 throughput and thus do not penalizes the overall averaging and provides a much better PHY performance indicator. | BEAM: 2007-11-15 14:06:08Z Reject - as in 11-07/2848r0 | BEAM | Beam November Motion #1 | [5 empty] | 2007-11-15 15:09 | BEAM
5513 | Scarpa, Vincenzo | 115 | 3 | 7.3.2.52.5 | 73 | 31-32 | E | N | 73.31 | 31 | 7.3.2.52.5 |  | C | Bjorn Bjerke | 11-07-2719-00-000n-lb115-beam-comment-resolutions-link-adaptation.doc |  | According to the resolution to CID 1876 of LB97, the text related to the value 3 in the MCS feedback field means that the station supports at least one of the MCS feedback policies described in section 9.16.1. If my interpretation is correct I would suggest to use a more explicit sentence. | Replace the text with: "Set to 3 if the STA supports at least one of the MCS feedback policies as described in clause 9.16.1" | BEAM: 2007-11-13 19:27:02Z Counter - as in 11-07/2719r0 | BEAM | Beam November Motion #1 |  | BEAM: 2007-11-06 15:51:18Z - Submission in November. EDITOR: 2007-10-31 12:50:49Z - Transferred to Beam. In my view the text is quiet clear, it is set to 3 when the STA supports *both* policies. The proposed change ends up with the equivalent of "at least one of the policies - but I won't tell you which". Transferring as this is, as far as I can tell, asking for a technical change. |  |  |  | 2007-11-15 15:09 | BEAM
5658 | Stephens, Adrian | 115 | 3 | 9.16.2 | 155 | 9 | T | N | 155.09 | 9 | 9.16.2 |  | A | Bjorn Bjerke | 11-07-2719-00-000n-lb115-beam-comment-resolutions-link-adaptation.doc |  | "If the HT Control field is included in more than one +HTC frame within the same PPDU, the MRQ field and the MSI field in each +HTC frame shall be set to the same value." This is unnecessary given 118.54: "The HT Control field of all MPDUs containing the HT Control field aggregated in the same A-MPDU shall be set to the same value." | Delete first cited sentence. | BEAM: 2007-11-13 19:29:07Z Accept as in 11-07/2719r0 | BEAM | Beam November Motion #1 |  | BEAM: 2007-11-06 15:51:18Z - Submission in November. |  |  |  | 2007-11-15 15:09 | BEAM
5845 | Yamaura, Tomoya | 115 | 3 | 9.16.2 | 155 | 9 | T | N | 155.09 | 9 | 9.16.2 |  | A | Bjorn Bjerke | 11-07-2719-00-000n-lb115-beam-comment-resolutions-link-adaptation.doc |  | From line-9 to line-13, there is a description how to do with multiple HTC in an A-MPDU. However, now we have a general rule for it in 9.7a (page-118, line 51~55) that is not included in D2.0. So, the sentence here is not necessary, I think. | Remove "If the HT Control field is included in more than one +HTC frame within the same PPDU, the MRQ field and the MSI field in each +HTC frame shall be set to the same value." | BEAM: 2007-11-13 19:28:45Z Accept as in 11-07/2719r0 | BEAM | Beam November Motion #1 |  | BEAM: 2007-11-06 15:51:18Z - Submission in November. |  |  |  | 2007-11-15 15:09 | BEAM
5834 | Vlantis, George | 115 | 3 | 9.16.2 | 155 | 15 | T | Y | 155.15 | 15 | 9.16.2 |  | R | Bjorn Bjerke | 11-07-2756-00-000n-lb115-beam-comment-resolutions-channel-sounding.doc |  | Sounding Packets: Sounding Packets can be sent with either of options: staggered sounding PPDU or NDP. Having both risks imcompatiibilities and undue complexity on the beamformee (if it wants to take advantage of both type of beamformers.) | Remove the staggered sounding packet option. | BEAM: 2007-11-13 19:16:42Z Reject - as in 11-07/2756r0 | BEAM | Beam November Motion #1 |  | BEAM: 2007-11-06 15:51:18Z - Submission in November. |  |  |  | 2007-11-15 15:09 | BEAM
5391 | Loc, Peter | 115 | 3 | 9.16.2 | 155 | 15 | T | Y | 155.15 | 15 | 9.16.2 |  | C | Bjorn Bjerke | 11-07-2719-02-000n-lb115-beam-comment-resolutions-link-adaptation.doc |  | There is no reason to send MRQ=1 in HTC with a non-sounding PPDU | change "should" to "shall", or add informative text explaining in what condition MRQ is sent in non-sounding PPDU | BEAM: 2007-11-15 13:22:45Z Counter - as in 11-07/2719r2 | BEAM | Beam November Motion #1 | D | BEAM: 2007-11-13 19:31:41Z - Defer until thursday BEAM: 2007-11-06 15:51:18Z - Submission in November. |  |  |  | 2007-11-15 15:09 | BEAM
5660 | Stephens, Adrian | 115 | 3 | 9.16.2 | 155 | 55 | T | N | 155.55 | 55 | 9.16.2 |  | A | Bjorn Bjerke | 11-07-2719-00-000n-lb115-beam-comment-resolutions-link-adaptation.doc |  | "On receipt of a +HTC frame with the MRQ field set to 1, the MFB responder initiates computation of the MCS estimate and associates the result of this computation with the MSI value" There's something not quite right here when the frame carrying the MRQ is an NDP announcement. | Replace with: "On receipt of a +HTC frame with the MRQ field set to 1, the MFB responder initiates computation of the MCS estimate based on the associated sounding PPDU and labels the result of this computation with the MSI value" | BEAM: 2007-11-13 19:33:41Z Accept as in 11-072719r0 | BEAM | Beam November Motion #1 |  | BEAM: 2007-11-06 15:51:18Z - Submission in November. |  |  |  | 2007-11-15 15:09 | BEAM
5663 | Stephens, Adrian | 115 | 3 | 9.16.2 | 156 | 42 | T | N | 156.42 | 42 | 9.16.2 |  | C | Bjorn Bjerke | 11-07-2719-02-000n-lb115-beam-comment-resolutions-link-adaptation.doc |  | "then it should use those matrices reported in Noncompressed Beamforming frame or a Compressed Beamforming frame with recommended MCS which is associated with it" It is not clear if this is a constraint on the EXPANSION_MAT parameter, or the MCS parameter or both. | Rephrase in terms of TXVECTOR parameters and remove the ambiguity. | BEAM: 2007-11-15 13:21:21Z Counter - as in 11-07/2719r2 | BEAM | Beam November Motion #1 | D | BEAM: 2007-11-13 19:39:33Z - Defer until Thursday BEAM: 2007-11-06 15:51:18Z - Submission in November. |  |  |  | 2007-11-15 15:09 | BEAM
5664 | Stephens, Adrian | 115 | 3 | 9.16.2 | 156 | 47 | T | N | 156.47 | 47 | 9.16.2 |  | C | Bjorn Bjerke | 11-07-2719-02-000n-lb115-beam-comment-resolutions-link-adaptation.doc |  | The inserted text has disturbed the logical order of this subcaluse. In line 41 we stop talking about the responder and talk about subsequent use of the response. Then in line 47 we start talking about the response again. | Move the sentence starting at line 41 into its own para at the end of this subclause. | BEAM: 2007-11-15 13:21:47Z Counter - as in 11-07/2719r2 | BEAM | Beam November Motion #1 | D | BEAM: 2007-11-13 19:41:55Z - defer until thursday BEAM: 2007-11-06 15:51:18Z - Submission in November. |  |  |  | 2007-11-15 15:09 | BEAM
5668 | Stephens, Adrian | 115 | 3 | 9.17.2.1 | 159 | 21 | T | N | 159.21 | 21 | 9.17.2.1 |  | A | John Ketchum | 11-07-2735-00-000n-proposed-resolutions-to-implicit-CIDs.doc |  | "the maximum expected number of ELTFs with its response." I think this statement ignores NDP sounding. | Replace with: "the longest valid sounding PPDU with its response". | BEAM: 2007-11-13 20:13:34Z Accept as per 11-07/2735r0 | BEAM | Beam November Motion #1 |  | BEAM: 2007-11-07 18:24:03Z - Submission in November. |  |  |  | 2007-11-15 15:09 | BEAM
5527 | Scarpa, Vincenzo | 115 | 3 | 9.17.3 | 166 | 27-31 | T | N | 166.27 | 27 | 9.17.3 |  | C | Bjorn Bjerke | 11-07-2756-00-000n-lb115-beam-comment-resolutions-channel-sounding.doc |  | Is there any technical reason to impose a sounding frame format for the CSI/Steering feedback information? I do not see any problem in allowing also regular (i.e. non-sounding) action frames to be used for the same purpose. | Allow the use of non-sounding action frames for CSI/Steering feedback purpose. | BEAM: 2007-11-13 19:20:33Z Counter - as in 11-07/2756r0 | BEAM | Beam November Motion #1 |  | BEAM: 2007-11-06 15:51:18Z - Submission in November. |  |  |  | 2007-11-15 15:09 | BEAM
5394 | Loc, Peter | 115 | 3 | 9.18.2 | 168 | 1-4 | T | N | 168.01 | 1 | 9.18.2 |  | C | Hongyuan Zhang, Andy Molisch | 11-07-2770-01-000n-lb115-asel-cids.doc |  | The requirements in this paragraph is only for ASEL initiator that supports Explicit CSI Feedback Tx ASEL. The statement here is vague. | Change as "A STA that supports explicit Csi feedback based Tx ASEL …." | BEAM: 2007-11-13 18:45:15Z Counter - as per 11-07/2770R1 | BEAM | Beam November Motion #1 | [5 empty] | 2007-11-15 15:09 | BEAM
5688 | Stephens, Adrian | 115 | 3 | 9.18.2 | 168 | 15 | T | N | 168.15 | 15 | 9.18.2 |  | A | Hongyuan Zhang, Andy Molisch | 11-07-2770-01-000n-lb115-asel-cids.doc |  | "A single sounding PPDU is transmitted over one antenna set;" This is confusing, following on from a description of "sends out consecutive sounding PPDUs" | Replace with "Each sounding PPDU is ..." | BEAM: 2007-11-13 18:46:49Z Accept As per 11-07/2770R1 | BEAM | Beam November Motion #1 | [5 empty] | 2007-11-15 15:09 | BEAM
5690 | Stephens, Adrian | 115 | 3 | 9.18.2 | 169 | 30 | T | Y | 169.3 | 30 | 9.18.2 |  | C | Hongyuan Zhang, Andy Molisch | 11-07-2770-01-000n-lb115-asel-cids.doc |  | "The receiver shall notify the transmitter that the ASEL feedback is stale by transmitting a +HTC MPDU with the MAI subfield set to ASELI and the ASEL Command subfield set to No feedback, ASEL training failure and the ASEL Data subfield set to zero." This is too broad, because there is no guard or condition - i.e., an ASEL receiver must always do this. | Replace with: "An ASEL receiver that determines that the ASEL feedback is stale shall notify the ASEL transmitter by transmitting a +HTC MPDU with the MAI subfield set to ASELI and the ASEL Command subfield set to No feedback, ASEL training failure and the ASEL Data subfield set to zero." | BEAM: 2007-11-13 18:55:11Z Counter - as in 11-07/2770r1 | BEAM | Beam November Motion #1 | [5 empty] | 2007-11-15 15:09 | BEAM
5691 | Stephens, Adrian | 115 | 3 | 9.18.2 | 169 | 34 | E | N | 169.34 | 34 | 9.18.2 |  | C | Hongyuan Zhang, Andy Molisch | 11-07-2770-01-000n-lb115-asel-cids.doc |  | The terms ASEL transmitter and ASEL receiver we introduced last time round, but the new material in this section doesn't use these terms. | Replace transmitter and receiver in this subclause with the appropriate terms. Also use these terms in the figures in this subclause. | BEAM: 2007-11-13 18:51:59Z Counter - countered as in 11-07/2770r1 | BEAM | Beam November Motion #1 |  | EDITOR: 2007-11-01 12:46:05Z - transferring to Beam. Note CID 5588 has replaced ASEL in these terms with "antenna selection". I think we actually need 4 terms: ASEL {transmitter¦receiver¦initiator¦responder}, or perhaps just the latter two. The problem is that the two ends of, say, a TXASSI exchange are an "antenna selection transmitter" and a "receiver" (not an antenna selection receiver). This gives rise to the following "then when the receiver transmits a response to the training sequence". "when the receiver transmits" is clearly oxymoronic. Note there are also uses of ASEL {initiator¦responder} in Clause 7 and the MIB. We need a review and a correct assignment of whatever terminology we come with throughout 9.18. This probably exceeds editorial license. |  |  |  | 2007-11-15 15:09 | BEAM
5693 | Stephens, Adrian | 115 | 3 | 9.18.2 | 170 | 58 | T | Y | 170.58 | 58 | 9.18.2 |  | C | Hongyuan Zhang, Andy Molisch | 11-07-2770-01-000n-lb115-asel-cids.doc |  | "When both transmitter and receiver have antenna selection capabilities, the peer station shall use a fixed subset of its antennas to receive or transmit the consecutive sounding PPDUs in the training processes defined in Figure 9-37 (Transmit antenna selection) and Figure 9-38 (Receive antenna selection)." The meaning of "peer STA" is unclear. And how can you have a normative requirement for your peer? | Replace with something like: "When acting as an ASEL receiver in transmit antenna selection, a STA shall use a fixed subset of antennas to receive all the sounding PPDUs an an ASEL sounding sequence. When acting as an ASEL transmitter in receive antenna selection, a STA shall use a fixed subset of antennas to transmit all the sounding PPDUs an an ASEL sounding sequence." | BEAM: 2007-11-13 18:58:46Z Counter - as in 11-07/2770r1 | BEAM | Beam November Motion #1 | [5 empty] | 2007-11-15 15:09 | BEAM
5696 | Stephens, Adrian | 115 | 3 | 9.19.1 | 171 | 27 | T | Y | 171.27 | 27 | 9.19.1 |  | A | John Ketchum | 11-07-2739-00-000n-proposed-resolutions-to-NDP-CIDs.doc |  | "A STA shall set the SOUNDING parameter of the TXVECTOR to SOUNDING in the PHY-TXSTART.request primitive corresponding to an NDP transmission to indicate that this PPDU is a sounding PPDU." This is redundant with 172.43: "A STA that transmits an NDP shall set the LENGTH, MCS, SOUNDING and NUM_EXTEN_SS parameters of the TXVECTOR as specified in this subclause. -- LENGTH shall be set to 0. -- SOUNDING shall be set to SOUNDING. -- MCS shall indicate two or more spatial streams." | Delete the first cited text. | BEAM: 2007-11-15 14:11:29Z Accept is in 11-07/2739r0 | BEAM | Beam November Motion #1 | [5 empty] | 2007-11-15 15:09 | BEAM
5697 | Stephens, Adrian | 115 | 3 | 9.19.1 | 171 | 41 | T | Y | 171.41 | 41 | 9.19.1 |  | A | John Ketchum | 11-07-2739-00-000n-proposed-resolutions-to-NDP-CIDs.doc |  | "The value of the Duration field of the NDP announcement frame shall be no less than the combined durationof the expected response frame (if any), the SIFS interval preceding the expected response frame, the NDP transmissions and the additional SIFS(s) that precede each NDP transmission." We already have rules for the duration field setting that comprehends the possible presence of NDP frames. Surely this is redundant. If it is not redundant, it should be merged with the logic of the Duration/ID field description in clause 7. | Remove the quoted text. | BEAM: 2007-11-15 14:17:36Z Accept as in 11-07/2739r0 | BEAM | Beam November Motion #1 | [5 empty] | 2007-11-15 15:09 | BEAM
5699 | Stephens, Adrian | 115 | 3 | 9.19.1 | 172 | 37 | T | Y | 172.37 | 37 | 9.19.1 |  | A | John Ketchum | 11-07-2739-00-000n-proposed-resolutions-to-NDP-CIDs.doc |  | "Feedback information generated from the reception of an NDP shall be transmitted using any of the feedback rules and signaling as appropriate, e.g., immediate or delayed." The rules for feedback suffice to generate this behaviour by themselves. | "shall be" -> "is" | BEAM: 2007-11-15 14:19:51Z Accept as in 11-07/2739r0 | BEAM | Beam November Motion #1 | [5 empty] | 2007-11-15 15:09 | BEAM
5174 | de Courville, Marc | 115 | 3 | 20.2.2 | 235 | 55 | T | N | 235.55 | 55 | 20.2.2 |  | R |  | 11-07-2848-00-000n-explicit-txbf-cids-5153-5174-and-5175.doc |  | Table 20-1 (TX Vector RX Vector parameters) requests for the SNR part to report an average of the SNR values in dB over the tones. When deep attenuations in the frequency domain occur this results in large negative SNR values which become predominent in the averaging result and yields to a very poor accuracy performance indicator. | Replace the SNR averaging in dB by the standard one in terms of information theory being the effective SNR representing the averaging of Shanon capacity: i.e. 10log10(2^(SUM(log2(1+SNR))/Nb_carriers-1)) in dB. With this one if a strong attenuation occurs it yields a 0 throughput and thus do not penalizes the overall averaging and provides a much better PHY performance indicator. | BEAM: 2007-11-15 14:06:33Z Reject - as in 11-07/2848r0 | BEAM | Beam November Motion #1 | [5 empty] | 2007-11-15 15:09 | BEAM
5530 | Siti, Massimiliano | 115 | 3 | 20.3.11 | 290 onwards | All | T | Y | 290.31 | 31 | 20.3.11 |  | R | John Ketchum |  |  | There is a proliferation of options regarding beamforming. This will make difficult to guarantee interoperability among different vendors, as also witnessed by the discussions ongoing in WFA. I move to keep implicit beamforming, and explicit beamforming limitedly to full CSI feedback (20.3.11.2.1). | Simplify this section by removing the non-compressed and compressed beamforming matrix feedback options, and amend the draft consequently. | BEAM: 2007-11-15 14:34:45Z Reject - Explicit beamforming is useful in a number of situations, including in the case where a device has different numbers of transmit and receive chains. Keeping only CSI feedback will reduce efficiency in this case. | BEAM | Beam November Motion #1 | [5 empty] | 2007-11-15 15:09 | BEAM
5325 | Gallizio, Edoardo | 115 | 3 | 20.3.11 | 290 onwards | All | T | Y | 290.31 | 31 | 20.3.11 |  | R | John Ketchum |  |  | There is currently a proliferation of options regarding all the "spatial mapping" categories, including both spatial expansion methods and beamforming. This will make difficult to guarantee interoperability among different vendors. I move to keep implicit beamforming, and explicit beamforming limitedly to full CSI feedback (20.3.11.2.1). | Simplify this section by removing the non-compressed and compressed beamforming matrix feedback options, and amend the draft consequently. | BEAM: 2007-11-15 14:37:05Z Reject - Explicit beamforming is useful in a number of situations, including in the case where a device has different numbers of transmit and receive chains. Keeping only CSI feedback will reduce efficiency in this case. | BEAM | Beam November Motion #1 | [5 empty] | 2007-11-15 15:09 | BEAM
5833 | Vlantis, George | 115 | 3 | 20.3.11.1 | 291 | 29 | T | Y | 291.29 | 29 | 20.3.11.1 |  | R | John Ketchum |  |  | Implicit Beamforming: Both Implicit and Explicit Beamforming are options in the standard. Having both risks imcompatibilities and undue complexity on the beamformee (if it wants to take advantage of both types of beamformers). | Remove implicit beamforming from the draft. | BEAM: 2007-11-15 14:39:43Z Reject - Implicit beamforming is useful in a number of situations. For example, no explicit feedback is required, thus reducing overhead in most situations. | BEAM | Beam November Motion #1 | [5 empty] | 2007-11-15 15:09 | BEAM
5389 | Loc, Peter | 115 | 3 | 20.3.11.1 | 291 | 52-56 | T | Y | 291.52 | 52 | 20.3.11.1 |  | C | John Ketchum | 11-07-2735-00-000n-proposed-resolutions-to-implicit-CIDs.doc |  | This paragraph says that for bidirectional implicit TxBF, Q_k in a sounding PPDU has to be of full row-rank, so Nsts+Ness = Ntx. But there is no text stating a similar requirement for unidirectional implicit TxBF, i.e.the (unsteered) sounding PPDU sent from the beamformee should sound the full channel dimentionality (Nrx). Furthermore, a similar statement should be added for the Q_k used for the sounding PPDU sent by the calibration responder during the calibration exchange | Modify as "NOTE-In order for the recipient of the sounding to compute steering matrices when steered or unsteered sounding is used, the spatial mapping matrices should …..", and add a similar Note in clause 20.3.12.2 (sounding PPDU for calibration) | BEAM: 2007-11-13 20:19:43Z Counter - as in 11-07/2735r0 | BEAM | Beam November Motion #1 |  | BEAM: 2007-11-07 18:24:03Z - Submission in November. |  |  |  | 2007-11-15 15:09 | BEAM
5058 | Chan, Douglas | 115 | 3 | 20.3.11.1 | 292 | 26-40 | T | Y | 292.26 | 26 | 20.3.11.1 |  | C | John Ketchum | 11-07-2735-00-000n-proposed-resolutions-to-implicit-CIDs.doc |  | Illustrate where is H_tilda relative to the figure here (Fig 20-15). | Illustrate where is H_tilda relative to the figure here (Fig 20-15). | BEAM: 2007-11-13 20:22:16Z Counter - accept figure given in 11-07/2735r0 | BEAM | Beam November Motion #1 |  | BEAM: 2007-11-07 18:24:03Z - Submission in November. |  |  |  | 2007-11-15 15:09 | BEAM
5777 | Stephens, Adrian | 115 | 3 | 20.3.11.2.1 | 294 | 7 | T | N | 294.07 | 7 | 20.3.11.2.1 |  | A | Eldad Perahia | 11-07-2836-00-000n-beam-explicit-quant.doc |  | "shall be decoded" - there's already a "shall be" in the previous line that covers all these steps. | "shall be" -> are | BEAM: 2007-11-13 19:46:45Z Accept as in 11-07/2836r0 | BEAM | Beam November Motion #1 |  | BEAM: 2007-11-06 18:17:40Z - Submission in January. |  |  |  | 2007-11-15 15:09 | BEAM
5061 | Chan, Douglas | 115 | 3 | 20.3.11.2.1 | 295 | 4-8 | T | Y | 295.04 | 4 | 20.3.11.2.1 |  | R | Eldad Perahia | 11-07-2836-00-000n-beam-explicit-quant.doc |  | The linear value of M_H(k) corresponding to (20-78) should be the min of what's written there and 10^(7/20). | The linear value of M_H(k) corresponding to (20-78) should be the min of what's written there and 10^(7/20). | BEAM: 2007-11-13 20:06:57Z Reject - as per 11-07/2836r0 | BEAM | Beam November Motion #1 |  | BEAM: 2007-11-06 18:17:40Z - Submission in January. |  |  |  | 2007-11-15 15:09 | BEAM
5258 | Erceg, Vinko | 115 | 3 | 20.3.11.2.2 | 295 | 30 | T | Y | 295.3 | 30 | 20.3.11.2.2 |  | A | Eldad Perahia | 11-07-2836-00-000n-beam-explicit-quant.doc |  | "In non-compressed beamforming matrix feedback, the beamformee removes the space-time.." there should be a "shall" statement in this sentence. | Write: "In non-compressed beamforming matrix feedback, the beamformee shall remove the space-time.. | BEAM: 2007-11-13 19:52:28Z Accept as in 11-07/2836r0 | BEAM | Beam November Motion #1 |  | BEAM: 2007-11-06 18:17:40Z - Submission in January. |  |  |  | 2007-11-15 15:09 | BEAM
5832 | Vlantis, George | 115 | 3 | 20.3.11.2.3 | 295 | 61 | T | Y | 295.61 | 61 | 20.3.11.2.3 |  | R | John Ketchum |  |  | Simplify Explicit Beamforming: Both Non-Compressed and Compressed forms of CSI feedback are optional. The risk of having multiple options that are incompatible is that perhaps neither will be widely accepted in the marketplace. To avoid the risk, one would have to implement both and suffer the complexity of both (and one would also have to factor in implicit beamforming, as well). (This comment seems similar to CID 2969 for LB97, except the reason for rejection by 11-07/0666r0 has been removed.) | Removed compressed CSI feeback from the draft. | BEAM: 2007-11-15 14:41:33Z Reject - there is no compressed CSI feedback in the draft. | BEAM | Beam November Motion #1 | [5 empty] | 2007-11-15 15:09 | BEAM
5259 | Erceg, Vinko | 115 | 3 | 20.3.11.2.3 | 295 | 64 | T | Y | 295.64 | 64 | 20.3.11.2.3 |  | A | Eldad Perahia | 11-07-2836-00-000n-beam-explicit-quant.doc |  | "In compressed beamforming matrix feedback, the beamformee removes the space.." there should be a "shall" statement in this sentence. | Write: "In compressed beamforming matrix feedback, the beamformee shall remove the space.." | BEAM: 2007-11-13 19:52:49Z Accept as in 11-07/2836r0 | BEAM | Beam November Motion #1 |  | BEAM: 2007-11-06 18:17:40Z - Submission in January. |  |  |  | 2007-11-15 15:09 | BEAM
5062 | Chan, Douglas | 115 | 3 | 20.3.11.2.2 | 296 | 7 | T | Y | 296.07 | 7 | 20.3.11.2.3 |  | R | Eldad Perahia | 11-07-2836-00-000n-beam-explicit-quant.doc |  | Should we keep the notation and say "per subcarrier" rather than "per tone"? | Change "per tone" to "per subcarrier". | BEAM: 2007-11-13 19:54:10Z Reject - as per 11-07/2836r0 | BEAM | Beam November Motion #1 |  | BEAM: 2007-11-06 18:17:40Z - Submission in January. |  |  |  | 2007-11-15 15:09 | BEAM
5779 | Stephens, Adrian | 115 | 3 | 20.3.11.2.3 | 298 | 28 | T | Y | 298.28 | 28 | 20.3.11.2.3 |  | A | Eldad Perahia | 11-07-2836-00-000n-beam-explicit-quant.doc |  | "shall be quantized as described in 7.4.8.8 (Compressed Beamforming frame format)." | Quantization is described in the MAC, and is presumably done in the MAC, having received the compressed beamforming matrices through the abstract interface with arbitrary precision. Putting a normative requirement inside the PHY is not in accord with this architecture. If we need to say anything here, it should be informative. Replace with: "are quantized by the MAC as described in 7.4.8.8 (Compressed Beamforming frame format)." | BEAM: 2007-11-13 19:58:58Z Accept as in 11-07/2836r0 | BEAM | Beam November Motion #1 |  | BEAM: 2007-11-06 18:17:40Z - Submission in January. |  |  |  | 2007-11-15 15:09 | BEAM
5261 | Erceg, Vinko | 115 | 3 | 20.2.12.3 | 300 | 44 | T | Y | 300.44 | 44 | 20.3.12.3 |  | C | Bjorn Bjerke | 11-07-2756-00-000n-lb115-beam-comment-resolutions-channel-sounding.doc |  | "If the requesting STA A sends an MCS request in a PPDU that uses fewer space time streams in the data portion than are available on the channel, the channel.." What does "available on the channel mean"? Make it more clear. | As in comment. | BEAM: 2007-11-13 19:22:53Z Counter - as in 11-07/2756r0 | BEAM | Beam November Motion #1 |  | BEAM: 2007-11-06 15:51:18Z - Submission in November. |  |  |  | 2007-11-15 15:09 | BEAM