## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-07-2749r0
Venue Date: | Nov 2007
First Author: | Ganesh Venkatesan (Intel Corporation)
Subject: | TGk Sponsor Ballot Resolutions
Full Date: | 2007-10-09
Author(s): | Ganesh Venkatesan (Intel Corporation)
Intel Corporation
2111NE 25th Ave, Hillsboro, OR 97124
| Phone: | +1 503 334 6720
Fax:
| email: | ganesh.venkatesan@intel.com
Abstract:
This spreadsheet holds the resolutions drafted by the CR group for CIDs #39, #76, #79 and #81 from the 1st Recirculation Sponsor Ballot comments.

## comments
Comment ID | Date | Comment # | Name | Email | Phone | Style | Index # | Classification | Vote | Category | Page | Subclause | Line | Comment | File | Must Be Satisfied | Proposed Change | Resolution Status | Resolution Detail | Other1 | Other2 | Other3
3276100023 | 10/04/2007 23:04:33 EDT | 184 | Engwer, Darwin A | dengwer@nortel.com | 408-495-2588 | Individual | 9 | Producer | Disapprove | Editorial | 2 | 3.16a | 25 | The added new definition for BSS transition is inconsistent with the well known legacy definition in IEEE Std. 802.11-2007 clause 5.4.2.1.b. |  | Yes | Correct the new definition to align with the existing definition in clause 5.4.2.1.b | O | PROPOSED ACCEPT IN PRINCIPLE. P2L22: Replace "another BSS" with "another BSS in the same ESS." Add two new definitions: "ESS Transition: A STA movement from one BSS in one ESS to another BSS in a different ESS." , "service transition: A STA movement fro | Kwak
3276000023 | 10/04/2007 23:01:38 EDT | 183 | Engwer, Darwin A | dengwer@nortel.com | 408-495-2588 | Individual | 8 | Producer | Disapprove | Technical | 127 | 11.10.3 | 35 | The added text addresses the issue of measurement activity load on a STA that receives measurement requests, but does not adequately address the point raised in SB01-CID 230 (or LB78-CID-957). The volume of measurement requests issued by a transmitting/ requesting station must be duty cycle limited in some way in order to avoid complete domination of the available network air time by measurement requests, especially in environments with hundreds or thousands of colocated STAs. |  | Yes | Add some mechanism to allow the duty cycle of measurements to be controlled wrt real data laden traffic. | O | PROPOSED REJECT. The issue is not the % of wireless capacity or STA capacity used by radio measurements, it is to consider each STA’s service load, power state and operating conditions. The AP has to consider traffic load and application requirements, regulatory requirements and specific measurement states from every STA in support of wireless network management. Guidelines and limits would have to consider regulatory requirements like 4 msec carrier sense and the detection of one microsecond radar pulses in Japan. There are no typical scenarios that describe 802.11 operation in all bands in most circumstances. Off-channel measurements are desireable to gather timely information about which channel to switch BSS operation to, and the noiser the operating environment, the more urgent the need for radio measurements off the serving channel. In any case, the STA can refuse any measurement request. We are unable to support a limit to measurements which precludes ‘normal’ 802.11 operation in a noisy environment, where collisions cause many retries. | Ecclesine
3275900023 | 10/04/2007 22:59:56 EDT | 182 | Engwer, Darwin A | dengwer@nortel.com | 408-495-2588 | Individual | 7 | Producer | Disapprove | Technical | 170 | Annex D | 1 | Missing mib definition for dot11MeasurementPilotCapability. |  | Yes | Add a mib definition for dot11MeasurementPilotCapability. Include all the value enumerations from table 11-11 on page 143. (alternatively this may instead belong in Annex Q) | O | PROPOSED ACCEPT IN PRINCIPLE. MIB definitions updated. See 2665/r0. Table 11-11 is left in Clause 11.10 for the sake of clarity. | Ganesh
3275800023 | 10/04/2007 22:57:38 EDT | 181 | Engwer, Darwin A | dengwer@nortel.com | 408-495-2588 | Individual | 6 | Producer | Disapprove | Editorial | 143 | 11.10.11 | 10 | Values of mib objects are typically not detailed in the operational clauses of the standard. |  | Yes | Move table 11-11 to the appropriate section of Annex D (or Annex Q as appropriate). | O | PROPOSED REJECT. Since the dot11MeasurementPilotCapability requires a detailed description and the sub-clauses of 11.10.11 refer to the description while describing the Measurement Pilot generation procedure. Having the table in 11.10.11 makes it easier for the reader to understand the settings. In the interest of clarity, this description deviates from the norm. | Ganesh
3275700023 | 10/04/2007 22:56:49 EDT | 180 | Engwer, Darwin A | dengwer@nortel.com | 408-495-2588 | Individual | 5 | Producer | Disapprove | Editorial | 123 | 11.1.3 | 16 | "primitivist"? |  | Yes | change to "primitive" | O | PROPOSED ACCEPT IN PRINCIPLE. P99L22: change "primitivist" to "primitive with", to match wording in the baseline draft. | Editor
3275600023 | 10/04/2007 22:56:11 EDT | 179 | Engwer, Darwin A | dengwer@nortel.com | 408-495-2588 | Individual | 4 | Producer | Disapprove | Editorial | 123 | 11.1.3 | 15 | "stout-hearted"? |  | Yes | change to "that"? | O | PROPOSED ACCEPT IN PRINCIPLE. P99L21: change "stoutheatrted" to "the desired", to match wording in the baseline draft. | Editor
3275500023 | 10/04/2007 22:55:29 EDT | 178 | Engwer, Darwin A | dengwer@nortel.com | 408-495-2588 | Individual | 3 | Producer | Disapprove | Editorial | 79 | 7.3.2.44b | 19 | If there are no optional sub-elements then why show that field at all? |  | Yes | Remove the optional sub-elements field from the diagram and the corresponding text note. | O | PROPOSED ACCEPT IN PRINCIPLE. Changedthe description of the 'optional sub-element' field. | Ganesh
3275400023 | 10/04/2007 22:54:24 EDT | 177 | Engwer, Darwin A | dengwer@nortel.com | 408-495-2588 | Individual | 2 | Producer | Disapprove | Editorial | 3 | 3.168b | 12 | incorrect reference to the term BSA |  | Yes | change "within the union of the BSAs of the APs" to "within the union of the APs" | O | PROPOSED ACCEPT IN PRINCIPLE. The intent of BSA is that the BSSIDs used are unique in the range of the APs. Nonetheless the text is rewritten to avoid this term. See 07/2669r0 Section 2 | Editor
3274900023 | 10/04/2007 22:52:50 EDT | 176 | Engwer, Darwin A | dengwer@nortel.com | 408-495-2588 | Individual | 1 | Producer | Disapprove | General | 2 | 3.16a | 25 | The added new definition for BSS transition is inconsistent with the well known legacy definition in IEEE Std. 802.11-2007 clause 5.4.2.1.b. |  | Yes | Correct the new definition to align with the existing definition in clause 5.4.2.1.b | O | PROPOSED ACCEPT IN PRINCIPLE. P2L22: Replace "another BSS" with "another BSS in the same ESS." Add two new definitions: "ESS Transition: A STA movement from one BSS in one ESS to another BSS in a different ESS." , "service transition: A STA movement from one BSS to another BSS, i.e., either a BSS transition or an ESS transtioin." Replace BSS transition" with "service transition" in all places: P2L36, P6L4, P54L36, P117L1&3, P121L4. | Kwak
3274600023 | 10/04/2007 20:28:42 EDT | 175 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 15 | User | Approve | Editorial | 44 | 7.3.2.22.8 | 26 | Figure7-68h format is not consistent with other frame format description figures in the draft. Same comment for Figures 7-68i, j, k, &n. |  | No | Use figure format from D8.0 to correct this inconsistency in all places. | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3274500023 | 10/04/2007 20:28:42 EDT | 174 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 14 | User | Approve | Editorial |  | General |  | Revise Figure and Table numbering to eliminate double letter numbering, e.g. 7-62ca. |  | No | Do it in all places | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak
3274400023 | 10/04/2007 20:28:42 EDT | 173 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 13 | User | Approve | Editorial | 158 | Annex Q | 1 | Update all MIB descriptions to align with spec text. |  | No | Update all descriptions. | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak
3274300023 | 10/04/2007 20:28:42 EDT | 172 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 12 | User | Approve | Editorial | 142 | Annex D | 1 | Update all MIB descriptions to align with spec text. |  | No | Update all descriptions. | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak
3274200023 | 10/04/2007 20:28:42 EDT | 171 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 11 | User | Approve | Technical | 140 | Annex A | 32 | Add new RRM element here for Annex Q. |  | No | Add it. | O | PROPOSED ACCEPT IN PRINCIPLE. Add new optional Annex Q PICS element for APs. | Kwak
3274100023 | 10/04/2007 20:28:42 EDT | 170 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 10 | User | Approve | Editorial | 141 | Annex A | 13 | References in RRM23 are incorrect. |  | No | Fix references | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3274000023 | 10/04/2007 20:28:42 EDT | 169 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 9 | User | Approve | Editorial | 139 | Annex A | 28 | References in RRM12 are incorrect. |  | No | Fix references | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3273900023 | 10/04/2007 20:28:42 EDT | 168 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 8 | User | Approve | Technical | 54 | 7.3.2.37 | 18 | Modify figure and text to use "Optional subelelements" consistent with other occurrences in the draft. |  | No | Modify terms for consistency | O | PROPOSED ACCEPT IN PRINCIPLE | Kwak
3273800023 | 10/04/2007 20:28:42 EDT | 167 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 7 | User | Approve | Technical | 53 | 7.3.2.22.10 | 8 | Need to incude a reference to Optional subelement figure I 7.3.2.21.6 |  | No | Add reference. | O | PROPOSED ACCEPT IN PRINCIPLE | Kwak
3273700023 | 10/04/2007 20:28:42 EDT | 166 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 6 | User | Approve | Technical | 46 | 7.3.2.22.8 | 27 | Need to incude a reference to Optional subelement figure I 7.3.2.21.6 |  | No | Add reference. | O | PROPOSED ACCEPT IN PRINCIPLE | Kwak
3273600023 | 10/04/2007 20:28:42 EDT | 165 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 5 | User | Approve | Technical | 37 | 7.3.2.22.6 | 28 | Need to incude a reference to Optional subelement figure I 7.3.2.21.6 |  | No | Add reference. | O | PROPOSED ACCEPT IN PRINCIPLE | Kwak
3273500023 | 10/04/2007 20:28:42 EDT | 164 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 4 | User | Approve | Technical | 31 | 7.3.2.21.11 | 24 | Need to incude a reference to Optional subelement figure I 7.3.2.21.6 |  | No | Add reference. | O | PROPOSED ACCEPT IN PRINCIPLE | Kwak
3273400023 | 10/04/2007 20:28:42 EDT | 163 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 3 | User | Approve | Technical | 25 | 7.3.2.21.8 | 1 | Need to incude a reference to Optional subelement figure I 7.3.2.21.6 |  | No | Add reference. | O | PROPOSED ACCEPT IN PRINCIPLE | Kwak
3273300023 | 10/04/2007 20:28:42 EDT | 162 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 2 | User | Approve | Technical | 23 | 7.3.2.21.7 | 43 | Need to incude a reference to Optional subelement figure I 7.3.2.21.6 |  | No | Add reference. | O | PROPOSED ACCEPT IN PRINCIPLE | Kwak
3273200023 | 10/04/2007 20:28:42 EDT | 161 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 1 | User | Approve | Technical | 22 | 7.3.2.21.6 | 49 | Need to include Optional Subelement figure and table |  | No | Add Figure and table. Refer to common figure in folowing sections. | O | PROPOSED ACCEPT IN PRINCIPLE | Kwak
3273000023 | 10/04/2007 19:04:09 EDT | 160 | Myles, Andrew F | andrew.myles@cisco.com | +61 2 94407860 | Individual | 3 | Producer | Disapprove | Technical | 52 | 7.3.22.10 | 15 | In the last ballot I commneted that it is not clear what "ready for transmission" means. The response was to change to "transmision (ie begins CSMA/CA access). However, this means this clause is not applicable to other froms of access, ie HCCA |  | Yes | Change to "& at which the first or only gramment begins transmission" | O | PROPOSED ACCEPT IN PRINCIPLE. P52L13: change "Queue Delay is measured from the time the MSDU is passed to the MAC until the point at which the first or only fragment is ready for transmission (i.e., begins CSMA/CA access), and is expressed in units of TUs." to "Queue Delay is expressed in TUs and is measured from the time the MSDU is passed to the MAC until the point at which the first or only fragment begins transmission." | Kwak
3272900023 | 10/04/2007 19:04:09 EDT | 159 | Myles, Andrew F | andrew.myles@cisco.com | +61 2 94407860 | Individual | 2 | Producer | Disapprove | Technical | 119 | 11.10.11.1 | 119 | The text states the MP uses "basic medium acess rules" if the medium is unavailable for an MP transmission at TMPTT. However, it does not specify which AC should be used, or if the MP still has to be the next frame transmitted by the AP |  | Yes | Decide on what is really required and document it (or remove MP's from draft altogether) | O | PROPOSED ACCEPT IN PRINCIPLE. Editor shall implement 07/2669r0 Section 2, wherein 11k is more closely harmonized with the MBSSID material in 11v, and MPs are converted to Action frames of Category Public. | Hart
3272800023 | 10/04/2007 19:04:09 EDT | 158 | Myles, Andrew F | andrew.myles@cisco.com | +61 2 94407860 | Individual | 1 | Producer | Disapprove | Technical | 98 | 11.13 |  | The text proposes the use of MPs to: * Rapidly discover BSS via passive scanning * Provide neighbour measurements via passive scanning * Provide link SNR information However, 07/0535r2 examines various use cases for MPs and concludes they have limited benefit. |  | Yes | Remove MPs. Note: this comment is carried over from the last ballot. I would respond to the response to my comment last time by saying that the case made in 07/0535r2 is more compelling that the limited uses of MPs, particularly given the costs of MPs | O | PROPOSED REJECT. Measurement Pilots may be useful in the DFS bands before association, and to quickly harvest RSSIs during roaming. | Hart
3272600023 | 10/04/2007 18:24:14 EDT | 157 | Hansen, C J | chansen@broadcom.com | 408 543 3378 | Individual | 2 | Producer | Disapprove | Technical | 107 | 10 | 9 | "NOTE--Since measurements on non-operating channels could potentially degrade a station's performance, non-operating channel measurements should be requested sparingly and for short durations." This language is too weak and does not do enough to protect network performance from poorly organized or excessive measurement requests that could severely degrade QoS. Don't leave this to the WiFi alliance to solve. This should be resolved in the IEEE. |  | Yes | Add specific requirements for when non-operating channel measurements can be made. For example, if an AP has data queued for a particular STA it is not allowed to request non-operating channel measurements for that STA. This needs to be a requirement on the AP, not on the STA. Only STAs have low activity (in terms of communicated data frames in either direction with the AP) should be requested to make non-operating channel measurements. | O | The issue is not protecting data performance, it is to consider each STA’s service load, power state and operating conditions. The AP has to consider traffic load and application requirements, regulatory requirements and specific measurement states from every STA in support of wireless network management. Guidelines and limits would have to consider regulatory requirements like 4 msec carrier sense and the detection of one microsecond radar pulses in Japan. There are no typical scenarios that describe 802.11 operation in all bands in most circumstances. Off-channel measurements are desireable to gather timely information about which channel to switch BSS operation to, and the noiser the operating environment, the more urgent the need for radio measurements off the serving channel. In any case, the STA can refuse any measurement request. We are unable to support a limit to measurements which precludes ‘normal’ 802.11 operation in a noisy environment, where collisions cause many retries. | Ecclesine
3272500023 | 10/04/2007 18:24:14 EDT | 156 | Hansen, C J | chansen@broadcom.com | 408 543 3378 | Individual | 1 | Producer | Disapprove | Technical | 102 | 10 | 28 | There are no guidlines or limits defined in this section for how often measurements can be made. This is unacceptable. All measurements will have an effect on the network capacity and the thoughput available to stations incorporating these measurements. Implementations need guidance from the IEEE as to how often to make these measurements. |  | Yes | Add new text describing typical scenarios for how measurements are to be used. | O | PROPOSED ACCEPT IN PRINCIPLE. The issue is not how often a measurement request can be made, it is to consider each STA’s service load, power state and operating conditions. The AP has to consider traffic load and application requirements, regulatory requirements and specific measurement states from every STA in support of wireless network management. Guidelines and limits would have to consider regulatory requirements like 4 msec carrier sense and the detection of one microsecond radar pulses in Japan. There are no typical scenarios that describe 802.11 operation in all bands in most circumstances. Off-channel measurements are desireable to gather timely information about which channel to switch BSS operation to, and the noiser the operating environment, the more urgent the need for radio measurements off the serving channel. In any case, the STA can refuse any measurement request. We are unable to support a limit to measurements which precludes ‘normal’ 802.11 operation in a noisy environment, where collisions cause many retries. | Ecclesine
3264500023 | 10/04/2007 12:40:05 EDT | 155 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 39 | Producer | Disapprove | Technical | 185 | J | 1 | WM: The scope of this amendment, as stated in the PAR, is "This project will define Radio Resource Measurement enhancements to provide interfaces to higher layers for radio and network measurements." This does not include changes to regulatory classes |  | No | Delete the changes to Annex J, and submit them to TGmb, or to a Task Group that includes regulatory matters in its scope. | O | PROPOSED REJECT. 802.11-2007 defines operation in Part 15 license-exempt bands for several PHYs, and this amendment enhances operation with means to specify radio measurements in those bands. To specify the radio channel for measurement, this amendment creates Regulatory Classes for Part 15 license-exempt bands, so that the combination of Regulatory Class and Channel Number uniquely specify channel measurement parameters e.g., channel bandwidth. 11k would be incomplete and incorrect without these changes. | Ecclesine
3264400023 | 10/04/2007 12:40:05 EDT | 154 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 38 | Producer | Disapprove | Technical | 183 | I | 1 | WM: The scope of this amendment, as stated in the PAR, is "This project will define Radio Resource Measurement enhancements to provide interfaces to higher layers for radio and network measurements." This does not include changes to regulatory matters |  | No | Delete the changes to Annex I, and submit them to TGmb, or to a Task Group that includes regulatory matters in its scope. | O | PROPOSED REJECT. 802.11-2007 defines operation in Part 15 license-exempt bands for several PHYs, and this amendment enhances operation with means to specify radio measurements in those bands. To specify the radio channel for measurement, this amendment creates Regulatory Classes for Part 15 license-exempt bands, so that the combination of Regulatory Class and Channel Number uniquely specify channel measurement parameters e.g., channel bandwidth. 11k would be incomplete and incorrect without these changes. | Ecclesine
3264300023 | 10/04/2007 12:40:05 EDT | 153 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 37 | Producer | Disapprove | Technical | 172 | D | 31 | WM: extraneous "[0..7]" appears |  | No | change to "Unsigned32 }" | O | PROPOSED ACCEPT | Kwak
3264200023 | 10/04/2007 12:40:05 EDT | 152 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 36 | Producer | Disapprove | Technical | 172 | D | 25 | WM: extraneous "[0..7]" appears |  | No | change to "Unsigned32," | O | PROPOSED ACCEPT | Kwak
3264100023 | 10/04/2007 12:40:05 EDT | 151 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 35 | Producer | Disapprove | Technical | 174 | D | 49 | WM: many new MIB variables were added to the Station Config Entry in D9.0 on page 172, but they have no description |  | No | add descriptions of each of the new MIB variables, e.g., dot11LinkMeasurementEnabled, dot11NeighborReportEnabled, dot11ParallelMeasurementsEnabled, etc | O | PROPOSED ACCEPT. The MIB table is now updated. See 2665/r0. | Kwak
3264000023 | 10/04/2007 12:40:05 EDT | 150 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 34 | Producer | Disapprove | Technical | 172 | D | 23 | WM: dot11AnnexQMIBSupportEnabled is a particularly bad name for a MIB variable, as the numbering of the Annex in IEEE Std 802.11 is subject to change with each revision. |  | No | change to dot11RRMMIBSupportEnabled | O | PROPOSED ACCEPT IN PRINCIPLE | Kwak
3263900023 | 10/04/2007 12:40:05 EDT | 149 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 33 | Producer | Disapprove | Technical | 171 | D | 43 | WM: extraneous " I" appears after dot11AssociateFailStatus |  | No | delete it | O | PROPOSED ACCEPT | Kwak
3263800023 | 10/04/2007 12:40:05 EDT | 148 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 32 | Producer | Disapprove | Editorial | 147 | 12.3.4.3 | 10 | WM: reference to Table 12.3 should be 12-3 |  | No | change 12.3 to 12-3 | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3263700023 | 10/04/2007 12:40:05 EDT | 147 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 31 | Producer | Disapprove | Editorial | 125 | 11.8 | 25 | WM: elsewhere the phrase commonly used is "Beacon and Probe Response frames" |  | No | make "Beacons" into singular | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3263600023 | 10/04/2007 12:40:05 EDT | 146 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 30 | Producer | Disapprove | Editorial | 125 | 11.8 | 15 | WM: "Reformat" is not a valid editor instruction |  | No | change editor's instruction to "Change", and insert an Editorial Note below the text indicating the formatting changes that are not shown with underlining and strikethrough | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3263500023 | 10/04/2007 12:40:05 EDT | 145 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 29 | Producer | Disapprove | Technical | 125 | 11.3 | 6 | WM: Action frames are Management frames, not Control frames |  | No | Move point 3.ii to 2.iii | O | PROPOSED ACCEPT IN PRINCIPLE. | Kwak
3263400023 | 10/04/2007 12:40:05 EDT | 144 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 28 | Producer | Disapprove | Editorial | 123 | 11.1.3 | 18 | WM: typo |  | No | change "vallue" to "value" | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3263300023 | 10/04/2007 12:40:05 EDT | 143 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 27 | Producer | Disapprove | Editorial | 90 | 10.3.6.2.1 | 39 | WM: wrong number in heading |  | No | change to 10.3.6.2.2 | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3263200023 | 10/04/2007 12:40:05 EDT | 142 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 26 | Producer | Disapprove | Editorial | 87 | 10.3.2.2.2 | 29 | WM: missing editor instructions regarding the table |  | No | insert the editor instrutions for the table rows | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3263100023 | 10/04/2007 12:40:05 EDT | 141 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 25 | Producer | Disapprove | Technical | 86 | 10.3.2.1.2 | 45 | WM: wrong primitive; this subclause is defining MLME-SCAN.request |  | No | Change "confirm" to "request" | O | PROPOSED ACCEPT IN PRINCIPLE. | Kwak
3263000023 | 10/04/2007 12:40:05 EDT | 140 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 24 | Producer | Disapprove | Technical | 87 | 10.3.2.1.2 | 11 | WM: New element in the MLME primitive needs to be conditioned on a MIB variable or equivalent |  | No | Insert at end, "Present only when the MIB attribute dot11RadioMeasurementEnabled is true" | O | PROPOSED ACCEPT IN PRINCIPLE. | Kwak
3262900023 | 10/04/2007 12:40:05 EDT | 139 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 23 | Producer | Disapprove | Technical | 87 | 10.3.2.1.2 | 3 | WM: VendorSpecificInfo should remain as last parameter to this primitive |  | No | Move "RequestInformation" to be prior to "VendorSpecificInfo". Change editor instruction at line 6 to reflect the proper positioning of the new row. | O | PROPOSED ACCEPT IN PRINCIPLE. | Kwak
3262800023 | 10/04/2007 12:40:05 EDT | 138 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 22 | Producer | Disapprove | Technical | 72 | 7.3.2.42 | 43 | WM: Text states "The Length field in octets is set to 1." BUT, this doesn't take into consideration any optional sub-elements |  | No | fix the statement about length to accommodate the optional sub-elements | O | PROPOSED ACCEPT IN PRINCIPLE. | Kwak
3262700023 | 10/04/2007 12:40:05 EDT | 137 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 21 | Producer | Disapprove | Editorial | 9 | 7.1 | 6 | WM: Without any changes being made to 7.1, the heading should not appear in the amendment |  | No | delete heading for 7.1 (line 6) | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3262600023 | 10/04/2007 12:40:05 EDT | 136 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 20 | Producer | Disapprove | Editorial | 64 | 7.3.2.22.10 | 14 | WM: All entries (except this row) are of the form "n <= Delay&". This one should be consistent |  | No | change to "160 <= Delay" | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3262500023 | 10/04/2007 12:40:05 EDT | 135 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 19 | Producer | Disapprove | Technical | 63 | 7.3.2.22.10 | 37 | WM: Bin range is wrong for i=5; formula applies only to 1<=i<5 |  | No | Change the formula at line 37 to be 1<=i<5. Add a new formula for Bin 5, "Bin 5 range: 2**i-1 * B0 <= Delay | O | PROPOSED ACCEPT IN PRINCIPLE. | Kwak
3262400023 | 10/04/2007 12:40:05 EDT | 134 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 18 | Producer | Disapprove | Editorial | 62 | 7.3.2.22.10 | 1 | WM: Don't split the table caption across pages |  | No | keep table caption on a single page | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3262300023 | 10/04/2007 12:40:05 EDT | 133 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 17 | Producer | Disapprove | Editorial | 30 | 7.3.2.21.7 | 32 | WM: Keep the figure within the margins |  | No | adjust size of the various columns so that the figure doesn't extend beyond the margins of the page. This is also a problem with figure 7-68c on page 45, and others. | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3262200023 | 10/04/2007 12:40:05 EDT | 132 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 16 | Producer | Disapprove | Editorial | 29 | 7.3.2.21.6 | 31 | WM: Table numbering is wrong |  | No | Make it follow the IEEE Style Guide. In this case, Table 7-29c, and renumber all the following tables. Same with 7-31aa, 7-31ba, 7-43ca, etc. | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3262100023 | 10/04/2007 12:40:05 EDT | 131 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 15 | Producer | Disapprove | Technical | 28 | 7.3.2.21.6 | 34 | WM: Reporting condition is shown above the box as bits B0-B4, and below the box as 6 bits. It is shown in Table 7-29b as containing values 0-31. |  | No | Make consistent -- either 5 bits or 6 bits. If only 5 bits are used, define B5 as Reserved in Figure 7-62ca. | O | PROPOSED ACCEPT. | Kwak
3262000023 | 10/04/2007 12:40:05 EDT | 130 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 14 | Producer | Disapprove | Editorial | 28 | 7.3.2.21.6 | 25 | WM: Figure numbering is wrong. |  | No | Make it follow the IEEE Style Guide. In this case, Figure 7-62d, and renumber all the following figures. Same with Figure 7-62fa on page 33, 7-62fb on page 34, etc | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3261900023 | 10/04/2007 12:40:05 EDT | 129 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 13 | Producer | Disapprove | Editorial | 26 | 7.3.2.21.4 | 35 | WM: non-justified text |  | No | fix the jagged right margin | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3261800023 | 10/04/2007 12:40:05 EDT | 128 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 12 | Producer | Disapprove | Editorial | 26 | 7.3.2.21.4 | 34 | WM: missing "see" |  | No | change "( 7.3.2.26)" to "(see 7.3.2.26)" | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3261700023 | 10/04/2007 12:40:05 EDT | 127 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 11 | Producer | Disapprove | Technical | 26 | 7.3.2.21.4 | 32 | WM: The change made to D9.0 allowing optional sub-elements to various RRM IEs is specified far less than needed. The amendment needs to define what an optional sub-element looks like, and to define a separate space of sub-element IDs for each of them |  | No | Insert a new figure with the format of an optional sub-element, consisting of a sub-element ID, length, followed by variable data. Insert a new table of sub-element IDs, with all entries reserved except 221 "Vendor Specific". Same change in 7.3.2.21.5, 7.3.2.21.6, and everywhere else the "Optional sub-elements" were added. | O | PROPOSED ACCEPT IN PRINCIPLE. | Kwak
3261600023 | 10/04/2007 12:40:05 EDT | 126 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 10 | Producer | Disapprove | Technical | 2 | 3.16a | 25 | WM: Definition of BSS transition is incomplete. It should match the definition given in 5.4.2.1 |  | No | Change to "A STA movement from one BSS in one ESS to another BSS within the same ESS." | O | PROPOSED ACCEPT IN PRINCIPLE. P2L22: Replace "another BSS" with "another BSS in the same ESS." Add two new definitions: "ESS Transition: A STA movement from one BSS in one ESS to another BSS in a different ESS." , "service transition: A STA movement from one BSS to another BSS, i.e., either a BSS transition or an ESS transtioin." Replace BSS transition" with "service transition" in all places: P2L36, P6L4, P54L36, P117L1&3, P121L4. | Kwak
3261500023 | 10/04/2007 12:40:05 EDT | 125 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 9 | Producer | Disapprove | Technical | 146 | 11.10.12 | 20 | "indicated AC (see Figure 112o)" I thought all figure references were changed to x-yyy, where x is the clause number |  | Yes | Correct the reference. | O | PROPOSED ACCEPT. P120L47: Change "112o" to "7-95o". | Kwak
3261400023 | 10/04/2007 12:40:05 EDT | 124 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 8 | Producer | Disapprove | Editorial | 128 | 11.10.3 | 4 | "therequested" therequested? I don't see any comment that triggered this change, and it's just flat out wrong. |  | Yes | "the requested" | O | PROPOSED ACCEPT | Editor
3261300023 | 10/04/2007 12:40:05 EDT | 123 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 7 | Producer | Disapprove | Editorial | 85 | 7.4.6.7 | 7 | "Figure 7101fc" |  | Yes | "Figure 7-101fc" | O | PROPOSED ACCEPT | Editor
3261200023 | 10/04/2007 12:40:05 EDT | 122 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 6 | Producer | Disapprove | Technical | 76 | 7.3.2.44a | 32 | Are four octets enough for all the possible RRM Capabilities? I note that there are only 6 bits unassigned out of 32. |  | Yes | Perhaps extend the RRM capability bit mask to more octets | O | PROPOSED ACCEPT. Redefined the RRM Bitmask as an octet string with a length field prefix. Octet strings can be extended to include future bitmask needs. | Ganesh
3261100023 | 10/04/2007 12:40:05 EDT | 121 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 5 | Producer | Disapprove | Editorial | 39 | 7.3.2.22 |  | "All other Measurement Types are used for radio measurement and is only included in Radio Measurement Report frames." "is" is used for a single case, "are" is used for multiple cases. |  | Yes | "All other Measurement Types are used for radio measurement and are only included in Radio Measurement Report frames." | O | PROPOSED ACCEPT | Editor
3261000023 | 10/04/2007 12:40:05 EDT | 120 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 4 | Producer | Disapprove | Editorial | 39 | 7.3.2.22 | 35 | "Measurement Types 0, 1 and 2 are used for spectrum management and is only included in spectrum management Measurement Report frames" "is" is used for a single case, "are" is used for multiple cases. |  | Yes | "Measurement Types 0, 1 and 2 are used for spectrum management and are only included in spectrum management Measurement Report frames" | O | PROPOSED ACCEPT | Editor
3260900023 | 10/04/2007 12:40:05 EDT | 119 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 3 | Producer | Disapprove | Technical | 10 | 7.2.3.1 | 27 | "1) when Available Admission Capacity Bitmask equals 0 (Available Admission Capacity List contains no entries), and 2) when the BSS Load element is present and the Available Capacity Bitmask equals 256 (Available Admission Capacity List contains only the AC_VO entry)." The two conditions are an "or" type situation, not an "and" type situation. |  | Yes | Change the "and" to "or": "1) when Available Admission Capacity Bitmask equals 0 (Available Admission Capacity List contains no entries), or 2) when the BSS Load element is present and the Available Capacity Bitmask equals 256 (Available Admission Capacity List contains only the AC_VO entry)." | O | PROPOSED ACCEPT. Changed "and" to "or" for the conditions under which a QoS AP does not include BSS Available Admission Capacity IE in the beacon. | Ganesh
3260800023 | 10/04/2007 12:40:05 EDT | 118 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 2 | Producer | Disapprove | Editorial | 5 | 5.2.7.2 | 26 | "informatioin" |  | Yes | "information" | O | PROPOSED ACCEPT | Editor
3260700023 | 10/04/2007 12:40:05 EDT | 117 | Chaplin, Clint F | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 1 | Producer | Disapprove | Technical | 3 | 3.168c | 17 | "A special BSSID value (all 1s) used to represent all BSSIDs" All 1s in what base? ASCII character 1s? Hexidecimal 1s? Binary 1s? |  | Yes | "A special BSSID value (all binary 1s) used to represent all BSSIDs" | O | PROPOSED ACCEPT. Changed as recommended. | Ganesh
3259300023 | 10/04/2007 00:13:32 EDT | 116 | Ponnuswamy, Subburajan | subbu@acm.org | 408-754-1213 | Individual | 4 | Producer | Disapprove | Editorial | 9 | 7.2.3.1 | 49 | The introduction of a new verb "can" is not needed, and introduces confusion between the meaning of "may" and "can". Only a single term is needed. |  | Yes | Revert to "may", deleting "can" throughout the document where it has been inserted, replacing "may". | O | PROPOSED REJECT. Clause 7 contains normative frame format descriptions but is not intended to contain requirement text. The terms "shall" and "may" are normative terms used for requirement definition and are not approporiate for frame format descriptions. The appropriate terms in clause 7 are "is" and "can". TGm editors have made efforts over that last few releases of the baseline draft to make these corrections on a piecemeal basis The effort is also carried out by the editors of all new ammendments. | Editor
3259200023 | 10/04/2007 00:09:06 EDT | 115 | Ponnuswamy, Subburajan | subbu@acm.org | 408-754-1213 | Individual | 3 | Producer | Disapprove | Editorial | 5 | 5.2.7.2 | 26 | Typo: "informatioin" should be "information" |  | Yes | Change "informatioin" to "information" | O | PROPOSED ACCEPT. | Editor
3259100023 | 10/04/2007 00:06:46 EDT | 114 | Ponnuswamy, Subburajan | subbu@acm.org | 408-754-1213 | Individual | 2 | Producer | Disapprove | Technical | 79 | 7.2.3.44b | 13 | It looks like part of the multiple BSSID capability defined in TGv Draft 1.0 is used here, without including the ability to create one beacon frame that provides information for all multiple BSSIDs. Why is there a restriction on the values for the BSSIDs: "The BSSIDs indicated are the range of BSSIDs starting with the base BSSID with its n LSBs set to 0s and ending with the base BSSID with its n LSBs set to 1s, inclusive". This seems overly restrictive. "Base BSSID" is more accurately described as "transmitted BSSID". |  | Yes | Include the complete multiple BSSID feature definition, including changes to 7.2.3.1, 7.2.3.9, 7.3.2.6, 7.3.2.68, 7.3.2.70, 11.20.5 from the TGv draft. Also, remove "virtual AP" from 11.10.11.1, using "multiple BSSID capability, Non-transmitted BSSIDs". | O | PROPOSED ACCEPT IN PRINCIPLE. Editor shall implement 07/2669r0 Section 2, wherein 11k is more closely harmonized with the MBSSID material in 11v, and MPs are converted to Action frames of Category Public. | Hart
3259000023 | 10/04/2007 00:03:11 EDT | 113 | Ponnuswamy, Subburajan | subbu@acm.org | 408-754-1213 | Individual | 1 | Producer | Disapprove | Technical | 3 | 3.168b | 11 | I question the wisdom of introducing the term Virtual AP into the standard, in 3.168b virtual AP set: The set of APs which all use a common regulatory class, channel and antenna connector , and whose BSSIDs satisfy the following condition: that, within the union of the BSAs of the APs, there exists a range of BSSIDs encompassing the BSSIDs of the APs and there are no BSSIDs of other APs that use a different antenna connector, where the extrema of the range of BSSIDs are constrained to be any BSSID with its n LSBs set to all 0s and to all 1s. We considered this for the multiple BSSID feature (TGv) and decided to use existing terms related to BSSIDs only, as this is sufficient. Also the term virtual is not really accurate. These are not virtual APs, they are indeed unique APs in the standard's use of the term, each with a unique BSSID. In an implementation, they may be collocated in a single device. Separately, this definition does not make sense: there are no BSSIDs of other APs that use a different antenna connector, where the extrema of the range of BSSIDs are constrained to be any BSSID with its n LSBs set to all 0s and to all 1s. What is n and where is it defined? Why is the restriction on the values of the BSSID present? The list of common attributes is not complete, and needs to be defined using applicable elements, see TGv 7.3.2.68, The Non-Transmitted BSSID Profile field includes the Capabilities field followed by a variable number of information elements.The Timestamp, Beacon Interval, DS Parameter Set, FH Parameter Set, IBSS Parameter Set, Country, FH Parameters, FH Pattern Table, Channel Switch Assignment, IBSS DFS, and ERP Information elements are not included in the Non-Transmitted BSSID Profile field; the values of these elements for each non-transmitted BSSID are always the transmitted BSSID element values. |  | Yes | Replace Virtual AP language with Multiple BSSID, transmitted and non-transmitted BSSIDs. Incorporate complete TGv solution for multiple BSSID support. | O | PROPOSED ACCEPT IN PRINCIPLE. Editor to implement 07/2670r0. | CRGroup
3251200023 | 10/02/2007 17:19:17 EDT | 112 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 26 | Producer | Disapprove | Technical | 199 | Annex Q | 10 | dot11RRMNeighborReportBeaconInterval is two octets, and an unsigned32 should have bounded SYNTAX (0..65535). Review other Annex Q unsigned32 elements for correct SYNTAX. |  | Yes | per comment | O | PROPOSED ACCEPT IN PRINCIPLE. Change MIB entry to read; "dot11RRMNeighborReportBeaconInterval OBJECT-TYPE SYNTAX Unsigned32 (0..65535) UNITS "TUs" MAX-ACCESS read-create STATUS current DESCRIPTION "The Beacon Interval field is as defined in clause 7.3.2.37." ::= { dot11RRMNeighborReportEntry 19 }" | Gray
3251100023 | 10/02/2007 17:19:17 EDT | 111 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 25 | Producer | Disapprove | Technical | 196 | Annex Q | 39 | dot11RRMNeighborReportNeighborTSFInfo is now six octets, not Unsigned32. Fix SYNTAX statement here and p198. Review the other Sub-Element info OBJECT-TYPES to ensure correct SYNTAX. |  | Yes | per comment | O | PROPOSED ACCEPT IN PRINCIPLE: dot11RRMNeighborReportNeighborTSFInfo OBJECT-TYPE SYNTAX OCTET STRING (SIZE (6)) MAX-ACCESS read-create STATUS current DESCRIPTION "The Neighbor TBTT info sub-element is as defined in clause 7.3.2.36." ::= { dot11RRMNeighborReportEntry 16 }" | Gray
3251000023 | 10/02/2007 17:19:17 EDT | 110 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 24 | Producer | Disapprove | Editorial | 153 | Annex D | 50 | SMTBase 7 should be numbered dot11Groups 36. |  | No | per comment | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3250900023 | 10/02/2007 17:19:17 EDT | 109 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 23 | Producer | Disapprove | Technical | 153 | Annex D | 43 | Missing OBJECT-TYPES for dot11RadioMeasurementCapable and dot11RadioMeasurementEnabled. |  | Yes | Add OBJECT-TYPE elements and syntax. | O | PROPOSED ACCEPT IN PRINCIPLE. No text change needed. Draft9.0 P145L24 through 37 has the OBJECT_TYPES for dot11RadioMeasurementCapable and dot11RadioMeasurementEnabled. | Kwak
3250800023 | 10/02/2007 17:19:17 EDT | 108 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 22 | Producer | Disapprove | Technical | 143 | Annex D | 45 | 22 missing OBJECT-TYPES for entries from dot11LinkMeasurementEnabled through dot11MeasurementPilotSupport. |  | Yes | Add OBJECT-TYPE elements and syntax. | O | PROPOSED ACCEPT IN PRINCIPLE. See 2665/r0. | Kwak
3250700023 | 10/02/2007 17:19:17 EDT | 107 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 21 | Producer | Disapprove | Technical | 11 | 7.2.3.9 | 24 | Second struckthru sentence "Note that &" contains text that does not appear elsewhere, and should not be removed from 802.11-2007. It should be moved to the end of 11.1.2 after the relocated 7.2.3.1 requirement sentence. |  | Yes | per comment | O | C Add deleted NOTE sentence to end of paragraph in 9.8.2.1 at P73L5. | Kwak
3250600023 | 10/02/2007 17:19:17 EDT | 106 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 20 | Producer | Disapprove | Technical | 8 | 7.3.2.1 | 16 | The second struckthru sentence "Optionally, ...'' is related to the second paragraph of 9.8.1 and all of 9.8.2, which should be changed to include it: " Optionally, the Beacon frame format may also include the information described in either or both of FH Parameters and FH Pattern Table elements." |  | Yes | Insert text into 9.8.2.1 per comment. | O | PROPOSED ACCEPT IN PRINCIPLE. Equivalent text has been added to 9.8.2.1 in D9.0. No additonal text change is needed. | Kwak
3250500023 | 10/02/2007 17:19:17 EDT | 105 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 19 | Producer | Disapprove | Technical | 8 | 7.3.2.1 | 15 | First struckthru sentence contains 'shall' requirement that does not appear elsewhere, and should not be removed from 802.11-2007. It should be moved to become the last sentence of 11.1.2 Maintaining synchronization. |  | Yes | per comment | O | PROPOSED ACCEPT IN PRINCIPLE. In fact the first strikethrough sentence here is redundant and is completely captured in Notes column of Table 7-8. However, if for emphasis, the commenter would like to include a redundant requirement in section 11, this can be accommodated. Add new sentences to end of 11.1.3.3, "A STA shall include a Country information element in the transmission of Beacon frames if either dot11MultiDomainCapability Enabled, dot11SpectrumManagementRequired or dot11RadioMeasurementEnabled is true. See 7.2.3.1 for description of properly formed Beacon frame." | Kwak
3250400023 | 10/02/2007 17:19:17 EDT | 104 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 18 | Producer | Disapprove | Editorial | 200 | Annex Q | 15 | dot11SMTRRMRequest is not the 36th member of dot11Groups. Neew another name for RRMRequest/Report/Config groups. |  | Yes | fix | O | PROPOSED ACCEPT IN PRINCIPLE. P200L15: change 36 to 37.P202L20: change 37 to 38. P202L50: change 38 to 39. | Kwak
3250300023 | 10/02/2007 17:19:17 EDT | 103 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 17 | Producer | Disapprove | Editorial | 195 | Annex Q | 35 | Description has wrong reference, should be 7.3.2.36 |  | No | per comment | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3250200023 | 10/02/2007 17:19:17 EDT | 102 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 16 | Producer | Disapprove | Editorial | 170 | Annex Q | 3 | Shoud be a blank line before dot11ChannelLoadRprtRegulatoryClass |  | No | per comment | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3250100023 | 10/02/2007 17:19:17 EDT | 101 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 15 | Producer | Disapprove | Editorial | 165 | Annex Q | 35 | Description has wrong reference, should be 7.3.2.28 |  | No | per comment | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3250000023 | 10/02/2007 17:19:17 EDT | 100 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 14 | Producer | Disapprove | Editorial | 131 | 18.2.6 | 29 | List element 'e' should not be struckthru. |  | No | per comment | O | PROPOSED ACCEPT. In three places: P121L4&15&16. | Editor
3249900023 | 10/02/2007 17:19:17 EDT | 99 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 13 | Producer | Disapprove | Editorial | 131 | 18.2.6 | 18 | Change the sentence so PMD_SQ and SQ are last, as SQ is last in subsequent tables and text. I know the baseline sentence has PMD_SQ first, but it should follow PMD_RCPI to match Table 18-6. |  | No | per comment | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3249800023 | 10/02/2007 17:19:17 EDT | 98 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 12 | Producer | Disapprove | Editorial | 128 | 17.3.10.6 | 31 | Tab missing after 254: here and 18.4.8.5 |  | No | per comment | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3249700023 | 10/02/2007 17:19:17 EDT | 97 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 11 | Producer | Disapprove | Editorial | 119 | 11.10.11.1 | 27 | insert 'the' into sentence: members of the Virtual AP Set . . . |  | No | per comment | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3249600023 | 10/02/2007 17:19:17 EDT | 96 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 10 | Producer | Disapprove | Editorial | 111 | 11.10.8.2 | 35 | Remove underline and fix font of first sentence. |  | No | per comment | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3249500023 | 10/02/2007 17:19:17 EDT | 95 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 9 | Producer | Disapprove | Editorial | 103 | 11.10.3 | 32 | Equation lacks a pair of parentheses that clarify whether duration is (2 ^ (..)) * TBTT or 2 ^ ((..) * TBTT) |  | No | fix | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3249400023 | 10/02/2007 17:19:17 EDT | 94 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 8 | Producer | Disapprove | Editorial | 99 | 11.1.3 | 23 | Spelling 'vallue' |  | No | fix | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3249300023 | 10/02/2007 17:19:17 EDT | 93 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 7 | Producer | Disapprove | Editorial | 99 | 11.1.3 | 21 | The unchanged third sentence is shown incorrectly. |  | No | Restore the unchanged third sentence as shown in 802.11-2007. | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3249200023 | 10/02/2007 17:19:17 EDT | 92 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 6 | Producer | Disapprove | Editorial | 203 | Annex Q | 1 | Four trailing white pages should be deleted. |  | No | per comment | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3249100023 | 10/02/2007 17:19:17 EDT | 91 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 5 | Producer | Disapprove | Editorial | 144 | Annex D | 11 | The last two entries are shown as type Unsigned32 (0 .. 7), when they should be Unsigned32. |  | No | per comment | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3249000023 | 10/02/2007 17:19:17 EDT | 90 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 4 | Producer | Disapprove | Editorial | 143 | Annex D | 37 | dot11AssociateFailStatus I has an extraneous ' I', which should be deleted |  | No | per comment | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3248900023 | 10/02/2007 17:19:17 EDT | 89 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 3 | Producer | Disapprove | Editorial | 28 | 7.3.2.21.10 | 18 | There are several Sub-Element format figures that are identical - 7-62fa, 7-62ia, 7-68ea, 7-68la, 7-95e, 7-95la and 7-101fc. You could introduce a canonical Sub-Element format figure in 7.3.2.21, and refer to it in all subsequent instances. |  | No | Create canonical Sub-Element format figure in 7.3.2.21, remove other Sub-Element format figures, and change all text to refer to the canonical figure. | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3248800023 | 10/02/2007 17:19:17 EDT | 88 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 2 | Producer | Disapprove | Editorial | 72 | 9.8.2.1 | 47 | The editing instruction should be to insert a new first sentence, and the paragraph on p73 should be deleted, as it is unchanged. If you retain the existing paragraph, then correct the reference to the equation on p73 line 5. |  | No | Change editing instruction to insert. | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3248700023 | 10/02/2007 17:19:17 EDT | 87 | Ecclesine, Peter | petere@cisco.com | 408-527-0815 | Individual | 1 | Producer | Disapprove | Editorial | 21 | 7.3.2.21.6 | 17 | The numbering of Figure 7-62ca following Figure 7-62c is bizarre, and should be 7-62d. All figures and tables in a draft should be numbered sequentially. |  | Yes | Renumber Figures and Tables sequentially in the next draft. | O | PROPOSED ACCEPT. | Editor
3248600023 | 10/02/2007 16:48:55 EDT | 86 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 76 | Producer | Disapprove | Technical | 61 | 7.3.2.43 |  | Daves: CID 84 refers to 07/2327r2 wherein the text states, "An Available Admission Capacity value of 0 transmitted in the BSS Available Admission Capacity element indicates that no admission capacity is available at the calculation time and that no explicit admissions will be granted by the AP for that UP or AC category at the calculation time." This is meaningless since the non-AP STA has no way of knowing the "calculation time". |  | Yes | Delete these two sentences since the final paragraph stating, "Note: STAs are advised that requesting admission for any TSPEC at an UP or AC which requires more medium time than is reported as available for the requested UP or AC is possible yet unlikely to be successful." suffices. | O | PROPOSED ACCEPT IN PRINCIPLE. P121L14: Change second "at the calculation time" to "unless additional capacity becomes available." | Kwak
3248500023 | 10/02/2007 16:48:55 EDT | 85 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 75 | Producer | Disapprove | Editorial | 121 | 11.10.3 | 4 | Daves: CID 84 refers to 07/2327r2 wherein the phrase "AC category" is used in several places. The term AC (from IEEE 802.11-2007 clause 4) means access category. Therefore the phrase "AC category" can be translated to "access category category" which is redundant. [Fix 3x in this section] |  | Yes | Delete the word "category" wherever the referenced phrase occurs. | O | PROPOSED ACCEPT IN PRINCIPLE. Change "AC category" to AC (3x in subclause) | Hart
3248400023 | 10/02/2007 16:48:55 EDT | 84 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 74 | Producer | Disapprove | Technical | 8 | 7.2.3.1 | 26 | Daves: Although I agree with the intent of the resolution to CID 85 (that is, reducing beacon bloat), the proposed resolution conditionally and dynamically adds and removes information elements to beacon frames. This un-necessarily complicates beacon generation. To my knowledge, this has never been done (with the exception of CSA--which has a very different use case) and could possible break some STA implementations. |  | Yes | Define a MIB variable which allows these elements to be conditionally used in the beacon dependent on whether the MIB variable is true or false. This allows the elements in the beacon to be statically present. I suspect there are other solutions which have a similar characteristic. | O | PROPOSED ACCEPT IN PRINCIPLE. Editor shall implement 07/2669r0 Section 1, wherein valueless elements may now be optionally removed | Hart
3248300023 | 10/02/2007 16:48:55 EDT | 83 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 73 | Producer | Disapprove | Technical | 4 | 3 | 9 | Daves: Resolution to CID 83 provides a definition of "3.999k Virtual AP Set" which is un-intelligible. If it is really this complicated, an example should be provided. |  | Yes | Simplify the definition. | O | PROPOSED ACCEPT IN PRINCIPLE. Editor shall implement 07/2669r0 Section 2, wherein 11k is more closely harmonized with the MBSSID material in 11v, and MPs are converted to Action frames of Category Public. | Hart
3248200023 | 10/02/2007 16:48:55 EDT | 82 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 72 | Producer | Disapprove | Technical | 71 | 7.4.6.7 | 6 | Daves: Resolution to CID 83 proposes changing frame subtype of Measurement Pilot to an Action frame. The problem with this is that a STA's MAC can which is looking for a MP frame can no longer filter based on frame subtype; the STA's MAC now has to accept all action frames and parse the category and action fields to determine whether it is the MP frame. Moreover, since MPs are transmitted to the broadcast destination MAC address, all STAs must receive and process them (at least as far as to delete them after some parsing) even when they are not interested in them. This is inefficient. |  | Yes | Re-instate old subtype. | O | PROPOSED REJECT. Editor shall implement 07/2669r0 Section 3, wherein 11k is more closely harmonized with the MBSSID material in 11v, and MPs are converted to Action frames of Category Public. | Hart
3248100023 | 10/02/2007 16:48:55 EDT | 81 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 71 | Producer | Disapprove | Technical | 85 | 11.1 | 35 | Daves: There are, what I consider to be, several errors in the submission 07/2285r0. They are: [7.2.3.1; 7.2.3.8; 7.2.3.9] 1. RRM Capability Enabled Bitmask element is not present in Beacon frames (but is present in Probe Response frames) [Present in neither] [7.3.2.44a] 2. First sentence in clause 7.3.2.45 gives incorrect length (4) of this element. Length should be 6 octets. [???] 3. There is a <tbd> in notes for measurement pilot capability. [No TBD's in draft9.0] [Annex D/Q] 4. Definitions for new MIB table entries are undefined. |  | Yes | 1. Add the element to the beacon frame. 2. Change the text. 3. Fix TBD or provide an editing instruction. 4. Supply text for new MIB variables. | O |  | Hart
3247800023 | 10/02/2007 12:00:28 EDT | 80 | O'Hara, Robert | bob.ohara@ieee.org | +1 408 496 0560 | Individual | 1 | Producer | Disapprove | Technical | 123 | 11.1.3 | 18 | Referring to my comment #195 in the initial ballot, the resolution status and the resolution detail conflict. The resolution status indicates the comment is accepted. The resolution detail indicates the comment is rejected. The draft was not changed as requested in the comment. |  | Yes | Since this comment is accepted, change the draft to implement the requested change in the original comment (myballot #195). | O | ACCEPT IN PRICIPLE. The inconsistency noted by the commenter in the MyBallot website will be corrected. All other BRC committee documents clearly indicate that CID195 was rejected. In the MyBallot Resolution Detail column, it is clearly indicated that the comment was rejected. The MyBallot Resolution Status column which indicates AGREE will be changed to DISAGREE, if the website permits this. No text change is needed. | Kwak
3244000023 | 10/01/2007 17:40:42 EDT | 79 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 70 | Producer | Disapprove | Technical | 144 | D | 15 | Review from P144L15 to P151L29 and move to Annex Q is referenced from Annex Q and nowhere else |  | Yes | Review from P144L15 to P151L29 and move to Annex Q if referenced from Annex Q and nowhere else | O |  | Ganesh
3243900023 | 10/01/2007 17:40:42 EDT | 78 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 69 | Producer | Disapprove | Technical | 144 | D | 12 | dot11MPSupport is Capability elsewhere |  | Yes | Choose a name & stick to it | O | PROPOSED ACCEPT. dot11RRMMeasurementPilotCapability is the MIB variable all through the specification. | Ganesh
3243800023 | 10/01/2007 17:40:42 EDT | 77 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 68 | Producer | Disapprove | Technical | 143 | D | 43 | Delete dot11MPTxEn and dot11MPRxEn |  | Yes | Delete dot11MPTxEn and dot11MPRxEn. Also on P145 and 146 | O | PROPOSED ACCEPT. See 2665/r0 | Ganesh
3243700023 | 10/01/2007 17:40:42 EDT | 76 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 67 | Producer | Disapprove | Technical | 138 | A.4.17 | 7 | No PICS for Reporting Detail or AP channel list as a subelement |  | Yes | Add PICS entries | O |  | Ganesh
3243600023 | 10/01/2007 17:40:42 EDT | 75 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 66 | Producer | Disapprove | Technical | 121 | 11.10.13 | 11 | "shall be current or recently calculated" |  | Yes | This is not a testable shall - define "recent". Rewrite: e.g. should be | O | PROPOSED ACCEPT IN PRINCIPLE. P121L11: change "shall be current" to "should be current". | Kwak
3243500023 | 10/01/2007 17:40:42 EDT | 74 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 65 | Producer | Disapprove | Technical | 121 | 11.10.13 | 11 | "The AP shall recalculate" |  | Yes | This is not a testable shall. Change to "The AP recalculates" | O | PROPOSED ACCEPT IN PRINCIPLE | Kwak
3243400023 | 10/01/2007 17:40:42 EDT | 73 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 64 | Producer | Disapprove | Technical | 121 | 11.10.13 | 3 | The QBSS load IE is optional; thus the BSS AAC should be optional also |  | Yes | change to "may" in clause 7 in beacon & probe response | O | PROPOSED ACCEPT IN PRINCIPLE. Fix conditions on P9L3. | Kwak
3243300023 | 10/01/2007 17:40:42 EDT | 72 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 63 | Producer | Disapprove | Editorial | 120 | 11.10.11.2 | 36 | 11.13.1 |  | No | Change to 11.10.11.1 | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3243200023 | 10/01/2007 17:40:42 EDT | 71 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 62 | Producer | Disapprove | Technical | 120 | 11.10.11.1 | 10 | "to 2" |  | Yes | "to 0 or 1" | O | PROPOSED ACCEPT. Fixed as recommended | Ganesh
3243100023 | 10/01/2007 17:40:42 EDT | 70 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 61 | Producer | Disapprove | Editorial | 120 | 11.10.11.1 | 4 | Fontsize |  | No | Fix | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3243000023 | 10/01/2007 17:40:42 EDT | 69 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 60 | Producer | Disapprove | Editorial | 119 | 11.10.11.1 | 7 | is set |  | No | set | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3242900023 | 10/01/2007 17:40:42 EDT | 68 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 59 | Producer | Disapprove | Technical | 118 | 11.10.11 | 33 | What is "actively receiving"? |  | Yes | Change to "The AP STA is transmitting MPs &" | O | PROPOSED ACCEPT. Fixed as recommended | Ganesh
3242800023 | 10/01/2007 17:40:42 EDT | 67 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 58 | Producer | Disapprove | Technical | 118 | 11.10.11 | 27 | What is "actively receiving"? |  | Yes | Change to "The non-AP STA is making use of the MPs it receives or would receive if they were being transmitted" | O | PROPOSED ACCEPT. Fixed as recommended | Ganesh
3242700023 | 10/01/2007 17:40:42 EDT | 66 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 57 | Producer | Disapprove | Editorial | 118 | 11.10.11 | 13 | Would this be clearer as two tables? |  | No | Two tables | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3242600023 | 10/01/2007 17:40:42 EDT | 65 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 56 | Producer | Disapprove | Editorial | 118 | 11.10.11 | 4 | "Enable a Probe Req" |  | Yes | Change to "Enable the transmission of a probe request" | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3242500023 | 10/01/2007 17:40:42 EDT | 64 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 55 | Producer | Disapprove | Editorial | 111 | 11.10.8.2 | 35 | Fontsize |  | No | Fix | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3242400023 | 10/01/2007 17:40:42 EDT | 63 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 54 | Producer | Disapprove | Editorial | 109 | 11.10.8.1 | 7 | ".." |  | No | Change to "." | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3242300023 | 10/01/2007 17:40:42 EDT | 62 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 53 | Producer | Disapprove | Technical | 106 | 11.10.5 | 29 | Actual Measurement Start time is ambiguous in a split element/frame |  | Yes | On L29 and L34, indicate same token AND same Actual Start Time if present | O | PROPOSED ACCEPT IN PRINCIPLE. Editor shall implement 07/2669r0 Section 4 | Hart
3242200023 | 10/01/2007 17:40:42 EDT | 61 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 52 | Producer | Disapprove | Technical | 104 | 11.10.3 | 36 | Create two MaxMeasDuration's: one on-channel; one off-channel. |  | Yes | Create two MaxMeasDuration's: one on-channel; one off-channel. | O | PROPOSED ACCEPT. Two durations are now defined. Bitmask:20-22 for on channel and BitMask:42-45 for off channel Measurements. See 2665/r0. | Ganesh
3242100023 | 10/01/2007 17:40:42 EDT | 60 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 51 | Producer | Disapprove | Technical | 104 | 11.10.3 | 24 | Don't compare against dot11MaxMEasDur. |  | Yes | Compare against MaxMeasDuration in TU from equation | O | PROPOSED ACCEPT. Changed as recommended. | Ganesh
3242000023 | 10/01/2007 17:40:42 EDT | 59 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 50 | Producer | Disapprove | Technical | 103 | 11.10.3 | 32 | ^ is ambiguous since is can be power or xor; also TBTT should be beacon period |  | Yes | Choose a non-ambiguous notation or define. Change ot beacon period | O | PROPOSED ACCEPT IN PRINCIPLE. The operation is obvious from the context. Table 178 in the base standard uses this operator for exponentiation. Fixed TBTT to Beacon Period. | Ganesh
3241900023 | 10/01/2007 17:40:42 EDT | 58 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 49 | Producer | Disapprove | Technical | 99 | 11.1.3 | 30 | In the industry, the Request element is deprecated except for FH parameters since the extra computation slows down probe responses & it is insecure. Also this text does not belong in 11.1.3 which refers to sync. Its application to NeighRep is undefined since that is many IEs not just 1. |  | Yes | Best to just delete this note. | O | Add APChanReport, BSSAvgAccessDelay, AntennaInfromation, BSSAvailAdmissCapacity, and BssAccessDelay to Probe Response as required elements. Delet note at P99L30. | Kwak
3241800023 | 10/01/2007 17:40:42 EDT | 57 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 48 | Producer | Disapprove | Technical | 99 | 11.1.3 | 24 | Replace dott11MPRxEn by dot11MPCapablity |  | Yes | Replace dott11MPRxEn by dot11MPCapablity | O | PROPOSED ACCEPT IN PRINCIPLE | Kwak
3241700023 | 10/01/2007 17:40:42 EDT | 56 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 47 | Producer | Disapprove | Editorial | 99 | 11.1.3 | 24 | "vallue" |  | No | value | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3241600023 | 10/01/2007 17:40:42 EDT | 55 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 46 | Producer | Disapprove | Editorial | 97 | 10.3.32.2.2 | 43 | Underlining not necessary |  | No | Don't underline. | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3241500023 | 10/01/2007 17:40:42 EDT | 54 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 45 | Producer | Disapprove | Editorial | 96 | 10.3.32.1.1 | 36 | path loss, the |  | No | Change to "pathloss and the" | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3241400023 | 10/01/2007 17:40:42 EDT | 53 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 44 | Producer | Disapprove | Technical | 94 | 10.3.31.1.2 | 19 | "MIB table dot11RRMNeighRepTab" |  | Yes | What if Annex Q is not implemented? Rplace by appropriate text | O | PROPOSED ACCEPT IN PRINCIPLE. In 10.3.31.3.2, delete "derived from the MIB table dot11RRMNeighborReportTable" | Hart
3241300023 | 10/01/2007 17:40:42 EDT | 52 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 43 | Producer | Disapprove | Technical | 74 | 10.3.2.2.2 | 38 | Bad MIB variable |  | Yes | Change dot11MPRxEn to dot11MeasurementPilotCapability. Search other examples of dot11MPRxEn & appropriately replace | O | PROPOSED ACCEPT IN PRINCIPLE. Also define MeasPiltCapab in the MIB. | Kwak
3241200023 | 10/01/2007 17:40:42 EDT | 51 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 42 | Producer | Disapprove | Editorial | 71 | 7.4.6.7 | 11 | Style error |  | No | Change last field to "Optional sub-elements" | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3241100023 | 10/01/2007 17:40:42 EDT | 50 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 41 | Producer | Disapprove | Technical | 70 | 7.4.6.5 | 11 | Allow VS elements to be added |  | Yes | Allow VS elements to be added, here and clause 10 | O | PROPOSED ACCEPT IN PRINCIPLE. Editor shall implement 07/2669r0 Section 3 | Hart
3241000023 | 10/01/2007 17:40:42 EDT | 49 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 40 | Producer | Disapprove | Technical | 70 | 7.4.6.4 | 49 | "in dBm" |  | Yes | Change to "in a dB scale" | O | PROPOSED ACCEPT IN PRINCIPLE | Kwak
3240900023 | 10/01/2007 17:40:42 EDT | 48 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 39 | Producer | Disapprove | Technical | 69 | 7.4.6.4 | 49 | "in dBm" |  | Yes | Change to "in a dBm scale" | O | PROPOSED ACCEPT IN PRINCIPLE | Kwak
3240800023 | 10/01/2007 17:40:42 EDT | 47 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 38 | Producer | Disapprove | Editorial | 69 | 7.4.6.3 | 13 | 7.3.1.21 doesn't exist |  | No | Update reference | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3240700023 | 10/01/2007 17:40:42 EDT | 46 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 37 | Producer | Disapprove | Editorial | 69 | 7.4.6.3 | 9 | 7.3.1.22 doesn't exist |  | No | Update reference | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3240600023 | 10/01/2007 17:40:42 EDT | 45 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 36 | Producer | Disapprove | Editorial | 69 | 7.4.6.3 | 9 | "Transmit Power element" |  | No | Change to field | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3240500023 | 10/01/2007 17:40:42 EDT | 44 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 35 | Producer | Disapprove | Technical | 67 | 7.4.6 | 28 | 11y is creating an Action Category of value Public. MPs belong in this category. |  | Yes | Move MPs to Public action frames. Change 7.4.6.7, 11.3 to suit | O | PROPOSED ACCEPT IN PRINCIPLE. Editor shall implement 07/2669r0 Section 2, wherein 11k is more closely harmonized with the MBSSID material in 11v, and MPs are converted to Action frames of Category Public. | Hart
3240400023 | 10/01/2007 17:40:42 EDT | 43 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 34 | Producer | Disapprove | Technical | 66 | 7.3.2.44a | 25 | There are no enables for 11k measurements in the beacon & probeReq |  | Yes | Add an enable for AP-side measurements so the AP has parity with the client | O | PROPOSED ACCEPT. Information Elements in the Beacon and Probe Response are also indicated in the Supported RRM Bitmask IE | Ganesh
3240300023 | 10/01/2007 17:40:42 EDT | 42 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 33 | Producer | Disapprove | Technical | 66 | 7.3.2.44a | 15 | Maximum Measurement Duration is for the serving channel. |  | Yes | First and foremost Maximum Measurement Duration should be for off-channel measurements. Probably we are best off with off-channel and on-channel durations. | O | PROPOSED ACCEPT IN PRINCIPLE. Two durations are now defined. Bitmask:20-22 for on channel and BitMask:42-45 for off channel Measurements. See 2665/r0. | Ganesh
3240200023 | 10/01/2007 17:40:42 EDT | 41 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 32 | Producer | Disapprove | Technical | 66 | 7.3.2.44a | 6 | Does MIB support need to be sent over the air? Most users will be over the wire. |  | Yes | Delete from table | O | PROPOSED REJECT. Accept that this bit is not needed but defined for completeness. | Ganesh
3240100023 | 10/01/2007 17:40:42 EDT | 40 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 31 | Producer | Disapprove | Editorial | 65 | 7.3.2.44a | 43 | "as described in" for bitpos 15,16 |  | No | See x2 | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3240000023 | 10/01/2007 17:40:42 EDT | 39 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 30 | Producer | Disapprove | Technical | 65 | 7.3.2.44a | 18 | Tie description to MIB variables where they exist |  | Yes | e.g. refer to dot11TableBeacon MeasurementEnabled | O |  | Kwak
3239900023 | 10/01/2007 17:40:42 EDT | 38 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 29 | Producer | Disapprove | Technical | 65 | 7.3.2.44a | 26 | Beacon Req/Rep is silent on "Reporting Detail". More gneerally, how does this table extend if extra options are added. |  | Yes | Rewrite language to indicate that support is for non-optional features/subelements, & explicitly note if this is not the case. Add an extra bit for Reporting Detail? Also Azimuth in LCI? | O | PROPOSED ACCEPT IN PRINCIPLE. RRM Capability Bitmask is redefined as an octet string and is extensible. Beacon Req/Rep reporting detail and Azimuth are now included in the bitmask. See 2665/r0. | Ganesh
3239800023 | 10/01/2007 17:40:42 EDT | 37 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 28 | Producer | Disapprove | Technical | 64 | 7.3.2.44a | 40 | "=0 and =1 must be complementary conditions. Bitpos 3, 4,6,9,17,18 are not. |  | Yes | Rewrite to be complementary. E.g. "=0 otherwise" throughout table | O | PROPOSED ACCEPT IN PRINCIPLE. See 2665/r0. | Ganesh
3239700023 | 10/01/2007 17:40:42 EDT | 36 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 27 | Producer | Disapprove | Technical | 60 | 7.3.2.42 | 30 | No text for MBSSID element |  | Yes | Insert "If present, the multiple BSSID element indicates the range of BSSIDs of the Virtual AP Set that the Measurement Pilot is transmitted on behalf of." | O | PROPOSED ACCEPT IN PRINCIPLE. Editor shall implement 07/2669r0 Section 2, wherein 11k is more closely harmonized with the MBSSID material in 11v, and MPs are converted to Action frames of Category Public. | Hart
3239600023 | 10/01/2007 17:40:42 EDT | 35 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 26 | Producer | Disapprove | Technical | 60 | 7.3.2.41 | 1 | Not really "units" |  | Yes | Replace by "0.5 dB steps" | O | PROPOSED ACCEPT IN PRINCIPLE. Change "units" to "steps" (two times in this subclause) | Hart
3239500023 | 10/01/2007 17:40:42 EDT | 34 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 25 | Producer | Disapprove | Technical | 59 | 7.3.2.40 | 27 | The antenna ID field is used in the MeasRep, not the antenna element. |  | Yes | Move this descriptive text elsewhere; e.g. create an antenna ID field description. | O | PROPOSED ACCEPT IN PRINCIPLE. The Antenna Information element is defined only in one place and contains the definition of the Antenna ID field, which is also defined only in one place. Moving the field description to another new paragraph would not change the draft in any way and editorially is not the most compact solution. All references to Antenna Information or Antenna ID should be made to 7.3.2.40. There are errors in the draft. P69L44&47 change "7.3.2.30" to "7.3.2.40". P98L39&43: change "7.3.2.29" to"7.3.2.40". | Hart
3239400023 | 10/01/2007 17:40:42 EDT | 33 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 24 | Producer | Disapprove | Technical | 56 | 7.3.2.37 | 25 | Make MPI sub-element same as MPTI element. This has MBSSID as a subelement. |  | Yes | Delete MBSSID as a subelement. Delete definition of mpi subelement and replace by definition of MPTI subelement as same as MPTI element. | O | PROPOSED ACCEPT IN PRINCIPLE. Editor shall implement 07/2669r0 Section 2, wherein 11k is more closely harmonized with the MBSSID material in 11v, and MPs are converted to Action frames of Category Public. | Hart
3239300023 | 10/01/2007 17:40:42 EDT | 32 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 23 | Producer | Disapprove | Editorial | 56 | 7.3.2.37 | 1 | "elemetns" |  | No | Fix typo | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak
3239200023 | 10/01/2007 17:40:42 EDT | 31 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 22 | Producer | Disapprove | Technical | 53 | 7.3.2.36 | 36 | "to find an AP" is ambiguous |  | Yes | Change to "to find an AP other than itself" | O | PROPOSED ACCEPT IN PRINCIPLE. Add new 11.10.14 AP Channel Report: "The AP Channel Report element contains a list of channels in a regulatory class where a STA is likely to find an AP, excluding the AP transmitting the AP Channel Report. An AP Channel Report element only includes channels that are valid for the regulatory domaine in which the AP transmitting the element is operating and consistent with the Country element in the frame in which it appears. One AP Channel Report element is included in the Beacon frame for each regulatory domain which includes channels on which a STA is likely to find an AP. The contents of the AP Channel Report elements may be compiled from the list of unique regulatory/channel pairs found in the Neighbor Report. The contents of the AP channel report may be configured or obtained by other means beyond the scope of this specification." P53L37: add new sentence "See 11.10.14 for details." Delete P54L8&9 as this is now part of 11.10.14. | Kwak
3239100023 | 10/01/2007 17:40:42 EDT | 30 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 21 | Producer | Disapprove | Technical | 48 | 7.3.2.22.9 | 33 | Azimuth Report is 2 octets |  | Yes | 1 -> 2 | O | PROPOSED ACCEPT IN PRINCIPLE based on discussion in 07/2661r2: 157 | Ecclesine
3239000023 | 10/01/2007 17:40:42 EDT | 29 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 20 | Producer | Disapprove | Editorial | 38 | 7.3.2.22.7 | 11 | defined _ _ an (double space) |  | No | Convert to single space | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3238900023 | 10/01/2007 17:40:42 EDT | 28 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 19 | Producer | Disapprove | Editorial | 31 | 7.3.2.22 | 37 | Also line 39. is -> are |  | No | is -> are, 2x | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3238800023 | 10/01/2007 17:40:42 EDT | 27 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 18 | Producer | Disapprove | Editorial | 29 | 7.3.2.21.10 | 17 | Triggered Reporting field is separate . |  | No | Merge diagrams 7062ib and j. Delete line "The Triggered Reporting field & Fig 7-62j" | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3238700023 | 10/01/2007 17:40:42 EDT | 26 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 17 | Producer | Disapprove | Technical | 21 | 7.3.21.6 | 22 | Bit labels are wrong |  | Yes | B5-B7 at top; 5 and 3 at bottom | O | PROPOSED ACCEPT. | Kwak
3238600023 | 10/01/2007 17:40:42 EDT | 25 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 16 | Producer | Disapprove | Editorial | 20 | 7.3.21.5 | 4 | Here and elsewhere in 7.3.2.21.x and 7.3.2.21.x, subelement format should precede subelement description. Refer to a common subelement format diagram. |  | Yes | Move the "The only optional & VS sub-element" to be after "Any optional & non-decreasing & ID". At least 5 occurrences. If not present already, add at the para start ""The format of the optional sub-lements is shown in Figure xxx." Use a common figure for all of section 7.3.2.21 and .22. | O | PROPOSED ACCEPT IN PRINCIPLE. | Editor
3238500023 | 10/01/2007 17:40:42 EDT | 24 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 15 | Producer | Disapprove | Editorial | 19 | 7.3.21.4 | 26 | Remove "only" and make singular |  | No | Change to "The optional sub-element defined is the Vendor Specific subelement &. The VS subelement has the same format as the corresponding element" | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3238400023 | 10/01/2007 17:40:42 EDT | 23 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 14 | Producer | Disapprove | Technical | 17 | 7.3.2.21 | 5 | should |  | No | is | O | PROPOSED ACCEPT. | Kwak
3238300023 | 10/01/2007 17:40:42 EDT | 22 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 13 | Producer | Disapprove | Editorial | 14 | 7.3.2 | 38 | Editors note is outdated |  | Yes | Remove | O | PROPOSED ACCEPT. | Editor
3238200023 | 10/01/2007 17:40:42 EDT | 21 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 12 | Producer | Disapprove | Technical | 8 | 7.2.3.1 | 44 | Measurement Pilot element not present in the beacon |  | Yes | Add to the beacon | O | PROPOSED ACCEPT IN PRINCIPLE. Editor shall implement 07/2669r0 Section 2, wherein 11k is more closely harmonized with the MBSSID material in 11v, and MPs are converted to Action frames of Category Public. | Hart
3238100023 | 10/01/2007 17:40:42 EDT | 20 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 11 | Producer | Disapprove | Technical | 8 | 7.2.3.1 | 44 | Re reducing beacon bloat, we have done "X is present if Y and if Z" for the new 11k elements |  | Yes | Change to "X is present if Y and if Z. X can be present if Y" for the new 11k elements. | O | PROPOSED ACCEPT IN PRINCIPLE. Editor shall implement 07/2669r0 Section 1, wherein valueless elements may now be optionally removed | Hart
3238000023 | 10/01/2007 17:40:42 EDT | 19 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 10 | Producer | Disapprove | Technical | 5 | 5.2.7.5 | 27 | "CCA indicates idle" |  | Yes | Inconsistent with 11.10.8.4 | O | PROPOSED ACCEPT IN PRINCIPLE. Change "when CCA indicates idle" to "when virtual carrier sense indicates idle and the STA is neither transmitting nor receiving a frame" | Hart
3237900023 | 10/01/2007 17:40:42 EDT | 18 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 9 | Producer | Disapprove | Editorial | 4 | 5.2.7 | 20 | request/response |  | No | request/report. Ditto response-only -> report-only | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3237800023 | 10/01/2007 17:40:42 EDT | 17 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 8 | Producer | Disapprove | Editorial | 2 | 3.79a | 33 | ", includes" |  | No | "; includes" | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3237700023 | 10/01/2007 17:40:42 EDT | 16 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 7 | Producer | Disapprove | Technical | 1 | All | 1 | There are technical problems with the draft: e.g. P2L17, ANPI definition has "but" yet this should be "and" or "," |  | Yes | Fix | O | PROPOSED ACCEPT IN PRINCIPLE. Replace ", i.e.,…." with "as defined by three simultaneous conditions: 1) the Virtual CS mechanism indicates idle chanel, 2) the STA is not transmitting a frame, and 3) the STA is not receiving a frame." | Kwak
3237600023 | 10/01/2007 17:40:42 EDT | 15 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 6 | Producer | Disapprove | Technical | 53 | 7.3.2.43 |  | Daves: CID 84 refers to 07/2327r2 wherein the text states, "An Available Admission Capacity value of 0 transmitted in the BSS Available Admission Capacity element indicates that no admission capacity is available at the calculation time and that no explicit admissions will be granted by the AP for that UP or AC category at the calculation time." This is meaningless since the non-AP STA has no way of knowing the "calculation time". |  | Yes | Delete these two sentences since the final paragraph stating, "Note: STAs are advised that requesting admission for any TSPEC at an UP or AC which requires more medium time than is reported as available for the requested UP or AC is possible yet unlikely to be successful." suffices. | O | PROPOSED ACCEPT IN PRINCIPLE. P121L15 replace second "at the calculation time" with "unless additional capacity subsequently becomes available".. | Kwak
3237500023 | 10/01/2007 17:40:42 EDT | 14 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 5 | Producer | Disapprove | Editorial | 53 | 7.3.2.43 |  | Daves: CID 84 refers to 07/2327r2 wherein the phrase "AC category" is used in several places. The term AC (from IEEE 802.11-2007 clause 4) means access category. Therefore the phrase "AC category" can be translated to "access category category" which is redundant. |  | Yes | Delete the word "category" wherever the referenced phrase occurs. | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3237400023 | 10/01/2007 17:40:42 EDT | 13 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 4 | Producer | Disapprove | Technical | 9 | 7.2.3.1 | 9 | Daves: Although I agree with the intent of the resolution to CID 85 (that is, reducing beacon bloat), the proposed resolution conditionally and dynamically adds and removes information elements to beacon frames. This un-necessarily complicates beacon generation. To my knowledge, this has never been done (with the exception of CSA--which has a very different use case) and could possible break some STA implementations. |  | Yes | Define a MIB variable which allows these elements to be conditionally used in the beacon dependent on whether the MIB variable is true or false. This allows the elements in the beacon to be statically present. I suspect there are other solutions which have a similar characteristic. | O | WITHDRAWN by commenter | Hart
3237300023 | 10/01/2007 17:40:42 EDT | 12 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 3 | Producer | Disapprove | Technical | 3 | 4 | 30 | Daves: Resolution to CID 83 provides a definition of "3.999k Virtual AP Set" which is un-intelligible. If it is really this complicated, an example should be provided. |  | Yes | Simplify the definition. | O | WITHDRAWN by commenter | Hart
3237200023 | 10/01/2007 17:40:42 EDT | 11 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 2 | Producer | Disapprove | Technical | 3 | 4 | 30 | Daves: Resolution to CID 83 proposes changing frame subtype of Measurement Pilot to an Action frame. The problem with this is that a STA's MAC can which is looking for a MP frame can no longer filter based on frame subtype; the STA's MAC now has to accept all action frames and parse the category and action fields to determine whether it is the MP frame. Moreover, since MPs are transmitted to the broadcast destination MAC address, all STAs must receive and process them (at least as far as to delete them after some parsing) even when they are not interested in them. This is inefficient. |  | Yes | Re-instate old subtype. | O | WITHDRAWN by commenter | Hart
3237100023 | 10/01/2007 17:40:42 EDT | 10 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 1 | Producer | Disapprove | Technical | 85 | 11.1 | 35 | Daves: There are, what I consider to be, several errors in the submission 07/2285r0. They are: 1. RRM Capability Enabled Bitmask element is not present in Beacon frames (but is present in Probe Response frames) 2. First sentence in clause 7.3.2.45 gives incorrect length (4) of this element. Length should be 6 octets. 3. There is a <tbd> in notes for measurement pilot capability. 4. Definitions for new MIB table entries are undefined. |  | Yes | 1. Add the element to the beacon frame. 2. Change the text. 3. Fix TBD or provide an editing instruction. 4. Supply text for new MIB variables. | O | WITHDRAWN by commenter | Hart
3233500023 | 10/01/2007 09:43:01 EDT | 9 | Stephens, Adrian P | adrian.p.stephens@intel.com | +44 1223 763457 | Individual | 9 | Producer | Approve | Editorial |  |  |  | General - Figure numbering of Figure 7-68la using "a" as an "insertion after" causes problems. |  | No | Use alternating letters and numbers e.g. Figure 7-68l1 (ell, one) Make similar changes throughout where necessary to table and figure numbers. | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3233400023 | 10/01/2007 09:43:01 EDT | 8 | Stephens, Adrian P | adrian.p.stephens@intel.com | +44 1223 763457 | Individual | 8 | Producer | Approve | Editorial |  | 11.10.13 |  | "<mu>sec" - not the correct abbreviation (can't quote <mu> directly due to limitation of this tool) |  | No | should be <mu>s | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3233300023 | 10/01/2007 09:43:01 EDT | 7 | Stephens, Adrian P | adrian.p.stephens@intel.com | +44 1223 763457 | Individual | 7 | Producer | Approve | Editorial |  | 11.10.7 |  | The uncaptioned figure in this subclause is a mess. Why the big and little arrows? Why no caption? The text appears to be a low resolution font. |  | No | Redraw and add a caption. | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3233200023 | 10/01/2007 09:43:01 EDT | 6 | Stephens, Adrian P | adrian.p.stephens@intel.com | +44 1223 763457 | Individual | 6 | Producer | Approve | General |  | 11.10.3 |  | "Maximum Measurement Duration in TUs = 2 ^ (dot11MaximumMeasurementDuration - 4) * TBTT" Most, but not all, people will know ^ means exponentiation. |  | No | Either define this operator or use superscript to show the exponent. | O | PROPOSED ACCEPT IN PRINCIPLE | Kwak
3233100023 | 10/01/2007 09:43:01 EDT | 5 | Stephens, Adrian P | adrian.p.stephens@intel.com | +44 1223 763457 | Individual | 5 | Producer | Approve | Technical |  | 11.3 |  | "Action: Within an infrastructure BSS, action frames are class 3 except for Action frames with Category field equal to Radio Measurement and Action field equal to Measurement Pilot." An Action frame is not a control frame - wrong subtype. |  | No | Remove this bullet item. | O | PROPOSED ACCEPT IN PRINCIPLE. Editor shall implement 07/2669r0 Section 2, wherein 11k is more closely harmonized with the MBSSID material in 11v, and MPs are converted to Action frames of Category Public. | Hart
3233000023 | 10/01/2007 09:43:01 EDT | 4 | Stephens, Adrian P | adrian.p.stephens@intel.com | +44 1223 763457 | Individual | 4 | Producer | Approve | Editorial |  | 7.3.2.37 |  | "sub-elemetns" - please run the speelung chocker. |  | No |  | O | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Editor
3232900023 | 10/01/2007 09:43:01 EDT | 3 | Stephens, Adrian P | adrian.p.stephens@intel.com | +44 1223 763457 | Individual | 3 | Producer | Approve | Editorial |  | 7.3.2.22.8 |  | Figure 7-68j. I have to contratulate this group on finding yet another way to express a frame format. |  | No | Seeing as you need a table, define the structure in the table, rather than requiring a figure and a table. | O | PROPOSED REJECT. The issue is not the % of wireless capacity or STA capacity used by radio measurements, it is to consider each STA’s service load, power state and operating conditions. The AP has to consider traffic load and application requirements, regulatory requirements and specific measurement states from every STA in support of wireless network management. Guidelines and limits would have to consider regulatory requirements like 4 msec carrier sense and the detection of one microsecond radar pulses in Japan. There are no typical scenarios that describe 802.11 operation in all bands in most circumstances. Off-channel measurements are desireable to gather timely information about which channel to switch BSS operation to, and the noiser the operating environment, the more urgent the need for radio measurements off the serving channel. In any case, the STA can refuse any measurement request. We are unable to support a limit to measurements which precludes ‘normal’ 802.11 operation in a noisy environment, where collisions cause many retries. | Ecclesine
3232800023 | 10/01/2007 09:43:01 EDT | 2 | Stephens, Adrian P | adrian.p.stephens@intel.com | +44 1223 763457 | Individual | 2 | Producer | Approve | General |  | 5.2.7.2 |  | "pseudo-periodically" - ug. If "pseudo-" adds any value, define this term, otherwise remove it. |  | No | Remove "pseudo-" | O | PROPOSED ACCEPT IN PRINCIPLE | Kwak
3232700023 | 10/01/2007 09:43:01 EDT | 1 | Stephens, Adrian P | adrian.p.stephens@intel.com | +44 1223 763457 | Individual | 1 | Producer | Approve | Technical |  |  |  | Subclause 3.168b - This is a horribly confusing definition. That aside, what is the "n" in this definition? |  | No | Define or constrain the range of n. | O | PROPOSED ACCEPT IN PRINCIPLE. Editor shall implement 07/2669r0 Section 2, wherein 11k is more closely harmonized with the MBSSID material in 11v, and MPs are converted to Action frames of Category Public. | Kwak

## Approved Resolutions
3248100023 | 10/02/2007 16:48:55 EDT | 81 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 71 | Producer | Disapprove | Technical | 85 | 11.1 | 35 | Daves: There are, what I consider to be, several errors in the submission 07/2285r0. They are: [7.2.3.1; 7.2.3.8; 7.2.3.9] 1. RRM Capability Enabled Bitmask element is not present in Beacon frames (but is present in Probe Response frames) [Present in neither] [7.3.2.44a] 2. First sentence in clause 7.3.2.45 gives incorrect length (4) of this element. Length should be 6 octets. [???] 3. There is a <tbd> in notes for measurement pilot capability. [No TBD's in draft9.0] [Annex D/Q] 4. Definitions for new MIB table entries are undefined. | Yes | 1. Add the element to the beacon frame. 2. Change the text. 3. Fix TBD or provide an editing instruction. 4. Supply text for new MIB variables. | O | Part-1 of this comment needs more discussion in the CRCommitee. There are two options. (a) Make no additional changes to RRM Capability Enabled Bitmask beyond what is described in document 07/2665r1. Arguments in support of this are (1) RRM Capability Enabled Bitmask is already complex, do not make it more complex, (2) Passive scanning DFS STAs can first listen to beacons, determine what channels are safe for transmission, send probe request on one of those channels and obtain the RRM Capability Enabled Bitmask corresponding to an AP, (3) in a typical enterprise environment, all APs are homogeniously configured -- meaning if RRM Capability Enabled Bitmask of an AP in the enterprise is known, RRM Capability Enabled Bitmask of all APs in that Mobility Domain is known and (4) RRM Capabiltiy Enabled Bitmask represents static information (STAs RRM capability is not expected to change on the fly) and hence including this information in the Beacon provides no additional information (and hence wasteful). (b) Beacon and Probe Response frames provide a high level RRM capability description -- this corresponds to the 9 measurements (1) Channel Load, (2) Noise Histogram, (3) Beacon Report, (4) Frame Measurement, (5) Statistics, (6) LCI, (7) Transmit Stream Measurements, (8) Measurement Pause, (9) Measurement Pilot, (10) Neighbor Report and (11) Link Measurement -- and hence is a 2 octet capability bitmask. Based on this information, the STA can select one of the many APs in the radio range for association and obtain more detailed RRM capability information at that time. Part-2, 3 and 4 are addressed in document 07/2665r1. | Hart
3244000023 | 10/01/2007 17:40:42 EDT | 79 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 70 | Producer | Disapprove | Technical | 144 | D | 15 | Review from P144L15 to P151L29 and move to Annex Q is referenced from Annex Q and nowhere else | Yes | Review from P144L15 to P151L29 and move to Annex Q if referenced from Annex Q and nowhere else | W | PROPOSED ACCEPT IN PRINCIPLE. See document 07/2750r0. P145L38 -- P145L44 Change; there is a corresponding entry in dot11StationConfigEntry P145L45 -- P146L13 Delete P146L14 – P146L20 Change; there is a corresponding entry in dot11StationConfigEntry P147L39 – P147L40 delete and add to the end of dot11StationConfigEntry P147L45 – P148L15 delete and add after the last entry describing the entries in dot11StationConfigurationEntry. P148L17 – P151L29 Delete and move to Annex-Q after dot11SMTRRMConfig. | Ganesh
3243700023 | 10/01/2007 17:40:42 EDT | 76 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 67 | Producer | Disapprove | Technical | 138 | A.4.17 | 7 | No PICS for Reporting Detail or AP channel list as a subelement | Yes | Add PICS entries | W | PROPOSED ACCEPT IN PRINCIPLE. See document 07/2750r0. PICS (Annex-A) is now updated to include all elements that can be requested using the optional sub-elements. RRM4.7 is the only entry that needs to be added. Azimuth is covered by RRM9.3 and Triggered Transmit Stream/Category Measurement is covered by RRM10.3. | Ganesh
3240000023 | 10/01/2007 17:40:42 EDT | 39 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 30 | Producer | Disapprove | Technical | 65 | 7.3.2.44a | 18 | Tie description to MIB variables where they exist | Yes | e.g. refer to dot11TableBeacon MeasurementEnabled | W | PROPOSED ACCEPT IN PRINCIPPLE. See document 07/2665r1. Table 7-43ca now uses the MIB variables in the description of the individual bits in the bitmask. | Ganesh