## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-08/0226r0
Venue Date: | January 2008
First Author: | Peter Ecclesine, Cisco
Subject: | P802.11y_D7.0 comments spreadsheet
Full Date: | 2008-01-31
Author(s): | Name(s) | Peter Ecclesine
| Affiliation | Cisco
| Address | 170 W. Tasman Dr., San Jose, CA 95134-1706
| Phone: | +1-408-527-0815
Fax:
| email: | petere@cisco.com
Abstract:
P802.11y Sponsor Ballot of D7.0 started 21 Dec, 2007 at 23:59 ET, and completed 30 Jan, 2008 at 23:59 ET. This spreadsheet records the comments received.

## Initial Comments
Comment ID | Date | Comment # | Name | Email | Phone | Style | Index # | Classification | Vote | Category | Page | Subclause | Line | Comment | File | Must Be Satisfied | Proposed Change | Resolution Status | Resolution Detail | Other1 | Other2 | Other3
3797200023 | 01/30/2008 23:54:41 EST | 146 | Palm, Stephen | X | X | Individual | 5 | General Interest | Disapprove | Editorial | 29 | 9.8.4 | 46 | use a non-breaking hyphen in aSlot-Time |  | Yes | use a non-breaking hyphen in aSlot-Time |  |  | AIP |  | editor
3797100023 | 01/30/2008 23:51:26 EST | 145 | Palm, Stephen | X | X | Individual | 4 | General Interest | Disapprove | Technical | 28 | 9.8.1 | 60 | "accross" seems to have specialized but undefined regulatory meaning |  | Yes | Clarify
3797000023 | 01/30/2008 21:23:34 EST | 144 | Myles, Andrew | X | X | Individual | 9 | Producer | Disapprove | Technical |  | 11.9a.1 |  | ECS has been described in terms of the regulations in the 3.6GHz band in the US However, ECS is a general features that does not need justification in this way |  | No | Remove all references to 3.6GHz band in 11.9a.1 (and in 11.9a.3.1/2 and 11.9.3.2). The use of ECS to satisfy 3.6GHz band rules can be described in a new section (probably 11.11.x) |  |  | AIP
3796900023 | 01/30/2008 21:23:34 EST | 143 | Myles, Andrew | X | X | Individual | 8 | Producer | Disapprove | Technical |  | 11.9a.1 |  | The text uses "dependent station" rather than "dependent STA". Are they the same? |  | No | If they are the same change the text to use one term only |  |  | AIP
3796800023 | 01/30/2008 21:23:34 EST | 142 | Myles, Andrew | X | X | Individual | 7 | Producer | Disapprove | Technical |  | 7.4.7.3 |  | The text mentions a "DSE STA" Where is this defined? |  | No | Clarify
3796700023 | 01/30/2008 21:23:34 EST | 141 | Myles, Andrew | X | X | Individual | 6 | Producer | Disapprove | Technical |  | 7.3.2.54 |  | The "Supported Regulatory Classes" element defines the regulatory classes that are supported What does it mean to "support" a regulatory class |  | No | Clarify |  |  | AIP
3796600023 | 01/30/2008 21:23:34 EST | 140 | Myles, Andrew | X | X | Individual | 5 | Producer | Disapprove | Technical | 3 | 5.2.8.2 |  | The text states "The base level privilege of a registered STA is the ability to operate autonomously on a restricted channel (the STA does not need to participate in the DSE process)." This may be true for 3.65GHz band but is not necessarily true for other bands, ie in general terms registration does not always mean autonomous operation is allowed. I suspect what to you are really saying is that you are going to define a "registered STA" as one that is allowed to operate autonomously. |  | No | Rewrite so that a registered STA is defined as one that is allowed to operate autonomously |  |  |  |  | ScottB
3796500023 | 01/30/2008 21:23:34 EST | 139 | Myles, Andrew | X | X | Individual | 4 | Producer | Disapprove | Editorial | 1 | 3.52a |  | The text defines "extended channel switching" as "To simultaneously change either or both operating channel and Regulatory Class" However, one cannot "simultaneously" change "either" |  | No | Rewrite to avoid an impossibility |  |  |  |  | ScottB
3796400023 | 01/30/2008 21:23:34 EST | 138 | Myles, Andrew | X | X | Individual | 3 | Producer | Disapprove | Editorial | 1 | 3.52a |  | The text defines "extended channel switching" as "To simultaneously change either or both operating channel and Regulatory Class" However, this is an unsatisfatory definition because it is not a complete sentence. |  | No | Rewrite as a complete sentence |  |  |  |  | ScottB
3796300023 | 01/30/2008 21:23:34 EST | 137 | Myles, Andrew | X | X | Individual | 2 | Producer | Disapprove | Technical | 2 | 5.2.8 |  | The text mentions amendments to the standard. However, the standard should not mention the amendments because the amendments are technicaly part of the standard |  | No | Rewrite clause to remove reference to amendments |  |  |  |  | ScottB
3796200023 | 01/30/2008 21:23:34 EST | 136 | Myles, Andrew | X | X | Individual | 1 | Producer | Disapprove | Technical | 2 | 5.1.1.1 |  | The draft makes various changes to the text that seem to say that the function of aSTA can be modified. It is not clear why this is useful |  | No | Explain why changes to 5.1.1.1 are useful |  |  |  |  | ScottB
3796100023 | 01/30/2008 21:08:47 EST | 135 | Kwak, Joseph | X | X | Individual | 24 | User | Disapprove | Editorial | 65 | I.2.4 | 30 | Table 145 does not exist. |  | No | Should be Table 17-13 (?). |  |  | A |  | editor
3796000023 | 01/30/2008 21:08:47 EST | 134 | Kwak, Joseph | X | X | Individual | 23 | User | Disapprove | Technical | 65 | I.2.4 | 27 | Received signal strength (RSSI) cannot be used for any quantitative and verifiable performance requirement. RSSI is not defined in base standard. CCA-ED performance (which relies on RSSI) is not defined in base standard and cannot be used for any new Tgy performance requirements. |  | Yes | Suggest that Tgy modify the TGk defined IPI measurments (in 12.3.5) to include new performance spec for accuracy of idle power measurement. Then Tgy should modify CCA-ED to rely on measurement of IPI values (in place of RSSI) for its specified and testable performance. Otherwise strike out all references to CCA-ED in the TGy draft. Repeating the errors of the past will only further degrade the baseline standard going forward.
3795900023 | 01/30/2008 21:08:47 EST | 133 | Kwak, Joseph | X | X | Individual | 22 | User | Disapprove | Technical | 51 | A.4.18 | 52 | Use TGk Frame request/report in place of DSE request/report |  | Yes | Replace "DSE" with "Frame" in 3 places in column 2. Replace in column 4 "CF1" with "CF1&CF13&RRM5". Replace in column 4 "CF2" with "CF2&CF13&RRM5".
3795800023 | 01/30/2008 21:08:47 EST | 132 | Kwak, Joseph | X | X | Individual | 21 | User | Disapprove | Technical | 47 | 17.3.10.5 | 62 | Received signal strength (RSSI) cannot be used for any quantitative and verifiable performance requirement. RSSI is not defined in base standard. CCA-ED performance (which relies on RSSI) is not defined in base standard and cannot be used for any new Tgy performance requirements. |  | Yes | Suggest that Tgy modify the TGk defined IPI measurments (in 12.3.5) to include new performance spec for accuracy of idle power measurement. Then Tgy should modify CCA-ED to rely on measurement of IPI values (in place of RSSI) for its specified and testable performance. Otherwise strike out all references to CCA-ED in the TGy draft. Repeating the errors of the past will only further degrade the baseline standard going forward.
3795700023 | 01/30/2008 21:08:47 EST | 131 | Kwak, Joseph | X | X | Individual | 20 | User | Disapprove | Technical | 44 | 11.11.4 | 18 | An enabled STA which is not providing any data services will not transmit DSE Registered Announcment frames. This will not permit coordinated ECS. |  | Yes | Add new sentence: "After any Extended Channel Switch, a dependent STA which is not providing any data services shall select a random time delay less than 300 msec; at the end of this delay the STA shall broadcast a DSE Registered Location Announcment frame." |  |  | R
3795600023 | 01/30/2008 21:08:47 EST | 130 | Kwak, Joseph | X | X | Individual | 19 | User | Disapprove | Technical | 44 | 11.11.4 | 15 | DSE Registered Location Announcement must never be encrypted. |  | Yes | Change "Action frame" to "unencrypted action frame" |  |  | R
3795500023 | 01/30/2008 21:08:47 EST | 129 | Kwak, Joseph | X | X | Individual | 18 | User | Disapprove | Technical | 36 | 11.9a.1 | 53 | What ECS procdures? Reference is not defined. |  | Yes | Define ECS procedures for non-AP STAs. All procedures here are limited to AP procedures. And even in this regard, there is no requirement for the AP to switch to advertised channel at any specific time. |  |  | AIP
3795400023 | 01/30/2008 21:08:47 EST | 128 | Kwak, Joseph | X | X | Individual | 17 | User | Disapprove | Technical | 42 | 11.11.4 |  | Procedure incomplete. |  | Yes | Need to add states to state machine for deenablement; need to add related text describing deenablement states, including path for denial of deenablement.
3795300023 | 01/30/2008 21:08:47 EST | 127 | Kwak, Joseph | X | X | Individual | 16 | User | Disapprove | Technical | 41 | 11.11.1.4 |  | Procedure incomplete. |  | Yes | Need to add procedure details for responder STA to deny deenablement and describe conditions to determine success vs failure to deenable. |  |  | R
3795200023 | 01/30/2008 21:08:47 EST | 126 | Kwak, Joseph | X | X | Individual | 15 | User | Disapprove | Technical | 40 | 11.11.1.2 |  | Procedure incomplete. |  | Yes | Need to add procedure details for responder STA to deny enablement and describe conditions to determine success vs failure to enable. |  |  | R
3795100023 | 01/30/2008 21:08:47 EST | 125 | Kwak, Joseph | X | X | Individual | 14 | User | Disapprove | Technical | 37 | 11.9a.3.1 | 12 | Incomplete description of requirement. |  | Yes | Needs rewording. "advertise with same parameters" doesn't describe requirement on AP to initiate the ECS procedures itself. New TBTT downcounter must be initialized and updated at each beacon transmission. Furthermore the Channel Switch count parameter received by the AP must NOT be retransmitted as indicated. The channel count value needs to be updated before each transmission.
3795000023 | 01/30/2008 21:08:47 EST | 124 | Kwak, Joseph | X | X | Individual | 13 | User | Disapprove | Technical | 36 | 11.9a |  | Imprecise use of "new channel" throughout this clause. |  | Yes | Change "new channel" to "new channel and/or new regulatory class" in all places in this clause. |  |  | AIP
3794900023 | 01/30/2008 21:08:47 EST | 123 | Kwak, Joseph | X | X | Individual | 12 | User | Disapprove | Technical | 15 | 7.4.7.8 |  | The DSE measurement function duplicates the functionality already defined in the TGk Frame Request/Report measurement. |  | Yes | Use and modify the TGk Frame Request/Report measurement in Tgy. A new optional sub-element in the frame measurement request may be used to specify a tailored level of detail for Tgy purposes. New optional sub-elements in the frame measurement report may be defined to deliver the TGy-specific content, DSE LCIs, etc.
3794800023 | 01/30/2008 21:08:47 EST | 122 | Kwak, Joseph | X | X | Individual | 11 | User | Disapprove | Technical | 15 | 7.4.7.8 |  | DSE measurement report is not fully specified. |  | Yes | As indicated in TGk draft, there is a very high overhead of procedure specification text (see TGk 11.10.0 - 11.10.5) needed to unambiguously specify the function of any measurment; Tgy draft does not include such required procedure detail and without such detail, no "standard" STA operation will result. Modify PICS to indicate that TGy STA is required to be TGk STA and will thus implement the already defined procedures for measurement request and report.
3794700023 | 01/30/2008 21:08:47 EST | 121 | Kwak, Joseph | X | X | Individual | 10 | User | Disapprove | Technical | 14 | 7.4.7.7 |  | The DSE measurement function duplicates the functionality already defined in the TGk Frame Request measurement. |  | Yes | Use and modify the TGk Frame Request measurement in Tgy. A new optional sub-element in the frame measurement request may be used to specify a tailored level of detail for Tgy purposes.
3794600023 | 01/30/2008 21:08:47 EST | 120 | Kwak, Joseph | X | X | Individual | 9 | User | Disapprove | Technical | 14 | 7.4.7.7 |  | DSE measurement request not fully specified. |  | Yes | As indicated in TGk draft, there is a very high overhead of procedure specification text (see TGk 11.10.0 - 11.10.5) needed to unambiguously specify the function of any measurment; Tgy draft does not include such required procedure detail and without such detail, no "standard" STA operation will result. Modify PICS to indicate that TGy STA is required to be TGk STA and will thus implement the already defined procedures for measurement request and report.
3794500023 | 01/30/2008 21:08:47 EST | 119 | Kwak, Joseph | X | X | Individual | 8 | User | Disapprove | Technical | 13 | 7.4.7.4 | 33 | Use of "Peer STA" is not clear here. |  | Yes | Elaborate meaning in table or add complete reason code definitions to new referenced clause in procedures, clause 11.
3794400023 | 01/30/2008 21:08:47 EST | 118 | Kwak, Joseph | X | X | Individual | 7 | User | Disapprove | Technical | 12 | 7.4.7.3 | 31 | Use of "Peer STA" is not clear here. |  | Yes | Elaborate meaning in table or add complete reason code definitions to new referenced clause in procedures, clause 11.
3794300023 | 01/30/2008 21:08:47 EST | 117 | Kwak, Joseph | X | X | Individual | 6 | User | Disapprove | Technical | 1 | 3 | 65 | Definition is ambiguous or incomplete. |  | Yes | Change "before it is allowed to transmit" to "to obtain authorization to operate on a restricted channel". |  |  |  |  | ScottB
3794200023 | 01/30/2008 21:08:47 EST | 116 | Kwak, Joseph | X | X | Individual | 5 | User | Disapprove | Technical | 1 | 3 | 61 | Definition is ambiguous or incomplete. |  | Yes | Change "only authorized to operate" to "is operating on a restricted channel as a registered STA with authorization to transmit limited to transmissions from its specific registered location". |  |  |  |  | ScottB
3794100023 | 01/30/2008 21:08:47 EST | 115 | Kwak, Joseph | X | X | Individual | 4 | User | Disapprove | Technical | 1 | 3 | 57 | Definition is ambiguous or incomplete. |  | Yes | Change "To simultaneously change" to "Procedure intitiated by an AP or DFS owner to coordinate a change of"; Change "Class" to "Class for all STAs in a BSS or IBSS" |  |  |  |  | ScottB
3794000023 | 01/30/2008 21:08:47 EST | 114 | Kwak, Joseph | X | X | Individual | 3 | User | Disapprove | Technical | 1 | 3 | 53 | Definition is ambiguous or incomplete. |  | Yes | Change "that broadcasts" to "authorized to operate and operating on a restricted channel to provide DSE and to broadcast". |  |  |  |  | ScottB
3793900023 | 01/30/2008 21:08:47 EST | 113 | Kwak, Joseph | X | X | Individual | 2 | User | Disapprove | Technical | 1 | 3 | 50 | Definition is ambiguous or incomplete. |  | Yes | Change "permission" to "temporary permission (enablement) from an enabling STA". |  |  |  |  | ScottB
3793800023 | 01/30/2008 21:08:47 EST | 112 | Kwak, Joseph | X | X | Individual | 1 | User | Disapprove | Technical | 1 | 3 | 46 | Definition is ambiguous or incomplete. |  | Yes | Change "permitted to transmit" to "permitted to transmit on a restricted channel". |  |  |  |  | ScottB
3793700023 | 01/30/2008 20:07:52 EST | 111 | Palm, Stephen | X | X | Individual | 3 | General Interest | Disapprove | Technical | 14 | 5.1.1.1 | 40 | Mobile STA term not defined nor is is the term used |  | Yes | Clarify and use |  |  |  |  | ScottB
3793600023 | 01/30/2008 20:05:42 EST | 110 | Palm, Stephen | X | X | Individual | 2 | General Interest | Disapprove | Technical | 14 | 5.1.1.1 | 40 | Portable STA term not defined nor is is the term used. |  | Yes | clarify |  |  |  |  | ScottB
3793500023 | 01/30/2008 20:03:31 EST | 109 | Palm, Stephen | X | X | Individual | 1 | General Interest | Disapprove | Technical | 14 | 5.1.1.1 | 46 | Hidden STA not defined |  | Yes | Clarify the term and why it is needed |  |  |  |  | ScottB
3793300023 | 01/30/2008 02:05:38 EST | 108 | Chaplin, Clint | X | X | Individual | 16 | General Interest | Disapprove | Editorial | 41 | 11.11.1.4 | 56 | The Enablement state variable for the deenablement requester STA shall be set to unenabled |  | Yes | The Enablement state variable for the deenablement requester STA shall be set to "unenabled" |  |  | AIP |  | editor
3793200023 | 01/30/2008 02:05:38 EST | 107 | Chaplin, Clint | X | X | Individual | 15 | General Interest | Disapprove | Editorial | 41 | 11.11.1.3 | 43 | If the deenablement is successful, the Enablement state variable for the deenablement responder STA shall be set to unenabled. |  | Yes | If the deenablement is successful, the Enablement state variable for the deenablement responder STA shall be set to "unenabled". |  |  | AIP |  | editor
3793100023 | 01/30/2008 02:05:38 EST | 106 | Chaplin, Clint | X | X | Individual | 14 | General Interest | Disapprove | Editorial | 41 | 11.11.1.3 | 14 | If the Enablement state variable for the deenablement responder STA is enabled, the STA shall send a DSE deenablement frame to the deenablement responder STA. |  | Yes | If the Enablement state variable for the deenablement responder STA is "enabled", the STA shall send a DSE deenablement frame to the deenablement responder STA. |  |  | AIP |  | editor
3793000023 | 01/30/2008 02:05:38 EST | 105 | Chaplin, Clint | X | X | Individual | 13 | General Interest | Disapprove | Editorial | 41 | 11.11.1.2 | 5 | If the enablement is successful, the Enablement state variable for the enablement requester STA shall be set to enabled. |  | Yes | If the enablement is successful, the Enablement state variable for the enablement requester STA shall be set to "enabled". |  |  | AIP |  | editor
3792900023 | 01/30/2008 02:05:38 EST | 104 | Chaplin, Clint | X | X | Individual | 12 | General Interest | Disapprove | Technical |  | 11.11.1.1 |  | The steps listed here are missing one important item: receiving an enablement response message. This section talks about the items in the enablement confirm indication, but doesn't talk about what triggers that indication. |  | Yes | Add a step to receive the enablement response message.
3792800023 | 01/30/2008 02:05:38 EST | 103 | Chaplin, Clint | X | X | Individual | 11 | General Interest | Disapprove | Editorial | 40 | 11.11.1.1 | 30 | If the enablement was successful, the Enablement state variable for the enablement responder STA shall be set to enabled. |  | Yes | If the enablement was successful, the Enablement state variable for the enablement responder STA shall be set to "enabled". |  |  | AIP |  | editor
3792700023 | 01/30/2008 02:05:38 EST | 102 | Chaplin, Clint | X | X | Individual | 10 | General Interest | Disapprove | Editorial | 39 | 11.11.1 | 23 | Enablement state: The values are unenabled and enabled. |  | Yes | Enablement state: The values are "unenabled" and "enabled". |  |  | AIP |  | editor
3792600023 | 01/30/2008 02:05:38 EST | 101 | Chaplin, Clint | X | X | Individual | 9 | General Interest | Disapprove | Technical | 37 | 11.9a.3.1 | 53 | "When a STA with dot11DSERequired false receives an Extended Channel Switch Announcement element" "False receives"? What does that phrase mean? |  | Yes | Clarify, please |  |  | AIP
3792500023 | 01/30/2008 02:05:38 EST | 100 | Chaplin, Clint | X | X | Individual | 8 | General Interest | Disapprove | Editorial | 23 | 10.3.7.4.2 | 42 | "DSEregisteredlocation" doesn't seem to follow the normal capitalization scheme of the other parameters. |  | No | "DSERegisteredLocation" |  |  | R |  | editor
3792400023 | 01/30/2008 02:05:38 EST | 99 | Chaplin, Clint | X | X | Individual | 7 | General Interest | Disapprove | Editorial | 22 | 10.3.7.3.2 | 57 | "DSEregisteredlocation" doesn't seem to follow the normal capitalization scheme of the other parameters. |  | No | "DSERegisteredLocation" |  |  | R |  | editor
3792300023 | 01/30/2008 02:05:38 EST | 98 | Chaplin, Clint | X | X | Individual | 6 | General Interest | Disapprove | Editorial | 20 | 10.3.6.4.2 | 57 | "DSEregisteredlocation" doesn't seem to follow the normal capitalization scheme of the other parameters. |  | No | "DSERegisteredLocation" |  |  | R |  | editor
3792200023 | 01/30/2008 02:05:38 EST | 97 | Chaplin, Clint | X | X | Individual | 5 | General Interest | Disapprove | Editorial | 20 | 10.3.6.3.2 | 8 | "DSEregisteredlocation" doesn't seem to follow the normal capitalization scheme of the other parameters. |  | No | "DSERegisteredLocation" |  |  | R |  | editor
3792100023 | 01/30/2008 02:05:38 EST | 96 | Chaplin, Clint | X | X | Individual | 4 | General Interest | Disapprove | Technical |  | 7.4.7.8 |  | Why is the Length field in the middle of the frame? |  | Yes | Put the Length field between the Action Value field and the Requestor STA Address field |  |  | ?
3792000023 | 01/30/2008 02:05:38 EST | 95 | Chaplin, Clint | X | X | Individual | 3 | General Interest | Disapprove | Technical | 15 | 7.4.7.8 | 33 | "The Length field indicates the length of the remaining frame fields in octets, and is variable." What is variable? The length of the length field? Or the value of the length field? |  | Yes | "The Length field indicates the length of the remaining frame fields in octets, and the value is variable." |  |  | AIP
3791900023 | 01/30/2008 02:05:38 EST | 94 | Chaplin, Clint | X | X | Individual | 2 | General Interest | Disapprove | Technical | 6 | 7.3.2 | 44 | IEEE 802.11k has added a fourth column to this table (7-26) |  | Yes | Add and populate a fourth column to table 7-26. |  |  | A
3791800023 | 01/30/2008 02:05:38 EST | 93 | Chaplin, Clint | X | X | Individual | 1 | General Interest | Disapprove | General |  |  |  | Time to update the copyright notices |  | Yes | Update the copyright notices to 2008 |  |  | A |  | editor
3791700023 | 01/29/2008 15:31:42 EST | 92 | Hart, Brian D | X | X | Individual | 29 | Producer | Approve | Technical | 35 | 11.3 | 44 | Verify changes and changed clause are correct. |  | No | Verify changes and changed clause are correct. Make changes to clause as needed
3790600023 | 01/28/2008 19:34:23 EST | 91 | Stanley, Dorothy | X | X | Individual | 5 | Producer | Approve | Editorial | 67 | J.2 | 22 | "is introduced" will not be accurate with the passage of time. |  | No | Change from "is introduced as a framework" to "provides a framework". Also in line 29, suggest changing from "802.11" to "IEEE Std 802.11" |  |  |  |  | editor
3790500023 | 01/28/2008 19:31:47 EST | 90 | Stanley, Dorothy | X | X | Individual | 4 | Producer | Approve | Technical | 12 | 7.4.7.3 | 10 | The meaning of the "X" markings and all of the blank rows seem incomplete, or not needed. |  | No | Suggest deleting the last two columns of tables 7-57d1 and 7-57d2, and add a text description of the allowed use of the Reason Result Code values.
3790400023 | 01/28/2008 19:24:44 EST | 89 | Stanley, Dorothy | X | X | Individual | 3 | Producer | Approve | Technical | 4 | 7.2.3.1 | 43 | "may be present only if" What is the difference between this and "may be present if" |  | No | Change to "may be present if"
3790300023 | 01/28/2008 19:23:01 EST | 88 | Stanley, Dorothy | X | X | Individual | 2 | Producer | Approve | Editorial | 2 | 5.1.1.1 | 44 | Change from "It is important to realize that a station.." to "A station.." |  | No | As in comment |  |  |  |  | ScottB
3790200023 | 01/28/2008 19:21:32 EST | 87 | Stanley, Dorothy | X | X | Individual | 1 | Producer | Approve | General | 2 | 5.2.8 | 54 | The text describes amendments, which will not be distinct after the amendments will be rolled up into the next revision of the standard |  | No | Change lines 54-59 from "IEEE 802.11 has been amended...... to those specified in this standard." to "IEEE Std 802.11 can be used with a number of frequencies that are licensed by the national regulators for a given country. While effort is made to generalize use of the same bands in other countries, the specification is focused on the rules of a single country. Countries may impose specific requirements for radio equipment in addition to those specified in this standard." |  |  |  |  | ScottB
3790100023 | 01/28/2008 18:17:57 EST | 86 | Ecclesine, Peter | X | X | Individual | 4 | Producer | Disapprove | Technical | 63 | Annex I | 4 | Annex I should be made normative, with an additional sentence at the end of the second paragraph: "The external regulatory references in this annex are informative, and are likely to change." |  | Yes | Change Annex I to be normative, and revise PICs OF3.2.7 and elsewhere to refer to Annex I requirements. |  |  | AIP
3790000023 | 01/28/2008 18:17:57 EST | 85 | Ecclesine, Peter | X | X | Individual | 3 | Producer | Disapprove | Technical | 48 | 17.3.10.5 | 1 | The clause 17 description of the use of CCA-ED in bands where it is not required by Annex J should be normative, not an informative note. |  | Yes | Change text to be a normative paragraph, if necessary add PICs OF2.19.3.3 for those uses.
3789900023 | 01/28/2008 18:17:57 EST | 84 | Ecclesine, Peter | X | X | Individual | 2 | Producer | Disapprove | Technical | 35 | 11.3 | 45 | Because 11y's baseline includes11k, and 11k D12.0 changes clause 11.3 incompletely, 11y must fix whatever errors remain in a2 and c2, as 11y needs them to be correct. |  | No | Review 802.11-2007 as amended by 11k and 11r and 11y, and ensure 11y changes result in correct 11.3 specifications for Public Action frames.
3789800023 | 01/28/2008 18:17:57 EST | 83 | Ecclesine, Peter | X | X | Individual | 1 | Producer | Disapprove | General |  |  |  | The 11y PAR Purpose speaks of extending TPC to this band, but no band-specific extensions are proposed. The 3650 MHz power regulations are in mW/MHz, but existing TPC tools are in Transmit Power and EIRP, and cannot be sent by the Enabling STA to any STA that is not associated with it. |  | Yes | It would be useful to have a Public Action Power Constraint command with units of dB relative to 1 mW/MHz, with Requester STA and Responder STA address fields, so the power constraint can be sent by the Enabling STA to any of its dependent STAs. Commenter will submit draft text revisions to add a DSE Power Constraint frame. |  |  | AIP
3789700023 | 01/28/2008 16:13:16 EST | 82 | Sohrabi, Katayoun | X | X | Individual | 1 | Producer | Approve | Technical | 42 | 11.11.2 | 24 | Subcaluse 11.11.2, line 24, page 42 says: "A registered STA that is not an enabling STA may operate as an AP in an infrastructure BSS, and relay Public Action frames from a dependent STA to its enabling STA." This means a "registered, fixed" station may relay public action frames, including "DSE" related frames on behalf of a dependent STA to an "enabling" station. As a result a dependent STA may become enabled via "indirect" exchange with an enabling STA. At the same time, subcluase 11.11.3, page 42, line 35 says: "Dependent STA operation is conditional on receiving and decoding a DSE registered location element with RegLoc DSE bit set to 1 directly from an enabling STA." This means a dependent STA must received an enabling message DIRECTLY. The above two sentences appear to be in conflict, one allowing INDIRECT "enabling", one requiring DIRECT "enablement". |  | No | Add a clarifying sentence that provides the meaning of "Direct". If indeed the two conditions mentioned above are in conflict, then further clarifying text must be included in the document, and a final decision be made as to whether "indirect" enablement is allowed or not. |  |  | AIP
3788900023 | 01/28/2008 14:30:03 EST | 81 | Hart, Brian D | X | X | Individual | 28 | Producer | Approve | Technical | 47 | 17.3.10.5 | 56 | Appendix I/J define a channelization with overlapping 5 and 10 MHz channels; ditto 10 and 20 overlapping. This leads to poor CCA behavior - devices only defer if very loud. To enable mutually satisfactory sharing, BWs could be aligned, or we could define a better CCA: 10 (20) into 5 (10) and 5 (10) into 10 (20). |  | No | Add an improved CCA, so 20 (10) MHz STAs "may" defer for the frame duration when 10 (5) MHz preambles are detected on their upper or lower half-band. Ditto, in reverse, 10 (5) MHz STAs "may" defer when 20 (10) MHz STAs are transmitting, detected via preamble detection, held by detection of a regular pattern of OFDM symbols with cyclic extensions.
3788800023 | 01/28/2008 14:30:03 EST | 80 | Hart, Brian D | X | X | Individual | 27 | Producer | Approve | Technical | 44 | 11.11.4 | 15 | "shall send &modulo & FragmentCount. When fragments are sent they are sent at SIFS. Another announcementframe cannot be sent mid-frag-ed frame. |  | No | Allow announcement to be sent at end of a frag-ged packet |  |  | AIP
3788700023 | 01/28/2008 14:30:03 EST | 79 | Hart, Brian D | X | X | Individual | 26 | Producer | Approve | Technical | 43 | 11.11.4 | 59 | "shall only transmit for up to & seconds" is ambiguous. Is this actual on-air time, or time from last packet sent minus time from first packet sent? |  | No | Clarify |  |  | AIP
3788600023 | 01/28/2008 14:30:03 EST | 78 | Hart, Brian D | X | X | Individual | 25 | Producer | Approve | Editorial | 43 | 11.11.4 | 47 | Is "as mandated" correct? |  | No | Replace by "mandated to be allowed" |  |  | AIP |  | editor
3788500023 | 01/28/2008 14:30:03 EST | 77 | Hart, Brian D | X | X | Individual | 24 | Producer | Approve | Technical | 42 | 11.11.3 | 41 | "unique among enabled STAs" - hard to do distributedly across the US, unless the id is 48+16 bits (i.e. enabler MAC address + 16 locally administered bits). Or do u mean "unique among STAs enabled by this enabling STA"? Then16 bits is plenty. Or unique within interference range + randomly assigned? |  | No | Clarify or fix |  |  | AIP
3788400023 | 01/28/2008 14:30:03 EST | 76 | Hart, Brian D | X | X | Individual | 23 | Producer | Approve | Technical | 42 | 11.11.2 | 13 | Lines 13-17 are powerfully helpful language. |  | No | Move to or duplicate in 5.2.8.2 and/or 11.11 |  |  | AIP
3788300023 | 01/28/2008 14:30:03 EST | 75 | Hart, Brian D | X | X | Individual | 22 | Producer | Approve | Technical | 41 | 11.11.1.3 | 15 | If enablement state is disabled, is this a success or failure, & what is sent to MLME? |  | No | Add a new reason code.
3788200023 | 01/28/2008 14:30:03 EST | 74 | Hart, Brian D | X | X | Individual | 21 | Producer | Approve | Editorial | 38 | 11.11 | 38 | "satisfy US" |  | No | "satisfy the US" |  |  |  |  | editor
3788100023 | 01/28/2008 14:30:03 EST | 73 | Hart, Brian D | X | X | Individual | 20 | Producer | Approve | Technical | 36 | 11.9a.1 | 55 | May a STA seek parallel enablement by multiple enablers? I assume not, yet "for the enabling STA" seems to imply this is possible. |  | No | Clarify here and in clause 11.11.4
3788000023 | 01/28/2008 14:30:03 EST | 72 | Hart, Brian D | X | X | Individual | 19 | Producer | Approve | Editorial | 36 | 11.9a.1 | 30 | "STAs and APs and DFS owners" |  | No | replace first and by comma |  |  | AIP |  | editor
3787900023 | 01/28/2008 14:30:03 EST | 71 | Hart, Brian D | X | X | Individual | 18 | Producer | Approve | Technical | 17 | 9.8.3 | 37 | Clarify whether the STA is allowed to attempt assocation when the reg class etc are unknown |  | No | As in comment
3787800023 | 01/28/2008 14:30:03 EST | 70 | Hart, Brian D | X | X | Individual | 17 | Producer | Approve | Technical | 17 | 9.8.1 | 1 | Extend MP to add DSE enabling bit. Update language to allow for MPs |  | No | As in comment
3787700023 | 01/28/2008 14:30:03 EST | 69 | Hart, Brian D | X | X | Individual | 16 | Producer | Approve | Editorial | 16 | 7.4.7.8 | 1 | , 3 times |  | No | Change elements to fields |  |  |  |  | editor
3787600023 | 01/28/2008 14:30:03 EST | 68 | Hart, Brian D | X | X | Individual | 15 | Producer | Approve | Technical | 15 | 7.4.7.8 | 7 | "Length" field helps extensibility only yet no language defining parsing rules is provided. |  | No | Define parsing rules for extending frames
3787500023 | 01/28/2008 14:30:03 EST | 67 | Hart, Brian D | X | X | Individual | 14 | Producer | Approve | Editorial | 15 | 7.4.7.8 | 47 | "Reported DSE LCI field" yet "LCIs" in figure. Does figure indicate a list of LCIs? If so, align text with figure or change "variable" in figure to nx20 octets. (replacing 20 w/ correct value) |  | No | As in comment |  |  |  |  | editor
3787400023 | 01/28/2008 14:30:03 EST | 66 | Hart, Brian D | X | X | Individual | 13 | Producer | Approve | Editorial | 14 | 7.4.7.7 | 31 | Text is silent on which measurement is requested. |  | No | Identify that DSE meas request indicates a request for a DSE meas report |  |  |  |  | editor
3787300023 | 01/28/2008 14:30:03 EST | 65 | Hart, Brian D | X | X | Individual | 12 | Producer | Approve | Technical | 13 | 7.4.7.4 | 18 | Amendment does not provide for gratuitous deenablement from the enabler: e.g. for when emergency services come & need to shut everybody up immediately. In clause 11.11.1.3 deenablement begins for the enabled STA. Gratuitos deenablement presumably comes from a time-out instead. |  | No | Determine if a timeout is sufficient. If not, provide a gratuitous method. |  |  | ?
3787200023 | 01/28/2008 14:30:03 EST | 64 | Hart, Brian D | X | X | Individual | 11 | Producer | Approve | Editorial | 11 | 7.4.7.3 | 4 | Definition of DSE in clause 3 emphasises the process of DSE, not an aspect of an individual STA. Therefore DSE makes little sense as an adjective modifying "STA" |  | No | Change the definition of DSE so it can be dropped in here, or add a new definition for "DSE STA" |  |  |  |  | editor
3787100023 | 01/28/2008 14:30:03 EST | 63 | Hart, Brian D | X | X | Individual | 10 | Producer | Approve | Technical | 10 | 7.3.2.54 | 19 | Reg Class/channel number need a country string. |  | No | Identify which country string to use; here and wherever a reg class is mentioned. Especially consider 7.3.2.54 when sent in a broadcast probe request, which does not indicate country.
3787000023 | 01/28/2008 14:30:03 EST | 62 | Hart, Brian D | X | X | Individual | 9 | Producer | Approve | Technical | 6 | 7.3.2 | 51 | Upper limit is 257 since length includes id & len |  | No | Change 255 to 257
3786900023 | 01/28/2008 14:30:03 EST | 61 | Hart, Brian D | X | X | Individual | 8 | Producer | Approve | Technical | 10 | 7.3.2.54 | 15 | Length of elements is ambiguous. |  | No | Change to "The Length field". Change upper limit to 255
3786800023 | 01/28/2008 14:30:03 EST | 60 | Hart, Brian D | X | X | Individual | 7 | Producer | Approve | Editorial | 9 | 7.3.2.53 | 62 | Sentence is odd: it mixes two distinct quanities in an Ored list: "meaningOfValues or Value" |  | No | Change to "meaningOfValue or meaningOfValue" |  |  |  |  | editor
3786700023 | 01/28/2008 14:30:03 EST | 59 | Hart, Brian D | X | X | Individual | 6 | Producer | Approve | Technical | 9 | 7.3.2.52 | 1 | Reg Class/channel number need a country string. |  | No | Identify which country string to use; here and wherever a reg class is mentioned. Especially consider 7.3.2.54 when sent in a broadcast probe request, which does not indicate country. |  |  | ?
3786600023 | 01/28/2008 14:30:03 EST | 58 | Hart, Brian D | X | X | Individual | 5 | Producer | Approve | Editorial | 8 | 7.3.2.52 | 53 | Significance of nat policy area is not clear. |  | No | Add reference to 11.11.2 |  |  |  |  | editor
3786500023 | 01/28/2008 14:30:03 EST | 57 | Hart, Brian D | X | X | Individual | 4 | Producer | Approve | Editorial | 8 | 7.3.2.52 | 45 | "AT code 3 & is formatted in 2's C &". Rather the altitude is formatted as 2's C |  | No | Change the subject of "is" |  |  |  |  | editor
3786400023 | 01/28/2008 14:30:03 EST | 56 | Hart, Brian D | X | X | Individual | 3 | Producer | Approve | Technical | 6 | 7.3.2 | 47 | Element ID table is missing "Extensibility column" introduced by 11k |  | No | Identify DSE reg and ECSA as extensible |  |  | AIP
3786300023 | 01/28/2008 14:30:03 EST | 55 | Hart, Brian D | X | X | Individual | 2 | Producer | Approve | Editorial | 6 | 7.2.3.9 | 22 | Consistency - no subject with verb |  | No | Add "The DSE reg loc &" |  |  |  |  | editor
3785700023 | 01/27/2008 15:08:48 EST | 54 | Petranovich, James | X | X | Individual | 7 | Producer | Disapprove | Technical | 48 | 17.3.10.5 | 1 | The note says the CCA-ED threshold should be 20 dB above sensitivity. While this is a tradition in 802.11, it is based on old technology. |  | No | consider recommending a level 15 dB above noise floor.
3785600023 | 01/27/2008 15:08:48 EST | 53 | Petranovich, James | X | X | Individual | 6 | Producer | Disapprove | Technical | 45 | 17.3.9.2 | 42 | The mask is speciifed only in a relative measure, dBr. But a low power device might have trouble meeting these dBr requirements and yet would generate less interference than a full power device that meets the dBr requirements. |  | Yes | Add a clause that indicates any transmission emmisions -45 dB from the maximum allower power level in the band are permitted with any frequency offset for all masks. |  |  | ?
3785500023 | 01/27/2008 15:08:48 EST | 52 | Petranovich, James | X | X | Individual | 5 | Producer | Disapprove | Technical | 45 | 17.3.8.3.1 | 27 | The text "The OFDM PHY shall operate in frequency bands, as allocated by a regulatory body in its operational region." is confusing. Is this a requirement for the device to operate in alll the bands allocated or only some of them? Is this a subtle hidden requirement? |  | Yes | change to : "The OFDM PHY shall not operate in frequency bands not allocated by a regulatory body in its operational region." |  |  | AIP
3785400023 | 01/27/2008 15:08:48 EST | 51 | Petranovich, James | X | X | Individual | 4 | Producer | Disapprove | Editorial | 5 | 7.2.3.6 | 37 | in the same table (7-12) one entry uses the contruct "shall be present" while another entry uses the contrcut "is present". One of these is incorrect usage. I preser "is", as this enter does not describe behavior but rather what is in a table, and anyway this is in the notes. |  | No | change "shall be" to "is" in table 7-12, order 8, under notes. |  |  | Same as baseline |  | editor
3785300023 | 01/27/2008 15:08:48 EST | 50 | Petranovich, James | X | X | Individual | 3 | Producer | Disapprove | Editorial | 4 | 7.2.3.4 | 62 | in the same table (7-10) one entry uses the contruct "shall be present" while another entry uses the contrcut "is present". One of these is incorrect usage. I preser "is", as this enter does not describe behavior but rather what is in a table, and anyway this is in the notes. |  | No | change "shall be" to "is" in table 7-10, order 7, under notes. |  |  | Same as baseline |  | editor
3785200023 | 01/27/2008 15:08:48 EST | 49 | Petranovich, James | X | X | Individual | 2 | Producer | Disapprove | General | 2 | 5.2.8.1 | 63 | It is nto clear what the purpose of the "types of licenses" section serves |  | No | delete this section |  |  |  |  | ScottB
3785100023 | 01/27/2008 15:08:48 EST | 48 | Petranovich, James | X | X | Individual | 1 | Producer | Disapprove | General | 2 | 5.1.1.1 | 35 | "In the design of wired LANs it is implicitly assumed that an address is equivalent to a physical location." is not strictly correct. A mobile device like a laptop may be unplugged form one place and plugged in another and may keep the same address. |  | No | delete this and the next sentence and instead say "In wireless LANs there is no implication that an address corresponds to a fixed physical locaiton". |  |  |  |  | ScottB
3781400023 | 01/24/2008 18:03:08 EST | 47 | Hart, Brian D | X | X | Individual | 1 | Producer | Approve | Technical | 11 | 7.4.7.3 | 7 | If a "ooffspring of 11y" were formed needing to extend 11y's action frames, no standards method is defined so new frames must be used in place of 111y's frames. |  | No | Define an extensibilty mechanism for 11y rfames. Make the mechanism extensible to other amendments also.
3778900023 | 01/23/2008 08:41:53 EST | 46 | Perahia, Eldad | X | X | Individual | 1 | Producer | Approve | Technical | 49 | A.4.3 | 5 | If my interpretation of the requirements of 11y is correct, it requires 11a. However 11a requires 24 Mbps (OF1.2.5), which requires a 10MHz or 20 MHz channel spacing. This conflicts with J.2 which states "all stations shall be capable of transmitting using 5 MHz channel bandwidths", which I interpret as not requiring transmission with 10MHz or 20MHz channel spacing. |  | No | correct the PICS to match the requirements in J.2 |  |  | ?
3605000023 | 01/03/2008 05:30:14 EST | 45 | Stephens, Adrian P | X | X | Individual | 43 | Producer | Disapprove | Technical |  | Annex D |  | The definition of dot11LCIDSETable uses ::= { dot11smt 14 }. But in the comments against dot11smt this is shown (correctly, I believe) to be 16. |  | Yes | Change definition of dot11LCIDSETable to use ::= { dot11smt 16} |  |  | ?
3601300023 | 01/02/2008 12:29:37 EST | 44 | Stephens, Adrian P | X | X | Individual | 42 | Producer | Disapprove | Technical |  | J.2 |  | "All stations shall use" Two problems with this: 1. Normative behaviour is for a protocol entity, not all such entities. 2. "shall use" is normatively meaningless. |  | No | Just provide a list of required behaviours and a list of forbidden behaviours, perhaps as a table with a column for name, reference, and required/forbidden? |  |  | AIP
3601200023 | 01/02/2008 12:29:37 EST | 43 | Stephens, Adrian P | X | X | Individual | 41 | Producer | Disapprove | Technical |  | I.1 |  | I don't have a clear picture of how the behavior limit sets 11 and 12 are used. How do they map onto the terminology of "fixed", "enabling" and "dependent" STA used in 11.11? If a registered fixed AP is allowed to transmit in the higher power, what behaviour set does it put in its beacon? Where is this described? |  | Yes | Add to J.2 a description of how the behaviour limit sets map onto the terminology of 11.11. |  |  | AIP
3601100023 | 01/02/2008 12:29:37 EST | 42 | Stephens, Adrian P | X | X | Individual | 40 | Producer | Disapprove | Technical |  | D |  | Annex D generally. There is a syntax for specifying default values. This annex uses text in the description for some of its MIB entries (e.g., "dot11LCIDSEImplemented") |  | Yes | Replace all textual indications of default values with the appropriate syntax. |  |  | AIP
3601000023 | 01/02/2008 12:29:37 EST | 41 | Stephens, Adrian P | X | X | Individual | 39 | Producer | Disapprove | Technical |  | 17.3.10.5 |  | "NOTE--CCA-ED may be used in bands when not required by Annex J. In these cases, the CCA-ED threshold should equal 20 dB above the minimum modulation and coding rate sensitivity (-62 dBm for 20 MHz channel spacing, -65 dBm for 10 MHz channel spacing, and -68 dBm for 5 MHz channel spacing)." Although this claims to be a note, it has one "may" and one "should" |  | Yes | Either use non-normative verbs here, or remove its informative status. |  |  | AIP
3600900023 | 01/02/2008 12:29:37 EST | 40 | Stephens, Adrian P | X | X | Individual | 38 | Producer | Disapprove | Technical |  | 11.11.5 |  | "shall send this Action frame to the broadcast address using normal frame transmission rules" This implies that somewhere in our finely crafted standard we have some "abnormal rules". Such a vile slur requires a response. Or put another way, what the heck are "normal frame transmission rules"? |  | Yes | Reference the relevant rules or remove "using normal frame transmission rules" |  |  | AIP
3600800023 | 01/02/2008 12:29:37 EST | 39 | Stephens, Adrian P | X | X | Individual | 37 | Producer | Disapprove | Editorial |  | 11.11.5 |  | <DSE measurement request frame shall not contain a value of "1" for the "incapable" subfield> This is a virulent attack of quoters disease. |  | No | Innoculate. |  |  | AIP |  | editor
3600700023 | 01/02/2008 12:29:37 EST | 38 | Stephens, Adrian P | X | X | Individual | 36 | Producer | Disapprove | Technical |  | 11.11.5 |  | "RegLoc DSE bit set to 1 in the DSE registered location element, and set all fields in bits 16-175 of its DSE registered location element to zero;" Structural information such as the bit locations should not be repeated as it creates a maintenance risk. |  | Yes | Replace bit positions with names of field(s). |  |  | AIP
3600600023 | 01/02/2008 12:29:37 EST | 37 | Stephens, Adrian P | X | X | Individual | 35 | Producer | Disapprove | Technical |  | 11.11.5 |  | "A dependent STA shall only attempt enablement with an enabling STA if" BEWARE, "shall only" is considered dangerous. The point is that a sentence with "shall only" in it will probably be misread. Consider A shall only B if C. In my experience in TGn, I have found cases where people interpret this as: 1. A shall not B if not C 2. A may B if C 3. A shall B if C The question is whether "shall only" expresses a constraint, or requires or permits action. |  | No | Replace with "shall not attempt enablement with an enabling STA unless" |  |  | AIP
3600500023 | 01/02/2008 12:29:37 EST | 36 | Stephens, Adrian P | X | X | Individual | 34 | Producer | Disapprove | Technical |  | 11.11.5 |  | "shall only transmit" BEWARE, "shall only" is considered dangerous. The point is that a sentence with "shall only" in it will probably be misread. Consider A shall only B if C. In my experience in TGn, I have found cases where people interpret this as: 1. A shall not B if not C 2. A may B if C 3. A shall B if C The question is whether "shall only" expresses a constraint, or requires or permits action. |  | No | Replace with "shall not transmit beyond dot11DSEEnablementTimeLimit seconds" |  |  | AIP
3600400023 | 01/02/2008 12:29:37 EST | 35 | Stephens, Adrian P | X | X | Individual | 33 | Producer | Disapprove | Technical |  | 11.11.4 |  | "A dependent STA shall create a dependent DSE registered location element" Great. Presumably it can also lock this element into a nice safe vault where nobody can see it. Just how do I test "shall create"? |  | Yes | Relate to the transmission of this data, which is an observable |  |  | AIP
3600300023 | 01/02/2008 12:29:37 EST | 34 | Stephens, Adrian P | X | X | Individual | 32 | Producer | Disapprove | Technical |  | 11.11.4 |  | "An associated dependent STA shall operate under the control of the enabling STA from which it attained enablement;" "...shall operate under the control..." more sublime ineffability - i.e., what does this mean? |  | Yes | Refer to those procedures that constitute "operation under control", i.e., by subclause number |  |  | AIP
3600200023 | 01/02/2008 12:29:37 EST | 33 | Stephens, Adrian P | X | X | Individual | 31 | Producer | Disapprove | Technical |  | 11.11.4 |  | "A STA with dot11DSERequired set to true shall not operate in an infrastructure BSS or IBSS unless it has received a Beacon frame from a enabling STA" "shall not operate" is ineffably explicit. Exactly what can it do and not do. |  | No | Replace "shall not operate" with a more precise description of what it can't do (i.e. shall not transmit any frames). |  |  | AIP
3600100023 | 01/02/2008 12:29:37 EST | 32 | Stephens, Adrian P | X | X | Individual | 30 | Producer | Disapprove | Technical |  | 11.11.4 |  | A state machine is driven by events. So how is the transition "enabling message received? = No" taken? |  | Yes | Review this state machine and ensure that all transitions relate to events, not non-events. |  |  | AIP
3600000023 | 01/02/2008 12:29:37 EST | 31 | Stephens, Adrian P | X | X | Individual | 29 | Producer | Disapprove | Technical |  | 11.11.4 |  | While figure 11-19 is carrying on the fine tradition of abusing a defined graphical methodology with all the gusto and aplomb of the baseline, please listen to this lone voice crying in the wilderness "make straight your state machines". |  | Yes | The boxes below the state machine title contain actions, not conditional tests. Put conditions on the exit paths. Leave just actions there and move the conditions out to the exit paths. |  |  | AIP
3599900023 | 01/02/2008 12:29:37 EST | 30 | Stephens, Adrian P | X | X | Individual | 28 | Producer | Disapprove | Editorial |  | 11.11.3 |  | "may contain elements received from stations that are not yet associated to a BSS." While pedantry is something up with which I will not put, is this the right preposition? |  | No | "... associated with a BSS" |  |  |  |  | editor
3599800023 | 01/02/2008 12:29:37 EST | 29 | Stephens, Adrian P | X | X | Individual | 27 | Producer | Disapprove | Technical |  | 11.11.3 |  | "NOTE--An enabling STA may request its dependent STAs perform DSE measurement requests and make DSE reports over the DS. How information is exchanged over a DS is beyond the scope of this standard." Great. How does this help create interoperable equipment? |  | No | Either indicate how this is done, or reference the external standard that defines this communication, or remove the note.
3599700023 | 01/02/2008 12:29:37 EST | 28 | Stephens, Adrian P | X | X | Individual | 26 | Producer | Disapprove | Technical |  | 11.11.2 |  | "A registered STA that is not an enabling STA may operate as an AP in an infrastructure BSS, and relay Public Action frames from a dependent STA to its enabling STA." Exactly where is this "relay" operation defined? Clearly the AP cannot just retransmit these frames, so it must overwrite some fields but not others. Seeing as the addressing must be carried in the management frame body, how can it be generic to all public action frames? |  | Yes | Add a subclause "relaying of DSE frames" and describe how the AP does this. Change "may relay public action frames" to "may relay DSE frames as specified in x.x.x.x".
3599600023 | 01/02/2008 12:29:37 EST | 27 | Stephens, Adrian P | X | X | Individual | 25 | Producer | Disapprove | Technical |  | 11.11.1.3 |  | "The deenablement message confirm Reason Result Code indicates when the deenablement is successful." The transmission of the deenablement may fail (missing ack). This doesn't allow for that. |  | Yes | Replace "when" with "whether".
3599500023 | 01/02/2008 12:29:37 EST | 26 | Stephens, Adrian P | X | X | Individual | 24 | Producer | Disapprove | Technical |  | 11.11.1.1 |  | Now I'm even more confused. The title says "enablement requester STA" but the second message type is sent by the enablement responder STA. And the frame under bullet a) of 11.11.1.2 looks very much like the second one in bullet a) of 11.1.1.1 |  | Yes | Let's specify what goes in that frame in just one place.
3599400023 | 01/02/2008 12:29:37 EST | 25 | Stephens, Adrian P | X | X | Individual | 23 | Producer | Disapprove | Technical |  | 11.11.1.1 |  | "Specific items in the enablement confirm indication are as follows:" I know that it's easy to confuse me, but this did it. Firstly I see the name of a primitive "confirm". Then I see the name of another primitive "indication". But it's actually talking about the contents of a frame! |  | Yes | Replace cited text with: "Specific items in the enablement message sent by the enablement responder are as follows:"
3599300023 | 01/02/2008 12:29:37 EST | 24 | Stephens, Adrian P | X | X | Individual | 22 | Producer | Disapprove | Technical |  | 11.11 |  | In table 11.11a STA is used to include APs in the first two rows, but then the fourth row implies that the third row doesn't include AP. |  | No | Either add "non-AP" in the third non-header row to the unlabelled column, or remove the fourth row. And while you're at it, label the blank column, i.e., "Type of STA".
3599200023 | 01/02/2008 12:29:37 EST | 23 | Stephens, Adrian P | X | X | Individual | 21 | Producer | Disapprove | Editorial |  | 11.11.1 |  | This is a hanging subclause |  | No | Add a new 11.11.1.1 General |  |  | AIP |  | editor
3599100023 | 01/02/2008 12:29:37 EST | 22 | Stephens, Adrian P | X | X | Individual | 20 | Producer | Disapprove | Editorial |  | 11.11 |  | This is a hanging subclause |  | No | Add a new 11.11.1 General |  |  | AIP |  | editor
3599000023 | 01/02/2008 12:29:37 EST | 21 | Stephens, Adrian P | X | X | Individual | 19 | Producer | Disapprove | Technical |  | 11.9a.3.2 |  | "when the requirements signified by the new regulatory class are met by the DFS owner." What does this mean? Surely if the DFS owner does not meet any of the requirements of a candidate regulatory class, it cannot select it. |  | Yes | Tell me something that makes sense. |  |  | AIP
3598900023 | 01/02/2008 12:29:37 EST | 20 | Stephens, Adrian P | X | X | Individual | 18 | Producer | Disapprove | Technical |  | 11.9a.3.2 |  | "A STA in a BSS that is not the AP shall not transmit the Extended Channel Switch Announcement element." I suspect the author of this wrongly equates "in a BSS" with "infrastructure BSS". But BSS covers both infrastructure and independent (IBSS) cases and "in a BSS" relates more the adoption of timing parameters and BSSID. |  | Yes | replace "in a BSS" with "in an infrastructure BSS" Also a "STA ... that is not the AP" can be shortened to "non-AP STA". |  |  | ?
3598800023 | 01/02/2008 12:29:37 EST | 19 | Stephens, Adrian P | X | X | Individual | 17 | Producer | Disapprove | Technical |  | 11.9a.3.1 |  | "When a STA with dot11DSERequired false receives an Extended Channel Switch Announcement element, it may choose not to perform the specified switch, but to take alternative action, as described in 11.9.7.1." This is fine for an AP, but for an infrastructure STA, the reference makes no sense. |  | Yes | Add reference or other behaviour appropriate to a non-AP STA.
3598700023 | 01/02/2008 12:29:37 EST | 18 | Stephens, Adrian P | X | X | Individual | 16 | Producer | Disapprove | Technical |  | 11.9a.3.1 |  | "The AP may send the Extended Channel Switch Announcement frame in a BSS" How can it send such a frame "not in a BSS?" |  | No | remove "in a BSS". |  |  | ?
3598600023 | 01/02/2008 12:29:37 EST | 17 | Stephens, Adrian P | X | X | Individual | 15 | Producer | Disapprove | Technical |  | 11.9a.3.1 |  | "The AP may force STAs in the BSS to stop transmissions until the channel switch takes place by setting the Extended Channel Switch Mode field to 1 in the Extended Channel Switch Announcement element." This is only partly successful. A power-saving STA may wake, determine the medium is idle and start transmitting. As such the cited sentence is misleading. |  | No | Add note indicating that this is only partly successfull. |  |  | AIP
3598500023 | 01/02/2008 12:29:37 EST | 16 | Stephens, Adrian P | X | X | Individual | 14 | Producer | Disapprove | Technical |  | 11.9a.3.1 |  | "When dot11ExtendedChannelSwitchEnabled is true, an AP shall inform associated STAs that the AP is moving to a new channel and maintain the association by advertising the switch using Extended Channel Switch Announcement elements in Beacon frames, Probe Response frames, and Extended Channel Switch Announcement frames until the intended channel switch time." This statement requires the AP to transmit probe response frames. But if there are no probe requests, this is not possible. Likewise, we are required to transmit "Extended Channel Switch Announcement frames until the intended channel switch time". How many? Do we transmit them constantly until the appointed time? |  | No | recommend adding "any transmitted" here on the assumption that this shall relates to the contents, not whether they should be transmitted.
3598400023 | 01/02/2008 12:29:37 EST | 15 | Stephens, Adrian P | X | X | Individual | 13 | Producer | Disapprove | Technical |  | 11.9a.3.1 |  | "If dot11ExtendedChannelSwitchEnabled is false, the AP shall send the Channel Switch Announcement element and frame, or both the Extended Channel Switch Announcement and the Channel Switch Announcement elements and frames." Don't be fooled by the name, dot11ExtendedChannelSwitchEnabled is a capability. If if we are incapable of "extended channel switching", what the heck are we doing transmitting an extended channel switch frame? |  | No | Resolve this inconsistency.
3598300023 | 01/02/2008 12:29:37 EST | 14 | Stephens, Adrian P | X | X | Individual | 12 | Producer | Disapprove | Technical |  | 11.9a.3.1 |  | "In addition, the AP may also send Channel Switch Announcement elements and frames when the requirements signified by the new regulatory class are met by all associated STAs that are intended to act on the Channel Switch Announcement." This is a normative statement, but it refers to an AP's intentions, which are anthopomorphic, and certainly not testable. |  | Yes | Replace with a statement that avoids "intended" and is testable. |  |  | AIP
3598200023 | 01/02/2008 12:29:37 EST | 13 | Stephens, Adrian P | X | X | Individual | 11 | Producer | Disapprove | Technical |  | 11.9a.3.1 |  | "The decision to switch to a new operating channel in an infrastructure BSS is made by the AP." This flatly contradicts the previous para. |  | Yes | Indicate this is limited to the case when dot11DSERequired is false.
3598100023 | 01/02/2008 12:29:37 EST | 12 | Stephens, Adrian P | X | X | Individual | 10 | Producer | Disapprove | Technical |  | 11.9a.3.1 |  | "When an AP, with dot11DSERequired set to true, receives frames containing Extended Channel Switch Announcement elements from the enabling STA, it shall advertise an extended channel switch with the parameters received in the Extended Channel Switch Announcement elements." What if it receives such frames from two enabling STAs? |  | No | Either this is not possible, or the AP needs to be allowed to choose between enabling STAs, or its enabling STA. |  |  | AIP
3598000023 | 01/02/2008 12:29:37 EST | 11 | Stephens, Adrian P | X | X | Individual | 9 | Producer | Disapprove | Editorial |  | 11.9a.1 |  | "A STA shall not transmit the Extended Capabilities information element with the Extended Channel Switching field set to 1 unless dot11ExtendedChannelSwitchEnabled is set to true." Theres a lot of redundancy between this and the previous para. |  | No | I think you can simplify these two paras by having this statement: "A STA shall set the Extended Channel Switching field to 1 in a transmitted Extended Capabilities information element if and only if dot11ExtendedChannelSwitchEnabled is set to true." And then removing everything else related to the setting of this field. |  |  |  |  | editor
3597900023 | 01/02/2008 12:29:37 EST | 10 | Stephens, Adrian P | X | X | Individual | 8 | Producer | Disapprove | Editorial |  | 11.9a.1 |  | "When dot11ExtendedChannelSwitchEnabled is false, the Extended Channel Switching field of the Extended Capabilities information element shall be set to 0." I think there's a mismatch here. Capabilities describe what the STA is able (i.e. has hardware and software support for) to do. These are static. An "enabled" MIB variable implies something more dynamic. And just to add confusion we've also got some "capabilityEnabled" variables. |  | No | Are any of these truly dynamic - if so, "enabled" might be the right name, but then the dependency of a capability field bit on a dynamic field is highly questionable. If they are not dynamic, suggest renaming "[capability]enabled" with "supported" for the variables mentioned in this subclause. |  |  |  |  | editor
3597800023 | 01/02/2008 12:29:37 EST | 9 | Stephens, Adrian P | X | X | Individual | 7 | Producer | Disapprove | Technical |  | 9.8.4 |  | "When dot11RegulatoryClassesRequired and dot11ExtendedChannelSwitchEnabled are true, the Coverage Class field of the Country Information element shall be processed when received by the associated STA or dependent STA, replacing the current aAirPropagationTime with one indicated by the Coverage Class field." "shall be processed" is an incomplete normative specification. The PHY characteristics interface returns SIFS and slot time. So where is this processing done (MAC, in which case we need to describe how to adjust the values from the PHY; or PHY, in which case this specification needs to go into the PHY, and the characteristics interface needs to communicate the aAirPropagationTime value to the PHY)? |  | Yes | Either refer to the subclause defining that processing (in which case why is this shall required?) or define that processing.
3597700023 | 01/02/2008 12:29:37 EST | 8 | Stephens, Adrian P | X | X | Individual | 6 | Producer | Disapprove | Editorial |  | 7.4.7.3 |  | "The Category field is set to 4 (representing Public Action)." This is not where to define this value - it should be in table 7-24. |  | Yes | Replace with "The Category field is set to the value for Public Action defined in Table 7-24". Make similar edits where the cited text is used throughout 7.4.7. Add editing instructions to insert in table 7-24 the values "4; Public Action". |  |  | AIP |  | editor
3597600023 | 01/02/2008 12:29:37 EST | 7 | Stephens, Adrian P | X | X | Individual | 5 | Producer | Disapprove | Technical |  | 7.3.2.54 |  | "The length of the Supported Regulatory Classes element is between 1 and 253 octets." Wrong - the value of the length field is between these limits. The length of the element is 2 bytes more. |  | Yes | Replace cited text with: "The value of the Length field of the Supported Regulatory Classes element is between 1 and 253." |  |  | AIP
3597500023 | 01/02/2008 12:29:37 EST | 6 | Stephens, Adrian P | X | X | Individual | 4 | Producer | Disapprove | Editorial |  |  |  | "may" is misused 3 times in 5.2.8.2. I suspect this might be systemmatic. |  | Yes | Review all use of "may" and replace with "can" (is able to) or "might" as appropriate (i.e. where the text is not granting permission) |  |  |  |  | ScottB
3597400023 | 01/02/2008 12:29:37 EST | 5 | Stephens, Adrian P | X | X | Individual | 3 | Producer | Disapprove | Technical |  | 5.2.8.2 |  | "a wireless device or its license holder may have to change how the device is operated" "may" has a special normative interpretation that is not relevant here. |  | No | Replace "may" with "might" |  |  |  |  | ScottB
3597300023 | 01/02/2008 12:29:37 EST | 4 | Stephens, Adrian P | X | X | Individual | 2 | Producer | Disapprove | Editorial |  | 5.2.8 |  | "Countries may impose specific requirements for radio equipment in addition to those specified in this standard." "may" is a normative verb equivalent to "are permitted to by this standard". But I don't think they need our permission. |  | No | Replace "may" with "can" |  |  |  |  | ScottB
3597200023 | 01/02/2008 12:29:37 EST | 3 | Stephens, Adrian P | X | X | Individual | 1 | Producer | Disapprove | Technical |  | 3 |  | "Hidden STA" is used in 5.1.1.1, but not defined. |  | Yes | Add definition of "Hidden STA" to clause 3. |  |  |  |  | ScottB
3568500023 | 12/23/2007 11:50:47 EST | 2 | Nikolich, Paul | X | X | Individual | 1 | User | Approve | Editorial | 2 | 5.2.8 | 54 | The process by which 802.11 has been updated (amending the base std) to allow use of licensed freqs is not material. The text should be made independent of the amendment process. Improve wording of "IEEE 802.11 has been amended to make use of a number of frequencies that are licensed by the national regulators for a given country. While effort is made to generalize these amendments so that they can be reused in the same bands in other countries, it must be noted that the projects that drafted said changes were focused on the rules of a single country. Countries may impose specific requirements for radio equipment in addition to those specified in this standard." There may be other portions of the text to which similar logic applies that I have not had a chance to read--please try to fix those too if they exist. |  | No | IEEE 802.11 may make use of a number of frequencies that are licensed by the national regulators for a given country. While effort is made to generalize the licensed frequency portions of the standard so it can be reused in the same bands in other countries, it must be noted that those portions are focused on the rules of a single country. Countries may impose specific requirements for radio equipment in addition to those specified in this standard. |  |  |  |  | ScottB
3568300023 | 12/22/2007 17:42:54 EST | 1 | Coordination, Scc14 | X | X |  | 1 |  |  | General |  |  |  | SCC14 Coordination OK. |  | Yes |  |  |  | A |  | editor

## References
WHATIS:
Comments |  | Accumulated comments to be processed in this letter ballot. This includes all the new comments received during this ballot, and all un-acknowledged carryover comments from previous ballots. Each is assigned a "Comment Group#" when a proposed resolution is given (matching an entry on the "Status" page). Each comment may be assigned a "Issue #" as a means of grouping similar comments that deal with a single technical/editorial issue. Each comment may be assigned to an individual for developing a resolution.
| A | CID: Comment identifer, a sequential number assigned by the editor. These values start at 4 (so that the comment number can match the row number in the Excel spreadsheet), and are generated after all comments are received and the spreadsheet is sorted by page/line.
| B | CommentID: assigned and provided by MyBallot (apparently assigned in order of votes received)
| C | CommenterName: submitter, as provided by MyBallot
| D | Subclause: Clause and subclause, as provided by the submitter, and passed to us from MyBallot
| E | Page: Page number, as provided by the submitter, and passed to us from MyBallot
| F | Line: Line number, as provided by the submitter, and passed to us from MyBallot
| G | Pg.ln: Combined page number and line number, verified by Editor, and used for sorting the resulting spreadsheet
| H | CommentType: Either Editorial (E), Technical (T), or General (G), as provided by the submitter. This letter is optionally followed by "R" if commenter has identified it as a required change.
| I | CommentStatus: Accepted (A) or Rejected (R). During the comment resolution process, this column may have other strange values and should be ignored
| J | ResponseStatus: Closed (C), or Unsatisfied (U). During the comment resolution process, this column may have other strange values and should be ignored
| K | Comment: text of comment as provided by the submitter, and passed to us from MyBallot
| L | SuggestedRemedy: Proposed resolution suggested by submitter
| M | Response: Resolution, (ACCEPT, ACCEPT IN PRINCIPLE, or REJECT) as voted on by 802.11 Working Group. Until the response has been voted on, it will appear as "PROPOSED xxx"
| N | Group#: Comment Group # (matching one of the entries on the "Status" page), used to simplify the naming of sets of comments in motions.
| O | Topic: String provided by editor for identifying groups of comments that identify a single technical or editorial issue.
Status |  | Table giving the resolution status of each "comment group", and overall statistics for resolution progress.
| A | Group#, generally a numeric value 1-99 (but could be any arbitrary alphanumeric string). This number/string matches entries in column N of the "Comments" page.
| B | Status value, either "Approved", "Pending", or "Duplicate"
| C | If column B is "Approved", then this column gives the date of the motion in the Task Group that accepted these resolutions
| D | If column B is "Approved" or "Pending", then this column is the draft version (or editor's temporary version) that contains the updates
| E | Quantity of comments in this group#
| F | Description of the comment group
Deferred |  | Comments from prior recirculation ballots that were rejected because the text was not subject to further comments. While these comments were rejected, they are being remembered for submission by the TG chair in the next revision of the standard.
| A-O | copied directly from the "Comments" sheet.
Submitters |  | Summary information of the submitters of the comments in each letter ballot, and the number of their comments that remain unacknowledged. Anyone who has ever submitted a common the draft has an entry on this page.
| A | Name of voter
| B | unused
| C-D | First ballot, Total number of comments submitted, and number of those comments remaining unacknowledged.
| E-F | Second ballot, Total number of comments submitted,and number of those comments remaining unacknowledged.
| G-H | Third ballot, Total number of comments submitted, and number of those comments remaining unacknowledged.
| I-J | Fourth ballot, Total number of comments submitted, and number of those comments remaining unacknowledged.
| K-L | Fifth ballot, Total number of comments submitted, and number of those comments remaining unacknowledged.
| etc | more groups of two columns, as needed for additional recirculation ballots
HOWTO:
Update this file at end of a ballot
| 1 | (If this is a recirculation ballot) Open the Spreadsheet file for the previous ballot. Change name of the "Comments" page to "Initial ballot", "First Recirculation", "Second Recirculation", etc. Get a new document number for the new ballot. Save as "11-07-xxxx-00-dx-comments.xls" (If this is an initial ballot) Open a template spreadsheet. Get a new document number for the new ballot. Save as "11-07-xxxx-00-dx-comments.xls"
| 2 | Download the .csv file from MyBallot
| 3 | Make a copy of "MyBallot_V4p4.mdb" and open the copy. When it asks "Do you want to block unsafe expressions?", answer "No". When it asks "Do you want to open this file?", answer "Yes". When it asks yet again "Do you want to open this file or cancel the operation?", answer "Open".
| 4 | In the "Start" form, click "Untilities". Fill in Project designation (e.g., P802.11r D7.0) and Project title (e.g., Fast BSS Transition). Doesn't hurt to "Clear Main Table" (but shouldn't be necessary).
| 5 | In the "Start" form, click "Input comment file", then "Select input datafile" (browse to select the actual file), then "MyBallot database file (*.csv, *.xls) Rough Import". Say "OK" to the record count (twice). Select "Transfer new and updated record to main table". Say "OK" twice. Return to Start menu. Exit MSAccess (File->Exit).
| 6 | Open "MyBallot_Tolls_ExportMyBallotToExcel.mdb". Same three security warning questions, and same answers. "Select MyBallot database file", and select the one generated in step 3. "Select target excel file", and select the .xls file with previous comment resolutions. Click "Pertform Export". It crashes. Kill the debug window (X in upper right corner), and click "Perform Export" again. It works. Exit MSAccess.
| 7 | Open the .xls file; insert column A with title "CID", column G with title "Pg.ln", and column N with title "Group#".
| 8 | Verify the Page (column E) and Line (column F) for each comment. They are easy to get wrong. Fill in the (corrected) value pg.ln in column G for each. Sorting by page.line should make the clause numbers strictly increasing, which serves as a check. Generally, when the difference between adjacent rows in the spreadsheet is only one line in the draft, there is a problem.
| 9 | Sort the comments by pg.ln (column G). Assign CIDs, matching the row# in the spreadsheet. Simplest way is "seq 2 xxx >foo1;wordpad foo1" in a shell window, where xxx is the highest row number used. Control-A then control-C in the wordpad window. Select cell A2 on the "Comments" page, then control-V.
Mark comment resolutions
| 1 | As resolutions are proposed, (1) enter the text in column O ("PROPOSED ACCEPT", "PROPOSED ACCEPT IN PRINCIPLE", or "PROPOSED REJECT"), (2) enter a group# in column P, and (3) enter the group# on the "Status" page with a description (e.g., resolutions reached at ad-hoc meeting, or resolutions reached on teleconference, etc), and status as "Pending".
| 2 | Iterate until done. There should be no rows in the spreadsheet without a value in column M (Respons). There should be no rows in the spreadsheet without a value in column N (Group#). All of the text in column M should start with "PROPOSED".
| 3 | Approve the spreadsheet by a technical motion in a Working Group plenary session
Update spreadsheet and the MyBallot system with approved comment resolutions
| 1 | Do a global replace of "PROPOSED ACCEPT" to "ACCEPT", and "PROPOSED REJECT" to "REJECT". Check column M for anything that doesn't start with "ACCEPT" or "REJECT" and fix. Sort by the Response (column M), so all "ACCEPT" and "ACCEPT IN PRINCIPLE" are first. Change the "CommentStatus" for each "ACCEPT" or "ACCEPT IN PRINCIPLE" to "A". Change the "CommentStatus" for each "REJECT" to "R".
| 2 | Update the ResponseStatus column. In cell P2, enter formula "=if(OR(H2="ER",H2="TR", H2="GR"),"U","C")" Copy the formula into column P for each row. Select cells P2:P<last>, control C. Select cell J2, then Edit->PasteSpecial, select Values, then "OK". Change title of column P to "Date of E-mail accept/non-accept", and delete all the U/C formulas from this column. Save the .xls file, then close it (otherwise MSAccess goes crazy because the file is locked and it can't do whatever it needs to do).
| 3 | Open "MyBallot_Tools_ExportExcelToTilde.mdb". Same three questions as all other MSAccess files. Click "Select comment spreadsheet" and select the .xls file with the accepted resolutions. Select the sheet "Comments". It tells number of comments processed. Click "Select output file and perform export", and store the results in 11-07-xxxx-000r-d7-comments-tilde.txt (e.g., same file name as .xls file, but with "-tilde.txt" replacing ".xls". Exit MSAccess.
| 4 | Open the copy of MyBallot_V4p4.mdb for this ballot. Same three questions as all other MSAccess files. Click "Input". Click "Select input data file", and select the just-created tilde.txt file. Click "Tilde file rough import", then "Transfer rough records to main table". The MSAccess database now includes all the status values, and the comment resolutions.
| 5 | (Still in the copy of MyBallot_V4p4.mdb) On the "Start" page, click "Output", then "Output all comments, MyBallot csv format". Pipe the output through csv-fix (changes the newline characters inside double quotes to " \n"). Save the output as "11-07-2295-09-d7-comments (resolutions-final).csv"
Receive acknowledgement (or non-acknowledgement) of comments in previous letter ballots
| 1 | Find the row for each comment identified in the E-mail. Insert date of email into column P. If this is an acceptance, change the "Response Status" in column J to "C".
| 2 | For all that are explicitely not satisfactory, copy the row onto the page "Unsatisfied Comments". Set column A to the Ballot ("Initial", "1st Recirc", etc). Update the resolution to incude "Resolution as agreed during xxx:"
Updating draft in FrameMaker
| 1 | In Dx.yy-frontmatter.fm, Note that FrameMaker for some unknown reason can't generate a redline; so tag all deleted text as Conditional text "Deleted", and all inserted/replacement text as Conditional text "Inserted". Comment tags as Conditional text "Comments"
| 2 | In Dx.yy-body.fm, just make the changes. Comment tags as conditional text "Comments". Will later use the FrameMaker File->Utilities->CompareDocuments to generate a starting point for the redline
Preparing to generate a new draft in FrameMaker
| 1 | In Dx.yy-frontmatter.fm, fix draft number and date in top line and first line of title
| 2 | In Dx.yy-frontmatter.fm, add any new presenters to 11r group
| 3 | In Dx.yy-frontmatter.fm, update change history table. Need to turn on display of EditorInfo text (Special->ConditionalText->Show/Hide, select "EditorInfo", press "<--", Set, Wait. Then exit the dialog box)
| 4 | In Dx.yy-body.fm, Master pages, 2 places to put draft number (keep overrides)
| 5 | In Dx.yy-body.fm, first line of title has draft number
| 6 | Turn off display of comment text (Special->Conditional Text->Show/Hide, select “Comment”, press “-->”, select "EditorInfo", press "-->", (Same for any and all others, too). Set. Wait. Then exit the dialog box.)
| 7 | Run spell checker -- Edit->Spelling Checker
| 8 | Save both Dx.yy-body.fm and Dx.yy-frontmatter.fm files
Generate the clean version of the draft (for publication on "members-only" area, and for WG letter ballots)
| 9 | Turn off display of comment text (Special->Conditional Text->Show/Hide, select “Comment”, press “-->”, select "EditorInfo", press "-->", (Same for any and all others, too). Set. Wait. Then exit the dialog box.)
| 10 | Delete any blank pages (often some have just appeared) at end of frontmatter and body.
| 11 | Load up file D0.0-numbers.fm (this is a 12-line file, “CONTENTS”, 3 blank lines, “FIGURES”, 3 blank lines, “TABLES”, 3 blank lines)
| 12 | New->Book, say “no” to adding current file.
| 13 | Add->Files, select Dx.yy-frontmatter.fm, then “Add”
| 14 | Add->Files, select Dx.yy-body.fm, then “Add”
| 15 | Select Dx.yy-body in the Book window
| 16 | Add->Table of Contents. Select tags: AH1, AH2, AI, H1, H2, H3, H4; add “before Dx.yy-body.fm”, then “Add”. Ignore the “Book error report”
| 17 | Go to the just-created window with the Table of Contents information, select it all, copy to clipboard
| 18 | Go back to Dx.yy-frontmatter.fm, and Paste TOC into the file
| 19 | Go back to D0.0-number.fm, and Paste TOC into the file (at middle line under “CONTENTS”)
| 20 | Select Dx.yy-body in the Book window
| 21 | Add->List->Figures. Select tags: FigCaption, FigTitle; add “before Dx.yy-body.fm”, then “Add”. Ignore the “Book error report”
| 22 | Go to the just-created window with the List of Figures, select it all, copy to clipboard
| 23 | Go back to the D0.0-numbers.fm, and Paste LOF into the file (at middle line under “FIGURES”)
| 24 | Select Dx.yy-body in the Book window
| 25 | Add->List->Tables. Select tags: TableCaption, TableTitle; add “before Dx.yy-body.fm”, then “Add”. Ignore the “Book error report”
| 26 | Go to the just-created window with the List of Tables, select it all, copy to clipboard
| 27 | Go back to the D0.0-numbers.fm, and Paste LOT into the file (at middle line under “TABLES”)
| 28 | Save the D0.0-numbers.fm as Dx.yy-numbers.fm
| 29 | Save the Dx.yy-frontmatter.fm file
| 30 | In the book window, select the TOC file, Edit->DeleteFileFromBook
| 31 | In the book window, select the LOF file, Edit->DeleteFileFromBook
| 32 | In the book window, select the LOT file, Edit->DeleteFileFromBook
| 33 | (If this is for a Sponsor Ballot) Various things to make the clean file unsuitable for generating comments. A) On the Master Pages, delete the text box on the left margin with line numbers. B) Make page numbers roman numerals Format->Document->Numbering, Page, Format Roman (XIV) [or Alphabetic(N) works too]. Save this file as Dx.x-xxbody.fm. Select the Book window, close it. File->New->Book, answer "no" to addint current file. Add->Files, select Dx.x-frontmatter.fm. Add->Files, select Dx.x-xxbody.fm.
| 34 | File->PrintBook, printer=”Adobe PDF”, GenerateAcrobatData=yes, PDF Setup should have (on the “Bookmarks” tab) “9>AH1, 17>AH2, 18>AH3, 18>AH4, 19>AH5, 8>AI, 8>AN, 8>Annexes, 8>AT, 9>H1, 12>H2, 14>H3, 15>H4, 16>H5”, File=Dx.yy.ps, Print. Ignore the errors about incompatible colors.
| 35 | Double-click on the Dx.yy.ps file; Acrobat Distiller will generate Dx.yy.pdf
| 36 | (Still in the Book window) File->CloseBook (don’t bother to save it)
| 37 | File->Close the *TOC.fm files, *LOF.fm files, *LOT.fm files, Summary.fm files; don’t save them
Generate the redline version of draft (for Sponsor Ballot recirculations, and for Supplemental information for WG recirculations)
| 38 | Load up previous Dx.0-body-clean.fm
| 39 | In the Dx.yy-body.fm window, File->Utilities->CompareDocuments. Select Dx.0-body-clean.fm as original. Compare. This takes a little while (typ 5-10 min)
| 40 | Special->ConditionalText, then Show/Hide, select “Comment”, <--, select "RedlineInfo", <--, select "EditorInfo", <--, Set.
| 41 | (Still on Conditional Text dialog box), select “Inserted” then Edit, change color to “Forest Green”, then “Set”, then exit the dialog box.
| 42 | A LOT of manual cleanup is needed of the CMP file generated by FrameMaker. Unchanged figures often show as deleted and re-inserted (delete the one of type "Deleted" to keep the cross reference tags pointing right). FrameMaker often guesses wrong about text changes, and shows something very complex when the changes was actually very simple. Leaving the complexity showing in the changebar file leads to Sponsor Ballot recirculation comments. After cleanup, set "Inserted" to show and "Deleted" to hide, and compare against the clean Dx.y-body.fm -- should be no changes. Next set "Inserted" to hide, and "Deleted" to show, and compare against the previous draft -- should be no text changes (but likely lots and lots of figure and cross reference changes, which can be safely ignored).
| 43 | (If this if for a WG letter ballot) Various things to make the redline file unsuitable for generating comments. A) on the Master Pages, delete the text box on the left margin with line numbers. B) Add “NOT FOR BALLOTING” to header (both sides) and footer (under page number) (Need to turn off changebar character style before doing this, Format->Character->Deisgner, uncheck Changebar). C) Make page numbers roman numerals Format->Document->Numbering, Page, Format Roman(XIV) [or Alphabetic(N) works too].
| 44 | File->SaveAs, name it Dx.yy-redline-body.fm (or Dx.yy-redline-body-cleaned.fm)
| 45 | Load up previous Dx.0-numbers.fm file
| 46 | Select Dx.yy-numbers.fm window; File->Utilities->CompareDocuments; Select Dx.0-numbers.fm as original; Compare. Manually adjust output as necessary to make it show the real changes.
| 47 | Save the Dx.yy-numbersCMP.fm as Dx.yy-redline-numbers.fm
| 48 | Select Dx.yy-redline-numbers.fm window, Select all text, copy to clipboard
| 49 | Select Dx.yy-frontmatter.fm window, Special->ConditionalText, then Show/Hide, select “Comment”, <--, select "EditorInfo", <--, Set.
| 50 | (If this is for a WG letter ballot) Insert at end "Numbering Changes", make that new text style "contheader", paste clipboard after it
| 51 | Special->ConditionalText, select “Inserted” then Edit, change color to “Forest Green”, then “Set”, then exit the dialog box.
| 52 | Adjust the draft number in top line, and in first line of title, to show the change from previous draft. Select current value, CTRL+4, up/dn to select "Inserted", then Enter. Insert previous value, select it, CTRL+4, up/dn to select "Deleted", then Enter.
| 53 | Adjust the date in top line to show the change from previous draft. Same procedure as previous step.
| 54 | Change the "EditorInfo" note on first page to indicate correct old/new draft numbers.
| 55 | Change the data in the new rows of the "Change History" table to conditional tag "Inserted"
| 56 | Save the Dx.yy-frontmatter.fm as Dx.yy-redline-frontmatter.fm
| 57 | New->Book, say “no” to adding current file.
| 58 | Add->Files, select Dx.yy-redline-frontmatter.fm, then “Add”
| 59 | Add->Files, select Dx.yy-redline-body.fm, then “Add”
| 60 | File->PrintBook, printer=”Adobe PDF”, GenerateAcrobatData=yes, PDF Setup should have (on the “Bookmarks” tab) “9>AH1, 17>AH2, 18>AH3, 18>AH4, 19>AH5, 8>AI, 8>AN, 8>Annexes, 8>AT, 9>H1, 12>H2, 14>H3, 15>H4, 16>H5”, File=Dx.yy-audit.ps, Print. Ignore the errors about incompatible colors.
| 61 | Double-click on the Dx.yy-audit.ps file; Acrobat Distiller will generate Dx.yy-audit.pdf
| 62 | In the Dx.yy-redline-body.fm window, Special->ConditionalText, Show/Hide, select "Comments", -->, select "EditorInfo", -->, Set. Delete any blank pages at end of file.
| 63 | In the Dx.yy-redline-frontmatter.fm window, Special->ConditionalText, Show/Hide, select "Comments", -->, select "EditorInfo", -->, Set. Delete any blank pages at end of file
| 64 | Re-generate the Table of Contents, to get the page numbers right for the redline version of the draft. Add->Table of Contents. Select tags: AH1, AH2, AI, H1, H2, H3, H4; add “before Dx.yy-redline-body.fm”, then “Add”. Ignore the “Book error report”. Go to the just-created window with the Table of Contents information, select it all, copy to clipboard. Go back to Dx.yy-redline-frontmatter.fm, and Paste TOC into the file. In the book window, select the TOC file, Edit->DeleteFilefromBook.
| 65 | File->PrintBook, printer=”Adobe PDF”, GenerateAcrobatData=yes, PDF Setup should have (on the “Bookmarks” tab) “9>AH1, 17>AH2, 18>AH3, 18>AH4, 19>AH5, 8>AI, 8>AN, 8>Annexes, 8>AT, 9>H1, 12>H2, 14>H3, 15>H4, 16>H5”, File=Dx.yy-redline.ps, Print. Ignore the errors about incompatible colors.
| 66 | Save the Dx.yy-redline-body.fm and Dx.yy-redline-frontmatter.fm files again (since printing changes the file somehow).
| 67 | Close the Dx.0.fm file (FrameMaker claim that it changed is wrong, don’t save it)
| 68 | Double-click on the Dx.yy-redline.ps file; Acrobat Distiller will generate Dx.yy-redline.pdf
| 69 | Add a copy of all the submissions that went into this draft to the directory
| 70 | Load Dx.yy-body.fm and Dx.yy-frontmatter.fm
| 71 | Delete the Comments. In the Dx.yy-frontmatter.fm window, Special->ConditionalText, select “Comments”, Edit, then Delete. Select “Delete the text”, then OK.
| 72 | Delete the Deleted text. (Still on ConditionalText dialog box), select "Deleted", Edit, then Delete. Select "Delete the text", then OK
| 73 | Keep the Inserted text (Still on ConditionalText dialog box), select "Inserted", Edit, then Delete. Select "Make the text unconditional", then OK
| 74 | (Still on ConditionalText dialog box), select Edit, make name “Comments”, Style “As is”, color “Magenta”, then Set; select Edit, make name "Inserted", Style "As Is", Color "Forest Green", Set; select Edit, make name "Deleted", Style "Strikethrough", Color "Red", Set. then exit the dialog box.
| 75 | File->SaveAs, name it Dx.yy-frontmatter-clean.fm (This is the file to use for future updates after the letter ballot completes).
| 76 | Delete the comments. In the Dx.yy-body.fm window, Special->ConditionalText, select “Comments”, Edit, then Delete. Select “Delete the text”, then OK.
| 77 | (Still on ConditionalText dialog box), select Edit, make name “Comments”, Style “As is”, color “Magenta”, then Set, then exit the dialog box.
| 78 | Search (CTRL+F) for "Conditional Text" (change the "Text" to "Conditional Text" to the left of the normal place to enter the search string, and then on the popup window select "RedlineInfo", "<--" (twice), Set). Delete any that are present as documentation of changes that can't be shown by the normal strikethrough/underlining
| 79 | File->SaveAs, name it Dx.yy-body-clean.fm (This is the file to use for future updates after the letter ballot completes).
| 80 | Make a .zip archive of the entire directory, containing all files since last ballot. Send it to TG chair for his records.