## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-08-0230r0
Venue Date: | Feb 2008
First Author: | Joe Kwak (InterDigital)
Subject: | TGk Sponsor Ballot Resolutions
Full Date: | 2008-02-04
Author(s): | Richard Paine (Boeing), Joe Kwak (InterDigital)
InterDigital
Bolingbrook, IL 60440
| Phone: | +1 630 739 4159
Fax:
| email: | joekwak@sbcglobal.net
Abstract:
This spreadsheet holds the resolutions drafted by the CR group for all the 4th Recirculation Sponsor Ballot comments. These proposed resolutions have been approved by the CR group. This file is updated to post progress as decsions are made by the CRGroup.

## 11-08-0230-00-000k-11k_SB_Comme
Comment ID | Date | Comment # | Name | Email | Phone | Style | Index # | Classification | Vote | Category | Page | Subclause | Line | Comment | File | Must Be Satisfied | Proposed Change | Resolution Status | Resolution Detail | Other1 | Other2 | Other3
3809500023 | 02/01/2008 18:27:20 EST | 5 | Chaplin, Clint | X | X | Individual | 5 | Producer | Disapprove | Technical | 181 |  | 47 | "FALSE::= { dot11RRMRequestEntry 36 }" This is the only place where the attribute is explicitly set to FALSE. No other place is this done. |  | Yes | "::= { dot11RRMRequestEntry 36 }" to delete the FALSE |  | PROPOSED REJECT. We deem this comment to be editorial. This editorial change and any other editorial MIB changes required for error free compilation will be made by the editor prior to publication.
3809400023 | 02/01/2008 18:27:20 EST | 4 | Chaplin, Clint | X | X | Individual | 4 | Producer | Disapprove | Editorial | 162 |  | 21 | "Non-OpMax Measurement Duration in TUs = 2<superscript> (dot11RRMNonOperatingChannelMaxMeasurementDuration - 4) </superscript> * BeaconInterval" Looks like some sort of formatting directives became text |  | Yes | delete the extraneous text, and format correctly |  | PROPOSED REJECT. The format in the draft text is defined in SNMP v2 as the correct way to indicate superscripting of characters.
3809300023 | 02/01/2008 18:27:20 EST | 3 | Chaplin, Clint | X | X | Individual | 3 | Producer | Disapprove | Editorial | 162 |  | 12 | "Max Measurement Duration in TUs = 2<superscript> (dot11RRMMaxMeasurementDuration - 4)</superscript> * BeaconInterval" Looks like some sort of formatting directives became text |  | Yes | delete the extraneous text, and format correctly |  | PROPOSED REJECT. The format in the draft text is defined in SNMP v2 as the correct way to indicate superscripting of characters.
3809200023 | 02/01/2008 18:27:20 EST | 2 | Chaplin, Clint | X | X | Individual | 2 | Producer | Disapprove | Technical |  |  |  | "The Sub-element ID field values for the defined optional sub-elements are shown in Table 7-29n. A Yes in the Extensible column of a sub-element listed in Table 7-29n indicates that the Length of the sub-element might be extended in future revisions or amendments of this standard. When the Extensible column of an element is set to Sub-elements, then the sub-element might be extended in future revisions or amendments of this standard by defining additional sub-elements within the sub-element. See 9.14.2." "Might be" or "can be"? Is this intended to be a warning, or a restriction on how the element might be extended? And why is a distinction being made between extending through simple data addition and through sub-elements? As far as the parser is concerned, it doesn't matter. Also, "When the Extensible column of an element is set to Sub-elements, then the sub-element might be extended in future revisions or amendments of this standard by defining additional sub-elements within the sub-element" will also extend the Length of the sub-element. |  | Yes | "The Sub-element ID field values for the defined optional sub-elements are shown in Table 7-29n. When the Extensible column of a sub-element is set to a value, then the sub-element might be extended in future revisions or amendments of this standard. If this value is "Yes", then this extension will be done by adding data onto the end of the sub-element; if this value is "Sub-elements", then the extension will be done by defining additional sub-elements within the sub-element. See 9.14.2." |  | PROPOSED REJECT. We can see no technical difference in the proposed change to existing text. The simplified language and changing a period to a semi-colon we see as editorial. Consideration to this editorial item will be given by the editor prior to publication.
3809100023 | 02/01/2008 18:27:20 EST | 1 | Chaplin, Clint | X | X | Individual | 1 | Producer | Disapprove | Editorial | 16 | 7.3.3 | 10 | This sub-section should not be numbered 7.3.3; it needs to come before all the 7.3.2.xxx information element descriptions. And, unfortunately, you cannot make a single sub-section. |  | Yes | Renumber as 7.3.2.1, or something like that. |  | PROPOSED REJECT. The referenced text is correct, but improperly placed in the TGk draft (D12.0). Prior to publication the publication editor shall move text at P16L9-L29 and insert this text at P73L25. Page and line references are in the clean draft (D12.0). Please note that the IEEE standards are edited professionally before publication.