## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-09/xxxxr0
Venue Date: | July 2009
First Author: | Michael Montemurro, Research in Motion
Subject: | Proposed resolutions to Security and MAC Management comments for LB 149
Full Date: | 2009-07-13
Author(s): | Michael Montemurro
TGmb Vice-Chair
RIM
Missisauga, ON, Canada
mmontemurro@rim.com
Abstract:
This spreadsheet contains a set of proposed resolutions to Security and MAC Management comments for LB 149

## Security - TKIP
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
1155 | Hamilton, Mark | 149 | 1 | 8.3.2.4.0a | 271 | 26 | T | Y | 271.26 | 26 | 8.3.2.4.0a | [5 empty] | This behavior for MLME-EAPOL.confirm is not consistent with a connectionless MAC and X.210-based primitive methods. It also does not appear to serve any real purpose in the EAPOL-Key exchanges since everything uses handshakes. | Delete the sentence describing the MLME-EAPOL.confirm primitive in this subclause, and delete 10.3.20.2. |  | SECURITY | Security - TKIP | Submission | SECURITY: 2009-07-14 01:28:07Z - Proposed Resolution: Need submission. Discuss with Mark H. |  |  |  | 2009-07-14 22:12 | SECURITY

## Security - key management
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
1042 | Cam-Winget, Nancy | 149 | 1 | 8.4.8 | 295 | 30 | T | Y | 295.3 | 30 | 8.4.8 | [5 empty] | Again, this section only applies to the non-FT (e.g. AKMs 1 and 2 only) and should be state as such. Or the clause could be adapted to referent 11A for the FT case as well. | In the comment |  | SECURITY | Security - key management | Follow-up | SECURITY: 2009-07-14 01:52:05Z Discuss with Commentor. |  |  |  | 2009-07-14 22:10 | SECURITY
1043 | Cam-Winget, Nancy | 149 | 1 | 8.4.10 | 296 | 64 | T | Y | 296.64 | 64 | 8.4.10 | [5 empty] | It is also possible to also invoke the FT Protocol. |  |  | SECURITY | Security - key management | Follow-up | SECURITY: 2009-07-14 01:53:08Z Discuss with Commentor |  |  |  | 2009-07-14 22:10 | SECURITY

## Security - General
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
1422 | Stephens, Adrian | 149 | 1 | 5.4.3 | 47 | 14 | T | N | 47.14 | 14 | 5.4.3 | [5 empty] | "Two services are provided to bring the IEEE 802.11 functionality in line with wired LAN assumptions: authentication and data confidentiality. Authentication is used instead of the wired media physical connection. Data confidentiality is used to provide the confidential aspects of closed wired media." This material has been superseded by the following two paras. | Delete cited text. |  | SECURITY | Security - General | Follow-up | SECURITY: 2009-07-14 22:19:35Z Follow-up with commentor |  |  |  | 2009-07-14 22:20 | SECURITY
1423 | Stephens, Adrian | 149 | 1 | 5.4.3.1 | 48 | 1 | T | N | 48.01 | 1 | 5.4.3.1 | [5 empty] | "Management information base (MIB) functions are provided in Annex D to support the standardized authentication schemes." What does this mean? I haven't the foggiest, and I suspect that TGmb won't either. | Remove cited text, or replace it with something meaningful. |  | SECURITY | Security - General | Discussion | SECURITY: 2009-07-14 22:20:25Z Proposed Accept. |  |  |  | 2009-07-14 22:21 | SECURITY
1427 | Stephens, Adrian | 149 | 1 | 5.8.3.3 | 59 | 28 | T | N | 59.28 | 28 | 5.8.3.3 | [5 empty] | "If the SME wants to set up a security association to the peer STA, but does not know the security policy of the peer, it should send a Probe Request frame to the peer STA to find its security policy before setting up a security association to the peer STA." How does it achieve this? What SAP interfaces does the SME use to send this probe request. | Remove cited sentence, or add appropriate SAP interfaces to support this function. |  | SECURITY | Security - General |  | SECURITY: 2009-07-14 22:21:05Z Proposed Accept. |  |  |  | 2009-07-14 22:21 | SECURITY
1254 | Montemurro, Michael | 149 | 1 | 8.1.0a | 253 | 7 | T | N | 253.07 | 7 | 8.1.0a | [5 empty] | This looks like an important place to state that WEP and TKIP are deprecated. | Either add a statement that TKIP and WEP are deprecated in this clause, or refer to clause 6.1.2. Alternative, move the statement that WEP and TKIP are deprecated to this clause and add a reference in clause 6.1.2. |  | SECURITY | Security - General | Follow-up | SECURITY: 2009-07-14 22:12:49Z Follow-up with commentor. |  |  |  | 2009-07-14 22:13 | SECURITY
1033 | Cam-Winget, Nancy | 149 | 1 | 8.1.3 | 253 | 60 | T | Y | 253.6 | 60 | 8.1.3 | [5 empty] | As there are now more than one key management protcol, this line number should be more explicit to this and perhaps define which ones are used based on the selected AKM. One possible fix ione of the protocols as defined by 8.5 (Keys and key distribution) or 11A (Fast BSS Transition).". | In the comment |  | SECURITY | Security - General | Follow-up | SECURITY: 2009-07-14 21:39:27Z Need discussion with commentor. |  |  |  | 2009-07-14 22:10 | SECURITY
1045 | Cam-Winget, Nancy | 149 | 1 | 8.7.2 | 353 | 40 | T | Y | 353.4 | 40 | 8.7.2 | [5 empty] | Given that state machine descriptions are already provided both in visual and long prose formats, there seems to be little value gained by providing this pseudo-code other than adding bloat to the document and another tedious section that may not be consistant with the state machine. Please consider removing this whole clause. | In the comment |  | SECURITY | Security - General | Discussion | SECURITY: 2009-07-14 01:58:59Z Discuss. Does anybody use this? |  |  |  | 2009-07-14 22:11 | SECURITY

## Security - Authentication
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
1357 | Rosdahl, Jon | 149 | 1 | 11.3 | 599-606 |  | T | Y |  |  | 11.3 | [5 empty] | The specification of STA authentication and association in section 11.3 is incomplete, ambiguous, inconsistent and sometimes just wrong. | Change as shown in doc:11-09/0705 |  | SECURITY | Security - Authentication | Discussion | SECURITY: 2009-07-14 22:18:25Z Resolution pending the result of the discussion on document 11-09/705 |  |  |  | 2009-07-14 22:19 | SECURITY
1342 | Ramamurthy, Harish | 149 | 1 | 11.3 | 599-600 |  | T | N |  |  | 11.3 | [5 empty] | The definitions of class 1 data frame and class 3 data frame are not clear especially in IBSS networks. A data frame with FromDS = ToDS = 0 belongs to class 1 in IBSS and class 3 in other cases. The question is how to determine whether a data frame belongs to class 1 in the IBSS or not when STA is in state 1? For example, if STA resets, it may lose state information and subsequently a data frame received from peer STA cannot be marked as IBSS or BSS frame, and therefore cannot be classified whether belongs to class 1 or 3. | Clarify. |  | SECURITY | Security - Authentication | Discussion | SECURITY: 2009-07-14 22:16:27Z Pending Resolution to document 11-09/705 discussion. |  |  |  | 2009-07-14 22:18 | SECURITY

## Radio management - MAC
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
1527 | Stephens, Adrian | 149 | 1 | 11.9.3 | 630 | 33 | T | N | 630.33 | 33 | 11.9.3 | [5 empty] | "A STA shall not transmit in a channel unless it has been tested for the presence of radars according to regulatory requirements." Presumably it uses its well-honed telepathic abilities to determine if the channel has been tested. | Relate to observable state or on-the-air signalling. |  | SECURITY | Radio management - MAC | Follow-up | SECURITY: 2009-07-14 20:58:42Z - Talk with Commentor. |  |  |  | 2009-07-14 22:23 | SECURITY
1256 | Montemurro, Michael | 149 | 1 | 11.10.8.1 | 644 | 59 | T | N | 644.59 | 59 | 11.10.8.1 | [5 empty] | The paragraph states that if the Channel Number field is 255, the STA conducts measurements on all channels included in the AP Channel Report. However it does not indicate where the STA receives the Channel Report (I assume the Beacon). In the next paragraph, the text states that an optional Channel Report sub-element can be used to supply a list of channels in the Beacon Report. | Clarify the use of AP Channel Report in the Beacon Report as follows: 1) If the Channel Number Field is 0, the STA shall use uses the regulatory domain information. 2) If the Channel Number Field is 255, the STA uses the AP Channel report sub-element(s) (if included) or the last AP Channel Report IE received in the last Beacon frame. 3) If the Channel Number Field specifies any other channel number, the STA will generate a Beacon Report response using that channel number. I can prepare a submission to clean up the last paragraph on pg 644 and first two paragraphs on pg. 645. |  | SECURITY | Radio management - MAC | Submission | SECURITY: 2009-07-14 21:01:52Z Talk to Commentor. Need a Submission. |  |  |  | 2009-07-14 22:14 | SECURITY
1167 | Hamilton, Mark | 149 | 1 | 11.10.11 | 653 | 48 | T | Y | 653.48 | 48 | 11.10.11 | [5 empty] | Multiple BSSID Set APs must share more facilities "in common" than those listed. | Add (at least), "Channel Access Functions" to the list of common facilities in the first bullet. There are probably more things that should be listed. This will need study. |  | SECURITY | Radio management - MAC | Discussion | SECURITY: 2009-07-14 21:09:01Z Discuss. |  |  |  | 2009-07-14 22:12 | SECURITY
1433 | Stephens, Adrian | 149 | 1 | 11.10.12 | 654 | 28 | T | N | 654.28 | 28 | 11.10.12 | [5 empty] | What we have here is a table that provides a mixture of static capability and active status as the encoding for a MIB variable. This is confusing, and counter to the ARC group's policy on MIB variables. | Separate out capability and status information into two MIB variables. |  | SECURITY | Radio management - MAC | Submission | SECURITY: 2009-07-14 21:10:55Z Propose Accept. Need Submission. |  |  |  | 2009-07-14 22:22 | SECURITY

## Fast transition
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
1551 | Stephens, Adrian | 149 | 1 | 11A.1 | 665 | 41 | T | N | 665.41 | 41 | 11A.1 | [5 empty] | If the terms defined in this note are used in normative text, it is not sufficient to define them in an informative note. | Promote material in note to body (i.e., regular text) |  | SECURITY | Fast transition | Follow-up | SECURITY: 2009-07-14 22:23:34Z Talk to Commentor |  |  |  | 2009-07-14 22:24 | SECURITY

## 1
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
1417 | Stephens, Adrian | 149 | 1 | 5.2.7 | 38 | 65 | T | N | 38.65 | 65 | 5.2.7 |  | A |  |  |  | "health and efficiency" is a possibly trademarked term, being the name of a Naturist magazine. | If anybody is going to confuse the 802.11 standard with a Naturist publication, this term should be changed. e.g. to "efficiency and health". | AGREE (SECURITY: 2009-07-14 22:00:32Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 21:12:07Z Proposed Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1703 | Venkatesan, Ganesh | 149 | 1 | 5.2.7.11 | 40 | 41-42 | T | N | 40 |  | 5.2.7.11 |  | P |  |  |  | "ongoing traffic stream link". Is there one such term? Ongoing traffic stream or ongoing traffic stream over the link is appropriate. | Replace "ongoing traffic stream link" with a more appropriate term. | AGREE IN PRINCIPLE (SECURITY: 2009-07-14 22:04:34Z) Replace the text with "ongoing traffic stream". | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 21:28:47Z Proposed Accept. Replace the text with "ongoing traffic stream". SECURITY: 2009-07-14 21:12:39Z Proposed Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1246 | McCann, Stephen | 149 | 1 | 5.4.4.1 | 50 | 3 | T | N | 50.03 | 3 | 5.4.4.1 |  | P |  |  |  | A reference to Annex I or J may be appropriate here. This also applies to clause 5.4.4.2. | Add a reference to Annex I and/or J to indicate more information is available for country radio regulations. | AGREE IN PRINCIPLE (SECURITY: 2009-07-14 21:56:08Z) Update the first sentence of Clause 5.4.4 as follows: "Two services are required to satisfy requirements in some regulatory domains ( See Annex I and Annex J for more information) for operation in the 5 GHz band." | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 01:24:49Z - Proposed Resolution: Counter. Update the first sentence of Clause 5.4.4 as follows: "Two services are required to satisfy requirements in some regulatory domains ( See Annex I and Annex J for more information) for operation in the 5 GHz band." |  |  |  | 2009-07-15 18:08 | SECURITY
1034 | Cam-Winget, Nancy | 149 | 1 | 8.1.3 | 254 | 64 | T | Y | 254.64 | 64 | 8.1.3 |  | A |  |  |  | "shared authentication" should be "Shared Key authentiation" as defined by 8.2.2.3. | In the comment | AGREE (SECURITY: 2009-07-14 21:40:10Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 01:58:02Z Proposed Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1442 | Stephens, Adrian | 149 | 1 | 8.2.2.3.0a | 260 | 48 | T | N | 260.48 | 48 | 8.2.2.3.0a |  | A |  |  |  | "Shared Key authentication can be used if and only if WEP has been selected." "can" and "if and only if" are conflicting - one implies information, the other expresses a constraint. | Replace with: "Shared Key authentication may be used if WEP has been selected and shall not be used otherwise." | AGREE (SECURITY: 2009-07-14 22:01:14Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 21:15:55Z Propose Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1225 | Marshall, Bill | 149 | 1 | 8.4.1.1.2 | 286 | 36 | T | N | 286.36 | 36 | 8.4.1.1.2 |  | A |  |  |  | "between Message 1 and Message 3 of a 4-Way Handshake." but the phrase should include the FT 4-Way Handshake added earlier in the sentence. | change "of a 4-Way Handshake" to "of the handshake" | AGREE (SECURITY: 2009-07-14 21:53:52Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 01:39:26Z Proposed Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1037 | Cam-Winget, Nancy | 149 | 1 | 8.4.1.1.2 | 286 | 45 | T | Y | 286.45 | 45 | 8.4.1.1.2 |  | D |  |  |  | A PTKSA should also be bound to the associated pairwise cipher suite. A new item under the PTKSA should be added to include "Pairwise cipher suite selector" | In the comment | DISAGREE (SECURITY: 2009-07-14 21:46:22Z) The text is already included. | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 01:40:03Z Propose Reject. The text is already included. |  |  |  | 2009-07-15 18:08 | SECURITY
1035 | Cam-Winget, Nancy | 149 | 1 | 8.4.1.1.2 | 286 | 51 | T | Y | 286.51 | 51 | 8.4.1.1.2 |  | A |  |  |  | A PTKSA should have the identities of its full lineage, including the PMKR0Name. Inlcude as a subitem "PMKR0Name" in the FT key hierarchy list. | In the comment | AGREE (SECURITY: 2009-07-14 21:40:22Z) Propose Accept. Add "PMKR0Name" to the bullet list. | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 01:40:34Z Propose Accept. Add "PMKR0Name" to the bullet list. |  |  |  | 2009-07-15 18:08 | SECURITY
1036 | Cam-Winget, Nancy | 149 | 1 | 8.4.1.1.3 | 286 | 60 | T | Y | 286.6 | 60 | 8.4.1.1.3 |  | A |  |  |  | The GTK is also distributed during the FT protocol. The sentence should be updated to read "….4-Way Handshake, FT 4-Way Handshake, FT Protocol, FT Resource Request Protocol or the Group Key Handshake…." | In the comment | AGREE (SECURITY: 2009-07-14 21:46:11Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 01:41:16Z Propose Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1140 | Hamilton, Mark | 149 | 1 | 8.4.1.1.3 | 286 | 61 | T | Y | 286.61 | 61 | 8.4.1.1.3 |  | A |  |  |  | 2nd sentence, "In an ESS, there is one GTKSA, …" is confusing. There is one GTKSA per BSS, in infrastructure mode. | Replace "In an ESS" with "In an infrastructure BSS". | AGREE (SECURITY: 2009-07-14 21:51:56Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 01:42:04Z Propose Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1038 | Cam-Winget, Nancy | 149 | 1 | 8.4.1.2.1 | 288 | 51 | T | Y | 288.51 | 51 | 8.4.1.2.1 |  | A |  |  |  | As TGmb is merging 802.11r into the base, this section seems to either focus on non-FT enabled STAs or this section must be updated to state that the key management invoked will depend on whether it is a "simple" RSN or an FT. One possible update to remedy this is to change this sentence to read "STA uses one of the key confirmation handshakes, e.g. the 4-Way Handshake or FT 4-Way Handshake, to complete...." | In the comment | AGREE (SECURITY: 2009-07-14 21:46:50Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 01:36:58Z - Proposed Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1039 | Cam-Winget, Nancy | 149 | 1 | 8.4.1.2.1 | 288 | 58 | T | Y | 288.58 | 58 | 8.4.1.2.1 |  | P |  |  |  | This first sentence is true only for the non-FT case. Perhaps the simplest update is to state "When FT is not enabled, the case of (re)association followed…." or in line 56, (since the rest of the items seems to also suggest non-FT) change the sentence to "When FT is not enabled, a STA roaming within an ESS establishes a new PMKSA by one of the three schemes:". A last alternative is to rename all of clause 8.4.1.2.1 to be non-FT Security association in an ESS. | In the comment | AGREE IN PRINCIPLE (SECURITY: 2009-07-14 21:46:57Z) Adopt the second change in the comment: Change the sentence to "When FT is not enabled, a STA roaming within an ESS establishes a new PMKSA by one of the three schemes:" | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 01:37:19Z Propose Accept in Principle: Adopt the second change in the comment: Change the sentence to "When FT is not enabled, a STA roaming within an ESS establishes a new PMKSA by one of the three schemes:" |  |  |  | 2009-07-15 18:08 | SECURITY
1040 | Cam-Winget, Nancy | 149 | 1 | 8.4.6 | 292 | 38 | T | Y | 292.38 | 38 | 8.4.6 |  | P |  |  |  | This section while parts can apply to an FT enabled link, is more relevant for when the link is not FT enabled. Suggest this be renamed to "non-FT enabled RSNA authentication in an ESS", otherwise, we'll have to sprinkle clarifications throughout this clause and sub-clauses for when FT kicks in. For instance, line 38 "Open System Authentication" is only usedwhen either the 4-Way Handshake or FT 4-Way Handshake are used and not during the FT Protocol or FT Resource Request PRotocol. | In the comment | AGREE IN PRINCIPLE (SECURITY: 2009-07-14 21:48:43Z) Change:"When establishing an RSNA…" to "When establishing an RSNA in a non-FT environment or for during an FT Initial mobility domain Association…" | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 01:35:27Z - Proposed Change: "Proposed Counter: Change:"When establishing an RSNA…" to "When establishing an RSNA in a non-FT environment or for during an FT Initial mobility domain Association…" |  |  |  | 2009-07-15 18:08 | SECURITY
1041 | Cam-Winget, Nancy | 149 | 1 | 8.4.6.2 | 293 | 55 | T | Y | 293.55 | 55 | 8.4.6.2 |  | P |  |  |  | As this is part of 8.4.6, my previous comment is highlighted by the relevance of this clause mainly applying to the non-FT case. Suggest this be renamed if the whole of 8.4.6 is not…to ensure that this section only applies to AKMs 1 and 2. | In the comment | AGREE IN PRINCIPLE (SECURITY: 2009-07-14 21:49:33Z) Change: "A STA" to "In a non-FT environment, A STA". | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 01:46:33Z Counter. Change: "A STA" to "In a non-FT environment, A STA". |  |  |  | 2009-07-15 18:08 | SECURITY
1227 | Marshall, Bill | 149 | 1 | 8.5.1.5.3 | 306 | 62 | T | N | 306.62 | 62 | 8.5.1.5.3 |  | P |  |  |  | unclear whether normative "shall" is neede here, or whether a simple declarative statement "SHA-256 is as defined in …" matching the style of the surrounding statements is sufficient | make the statements consistent. In either case, insert a hyphen into SHA-256 | AGREE IN PRINCIPLE (SECURITY: 2009-07-14 21:54:21Z) Replace "SHA256 shall be as defined in" with "SHA-256 is as defined in" | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 01:53:58Z Accept in Principle. Replace "SHA256 shall be as defined in" with "SHA-256 is as defined in" |  |  |  | 2009-07-15 18:08 | SECURITY
1258 | Montemurro, Michael | 149 | 1 | 8.5.2 | 310 | 5 | T | N | 310.05 | 5 | 8.5.2 |  | A |  |  |  | It would be beneficial to include the RFC reference as well as the FIPS publication reference. | Change the text from: "defined by FIPS SP800-38B" to: "defined by FIPS SP800-38B and also found in RFC 4493." and add RFC 4493 to the references. | AGREE (SECURITY: 2009-07-14 21:59:20Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 01:54:29Z Proposed Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1255 | Montemurro, Michael | 149 | 1 | 8.5.3.0a | 317 | 41 | T | N | 317.41 | 41 | 8.5.3.0a |  | A |  |  |  | The 4-way handshake is also used for FT Initial Association. It would be beneficial to add some text and a cross-reference to clause 11A.4.2. | Add the following text after the first paragraph. "The FT Initial Mobility Domain Association uses the FT 4-way handshake to establish an initial FT Security Association, that is based on this protocol. The FT 4-way handshake protocol is described in Clause 11A.4." | AGREE (SECURITY: 2009-07-14 21:58:31Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 01:54:59Z Proposed Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1260 | Montemurro, Michael | 149 | 1 | 8.5.3.2 | 320 | 23 | T | N | 320.23 | 23 | 8.5.3.2 |  | A |  |  |  | The RSN IE in message 2 of the FT Intial Association will not bitwise match the RSN IE used in the Reassociation Request. | Modify the text as follows: 2) If the MIC is valid, the Authenticator checks that the RSN information element bit-wise matches that from the (Re)Association Request message. For FT Intial Association, the RSN IE cannot be bit-wised compared because the PMKR1Name will be included in the RSN IE field as part of Message 2. In that case, the remainder of the RSN IE in message 2 is checked against the RSN IE included in the Reassociation Request. i) If these are not exactly the same, the Authenticator uses MLME-DEAUTHENTICATE. request primitive to terminate the association. ii) If they do match bit-wise, the Authenticator constructs Message 3. | AGREE (SECURITY: 2009-07-14 21:59:34Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 01:55:26Z Proposed Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1261 | Montemurro, Michael | 149 | 1 | 8.5.3.3 | 321 | 49 | T | N | 321.49 | 49 | 8.5.3.3 |  | A |  |  |  | The RSN IE in message 3 of the FT Intial Association will not match the RSN IE used in the Beacon or Probe Response. | Modify the text as follows: Verifies the RSNIE. If it is not identical to that the STA received in the Beacon or Probe Response frame, the STA shall disassociate. For FT Initial Association, the RSN IE will differ from the RSN IE in Beacon and Probe Response messages becuse it will contain the PMKR1Name in the PMKID field. For FT Initial Association, the PMKID field is ignored in the RSN IE comparison. If a second RSN information element is provided in the message,the Supplicant uses the pairwise cipher suite specified in the second RSNIE or deauthenticates. | AGREE (SECURITY: 2009-07-14 21:59:42Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 01:56:05Z Proposed Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1152 | Hamilton, Mark | 149 | 1 | 11.3.0a | 598 | 54 | T | Y | 598.54 | 54 | 11.3.0a | [5 empty] | With the addition of RSNA capability, the term "authentication" as it applies to states like the ones in 11.3.0a, has taken on multiple meanings. That's fine, except many people seem to get confused by which authentication is being referred to in different contexts. This could perhaps be alleviated by showing the RSNA authentication process in these state tables, like the simple authentication. | Add the concept of RSNA authentication to the state variables and state machine shown in 11.3.0a. This will need a submission. |  | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 21:52:24Z Dependent on the discussion and revision of document 11-09/705 |  |  |  | 2009-07-15 18:08 | SECURITY
1444 | Stephens, Adrian | 149 | 1 | 11.3.0a | 600 | 5 | T | N | 600.05 | 5 | 11.3.0a |  | A |  |  |  | Incorrect use of "if and only if" - which implies logical correspondance. i.e. line 5 implies that all frames are class 2 if the STA is authenticated - which is clearly rubbish. | Replace "if and only if" with "only if" on line 5 and line 23. | AGREE (SECURITY: 2009-07-14 22:01:40Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 21:19:02Z Proposed Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1507 | Stephens, Adrian | 149 | 1 | 11.3.0a | 600 | 30 | T | N | 600.3 | 30 | 11.3.0a |  | D |  |  |  | "Data frames between STAs in a BSS" - it means infrastructure BSS | Change BSS to "infrastructure BSS". | DISAGREE (SECURITY: 2009-07-14 22:02:15Z) The text cited applies to an IBSS. | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 21:26:45Z Propose Reject. The text cited applies to an IBSS. SECURITY: 2009-07-14 20:53:37Z Propose Reject. Infrastructure BSS is redundant. Discuss. |  |  |  | 2009-07-15 18:08 | SECURITY
1508 | Stephens, Adrian | 149 | 1 | 11.3.0a | 600 | 42 | T | N | 600.42 | 42 | 11.3.0a |  | A |  |  |  | BlockAck and BlockAckReq are permitted in an IBSS | Change cited location to be specified to infrastructure and add them as Class 1 frames for IBSS. | AGREE (SECURITY: 2009-07-14 22:02:28Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 20:55:02Z Propose Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1525 | Stephens, Adrian | 149 | 1 | 11.9.0a | 629 | 30 | T | N | 629.3 | 30 | 11.9.0a |  | A |  |  |  | It is not exactly clear which of the three dashed list items are part of the exception. | Indent the para starting "A STA may operate when..." | AGREE (SECURITY: 2009-07-14 22:02:34Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 20:55:33Z Proposed Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1526 | Stephens, Adrian | 149 | 1 | 11.9.2 | 630 | 11 | T | N | 630.11 | 11 | 11.9.2 |  | A |  |  |  | "Only the STA starting an IBSS may specify a schedule of quiet intervals" - isn't it the job of the DFS owner? The STA that started the IBSS may be long dead and buried. | Change to: "Only the STA that is the DFS owner in an IBSS may specify a schedule of quiet intervals" | AGREE (SECURITY: 2009-07-14 22:02:42Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 20:56:42Z Proposed Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1528 | Stephens, Adrian | 149 | 1 | 11.9.6 | 630 | 53 | T | N | 630.53 | 53 | 11.9.6 |  | A |  |  |  | The author has forgotten that the term BSS applies both to infrastructure and indepdendent. | p630.53: BSS->infrastructure BSS p630.58: "BSS or IBSS" -> BSS (make change globally) | AGREE (SECURITY: 2009-07-14 22:02:57Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 20:59:25Z Proposed Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1269 | Myles, Andrew | 149 | 1 | 11.9.7.2 | 632 |  | T | Y | 632.51 | 51 | 11.9.7.2 |  | D |  |  |  | The procedure to select a new channel in an IBSS is only claimed to be "best effort" at best. At worst, it may not even work. The reality is that after 5+ years there is no known implemenation of this feature, indicating it is unnecessary | Remove it | DISAGREE (SECURITY: 2009-07-14 21:35:44Z) The proposed change may make existing 802.11 devices non-compliant with the standard. The comment has not justified the change. | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 21:00:29Z - Discuss. |  |  |  | 2009-07-15 18:08 | SECURITY
1447 | Stephens, Adrian | 149 | 1 | 11.10.5 | 640 | 19 | T | N | 640.19 | 19 | 11.10.5 |  | A |  |  |  | Incorrect use of "if and only if" in the following: "A STA shall accept a Measurement Request with the parallel bit field enabled if and only if dot11RRMParallelMeasurenmentEnabled is true; otherwise, the STA shall reject the Measurement Request by returning a Measurement Report with the Incapable bit set in the Measurement Report Mode field." | Note, cited text already contains a normative requirement to reject "otherwise" so the wrong "and only if" is also redundant. Delete: "and only if" from the cited text. | AGREE (SECURITY: 2009-07-14 22:01:49Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 21:01:10Z Proposed Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1531 | Stephens, Adrian | 149 | 1 | 11.10.8.4 | 648 | 24 | T | N | 648.24 | 24 | 11.10.8.4 |  | A |  |  |  | "defined in dBm using the same units" But dBm are the units. | remove "units and" | AGREE (SECURITY: 2009-07-14 22:03:01Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 21:02:27Z Proposed Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1532 | Stephens, Adrian | 149 | 1 | 11.10.8.6 | 649 | 28 | T | N | 649.28 | 28 | 11.10.8.6 |  | A |  |  |  | "shall be as required for operation in the regulatory domain" - this is a useless statement. If regulations require something, this says effectively "you shall do what you shall do", without actually specifying what that is. | Turn para into note, and add references to any known regulations on this matter. | AGREE (SECURITY: 2009-07-14 22:03:05Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 21:03:52Z Talk to Commentor. |  |  |  | 2009-07-15 18:08 | SECURITY
1533 | Stephens, Adrian | 149 | 1 | 11.10.8.8 | 651 | 28 | T | N | 651.28 | 28 | 11.10.8.8 |  | A |  |  |  | "If dot11RRMTriggeredTransmitStreamCategoryMeasurementEnabled is true, a QoS STA shall accept a triggered Transmit Stream/Category Measurement and shall reject it otherwise." This contradicts the previous sentence that allows a resource limit to generate a rejection. | Change cited text to: If dot11RRMTriggeredTransmitStreamCategoryMeasurementEnabled is true and has no resource contraint that prevents it from being able to make the requested measurement, a QoS STA shall accept a triggered Transmit Stream/Category Measurement and shall reject it otherwise. | AGREE (SECURITY: 2009-07-14 22:03:10Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 21:04:31Z Proposed Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1263 | Montemurro, Michael | 149 | 1 | 11.10.8.8 | 651 | 46 | T | N | 651.46 | 46 | 11.10.8.8 |  | A |  |  |  | It makes sense that the Measurement Count field would be interpreted as the the total of successfully and unsuccessfully transmitted MSDU's. The current text is ambiguous. | Modify the first sentence of the paragraph as follows: Traffic stream metrics reported in a triggered transmit stream/category measurement report shall be the values accumulated over the number of successfully and unsuccessfully transmitted MSDUs prior to the trigger event given in the Measurement Count field of the transmit stream/category measurement request that established the trigger condition. | AGREE (SECURITY: 2009-07-14 21:59:54Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 21:05:11Z Proposed Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1534 | Stephens, Adrian | 149 | 1 | 11.10.9 | 652 | 18 | T | N | 652.18 | 18 | 11.10.9 |  | P |  |  |  | "A Neighbor Report is sent by an AP and it contains information on validated AP’s" The concept of a valid or invalid AP is not known to me. | Describe what "validated" means in this context. | AGREE IN PRINCIPLE (SECURITY: 2009-07-14 22:03:33Z) "Propose Counter. Replace ""on valdiated AP's"" with ""on neighboring AP's""" | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 21:05:53Z "Propose Counter. Replace ""on valdiated AP's"" with ""on neighboring AP's""" |  |  |  | 2009-07-15 18:08 | SECURITY
1536 | Stephens, Adrian | 149 | 1 |  | 653 | 1 | T | N | 653.01 | 1 | 11.10.9.2 |  | A |  |  |  | "A serving AP shall include a TSF information field in the Neighbor Report element only if it is able to guarantee an accumulated error of 1.5 TU or better on the TSF Offset subfield." "... shall <verb> only if <condition> " is highly ambiguous. What does it mean? A: "shall not <verb> if not <condition>" B: "may <verb> if <condition> and shall not <verb> otherwise" C: "shall <verb> if <condition> and shall not <verb> otherwise" | Scan the entire draft for occurances of "shall <verb> only if <condition>" and for each convert to one of these unambiguous forms. In this case (and, I suspect, in most), form A is appropriate. | AGREE (SECURITY: 2009-07-14 22:03:49Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 21:08:10Z Proposed Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1538 | Stephens, Adrian | 149 | 1 | 11.10.11 | 653 | 50 | T | N | 653.5 | 50 | 11.10.11 | [5 empty] | I'm sure that there are constraints within the system (e.g. in TIM encoding, or where per-BSSID information is packed into a single MMPDU) that limits the number of BSSIDs to less 2**46 - which is a guzumpingly large number. | Work out the actual constraint and insert it here. |  | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 21:09:40Z Discusss. |  |  |  | 2009-07-15 18:08 | SECURITY
1073 | Ecclesine, Peter | 149 | 1 | 11.10.12 | 654 | 5 | T | Y | 654.05 | 5 | 11.10.12 |  | D |  |  |  | The Measurement Pilot option specified here is obsolete, and is not in current products that claim 802.11 conformance. I do not know of any products or plans to implement Measurement Pilots. The option would add lots of noise in whatever band it is used in (Note 1 pg 655, Note 2 and NOTE, pg 656). Commenter will make a submission removing 7.3.2.42, 7.4.7.2, 11.10.12 and whatever other text changes are needed to remove the Measurement Pilot Transmission option from the standard. | Remove the Measurement Pilot option from the standard. | DISAGREE (SECURITY: 2009-07-14 21:36:43Z) Reject. This is a new feature that is less than a year old, and should be given time to be implemented before removal. The proposed change may make existing 802.11 devices non-compliant with the standard. The comment has not justified the change. This comment was previously rejected as CID 158 in 11-07/2642r9. | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 21:10:11Z Discuss. |  |  |  | 2009-07-15 18:08 | SECURITY
1231 | Marshall, Bill | 149 | 1 | 11A.3 | 668 | 17 | T | N | 668.17 | 17 | 11A.3 |  | A |  |  |  | dot11FTOver-DSEnabled doesn't have the hyphen in MIB | drop hyphen here | AGREE (SECURITY: 2009-07-14 21:55:15Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 21:55:00Z Proposed Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1233 | Marshall, Bill | 149 | 1 | 11A.4.2 | 670 | 31 | T | N | 670.31 | 31 | 11A.4.2 |  | A |  |  |  | The "Data(…)" notation came from an early draft of 11i; it was dropped before publication of 802.11i and never appeared in REVma, but was only caught in 11r at publication time (too late). | drop "Data(" and ")" from these four entries, and drop the note at line 61 | AGREE (SECURITY: 2009-07-14 21:55:47Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 21:55:34Z Proposed Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1305 | Ptasinski, Henry | 149 | 1 | 11A.8.4 | 689 | 7 | T | Y | 689.07 | 7 | 11A.8.4 |  | A |  |  |  | MIC calculation includes the IE headers. | Delete “Contents of the” from RSNIE, MDIE, and FTIE. | AGREE (SECURITY: 2009-07-14 22:00:09Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 21:13:38Z Proposed Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1306 | Ptasinski, Henry | 149 | 1 | 11A.8.5 | 690 | 4 | T | Y | 690.04 | 4 | 11A.8.5 |  | A |  |  |  | MIC calculation includes the IE headers. | Delete “Contents of the” from RSNIE, MDIE, and FTIE. | AGREE (SECURITY: 2009-07-14 22:00:15Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 21:14:10Z Proposed Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1257 | Montemurro, Michael | 149 | 1 | 11A.9.5.1 | 700 | 15 | T | N | 700.15 | 15 | 11A.9.5.1 |  | A |  |  |  | FT-Transition-Auth (R1KH-ID) to CALC-PMK_R1 S0KH SM occurs too early. The supplicant may not know the R1KH-ID at this point so it cannot calculate the PMK-R1. | Move "FT-Transition-Auth (R1KH-ID) to CALC-PMK_R1 S0KH SM" to the FT-PTK-CALC state, after the Reassociationdeadlinetimer. | AGREE (SECURITY: 2009-07-14 21:58:54Z) | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 21:14:34Z Proposed Accept. |  |  |  | 2009-07-15 18:08 | SECURITY
1097 | Gast, Matthew | 149 | 1 | 11A.10.1 | 702 | 33 | T | N | 702.33 | 33 | 11A.10.1 |  | A |  |  |  | "The current AP encapsulates the FT Action frame (Request or Confirm) inside a Remote Request frame and transmits it to the target AP over the DS." By definition, "encapsulate" (3.49) refers only to encrypting frames, not the act of putting a higher layer frame inside a lower layer type. | Two options: (1) change the definition of "encapsulate" in 3.49 so that it does not require cryptography, or (2) change the usage of "encapsulate" in this clause to some other word. | AGREE (SECURITY: 2009-07-14 21:51:08Z) Accept Option 1 in the Proposed Resolution. | SECURITY | 1 | Ready for motion | SECURITY: 2009-07-14 21:25:23Z Proposed Accept Option #1. |  |  |  | 2009-07-15 18:08 | SECURITY

## Comments
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
1342 | Ramamurthy, Harish | 149 | 1 | 11.3 | 599-600 |  | T | N |  |  | 11.3 | [5 empty] | The definitions of class 1 data frame and class 3 data frame are not clear especially in IBSS networks. A data frame with FromDS = ToDS = 0 belongs to class 1 in IBSS and class 3 in other cases. The question is how to determine whether a data frame belongs to class 1 in the IBSS or not when STA is in state 1? For example, if STA resets, it may lose state information and subsequently a data frame received from peer STA cannot be marked as IBSS or BSS frame, and therefore cannot be classified whether belongs to class 1 or 3. | Clarify. |  | SECURITY | Security - Authentication | Discussion | SECURITY: 2009-07-14 22:16:27Z Pending Resolution to document 11-09/705 discussion. |  |  |  | 2009-07-14 22:18 | SECURITY
1357 | Rosdahl, Jon | 149 | 1 | 11.3 | 599-606 |  | T | Y |  |  | 11.3 | [5 empty] | The specification of STA authentication and association in section 11.3 is incomplete, ambiguous, inconsistent and sometimes just wrong. | Change as shown in doc:11-09/0705 |  | SECURITY | Security - Authentication | Discussion | SECURITY: 2009-07-14 22:18:25Z Resolution pending the result of the discussion on document 11-09/705 |  |  |  | 2009-07-14 22:19 | SECURITY
1417 | Stephens, Adrian | 149 | 1 | 5.2.7 | 38 | 65 | T | N | 38.65 | 65 | 5.2.7 |  | A |  |  |  | "health and efficiency" is a possibly trademarked term, being the name of a Naturist magazine. | If anybody is going to confuse the 802.11 standard with a Naturist publication, this term should be changed. e.g. to "efficiency and health". | AGREE (SECURITY: 2009-07-14 22:00:32Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 21:12:07Z Proposed Accept. |  |  |  | 2009-07-14 22:19 | SECURITY
1703 | Venkatesan, Ganesh | 149 | 1 | 5.2.7.11 | 40 | 41-42 | T | N | 40 |  | 5.2.7.11 |  | P |  |  |  | "ongoing traffic stream link". Is there one such term? Ongoing traffic stream or ongoing traffic stream over the link is appropriate. | Replace "ongoing traffic stream link" with a more appropriate term. | AGREE IN PRINCIPLE (SECURITY: 2009-07-14 22:04:34Z) Replace the text with "ongoing traffic stream". | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 21:28:47Z Proposed Accept. Replace the text with "ongoing traffic stream". SECURITY: 2009-07-14 21:12:39Z Proposed Accept. |  |  |  | 2009-07-14 22:34 | SECURITY
1422 | Stephens, Adrian | 149 | 1 | 5.4.3 | 47 | 14 | T | N | 47.14 | 14 | 5.4.3 | [5 empty] | "Two services are provided to bring the IEEE 802.11 functionality in line with wired LAN assumptions: authentication and data confidentiality. Authentication is used instead of the wired media physical connection. Data confidentiality is used to provide the confidential aspects of closed wired media." This material has been superseded by the following two paras. | Delete cited text. |  | SECURITY | Security - General | Follow-up | SECURITY: 2009-07-14 22:19:35Z Follow-up with commentor |  |  |  | 2009-07-14 22:20 | SECURITY
1423 | Stephens, Adrian | 149 | 1 | 5.4.3.1 | 48 | 1 | T | N | 48.01 | 1 | 5.4.3.1 | [5 empty] | "Management information base (MIB) functions are provided in Annex D to support the standardized authentication schemes." What does this mean? I haven't the foggiest, and I suspect that TGmb won't either. | Remove cited text, or replace it with something meaningful. |  | SECURITY | Security - General | Discussion | SECURITY: 2009-07-14 22:20:25Z Proposed Accept. |  |  |  | 2009-07-14 22:21 | SECURITY
1246 | McCann, Stephen | 149 | 1 | 5.4.4.1 | 50 | 3 | T | N | 50.03 | 3 | 5.4.4.1 |  | P |  |  |  | A reference to Annex I or J may be appropriate here. This also applies to clause 5.4.4.2. | Add a reference to Annex I and/or J to indicate more information is available for country radio regulations. | AGREE IN PRINCIPLE (SECURITY: 2009-07-14 21:56:08Z) Update the first sentence of Clause 5.4.4 as follows: "Two services are required to satisfy requirements in some regulatory domains ( See Annex I and Annex J for more information) for operation in the 5 GHz band." | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 01:24:49Z - Proposed Resolution: Counter. Update the first sentence of Clause 5.4.4 as follows: "Two services are required to satisfy requirements in some regulatory domains ( See Annex I and Annex J for more information) for operation in the 5 GHz band." |  |  |  | 2009-07-14 22:12 | SECURITY
1427 | Stephens, Adrian | 149 | 1 | 5.8.3.3 | 59 | 28 | T | N | 59.28 | 28 | 5.8.3.3 | [5 empty] | "If the SME wants to set up a security association to the peer STA, but does not know the security policy of the peer, it should send a Probe Request frame to the peer STA to find its security policy before setting up a security association to the peer STA." How does it achieve this? What SAP interfaces does the SME use to send this probe request. | Remove cited sentence, or add appropriate SAP interfaces to support this function. |  | SECURITY | Security - General |  | SECURITY: 2009-07-14 22:21:05Z Proposed Accept. |  |  |  | 2009-07-14 22:21 | SECURITY
1254 | Montemurro, Michael | 149 | 1 | 8.1.0a | 253 | 7 | T | N | 253.07 | 7 | 8.1.0a | [5 empty] | This looks like an important place to state that WEP and TKIP are deprecated. | Either add a statement that TKIP and WEP are deprecated in this clause, or refer to clause 6.1.2. Alternative, move the statement that WEP and TKIP are deprecated to this clause and add a reference in clause 6.1.2. |  | SECURITY | Security - General | Follow-up | SECURITY: 2009-07-14 22:12:49Z Follow-up with commentor. |  |  |  | 2009-07-14 22:13 | SECURITY
1033 | Cam-Winget, Nancy | 149 | 1 | 8.1.3 | 253 | 60 | T | Y | 253.6 | 60 | 8.1.3 | [5 empty] | As there are now more than one key management protcol, this line number should be more explicit to this and perhaps define which ones are used based on the selected AKM. One possible fix ione of the protocols as defined by 8.5 (Keys and key distribution) or 11A (Fast BSS Transition).". | In the comment |  | SECURITY | Security - General | Follow-up | SECURITY: 2009-07-14 21:39:27Z Need discussion with commentor. |  |  |  | 2009-07-14 22:10 | SECURITY
1034 | Cam-Winget, Nancy | 149 | 1 | 8.1.3 | 254 | 64 | T | Y | 254.64 | 64 | 8.1.3 |  | A |  |  |  | "shared authentication" should be "Shared Key authentiation" as defined by 8.2.2.3. | In the comment | AGREE (SECURITY: 2009-07-14 21:40:10Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 01:58:02Z Proposed Accept. |  |  |  | 2009-07-14 22:09 | SECURITY
1442 | Stephens, Adrian | 149 | 1 | 8.2.2.3.0a | 260 | 48 | T | N | 260.48 | 48 | 8.2.2.3.0a |  | A |  |  |  | "Shared Key authentication can be used if and only if WEP has been selected." "can" and "if and only if" are conflicting - one implies information, the other expresses a constraint. | Replace with: "Shared Key authentication may be used if WEP has been selected and shall not be used otherwise." | AGREE (SECURITY: 2009-07-14 22:01:14Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 21:15:55Z Propose Accept. |  |  |  | 2009-07-14 22:22 | SECURITY
1155 | Hamilton, Mark | 149 | 1 | 8.3.2.4.0a | 271 | 26 | T | Y | 271.26 | 26 | 8.3.2.4.0a | [5 empty] | This behavior for MLME-EAPOL.confirm is not consistent with a connectionless MAC and X.210-based primitive methods. It also does not appear to serve any real purpose in the EAPOL-Key exchanges since everything uses handshakes. | Delete the sentence describing the MLME-EAPOL.confirm primitive in this subclause, and delete 10.3.20.2. |  | SECURITY | Security - TKIP | Submission | SECURITY: 2009-07-14 01:28:07Z - Proposed Resolution: Need submission. Discuss with Mark H. |  |  |  | 2009-07-14 22:12 | SECURITY
1225 | Marshall, Bill | 149 | 1 | 8.4.1.1.2 | 286 | 36 | T | N | 286.36 | 36 | 8.4.1.1.2 |  | A |  |  |  | "between Message 1 and Message 3 of a 4-Way Handshake." but the phrase should include the FT 4-Way Handshake added earlier in the sentence. | change "of a 4-Way Handshake" to "of the handshake" | AGREE (SECURITY: 2009-07-14 21:53:52Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 01:39:26Z Proposed Accept. |  |  |  | 2009-07-14 22:12 | SECURITY
1037 | Cam-Winget, Nancy | 149 | 1 | 8.4.1.1.2 | 286 | 45 | T | Y | 286.45 | 45 | 8.4.1.1.2 |  | D |  |  |  | A PTKSA should also be bound to the associated pairwise cipher suite. A new item under the PTKSA should be added to include "Pairwise cipher suite selector" | In the comment | DISAGREE (SECURITY: 2009-07-14 21:46:22Z) The text is already included. | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 01:40:03Z Propose Reject. The text is already included. |  |  |  | 2009-07-14 22:09 | SECURITY
1035 | Cam-Winget, Nancy | 149 | 1 | 8.4.1.1.2 | 286 | 51 | T | Y | 286.51 | 51 | 8.4.1.1.2 |  | A |  |  |  | A PTKSA should have the identities of its full lineage, including the PMKR0Name. Inlcude as a subitem "PMKR0Name" in the FT key hierarchy list. | In the comment | AGREE (SECURITY: 2009-07-14 21:40:22Z) Propose Accept. Add "PMKR0Name" to the bullet list. | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 01:40:34Z Propose Accept. Add "PMKR0Name" to the bullet list. |  |  |  | 2009-07-14 22:09 | SECURITY
1036 | Cam-Winget, Nancy | 149 | 1 | 8.4.1.1.3 | 286 | 60 | T | Y | 286.6 | 60 | 8.4.1.1.3 |  | A |  |  |  | The GTK is also distributed during the FT protocol. The sentence should be updated to read "….4-Way Handshake, FT 4-Way Handshake, FT Protocol, FT Resource Request Protocol or the Group Key Handshake…." | In the comment | AGREE (SECURITY: 2009-07-14 21:46:11Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 01:41:16Z Propose Accept. |  |  |  | 2009-07-14 22:09 | SECURITY
1140 | Hamilton, Mark | 149 | 1 | 8.4.1.1.3 | 286 | 61 | T | Y | 286.61 | 61 | 8.4.1.1.3 |  | A |  |  |  | 2nd sentence, "In an ESS, there is one GTKSA, …" is confusing. There is one GTKSA per BSS, in infrastructure mode. | Replace "In an ESS" with "In an infrastructure BSS". | AGREE (SECURITY: 2009-07-14 21:51:56Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 01:42:04Z Propose Accept. |  |  |  | 2009-07-14 22:11 | SECURITY
1038 | Cam-Winget, Nancy | 149 | 1 | 8.4.1.2.1 | 288 | 51 | T | Y | 288.51 | 51 | 8.4.1.2.1 |  | A |  |  |  | As TGmb is merging 802.11r into the base, this section seems to either focus on non-FT enabled STAs or this section must be updated to state that the key management invoked will depend on whether it is a "simple" RSN or an FT. One possible update to remedy this is to change this sentence to read "STA uses one of the key confirmation handshakes, e.g. the 4-Way Handshake or FT 4-Way Handshake, to complete...." | In the comment | AGREE (SECURITY: 2009-07-14 21:46:50Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 01:36:58Z - Proposed Accept. |  |  |  | 2009-07-14 22:10 | SECURITY
1039 | Cam-Winget, Nancy | 149 | 1 | 8.4.1.2.1 | 288 | 58 | T | Y | 288.58 | 58 | 8.4.1.2.1 |  | P |  |  |  | This first sentence is true only for the non-FT case. Perhaps the simplest update is to state "When FT is not enabled, the case of (re)association followed…." or in line 56, (since the rest of the items seems to also suggest non-FT) change the sentence to "When FT is not enabled, a STA roaming within an ESS establishes a new PMKSA by one of the three schemes:". A last alternative is to rename all of clause 8.4.1.2.1 to be non-FT Security association in an ESS. | In the comment | AGREE IN PRINCIPLE (SECURITY: 2009-07-14 21:46:57Z) Adopt the second change in the comment: Change the sentence to "When FT is not enabled, a STA roaming within an ESS establishes a new PMKSA by one of the three schemes:" | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 01:37:19Z Propose Accept in Principle: Adopt the second change in the comment: Change the sentence to "When FT is not enabled, a STA roaming within an ESS establishes a new PMKSA by one of the three schemes:" |  |  |  | 2009-07-14 22:10 | SECURITY
1040 | Cam-Winget, Nancy | 149 | 1 | 8.4.6 | 292 | 38 | T | Y | 292.38 | 38 | 8.4.6 |  | P |  |  |  | This section while parts can apply to an FT enabled link, is more relevant for when the link is not FT enabled. Suggest this be renamed to "non-FT enabled RSNA authentication in an ESS", otherwise, we'll have to sprinkle clarifications throughout this clause and sub-clauses for when FT kicks in. For instance, line 38 "Open System Authentication" is only usedwhen either the 4-Way Handshake or FT 4-Way Handshake are used and not during the FT Protocol or FT Resource Request PRotocol. | In the comment | AGREE IN PRINCIPLE (SECURITY: 2009-07-14 21:48:43Z) Change:"When establishing an RSNA…" to "When establishing an RSNA in a non-FT environment or for during an FT Initial mobility domain Association…" | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 01:35:27Z - Proposed Change: "Proposed Counter: Change:"When establishing an RSNA…" to "When establishing an RSNA in a non-FT environment or for during an FT Initial mobility domain Association…" |  |  |  | 2009-07-14 22:10 | SECURITY
1041 | Cam-Winget, Nancy | 149 | 1 | 8.4.6.2 | 293 | 55 | T | Y | 293.55 | 55 | 8.4.6.2 |  | P |  |  |  | As this is part of 8.4.6, my previous comment is highlighted by the relevance of this clause mainly applying to the non-FT case. Suggest this be renamed if the whole of 8.4.6 is not…to ensure that this section only applies to AKMs 1 and 2. | In the comment | AGREE IN PRINCIPLE (SECURITY: 2009-07-14 21:49:33Z) Change: "A STA" to "In a non-FT environment, A STA". | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 01:46:33Z Counter. Change: "A STA" to "In a non-FT environment, A STA". |  |  |  | 2009-07-14 22:10 | SECURITY
1042 | Cam-Winget, Nancy | 149 | 1 | 8.4.8 | 295 | 30 | T | Y | 295.3 | 30 | 8.4.8 | [5 empty] | Again, this section only applies to the non-FT (e.g. AKMs 1 and 2 only) and should be state as such. Or the clause could be adapted to referent 11A for the FT case as well. | In the comment |  | SECURITY | Security - key management | Follow-up | SECURITY: 2009-07-14 01:52:05Z Discuss with Commentor. |  |  |  | 2009-07-14 22:10 | SECURITY
1043 | Cam-Winget, Nancy | 149 | 1 | 8.4.10 | 296 | 64 | T | Y | 296.64 | 64 | 8.4.10 | [5 empty] | It is also possible to also invoke the FT Protocol. |  |  | SECURITY | Security - key management | Follow-up | SECURITY: 2009-07-14 01:53:08Z Discuss with Commentor |  |  |  | 2009-07-14 22:10 | SECURITY
1227 | Marshall, Bill | 149 | 1 | 8.5.1.5.3 | 306 | 62 | T | N | 306.62 | 62 | 8.5.1.5.3 |  | P |  |  |  | unclear whether normative "shall" is neede here, or whether a simple declarative statement "SHA-256 is as defined in …" matching the style of the surrounding statements is sufficient | make the statements consistent. In either case, insert a hyphen into SHA-256 | AGREE IN PRINCIPLE (SECURITY: 2009-07-14 21:54:21Z) Replace "SHA256 shall be as defined in" with "SHA-256 is as defined in" | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 01:53:58Z Accept in Principle. Replace "SHA256 shall be as defined in" with "SHA-256 is as defined in" |  |  |  | 2009-07-14 22:12 | SECURITY
1258 | Montemurro, Michael | 149 | 1 | 8.5.2 | 310 | 5 | T | N | 310.05 | 5 | 8.5.2 |  | A |  |  |  | It would be beneficial to include the RFC reference as well as the FIPS publication reference. | Change the text from: "defined by FIPS SP800-38B" to: "defined by FIPS SP800-38B and also found in RFC 4493." and add RFC 4493 to the references. | AGREE (SECURITY: 2009-07-14 21:59:20Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 01:54:29Z Proposed Accept. |  |  |  | 2009-07-14 22:15 | SECURITY
1255 | Montemurro, Michael | 149 | 1 | 8.5.3.0a | 317 | 41 | T | N | 317.41 | 41 | 8.5.3.0a |  | A |  |  |  | The 4-way handshake is also used for FT Initial Association. It would be beneficial to add some text and a cross-reference to clause 11A.4.2. | Add the following text after the first paragraph. "The FT Initial Mobility Domain Association uses the FT 4-way handshake to establish an initial FT Security Association, that is based on this protocol. The FT 4-way handshake protocol is described in Clause 11A.4." | AGREE (SECURITY: 2009-07-14 21:58:31Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 01:54:59Z Proposed Accept. |  |  |  | 2009-07-14 22:14 | SECURITY
1260 | Montemurro, Michael | 149 | 1 | 8.5.3.2 | 320 | 23 | T | N | 320.23 | 23 | 8.5.3.2 |  | A |  |  |  | The RSN IE in message 2 of the FT Intial Association will not bitwise match the RSN IE used in the Reassociation Request. | Modify the text as follows: 2) If the MIC is valid, the Authenticator checks that the RSN information element bit-wise matches that from the (Re)Association Request message. For FT Intial Association, the RSN IE cannot be bit-wised compared because the PMKR1Name will be included in the RSN IE field as part of Message 2. In that case, the remainder of the RSN IE in message 2 is checked against the RSN IE included in the Reassociation Request. i) If these are not exactly the same, the Authenticator uses MLME-DEAUTHENTICATE. request primitive to terminate the association. ii) If they do match bit-wise, the Authenticator constructs Message 3. | AGREE (SECURITY: 2009-07-14 21:59:34Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 01:55:26Z Proposed Accept. |  |  |  | 2009-07-14 22:15 | SECURITY
1261 | Montemurro, Michael | 149 | 1 | 8.5.3.3 | 321 | 49 | T | N | 321.49 | 49 | 8.5.3.3 |  | A |  |  |  | The RSN IE in message 3 of the FT Intial Association will not match the RSN IE used in the Beacon or Probe Response. | Modify the text as follows: Verifies the RSNIE. If it is not identical to that the STA received in the Beacon or Probe Response frame, the STA shall disassociate. For FT Initial Association, the RSN IE will differ from the RSN IE in Beacon and Probe Response messages becuse it will contain the PMKR1Name in the PMKID field. For FT Initial Association, the PMKID field is ignored in the RSN IE comparison. If a second RSN information element is provided in the message,the Supplicant uses the pairwise cipher suite specified in the second RSNIE or deauthenticates. | AGREE (SECURITY: 2009-07-14 21:59:42Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 01:56:05Z Proposed Accept. |  |  |  | 2009-07-14 22:15 | SECURITY
1045 | Cam-Winget, Nancy | 149 | 1 | 8.7.2 | 353 | 40 | T | Y | 353.4 | 40 | 8.7.2 | [5 empty] | Given that state machine descriptions are already provided both in visual and long prose formats, there seems to be little value gained by providing this pseudo-code other than adding bloat to the document and another tedious section that may not be consistant with the state machine. Please consider removing this whole clause. | In the comment |  | SECURITY | Security - General | Discussion | SECURITY: 2009-07-14 01:58:59Z Discuss. Does anybody use this? |  |  |  | 2009-07-14 22:11 | SECURITY
1152 | Hamilton, Mark | 149 | 1 | 11.3.0a | 598 | 54 | T | Y | 598.54 | 54 | 11.3.0a | [5 empty] | With the addition of RSNA capability, the term "authentication" as it applies to states like the ones in 11.3.0a, has taken on multiple meanings. That's fine, except many people seem to get confused by which authentication is being referred to in different contexts. This could perhaps be alleviated by showing the RSNA authentication process in these state tables, like the simple authentication. | Add the concept of RSNA authentication to the state variables and state machine shown in 11.3.0a. This will need a submission. |  | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 21:52:24Z Dependent on the discussion and revision of document 11-09/705 |  |  |  | 2009-07-14 22:11 | SECURITY
1444 | Stephens, Adrian | 149 | 1 | 11.3.0a | 600 | 5 | T | N | 600.05 | 5 | 11.3.0a |  | A |  |  |  | Incorrect use of "if and only if" - which implies logical correspondance. i.e. line 5 implies that all frames are class 2 if the STA is authenticated - which is clearly rubbish. | Replace "if and only if" with "only if" on line 5 and line 23. | AGREE (SECURITY: 2009-07-14 22:01:40Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 21:19:02Z Proposed Accept. |  |  |  | 2009-07-14 22:22 | SECURITY
1507 | Stephens, Adrian | 149 | 1 | 11.3.0a | 600 | 30 | T | N | 600.3 | 30 | 11.3.0a |  | D |  |  |  | "Data frames between STAs in a BSS" - it means infrastructure BSS | Change BSS to "infrastructure BSS". | DISAGREE (SECURITY: 2009-07-14 22:02:15Z) The text cited applies to an IBSS. | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 21:26:45Z Propose Reject. The text cited applies to an IBSS. SECURITY: 2009-07-14 20:53:37Z Propose Reject. Infrastructure BSS is redundant. Discuss. |  |  |  | 2009-07-14 22:22 | SECURITY
1508 | Stephens, Adrian | 149 | 1 | 11.3.0a | 600 | 42 | T | N | 600.42 | 42 | 11.3.0a |  | A |  |  |  | BlockAck and BlockAckReq are permitted in an IBSS | Change cited location to be specified to infrastructure and add them as Class 1 frames for IBSS. | AGREE (SECURITY: 2009-07-14 22:02:28Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 20:55:02Z Propose Accept. |  |  |  | 2009-07-14 22:22 | SECURITY
1525 | Stephens, Adrian | 149 | 1 | 11.9.0a | 629 | 30 | T | N | 629.3 | 30 | 11.9.0a |  | A |  |  |  | It is not exactly clear which of the three dashed list items are part of the exception. | Indent the para starting "A STA may operate when..." | AGREE (SECURITY: 2009-07-14 22:02:34Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 20:55:33Z Proposed Accept. |  |  |  | 2009-07-14 22:22 | SECURITY
1526 | Stephens, Adrian | 149 | 1 | 11.9.2 | 630 | 11 | T | N | 630.11 | 11 | 11.9.2 |  | A |  |  |  | "Only the STA starting an IBSS may specify a schedule of quiet intervals" - isn't it the job of the DFS owner? The STA that started the IBSS may be long dead and buried. | Change to: "Only the STA that is the DFS owner in an IBSS may specify a schedule of quiet intervals" | AGREE (SECURITY: 2009-07-14 22:02:42Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 20:56:42Z Proposed Accept. |  |  |  | 2009-07-14 22:22 | SECURITY
1527 | Stephens, Adrian | 149 | 1 | 11.9.3 | 630 | 33 | T | N | 630.33 | 33 | 11.9.3 | [5 empty] | "A STA shall not transmit in a channel unless it has been tested for the presence of radars according to regulatory requirements." Presumably it uses its well-honed telepathic abilities to determine if the channel has been tested. | Relate to observable state or on-the-air signalling. |  | SECURITY | Radio management - MAC | Follow-up | SECURITY: 2009-07-14 20:58:42Z - Talk with Commentor. |  |  |  | 2009-07-14 22:23 | SECURITY
1528 | Stephens, Adrian | 149 | 1 | 11.9.6 | 630 | 53 | T | N | 630.53 | 53 | 11.9.6 |  | A |  |  |  | The author has forgotten that the term BSS applies both to infrastructure and indepdendent. | p630.53: BSS->infrastructure BSS p630.58: "BSS or IBSS" -> BSS (make change globally) | AGREE (SECURITY: 2009-07-14 22:02:57Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 20:59:25Z Proposed Accept. |  |  |  | 2009-07-14 22:23 | SECURITY
1269 | Myles, Andrew | 149 | 1 | 11.9.7.2 | 632 |  | T | Y | 632.51 | 51 | 11.9.7.2 |  | D |  |  |  | The procedure to select a new channel in an IBSS is only claimed to be "best effort" at best. At worst, it may not even work. The reality is that after 5+ years there is no known implemenation of this feature, indicating it is unnecessary | Remove it | DISAGREE (SECURITY: 2009-07-14 21:35:44Z) The proposed change may make existing 802.11 devices non-compliant with the standard. The comment has not justified the change. | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 21:00:29Z - Discuss. |  |  |  | 2009-07-14 22:15 | SECURITY
1447 | Stephens, Adrian | 149 | 1 | 11.10.5 | 640 | 19 | T | N | 640.19 | 19 | 11.10.5 |  | A |  |  |  | Incorrect use of "if and only if" in the following: "A STA shall accept a Measurement Request with the parallel bit field enabled if and only if dot11RRMParallelMeasurenmentEnabled is true; otherwise, the STA shall reject the Measurement Request by returning a Measurement Report with the Incapable bit set in the Measurement Report Mode field." | Note, cited text already contains a normative requirement to reject "otherwise" so the wrong "and only if" is also redundant. Delete: "and only if" from the cited text. | AGREE (SECURITY: 2009-07-14 22:01:49Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 21:01:10Z Proposed Accept. |  |  |  | 2009-07-14 22:22 | SECURITY
1256 | Montemurro, Michael | 149 | 1 | 11.10.8.1 | 644 | 59 | T | N | 644.59 | 59 | 11.10.8.1 | [5 empty] | The paragraph states that if the Channel Number field is 255, the STA conducts measurements on all channels included in the AP Channel Report. However it does not indicate where the STA receives the Channel Report (I assume the Beacon). In the next paragraph, the text states that an optional Channel Report sub-element can be used to supply a list of channels in the Beacon Report. | Clarify the use of AP Channel Report in the Beacon Report as follows: 1) If the Channel Number Field is 0, the STA shall use uses the regulatory domain information. 2) If the Channel Number Field is 255, the STA uses the AP Channel report sub-element(s) (if included) or the last AP Channel Report IE received in the last Beacon frame. 3) If the Channel Number Field specifies any other channel number, the STA will generate a Beacon Report response using that channel number. I can prepare a submission to clean up the last paragraph on pg 644 and first two paragraphs on pg. 645. |  | SECURITY | Radio management - MAC | Submission | SECURITY: 2009-07-14 21:01:52Z Talk to Commentor. Need a Submission. |  |  |  | 2009-07-14 22:14 | SECURITY
1531 | Stephens, Adrian | 149 | 1 | 11.10.8.4 | 648 | 24 | T | N | 648.24 | 24 | 11.10.8.4 |  | A |  |  |  | "defined in dBm using the same units" But dBm are the units. | remove "units and" | AGREE (SECURITY: 2009-07-14 22:03:01Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 21:02:27Z Proposed Accept. |  |  |  | 2009-07-14 22:23 | SECURITY
1532 | Stephens, Adrian | 149 | 1 | 11.10.8.6 | 649 | 28 | T | N | 649.28 | 28 | 11.10.8.6 |  | A |  |  |  | "shall be as required for operation in the regulatory domain" - this is a useless statement. If regulations require something, this says effectively "you shall do what you shall do", without actually specifying what that is. | Turn para into note, and add references to any known regulations on this matter. | AGREE (SECURITY: 2009-07-14 22:03:05Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 21:03:52Z Talk to Commentor. |  |  |  | 2009-07-14 22:23 | SECURITY
1533 | Stephens, Adrian | 149 | 1 | 11.10.8.8 | 651 | 28 | T | N | 651.28 | 28 | 11.10.8.8 |  | A |  |  |  | "If dot11RRMTriggeredTransmitStreamCategoryMeasurementEnabled is true, a QoS STA shall accept a triggered Transmit Stream/Category Measurement and shall reject it otherwise." This contradicts the previous sentence that allows a resource limit to generate a rejection. | Change cited text to: If dot11RRMTriggeredTransmitStreamCategoryMeasurementEnabled is true and has no resource contraint that prevents it from being able to make the requested measurement, a QoS STA shall accept a triggered Transmit Stream/Category Measurement and shall reject it otherwise. | AGREE (SECURITY: 2009-07-14 22:03:10Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 21:04:31Z Proposed Accept. |  |  |  | 2009-07-14 22:23 | SECURITY
1263 | Montemurro, Michael | 149 | 1 | 11.10.8.8 | 651 | 46 | T | N | 651.46 | 46 | 11.10.8.8 |  | A |  |  |  | It makes sense that the Measurement Count field would be interpreted as the the total of successfully and unsuccessfully transmitted MSDU's. The current text is ambiguous. | Modify the first sentence of the paragraph as follows: Traffic stream metrics reported in a triggered transmit stream/category measurement report shall be the values accumulated over the number of successfully and unsuccessfully transmitted MSDUs prior to the trigger event given in the Measurement Count field of the transmit stream/category measurement request that established the trigger condition. | AGREE (SECURITY: 2009-07-14 21:59:54Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 21:05:11Z Proposed Accept. |  |  |  | 2009-07-14 22:15 | SECURITY
1534 | Stephens, Adrian | 149 | 1 | 11.10.9 | 652 | 18 | T | N | 652.18 | 18 | 11.10.9 |  | P |  |  |  | "A Neighbor Report is sent by an AP and it contains information on validated AP’s" The concept of a valid or invalid AP is not known to me. | Describe what "validated" means in this context. | AGREE IN PRINCIPLE (SECURITY: 2009-07-14 22:03:33Z) "Propose Counter. Replace ""on valdiated AP's"" with ""on neighboring AP's""" | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 21:05:53Z "Propose Counter. Replace ""on valdiated AP's"" with ""on neighboring AP's""" |  |  |  | 2009-07-14 22:23 | SECURITY
1536 | Stephens, Adrian | 149 | 1 |  | 653 | 1 | T | N | 653.01 | 1 | 11.10.9.2 |  | A |  |  |  | "A serving AP shall include a TSF information field in the Neighbor Report element only if it is able to guarantee an accumulated error of 1.5 TU or better on the TSF Offset subfield." "... shall <verb> only if <condition> " is highly ambiguous. What does it mean? A: "shall not <verb> if not <condition>" B: "may <verb> if <condition> and shall not <verb> otherwise" C: "shall <verb> if <condition> and shall not <verb> otherwise" | Scan the entire draft for occurances of "shall <verb> only if <condition>" and for each convert to one of these unambiguous forms. In this case (and, I suspect, in most), form A is appropriate. | AGREE (SECURITY: 2009-07-14 22:03:49Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 21:08:10Z Proposed Accept. |  |  |  | 2009-07-14 22:23 | SECURITY
1167 | Hamilton, Mark | 149 | 1 | 11.10.11 | 653 | 48 | T | Y | 653.48 | 48 | 11.10.11 | [5 empty] | Multiple BSSID Set APs must share more facilities "in common" than those listed. | Add (at least), "Channel Access Functions" to the list of common facilities in the first bullet. There are probably more things that should be listed. This will need study. |  | SECURITY | Radio management - MAC | Discussion | SECURITY: 2009-07-14 21:09:01Z Discuss. |  |  |  | 2009-07-14 22:12 | SECURITY
1538 | Stephens, Adrian | 149 | 1 | 11.10.11 | 653 | 50 | T | N | 653.5 | 50 | 11.10.11 | [5 empty] | I'm sure that there are constraints within the system (e.g. in TIM encoding, or where per-BSSID information is packed into a single MMPDU) that limits the number of BSSIDs to less 2**46 - which is a guzumpingly large number. | Work out the actual constraint and insert it here. |  | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 21:09:40Z Discusss. |  |  |  | 2009-07-14 22:23 | SECURITY
1073 | Ecclesine, Peter | 149 | 1 | 11.10.12 | 654 | 5 | T | Y | 654.05 | 5 | 11.10.12 |  | D |  |  |  | The Measurement Pilot option specified here is obsolete, and is not in current products that claim 802.11 conformance. I do not know of any products or plans to implement Measurement Pilots. The option would add lots of noise in whatever band it is used in (Note 1 pg 655, Note 2 and NOTE, pg 656). Commenter will make a submission removing 7.3.2.42, 7.4.7.2, 11.10.12 and whatever other text changes are needed to remove the Measurement Pilot Transmission option from the standard. | Remove the Measurement Pilot option from the standard. | DISAGREE (SECURITY: 2009-07-14 21:36:43Z) Reject. This is a new feature that is less than a year old, and should be given time to be implemented before removal. The proposed change may make existing 802.11 devices non-compliant with the standard. The comment has not justified the change. This comment was previously rejected as CID 158 in 11-07/2642r9. | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 21:10:11Z Discuss. |  |  |  | 2009-07-14 22:11 | SECURITY
1433 | Stephens, Adrian | 149 | 1 | 11.10.12 | 654 | 28 | T | N | 654.28 | 28 | 11.10.12 | [5 empty] | What we have here is a table that provides a mixture of static capability and active status as the encoding for a MIB variable. This is confusing, and counter to the ARC group's policy on MIB variables. | Separate out capability and status information into two MIB variables. |  | SECURITY | Radio management - MAC | Submission | SECURITY: 2009-07-14 21:10:55Z Propose Accept. Need Submission. |  |  |  | 2009-07-14 22:22 | SECURITY
1551 | Stephens, Adrian | 149 | 1 | 11A.1 | 665 | 41 | T | N | 665.41 | 41 | 11A.1 | [5 empty] | If the terms defined in this note are used in normative text, it is not sufficient to define them in an informative note. | Promote material in note to body (i.e., regular text) |  | SECURITY | Fast transition | Follow-up | SECURITY: 2009-07-14 22:23:34Z Talk to Commentor |  |  |  | 2009-07-14 22:24 | SECURITY
1231 | Marshall, Bill | 149 | 1 | 11A.3 | 668 | 17 | T | N | 668.17 | 17 | 11A.3 |  | A |  |  |  | dot11FTOver-DSEnabled doesn't have the hyphen in MIB | drop hyphen here | AGREE (SECURITY: 2009-07-14 21:55:15Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 21:55:00Z Proposed Accept. |  |  |  | 2009-07-14 22:12 | SECURITY
1233 | Marshall, Bill | 149 | 1 | 11A.4.2 | 670 | 31 | T | N | 670.31 | 31 | 11A.4.2 |  | A |  |  |  | The "Data(…)" notation came from an early draft of 11i; it was dropped before publication of 802.11i and never appeared in REVma, but was only caught in 11r at publication time (too late). | drop "Data(" and ")" from these four entries, and drop the note at line 61 | AGREE (SECURITY: 2009-07-14 21:55:47Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 21:55:34Z Proposed Accept. |  |  |  | 2009-07-14 22:12 | SECURITY
1305 | Ptasinski, Henry | 149 | 1 | 11A.8.4 | 689 | 7 | T | Y | 689.07 | 7 | 11A.8.4 |  | A |  |  |  | MIC calculation includes the IE headers. | Delete “Contents of the” from RSNIE, MDIE, and FTIE. | AGREE (SECURITY: 2009-07-14 22:00:09Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 21:13:38Z Proposed Accept. |  |  |  | 2009-07-14 22:15 | SECURITY
1306 | Ptasinski, Henry | 149 | 1 | 11A.8.5 | 690 | 4 | T | Y | 690.04 | 4 | 11A.8.5 |  | A |  |  |  | MIC calculation includes the IE headers. | Delete “Contents of the” from RSNIE, MDIE, and FTIE. | AGREE (SECURITY: 2009-07-14 22:00:15Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 21:14:10Z Proposed Accept. |  |  |  | 2009-07-14 22:16 | SECURITY
1257 | Montemurro, Michael | 149 | 1 | 11A.9.5.1 | 700 | 15 | T | N | 700.15 | 15 | 11A.9.5.1 |  | A |  |  |  | FT-Transition-Auth (R1KH-ID) to CALC-PMK_R1 S0KH SM occurs too early. The supplicant may not know the R1KH-ID at this point so it cannot calculate the PMK-R1. | Move "FT-Transition-Auth (R1KH-ID) to CALC-PMK_R1 S0KH SM" to the FT-PTK-CALC state, after the Reassociationdeadlinetimer. | AGREE (SECURITY: 2009-07-14 21:58:54Z) | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 21:14:34Z Proposed Accept. |  |  |  | 2009-07-14 22:15 | SECURITY
1097 | Gast, Matthew | 149 | 1 | 11A.10.1 | 702 | 33 | T | N | 702.33 | 33 | 11A.10.1 |  | A |  |  |  | "The current AP encapsulates the FT Action frame (Request or Confirm) inside a Remote Request frame and transmits it to the target AP over the DS." By definition, "encapsulate" (3.49) refers only to encrypting frames, not the act of putting a higher layer frame inside a lower layer type. | Two options: (1) change the definition of "encapsulate" in 3.49 so that it does not require cryptography, or (2) change the usage of "encapsulate" in this clause to some other word. | AGREE (SECURITY: 2009-07-14 21:51:08Z) Accept Option 1 in the Proposed Resolution. | SECURITY | 1 | Resolution | SECURITY: 2009-07-14 21:25:23Z Proposed Accept Option #1. |  |  |  | 2009-07-14 22:11 | SECURITY