## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-09/0865r6
Venue Date: | November 2009
First Author: | Michael Montemurro, Research in Motion
Subject: | Proposed resolutions to Security and MAC Management comments for LB 149
Full Date: | 2009-11-06
Author(s): | Michael Montemurro
TGmb Vice-Chair
RIM
Missisauga, ON, Canada
mmontemurro@rim.com
Abstract:
This spreadsheet contains a set of proposed resolutions to Security and MAC Management comments for LB 149

## Comments
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
1258 | Montemurro, Michael | 149 | 1 | 8.5.2 | 310 | 5 | T | N | 310.05 | 5 | 8.5.2 |  | P |  |  |  | It would be beneficial to include the RFC reference as well as the FIPS publication reference. | Change the text from: "defined by FIPS SP800-38B" to: "defined by FIPS SP800-38B and also found in RFC 4493." and add RFC 4493 to the references. | AGREE IN PRINCIPLE (SECURITY: 2009-11-06 16:07:28Z) - Change the text as proposed and add an inormative reference to RFC 4493. | SECURITY | recycled comments from editor | Ready for motion | SECURITY: 2009-11-06 16:08:56Z - After some additional discussion, it was decided that RFC 4493 should be added as an informative reference. EDITOR: 2009-10-21 06:00:39Z - Sept 2009 motion number was 10. SECURITY: 2009-07-14 01:54:29Z Proposed Accept. | NR | EDITOR2: 2009-10-12 21:21:43Z - Is RFC4493 a normative reference, or an informative one? What is the text to insert either in clause 2 or Annex 0A? |  | 2009-11-06 16:10 | SECURITY
1097 | Gast, Matthew | 149 | 1 | 11A.10.1 | 702 | 33 | T | N | 702.33 | 33 | 11A.10.1 |  | P |  |  |  | "The current AP encapsulates the FT Action frame (Request or Confirm) inside a Remote Request frame and transmits it to the target AP over the DS." By definition, "encapsulate" (3.49) refers only to encrypting frames, not the act of putting a higher layer frame inside a lower layer type. | Two options: (1) change the definition of "encapsulate" in 3.49 so that it does not require cryptography, or (2) change the usage of "encapsulate" in this clause to some other word. | AGREE IN PRINCIPLE (SECURITY: 2009-11-06 16:04:25Z) - Accept option 2. Change the sentence to "The current AP includes the contents of the FT Action frame (Request or Confirm) in a Remote Request frame" | SECURITY | recycled comments from editor | Ready for motion | SECURITY: 2009-11-06 16:05:58Z - After additional discussion, it was decided to use term other than encapsulate. EDITOR: 2009-10-21 06:00:39Z - Sept 2009 motion number was 10. SECURITY: 2009-07-14 21:25:23Z Proposed Accept Option #1. | NR | EDITOR2: 2009-10-13 22:17:20Z text needed for the new definition of "encapsulate" |  | 2009-11-06 16:07 | SECURITY