## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-10/0055r2
Venue Date: | January 2010
First Author: | Name, Affiliation
Subject: | 802.11aa Draft 0.03 Internal Review Comments
Full Date: | 2010-01-21
Author(s): | Ganesh Venkatesan
Intel Corporation
JF3-336 2111NE 25th Ave, Hillsboro, Oregon 97124
503 334 6720
ganesh.venkatesan@intel.com
Abstract:
Comments from internal review of D0.03. All Editorial comments are assigned to the editor. The technical comments with "editor" in column K are assigned to the editor.

## Comments
CommentID | CommenterName | CommenterCo | Subclause | Page | Line | CommentType | Comment | SuggestedRemedy | Response | Assigned to
1 | Ashley, Alex | NDS Ltd | 7.3.2.aa88 | 19 | 1 | TR | The "QLoad", "Allocated Traffic Self" and "Allocated Traffic Shared" should use a common structure. | Create a non-IE field definition in 7.3.1 using the structure currently in 7.3.2.95, remove figures 7-95o126, 7-95o127 and 7-95o128. Modify the text to refer to the new structure defined in 7.3.1 | as proposed | Editor
2 | Ashley, Alex | NDS Ltd | 7.3.2.aa88 | 20 | 1 | E | The overlap field definition is in the same paragraph as the HCCA access factor. | Move to its own paragraph.
3 | Ashley, Alex | NDS Ltd | 7.3.2.aa88 | 20 | 1 | TR | In the overlap field definition - which beacon period? This AP, or the beacon periods of overlapping APs? | change "within the last 100 beacon periods" to "within the last 100 beacon periods of this AP." | as proposed | Editor
4 | Ashley, Alex | NDS Ltd | 7.3.2.aa88 | 19 | 18 | TR | The HCCA Peak field is unused when HCCA is not implemented. | Add "The HCCA Peak field is set to zero if dot11CF_Pollable is false or dot11CF-Pollable is true." | The HCCA Peak field is reserved if HCCA is not supported -- See baseline for appropriate description of this field.
5 | Ashley, Alex | NDS Ltd | 7.3.2.aa88 | 18 | 26 | ER | Style guide is that "shall" is not used in clause 7 | In the QLoad field definition, change "Bi-directional streams shall be counted as two streams. " to "Bi-directional streams are counted as two streams. "
6 | Ashley, Alex | NDS Ltd | 11.aa22.1 | 69 | 42 | TR | "The QLoad element is contained in a public action frame that is provided by an AP and optionally, periodically in the Beacon." Do you mean the QLoad Report element? | Change "The QLoad element is contained in a public action frame that is provided by an AP and optionally, periodically in the Beacon." to "The QLoad Report element is contained in a public action frame that is provided by an AP and optionally, periodically in the Beacon." | as proposed | Editor
7 | Ashley, Alex | NDS Ltd | 11.aa22.1 | 69 | 47 | TR | "The QLoad Report shall not be included in Probe Response frames" - I think you mean the element. | Change "The QLoad Report shall not be included in Probe Response frames" to "The QLoad Report element shall not be included in Probe Response frames" | same as 7 | Editor
8 | Ashley, Alex | NDS Ltd | 11.aa22.1 | 70 | 4 | TR | When this proposal was presented, it was stated that method 2 had been removed. This feature is not required and adds unnecessary complexity to the OBSS solution. | Remove method 2 (using a low inactivity timeout). | Remove Method-2 and ensure references to it are removed from the draft
9 | Ashley, Alex | NDS Ltd | 11.aa22.1 | 70 | 8 | TR | Method 3: "At the deletion of such TSPECs, the AP may either keep the TSPEC as part of its QLoad, or not." Allowing an AP to keep this deleted TSPEC in its load calculation is a bad idea because it prohibits the ability to scale back bitrate requirements. A device could reduce its bitrate requirements in the presence of congestion, but according to this text, the AP would never adjust to this reduction. | Change "At the deletion of such TSPECs, the AP may either keep the TSPEC as part of its QLoad, or not." to "At the deletion of each such TSPEC, the AP shall remove the TSPEC from its QLoad Report." |  | Editor
10 | Ashley, Alex | NDS Ltd | 11.aa22.1 | 70 | 12 | TR | "If an AP where dot11QLoadReportEnabled is true receives a TSPEC request that has the Inactivity Interval field in the TSPEC element set to one, the AP shall note the values and use them to calculate the QLoad field. " When this proposal was presented, it was stated that this method had been removed. This feature is not required and adds unnecessary complexity to the OBSS solution. | Remove this method of QLoad reporting. | same as 8 | Editor
11 | Ashley, Alex | NDS Ltd | aa.2.1 | 80 | 29 | TR | Not all access points use processors that have floating point support, which makes square root an expensive operation. | Suggest providing integer approximations as well. | Recommend using a look up table to compute square root | Graham
12 | Ashley, Alex | NDS Ltd | aa.2.1 | 80 | 9 | TR | The QLoad calculations require min, max and mean medium times, but the TSPEC contains min, max and mean bitrates, plus mean medium time. Having to perform the bitrate to medium time calculation 3 times on every tspec is onerous. | Investigate if bitrates could be used instead of medium times, or if a simplified medium time calculation could be used. | Check why we switched from bitrates to Medium time in Qload element Can bitrates alone be used to represent load? Don't we need the actual rate(s) used to transmit the payload? | Ganesh
13 | Ashley, Alex | NDS Ltd | 10.3.aa69.4.2 | 59 | 35 | ER | "MLME-QLoadRequest.request" should be "MLME-QLoadReport.request" | As in comment
14 | Ashley, Alex | NDS Ltd | 10.3.aa69.5.2 | 60 | 21 | ER | "MLME-QLoadRequest.confirm" should be "MLME-QLoadReport.confirm" | As in comment
15 | Ashley, Alex | NDS Ltd | 10.3.aa69.6.2 | 61 | 1 | ER | "MLME-QLoadRequest.indication" should be "MLME-QLoadReport.indication" | As in comment
16 | Ashley, Alex | NDS Ltd | 10.3.aa70.1.2 | 62 | 1 | TR | What is the "measurement request" parameter used for? | Remove parameter? | Delete the "Measurement Request" parameter and the corrresponding row in the table below. | Editor
17 | Ashley, Alex | NDS Ltd | 10.3.aa70.3.2 | 63 | 2 | TR | What is the "measurement request" parameter used for? | Remove parameter? | Delete the "Measurement Request" parameter and the corrresponding row in the table below. | Editor
18 | Ashley, Alex | NDS Ltd | 10.3.aa70 | n/a | n/a | TR | How are potential TSPECs provided to the MLME? There seems to be no way to provide this information to allow a TSPEC request to be honoured. | Explain how a TSPEC request can be serviced. | MLME-TSPECRequirements.response from the SME is missing. | Ganesh
19 | Ashley, Alex | NDS Ltd | 11.aa22.1 | 69 | 40 | TR | How does an AP detect that a potential TSPEC (sent using the inactivity time=1) has become an actual active TSPEC? This is important to know, to avoid double counting a potential TSPEC that has become active when calculating QLoad. The TID cannot be used, because this might change between announcing potential TSPEC and activating the TSPEC. | Provide normative behaviour for potential TSPEC -> active TSPEC. Perhaps a solution would be to only allow a STA to register one potential TSPEC? | Could we have two pieces to the Qload element -- potential load part and a active load part? A potential load of 20Mbps is advertised and when the TV is turned on with a real load of 6Mbps what is the computed load? 26 Mbps, 14 potential + 6 active or 20 potential + 6 active? | teleconference
20 | Ashley, Alex | NDS Ltd | 11.aa22.1 | 69 | 40 | TR | Should a STA send potential TSPEC for any possible stream, without regard to the route to the destination? For example a wired + wireless device might connect to an HD source via the wired network and would not need to signal this as a potential TSPEC over 802.11 | Provide normative behaviour for potential TSPEC |  | defer
21 | Ashley, Alex | NDS Ltd | 11.aa22.1 | 70 | 33 | TR | For allocated traffic shared, should the mean be computed with respect to overlapping access points that are not 11aa APs? i.e. do you divide the sum by total number of APs or divide by the number of 11aa APs? |  | using the number of 11aa APs to calculate the AP provides a realistic estimate of the mean. This is probably a good first approximation. Ignoring legacy APs is not correct either. | teleconference
22 | Ashley, Alex | NDS Ltd | 7.4.2 | 21 | 16 | TR | The SCS adds new entries to the existing QoS Action frame, but MRG uses entries in a new "Robust AV Streaming Action frame". Shouldn't this be consistant? | Either move SCS to the "Robust AV Streaming Action frame" or put the MRG actions in the existing QoS action frame list. | Move the 3 actions (SCS Request, SCS Response and TSPEC Requirements Request) from table 7-45 to the table 7-aa6. | Editor
23 | Ashley, Alex | NDS Ltd | 7.4.13 | 27 | 13 | TR | The SCS adds new entries to the existing QoS Action frame, but MRG uses entries in a new "Robust AV Streaming Action frame". Shouldn't this be consistant? | Either move SCS to the "Robust AV Streaming Action frame" or put the MRG actions in the existing QoS action frame list. | no change required due to the resolution to CID #22.
24 | Ashley, Alex | NDS Ltd | 9.2.7.3.4 | 34 | 37 | TR | "… only accept either an MRG-SP or an MS agreement …" should that be DMS rather than FMS? | Check if it is FMS or DMS. | decline. The first line deals with FMS and the second one with DMS.
25 | Ashley, Alex | NDS Ltd | Annex D | 78 | 7 | TR | dot11ShortDEIRetryLimit is missing its DEFVAL entry | Add DEFVAL { 7 } | Add DEFVAL{5} | Editor
26 | Ashley, Alex | NDS Ltd | Annex D | 78 | 7 | TR | dot11ShortDEIRetryLimit should probably have a default smaller than dot11ShortRetryLimit as these MSDU have been tagged as drop eligible. | Change default to 5 | Need to provide more opportunity for retransmission of frames that are not Drop-eligible. Hence the recommendation to set this value to 5 (from 7). | Editor
27 | Ashley, Alex | NDS Ltd | Annex D | 78 | 19 | TR | dot11LongDEIRetryLimit should probably have a default smaller than dot11LongRetryLimit as these MSDU have been tagged as drop eligible. | Change default to 3 | Need to provide more opportunity for retransmission of frames that are not Drop-eligible. Hence the recommendation to set this value to 3 (from 4). A value of 2 is too small. | Editor
28 | Ashley, Alex | NDS Ltd | Annex D | 78 | 19 | TR | dot11LongDEIRetryLimit is missing its DEFVAL entry | Add DEFVAL { 4 } | Add DEFVAL{3} | Editor
29 | Ashley, Alex | NDS Ltd | Annex D | 76 | 31 | E | In dot11RobustAVStreaming, "DEFVAL { FALSE }" should be "DEFVAL { false }" | As in comment
30 | Ashley, Alex | NDS Ltd | Annex D | 76 | 42 | E | In dot11RobustAVStreamingAdvancedMRG, "DEFVAL { FALSE }" should be "DEFVAL { false }" | As in comment
31 | Ashley, Alex | NDS Ltd | 3.aa6 | 2 | 38 | T | Not sure what the definition of MRG-Directed frame is trying to convey. | Change "Frame (group address, MSDU, A-MSDU) subject to the MRG service with Ack policy equal to MRG-Directed" to "A group addressed MSDU or A-MSDU subject to the MRG service with Ack policy equal to MRG-Directed" | MRG-Directed {frame¦group address¦MSDU¦A-MSDU}: A {Frame¦group address¦MSDU¦A-MSDU} subject to the MRG service with Ack policy equal to MRG-Directed? Define the frame and at the end of the definition define group address, MSDU and A-MSDU versions cryptically? | defer
32 | Ashley, Alex | NDS Ltd | 3.aa6 | 2 | 41 | T | Not sure what the definition of MRG-Unsolicited-Retry frame is trying to convey. | Improve definition |  | similar to CID 38
33 | Ashley, Alex | NDS Ltd | 3.aa6 | 2 | 44 | T | Not sure what the definition of MRG-Block-Ack frame is trying to convey. | Improve definition |  | similar to CID 38
34 | Ashley, Alex | NDS Ltd | 3.aa6 | 2 | 47 | T | Not sure what the definition of MRG-SP frame is trying to convey. | Improve definition |  | similar to CID 38
35 | Ashley, Alex | NDS Ltd | 3.aa6 | 2 | 50 | T | Not sure what the definition of MRG-non-SP frame is trying to convey. | Improve definition |  | similar to CID 38
36 | Ashley, Alex | NDS Ltd | 11.24.2 | 71 | 14 | E | Incorrect section number | Change "11.24.2" to "11.aa22.2"
37 | Ashley, Alex | NDS Ltd | aa 2.2 | 81 | 1 | ER | In other sections, the term "AC2" and "AC3" is used, but in the EDCA BW factor, the terms "VI" and "VO" are used. | Decide if the correct style is to use the names AC2 / AC3 or VI / VO | Replace AC2 and AC3 with AC_VI and AC_VO respectively. | Editor
38 | Ashley, Alex | NDS Ltd | Front matter | 1 | 26 | E | The baseline references are incorrect. For example 11w and 11n have been published. | The correct order is " IEEE P802.11-2007  IEEE P802.11k-2008  IEEE P802.11r-2008  IEEE P802.11y-2008  IEEE P802.11w-2009  IEEE P802.11n-2009  IEEE P802.11p draft 9.0  IEEE P802.11s draft 3.0  IEEE P802.11u draft 8.0  IEEE P802.11v draft 7.0  IEEE P802.11z draft 6.0 "
39 | Stephens, Adrian | Intel | 7.3.2.30 | 12 | 13 | T | The APSD=0, Schedule=1 configuration is used by 802.11n. It cannot be re-used by 802.11aa. | See Table 7-41 in 802.11n-2009. | The bits are enabled in this configuration either in Scheduled PSMP or in MRG mode. Replace "Scheduled PSMP" in table 7-41 in 802.11n with "Schedule PSMP or MRG-SP" | Editor
40 |  |  | 11.aa.22.1 | 70 | 8 | E | "In addition to methods 1 and 2 above,". Since Method-2 is deleted by CID#8 reword this to "In addition to Method 1" |  |  | Editor
41 | Ashley, Alex | NDS Ltd | 11.aa.24.2 | 71 | 15 | TR | In between successfully received beacons (with HCCA TXOP Advertisement element) an AP is unaware of new HCCA allocations in neighboring QAPs. Multiple TSPEC requirements in adjacent BSSs will cause conflicting reservations. See document 10/0062r0 for a detailed description of the problem. | See document 10/0062r0 for potential solutions |  | Alex

## References
References: