## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-10/0900r1
Venue Date: | July 2010
First Author: | Kazuyuki Sakoda (Sony Corporation)
Subject: | List of unsatisfied comments
Full Date: | 2010-07-15
Author(s): | Kazuyuki Sakoda
Sony Corporation
5-1-12 Kitashinagawa, Shinagawa-ku, Tokyo, Japan
81-3-5448-4018
KazuyukiA.Sakoda(at)jp.sony.com
Abstract:
This is a cummulation of the comments that are not satisfied at the end of the comment resolution from IEEE 802.11 LB 165 on P802.11s Draft D6.0.

## Comments
CommentID | CommenterName | CommenterCo | Original Clause | Orig Page No. | Orig Line No. | CommentType | Part of No Vote? | Page | Line | CType | Subclause | Topic | Issue Ident. | Duplicate of CID | Asignee | Submission | Accept_RejectDate | ResponseStatus | Comment | SuggestedRemedy | Resolution Code | Resolution Notes | Response | Updated (to assist editor) | Edit Status | LB# | Edited in Draft | Closed by:
46 | Benveniste, Mathilde |  | General |  |  | TR | Y |  |  | T | General | MAC | M-General |  |  |  | 05/14/09 | Closed | The mesh portal of a wireless mesh that connects multiple mesh APs to the DS must be able to handle the sum of the throughput of the BSSs of all the mesh APs. To prevent potential traffic bottlenecks requires processing capacity of more than one radio at the mesh portal and its neighbors. The proposal does not provide information about how this will be handled. | Include a MAC with ability to handle concentrated traffic at mesh points near the portal and at the portal. | Counter | There are various submissions that show the benefits and the efficiency increase by using the MCCA protocol as described in TGs Draft spec. MCCA circumvents the issue claimed here. | Counter. There are various submissions that show the benefits and the efficiency increase by using the MCCA protocol as described in TGs Draft spec. MCCA circumvents the issue claimed here. |  | Done | 147 | 3.01
47 | Benveniste, Mathilde |  | 7.3.2.86.2 | 31 | 45 | TR | Y | 31 | 45 | T | 7.3.2.86.2 | RFI | R-LM |  |  |  | 07/16/09 | Closed | Airtime, whic is the link metric used for path selection, reflects only the amount of channel resources consumed by transmitting the frame over a particular link. Airtime represents, therefore, only a small portion of the end to end delay to be experienced by mesh frames traversing the multiple hop path on a mesh. | To be more useful, a different metric capturing queuing and access delays as well would be needed. | Reject | The commenter is correct in pointing that the airtime link metric only captures some of the channel resource impediments that will reduce end-to-end performance. However, all wireless link metrics suffer from the Heisenberg uncertainty principle. The more complex the metric, the more likely the use or non use of the link will affect the metric in an adverse manner, creating instabilities. We believe that the metric should be simple, straightforward to compute and limit the possibilities of creating instabilities. The path selection extensibility framework is designed to allow advanced implementations to use more sophisticated metrics. | Reject. The commenter is correct in pointing that the airtime link metric only captures some of the channel resource impediments that will reduce end-to-end performance. However, all wireless link metrics suffer from the Heisenberg uncertainty principle. The more complex the metric, the more likely the use or non use of the link will affect the metric in an adverse manner, creating instabilities. We believe that the metric should be simple, straightforward to compute and limit the possibilities of creating instabilities. The path selection extensibility framework is designed to allow advanced implementations to use more sophisticated metrics. |  | Done | 147 | NC
48 | Benveniste, Mathilde |  | 9.9a.2.7 | 79 | 56 | TR | Y | 79 | 56 | T | 9.9a.2.7 | MAC | M-MCCA |  | Guido, Dee, Liwen | 11-09/837r2, 11-09/872r0 | 07/16/09 | Closed | “ 2) Other times that it knows are busy/or reserved for individually addressed transmissions for which it is either the transmitter or the receiver.” | Please explain how (2) is different from (1). If (2) represents a distinct case, fix language and replace “it” with “the Mesh STA”. | Counter | Change "2) Other times that it knows are busy/or reserved for individually addressed transmissions for which it is either the transmitter or the receiver." to "2) Other times that are reserved for individually addressed transmissions for which the mesh STA is either the transmitter or the receiver." Also change under b) "Other times that it knows are busy/or reserved for group addressed transmissions for which it is either the transmitter or the receiver. A non exhaustive list includes expected HCCA times for an mesh AP and self or neighbor peer mesh STA’s expected beacon times." to "Other times that are reserved for group addressed transmissions for which the mesh STA is either the transmitter or the receiver. A non exhaustive list includes expected HCCA times for an AP and its own or neighbor peer mesh STA’s expected beacon times" | Counter. Change "2) Other times that it knows are busy/or reserved for individually addressed transmissions for which it is either the transmitter or the receiver." to "2) Other times that are reserved for individually addressed transmissions for which the mesh STA is either the transmitter or the receiver." Also change under b) "Other times that it knows are busy/or reserved for group addressed transmissions for which it is either the transmitter or the receiver. A non exhaustive list includes expected HCCA times for an mesh AP and self or neighbor peer mesh STA’s expected beacon times." to "Other times that are reserved for group addressed transmissions for which the mesh STA is either the transmitter or the receiver. A non exhaustive list includes expected HCCA times for an AP and its own or neighbor peer mesh STA’s expected beacon times" |  | Done | 147 | 3.03
529 | Hart, Brian | Cisco Systems | 7.2.3 | 15 | 65 | TR | Y | 15 | 65 | T | 7.2.3 | General | G-Frame |  |  | 11-09/968r0 969r0 | 09/22/09 | Closed | BSSID is undergoing great changes in 11s, but I don't see any text explaining the motivation or consequences of the change. | Add text to indicate why BSSID may be removed from management frames. For instance, what happens to the existing broadcast mgmt frames - are they forbidden? Or do they apply to all meshes in the neighborhood!!?? | Counter | No, no... It is a misunderstanding. TGs is just changing the name of the field (i.e., BSSID field -> Address 3 field) to make it generic, but the contents are kept as same. Please read the subclause 7.2.3. again. | Counter. No, no... It is a misunderstanding. TGs is just changing the name of the field (i.e., BSSID field -> Address 3 field) to make it generic, but the contents are kept as same. Please read the subclause 7.2.3. again. |  | Done | 147 | 3.03
530 | Hart, Brian | Cisco Systems | 3 | 3 | 10 | TR | Y | 3 | 10 | T | 3 | General | G-Def |  |  | 11-09/977r0 978r0 | 09/22/09 | Closed | "has a link" is very vague. My home AP and my company AP are 15 miles away yet they have a link because they carry the same brand name | Define the kind of link intended | Counter | The definition of neighbor STA is refined. Now it reads: A STA that is in direct communication range over a single instance of the wireless medium. This implies that the neighbor means the STA that is in the radio range. See submission https://mentor.ieee.org/802.11/dcn/09/11-09-0978-00-000s-general-arch-def-comment-resolution-text.doc | Counter. The definition of neighbor STA is refined. Now it reads: A STA that is in direct communication range over a single instance of the wireless medium. This implies that the neighbor means the STA that is in the radio range. See submission https://mentor.ieee.org/802.11/dcn/09/11-09-0978-00-000s-general-arch-def-comment-resolution-text.doc |  | Done | 147 | 3.04
534 | Hart, Brian | Cisco Systems | 7.2.3 | 16 | 1 | TR | Y | 16 | 1 | T | 7.2.3 | General | G-Frame |  |  | 11-09/968r0 969r0 | 09/22/09 | Closed | Renaming DA, SA and BSSID when thousands (tens of thousands?) of secondary documents depend upon those names is a poor choice. Moreover, have every instance of these fields names in the baseline, 11k, 11r, 11y, 11v, 11u, 11p etc etc (where applicable) been properly changed? | Profer some compromise where the existing established names can be retained, and TGs defines new alternative, equivalent names when dot11mesh is enabled | Counter | Although the TGs is changing the field name DA, SA, and BSSID to Address1, Address2, and Address3, the text in 7.2.3 contains clear description saying that the Address1 is set to RA(=DA), Address2 is set to TA(=SA), and Address3 is set to BSSID. This must be an appropriate changes which does not affect other task group's amendment. | Counter. Although the TGs is changing the field name DA, SA, and BSSID to Address1, Address2, and Address3, the text in 7.2.3 contains clear description saying that the Address1 is set to RA(=DA), Address2 is set to TA(=SA), and Address3 is set to BSSID. This must be an appropriate changes which does not affect other task group's amendment. |  | Done | 147 | 3.03
535 | Hart, Brian | Cisco Systems | 7.3.2.29 | 29 | 61 | TR | Y | 29 | 61 | T | 7.3.2.29 | MAC | M-QoSSTA |  | Youko Omori | 11-09/1054r1 | 09/24/09 | Closed | If we need to replace "non-AP STAs " by "non-AP STAs including mesh STAs" then regrefully I fear that there are hundreds of instances where this change is needed. | Judging by the size of the document, this work may not be complete. If required, please audit every instance of non-AP STA in your baseline (including 11k,11r,11y,11v?,11u?,11p?) and correct where needed | Accept | remove "(including mesh STAs)" | Accept. remove "(including mesh STAs)" |  | Done | 147 | 3.04
538 | Hart, Brian | Cisco Systems | 7.3.2.93 | 38 | 17 | TR | Y | 38 | 17 | T | 7.3.2.93 | MAC | M-PM |  | Jarkko Kneckt | 11-09/742r0 | 07/14/09 | Closed | The Mesh TIM would be improved if it reflected 11v changes to the TIM for MBSSID etc | as in comment | Reject | The focus of the 802.11s standard is to describe the basic operation logic of the MBSS. It is assumed that one mesh STA operates in one MBSS at a time and simultaneous use of multiple MBSS with the same MAC address is not considered | Reject. The focus of the 802.11s standard is to describe the basic operation logic of the MBSS. It is assumed that one mesh STA operates in one MBSS at a time and simultaneous use of multiple MBSS with the same MAC address is not considered |  | Done | 147 | NC
539 | Hart, Brian | Cisco Systems | 7.3.2.93 | 38 | 35 | TR | Y | 38 | 35 | T | 7.3.2.93 | MAC | M-PM |  | Jarkko Kneckt | 11-09/617r2 | 05/14/09 | Closed | "The length field indicates the length of this information element, which is constrained as described below." yet since an IE is a TLV, and the L field does not include lenmgth for TL | Fix | Counter | The ad hoc group plans to use the TIM element in stead of mesh tim, thus comment solved. Resolved by https://mentor.ieee.org/802.11/dcn/09/11-09-0617-02-000s-normative-text-including-pm-comment-resolutions.doc | Counter. The ad hoc group plans to use the TIM element in stead of mesh tim, thus comment solved. Resolved by https://mentor.ieee.org/802.11/dcn/09/11-09-0617-02-000s-normative-text-including-pm-comment-resolutions.doc |  | Done | 147 | 3.01
540 | Hart, Brian | Cisco Systems | 7.3.2.98.2 | 43 | 15 | TR | Y | 43 | 15 | T | 7.3.2.98.2 | MAC | M-MCCA |  | Guido, Dee, Liwen | 11-09/1079r0 1067r1 | 09/24/09 | Closed | 1/16 is a very large fraction in some deployments | Increase resolution. | Counter | Basically, accept in principle, increase to 8b, leave 4b as reserved, see contribution https://mentor.ieee.org/802.11/dcn/09/11-09-1079-00-000s-mcca-related-comment-resolution.xls | Counter. Basically, accept in principle, increase to 8b, leave 4b as reserved, see contribution https://mentor.ieee.org/802.11/dcn/09/11-09-1079-00-000s-mcca-related-comment-resolution.xls |  | Done | 147 | 3.04
678 | Cam-Winget, Nancy | Cisco Systems | 5.4.3.1 | 7 | 16 | ER | Y | 7 | 16 | E | 5.4.3.1 | General | G-Editor |  |  |  | 05/14/09 | Closed | This draft does not seem to have a Clause 11A? | Clause numbering needs to be updated and consistant. | Reject | The cited text is captured from TGr amendment (as one of the baseline standard for TGs) which contains 11A. | Reject. The cited text is captured from TGr amendment (as one of the baseline standard for TGs) which contains 11A. |  | Done | 147 | NC
681 | Cam-Winget, Nancy | Cisco Systems | General |  |  | TR | Y |  |  | T | General | General | G-Architecture |  |  | 11-09/977r0 978r0 | 09/22/09 | Closed | It is not clear from this draft when a STA is a "mesh" STA participating as a mesh node or a STA that is requiring 802.11 service and is thus behaving as a STA (not an AP STA)….this is first noticied in 7.1.3.1.6 where there is reference to an MBSS network vs. infrastructure of IBSS. | MBSS should be added to Clause 4. Definitions in Clause 3 or 5 need to clarify, distinguish a non-AP STA, mesh STA, AP STA…. | Counter | The definition of mesh BSS is described in Clause 3. MBSS is added to Clause 4. The new text in Clause 5 clarifies the mesh STA and its functionalities, differences between mesh STA and non-mesh STA. See submission https://mentor.ieee.org/802.11/dcn/09/11-09-0978-00-000s-general-arch-def-comment-resolution-text.doc | Counter. The definition of mesh BSS is described in Clause 3. MBSS is added to Clause 4. The new text in Clause 5 clarifies the mesh STA and its functionalities, differences between mesh STA and non-mesh STA. See submission https://mentor.ieee.org/802.11/dcn/09/11-09-0978-00-000s-general-arch-def-comment-resolution-text.doc |  | Done | 147 | 3.04
682 | Cam-Winget, Nancy | Cisco Systems | 7.1.3.5b.1 | 13 | 6 | TR | Y | 13 | 6 | T | 7.1.3.5b.1 | General | G-Frame |  |  | 11-09/968r0 969r0 | 09/22/09 | Closed | How does a mesh STA determine what the length of this field should be? There should be a forward reference if it is already described somewhere. | Clarify | Counter | The length of this field is set as defined in table s2. Reference to table s2 is added to clarify this. See submission https://mentor.ieee.org/802.11/dcn/09/11-09-0969-00-000s-general-frameformat-comment-resolution-text.doc | Counter. The length of this field is set as defined in table s2. Reference to table s2 is added to clarify this. See submission https://mentor.ieee.org/802.11/dcn/09/11-09-0969-00-000s-general-frameformat-comment-resolution-text.doc |  | Done | 147 | 3.04
683 | Cam-Winget, Nancy | Cisco Systems | 7.2.3 | 15 | 65 | TR | Y | 15 | 65 | T | 7.2.3 | General | G-Frame |  |  | 11-09/968r0 969r0 | 09/22/09 | Closed | The changes in this clause are changing legacy, normative behavior….is it also breaking compatibility? Specifically as the Addr 1 is now changed from DA ro RA? Also, what happens to the existing broadcast mgmt frames now that addressing is modified especially in an MBSS- are they forbidden? Or do they apply to all meshes in the neighborhood? | Clarify | Counter | TGs is just changing the name of the field (i.e., DA field -> Address 1 field) to make it generic, but the contents are kept as same. Please read the subclause 7.2.3. again. | Counter. TGs is just changing the name of the field (i.e., DA field -> Address 1 field) to make it generic, but the contents are kept as same. Please read the subclause 7.2.3. again. |  | Done | 147 | 3.03
684 | Cam-Winget, Nancy | Cisco Systems | 8.8 | 69 | 49 | TR | Y | 69 | 49 | T | 8.8 | Security | S-General |  |  | 11-09/581r2 | 05/12/09 | Closed | There is no additional security benefit for adopting yet another key derivation function. NIST has also stated that they will not recommend this mode. | There needs to be a rationale for why yet another KDF is needed and what real problem it is solving for 11s….this is currently not apparent. Worse so, the draft is approving of something that we know well known establishments such as NIST will not recommend and thus will not be approved by FIPS and HIPPA at minimum. | Counter | per adoption of https://mentor.ieee.org/802.11/dcn/09/11-09-0624-03-000s-yet-another-kdf.doc | Counter. per adoption of https://mentor.ieee.org/802.11/dcn/09/11-09-0624-03-000s-yet-another-kdf.doc |  | Done | 147 | 3.01
685 | Cam-Winget, Nancy | Cisco Systems | 8.9.1 | 71 | 31 | ER | Y | 71 | 31 | E | 8.9.1 | Security | S-General |  |  | 11-09/581r2 | 05/12/09 | Closed | Typo in the KDF function? Should MPMK be PMK or should this key hierarchy be rooted by MPMK vs. PMK? At minimum this nomencature needs to be consitant. | Clarify | Accept |  | Accept. |  | Done | 147 | 3.01
686 | Cam-Winget, Nancy | Cisco Systems | General |  |  | TR | Y |  |  | T | General | Security | S-SAE |  |  | 11-09/581r2 | 05/12/09 | Closed | The implementation and computational requirements for SAE are more demanding than that defined for the 802.11-2007 base PSK mechanism. It is not clear what significant deployment benefits the SAE mechanism provides over already defined ones (such as EKE, or even the 802.11-2007 PSK). This protocol also presumes that there is no need for proper authorization validation that is afforded by an AS that provides the authorization upon successful authentication. | Replace SAE with either the already defined one in 802.11-2007 or one that is better understood and accepted by the industry. In particular, one that is accepted by NIST and allowed for FIPS certification. | Reject | The PSK mode from 802.11-2007 does not meet the functional requirements for a mesh; the 802.11-2007 PSK mode was defined to satisfy the requirements of a client/server, not a peer-to-peer model which requires that all passwords in a mesh must be strictly pairwise and independent. Further, NIST we are not aware that NIST has certified PSK mode as defined in 802.11-2007. | Reject. The PSK mode from 802.11-2007 does not meet the functional requirements for a mesh; the 802.11-2007 PSK mode was defined to satisfy the requirements of a client/server, not a peer-to-peer model which requires that all passwords in a mesh must be strictly pairwise and independent. Further, NIST we are not aware that NIST has certified PSK mode as defined in 802.11-2007. |  | Done | 147 | NC
687 | Cam-Winget, Nancy | Cisco Systems | General |  |  | TR | Y |  |  | T | General | Security | S-General |  |  | 11-09/581r2 | 05/12/09 | Closed | The use of a new elliptic curve algorithm, while novel, must be well understood of its security properties and validated by either a security proof or accrued acceptable review by the security community. I do not believe either one have been provided for the proposed SAE mechanism. However, there are protocols that are similar to the one provided by 11s that has been accepted by the security community....so, why create a new one? | Either provide a proof that this new algorithm is secure or replace this mechanism by one that is. | Reject | While it is a good practice to construct security proofs, there is no requirement for a security proof for protocols in 802.11. The 4-Way and GTK Handshakes, for instance, come without security proofs. | Reject. While it is a good practice to construct security proofs, there is no requirement for a security proof for protocols in 802.11. The 4-Way and GTK Handshakes, for instance, come without security proofs. |  | Done | 147 | NC
688 | Cam-Winget, Nancy | Cisco Systems | General |  |  | TR | Y |  |  | T | General | Security | S-IPR |  |  | 11-09/1018r2 | 09/24/09 | Closed | It is unclear whether the defined elliptic curve algorithm is proprietary and unencumbered by IPR. Though from 11B.2 it appears similar enough to other protocols that are IPR encumbered. | Clarification of the proprietary nature and IPR encumberances must be addressed. | Out of Order | We refer to the resolution CID 374 for LB 126 | Out of Order. We refer to the resolution CID 374 for LB 126 |  | Done | 147 | NC
689 | Cam-Winget, Nancy | Cisco Systems | 11B.2.3.2.6 | 103 | 36 | TR | Y | 103 | 36 | T | 11B.2.3.2.6 | Security | S-SAE |  |  | 11-09/581r2 | 05/12/09 | Closed | Should PMK be MPMK? | Clarify | Counter | No; it should be PMK. Change "MPMK" to "PMK" in figure s54 | Counter. No; it should be PMK. Change "MPMK" to "PMK" in figure s54 |  | Done | 147 | 3.01
690 | Cam-Winget, Nancy | Cisco Systems | 11B.2.5.1.2 | 104 | 57 | TR | Y | 104 | 57 | T | 11B.2.5.1.2 | Security | S-SAE |  |  | 11-09/1018r2 | 09/24/09 | Closed | Does a peer really send both a Commit and Confirm message? Perhaps a protocol flow for this would help as well, as the "Committed" and "Confirmed" states do not seem to indicate the perspectives from the initiator and responder….or is it that both mesh STA's must initiate a "Commit and Confirm" message and if so, then how do they synchronize the SAE? How are the protocol instances synchronized between a transmitter and receiver? | Clarify | Reject | As indicated in section 8.2A.1 there is no notion of "initiator" and "responder" and therefore it would be inappropriate to show a protocol flow from either perspective. The rules in 8.2A.3.1 specifiy what messages are sent. For the protocol to "terminate" each party must have "confirmed" and for each party to "confirm" they both must have "committed". As noted, to be "committed" means to have sent a commit and to be "confirmed" means to have sent a confirm. The protocol instances are synchronized between the peers through the state machine as defined in 8.2A.6. Since this is a peer-to-peer protocol either side can view itself as the "initiator". | Reject. As indicated in section 8.2A.1 there is no notion of "initiator" and "responder" and therefore it would be inappropriate to show a protocol flow from either perspective. The rules in 8.2A.3.1 specifiy what messages are sent. For the protocol to "terminate" each party must have "confirmed" and for each party to "confirm" they both must have "committed". As noted, to be "committed" means to have sent a commit and to be "confirmed" means to have sent a confirm. The protocol instances are synchronized between the peers through the state machine as defined in 8.2A.6. Since this is a peer-to-peer protocol either side can view itself as the "initiator". |  | Done | 147 | NC
691 | Cam-Winget, Nancy | Cisco Systems | 7.2.3.10 | 20 | 36 | TR | Y | 20 | 36 | T | 7.2.3.10 | Security | S-SAE |  |  | 11-09/581r2 | 05/12/09 | Closed | Based on the description in 11B.2.5 there is the transmission of both a Commit and a Confirm message, is there a mapping of these message types to the sequencing? This needs to be described somewhere | Clarify | Reject | See 11B.2.6 | Reject. See 11B.2.6 |  | Done | 147 | NC
692 | Cam-Winget, Nancy | Cisco Systems | 11B.3.1 | 112 | 36 | TR | Y | 112 | 36 | T | 11B.3.1 | Security | S-General |  |  | 11-09/1025r3 | 09/24/09 | Closed | There seem to potentially be two types of "group" traffic in an MBSS, traffic intended to be consumed by mesh STAs and traffic intended to be consumed by STAs associated to an MBSS….these are two different groups and therefore should use differe group keys. | Suggest changing and clarifying "group" traffic and keys. GTK to serve non-mesh STAs and MGTK to serve mesh STAs | Reject | responder and therefore it would be inappropriate to show a protocol | Reject. responder and therefore it would be inappropriate to show a protocol |  | Done | 147 | NC
693 | Cam-Winget, Nancy | Cisco Systems | General |  |  | ER | Y |  |  | E | General | General | G-Editor |  |  |  | 05/14/09 | Closed | references (especially in Clause 7 referencing Clause 11B) need to be updated as there are quite a few incorrect ones. | In the comment | Accept | we will try our best to correct the cross references. | Accept. we will try our best to correct the cross references. |  | Done | 147
694 | Cam-Winget, Nancy | Cisco Systems | General |  |  | TR | Y |  |  | T | General | Security | S-General |  |  | 11-09/1017r2 | 09/23/09 | Closed | A full state machine, or protocol flow for how mesh STA's join or form a secure link is needed. Clause 11 describe the use of SAE and the abbreviated handshake, along with updates to beacons and probes but it is unclear on the ordering of the operations, affect on current 802.11 states and how/when (re)association and disassociation apply. | In the comment | Counter | See submission https://mentor.ieee.org/802.11/dcn/09/11-09-1017-02-000s-mesh-peering-protocol-interaction-and-text-re-org.doc | Counter. See submission https://mentor.ieee.org/802.11/dcn/09/11-09-1017-02-000s-mesh-peering-protocol-interaction-and-text-re-org.doc |  | Done | 147 | 3.04
695 | Cam-Winget, Nancy | Cisco Systems | 11B.3.1 | 112 | 16 | TR | Y | 112 | 16 | T | 11B.3.1 | Security | S-General |  |  | 11-09/1017r2 | 09/23/09 | Closed | the abbreviated handshake is a nice optimization of the 4-Way handshake and presumed to follow SAE but after or prior to association? Also, new 802.11 formats have been created along with new states that affect how and data traffic may flow, though no discussion is provided to this state (e.g. port control in 802.1X speak). The presumption is that Figure s56 provides such a state machine, but it is not readily obvious when data can begin flowing? | Clarify | Counter | See submission https://mentor.ieee.org/802.11/dcn/09/11-09-1017-02-000s-mesh-peering-protocol-interaction-and-text-re-org.doc | Counter. See submission https://mentor.ieee.org/802.11/dcn/09/11-09-1017-02-000s-mesh-peering-protocol-interaction-and-text-re-org.doc |  | Done | 147 | 3.04
799 | Chan, Douglas | Cisco Systems | 11.B.10 | 149 |  | TR | Y | 149 |  | T | 11B.10 | RFI | R-LM |  |  |  | 07/16/09 | Closed | The proposed Airtime Link Metric here is insufficient mostly due to the fact that the rate (r) used would not actually represent the rate that would actually be used by the mesh STA. For example, the frame sent may be unicast or multicast, and the rate used for each of these modes can be drastically different. Another example would be the fact that a mesh STA may be communicating to other STAs of different PHYs, in that case, the rates used would be different as well. So what rate should we be using to calculate the metric? The lowest denomination? | Determine a rate to be used so the metric is computed fairly. | Reject | Clause states "Airtime reflects the amount of channel resources consumed by transmitting the frame over a particular link" The question of multicast or transmission to STAs with different PHYs is not relevant because the estimate to made for one link and one link only. Multicast rates should not be used as a basis for computing a link metric. Comment 499 enjoins us to write an informative note in the Annex, which will make this fact obvious. | Reject. Clause states "Airtime reflects the amount of channel resources consumed by transmitting the frame over a particular link" The question of multicast or transmission to STAs with different PHYs is not relevant because the estimate to made for one link and one link only. Multicast rates should not be used as a basis for computing a link metric. Comment 499 enjoins us to write an informative note in the Annex, which will make this fact obvious. |  | Done | 147 | NC
800 | Chan, Douglas | Cisco Systems | 5.2.12.1 | 5 | 22 | TR | Y | 5 | 22 | T | 5.2.12.1 | RFI | R-Portal |  |  |  | 05/14/09 | Closed | It was mentioned in subclause 11B.9 that multiple portals from the a segment to the same external portals are not allowed. Why then does the figure illustrating general mesh network topologies show precisely this forbidden conifg? (See Portal 3 and 4.) Moreover, in this figure, which infrasture BSS does Mesh STA11 belong to? It looks like it's straddling between two infra. BSS. | Pls clarify Figure s1 and ensure it complies with 11B.9. | Counter | Mesh STA11 is clearly in the MBSS, but AP STA 12 indeed looks like it is straddling two infrastructure BSS so the editor should move it slightly to the left. What 11B.9 says is "In case two portals connect the MBSS to one external LAN segment, broadcast loops may occur and the IEEE 802.1D bridging protocol may cause the LAN ports of one of the portals to be closed. These cases can be prevented by proper configuration measures." Therefore the configuration in question is allowed and is valid. All 11B.9 is saying is "bad things can happen when you do this" -- that is true of many network topologies. | Counter. Mesh STA11 is clearly in the MBSS, but AP STA 12 indeed looks like it is straddling two infrastructure BSS so the editor should move it slightly to the left. What 11B.9 says is "In case two portals connect the MBSS to one external LAN segment, broadcast loops may occur and the IEEE 802.1D bridging protocol may cause the LAN ports of one of the portals to be closed. These cases can be prevented by proper configuration measures." Therefore the configuration in question is allowed and is valid. All 11B.9 is saying is "bad things can happen when you do this" -- that is true of many network topologies. |  | Done | 147
969 | Erceg, Vinko | Broadcom | 7.3.2.89 | 35 | 42 | TR | Y | 35 | 42 | T | 7.3.2.89 | MAC | M-CC |  |  |  | 05/14/09 | Closed | "The congestion notification expiration timer values are encoded as unsigned integers in units of 0.1 TUs." Please round this number to 100 us. | As in comment. | Counter | replace "The congestion notification expiration timer values are encoded as unsigned integers in units of 0.1 TUs." with "The congestion notification expiration timer values are encoded as unsigned integers in units of 100 microsecond." | Counter. replace "The congestion notification expiration timer values are encoded as unsigned integers in units of 0.1 TUs." with "The congestion notification expiration timer values are encoded as unsigned integers in units of 100 microsecond." |  | Done | 147 | 3.01
970 | Erceg, Vinko | Broadcom | 9.6 | 74 | 26 | TR | Y | 74 | 26 | T | 9.6 | MAC | M-General |  |  |  | 05/14/09 | Closed | "In the case of a mesh BSS, each of peer mesh STA's BSSBasicRateSet shall be identical throughout the MBSS." How is this achieved? | Please clarify. | Counter | Replace the first paragraph of 9.6.0ca with "Because a mesh STA does not establish a peering with a mesh STA using a different BSSBasicRateSet, all mesh STAs in an MBSS use the same BSSBasicRateSet. See 11B.5.2.1." | Counter. Replace the first paragraph of 9.6.0ca with "Because a mesh STA does not establish a peering with a mesh STA using a different BSSBasicRateSet, all mesh STAs in an MBSS use the same BSSBasicRateSet. See 11B.5.2.1." |  | Done | 147 | 3.01
971 | Erceg, Vinko | Broadcom | 7.3.2.94 | 39 | 44 | TR | Y | 39 | 44 | T | 7.3.2.94 | MAC | M-PM |  | Jarkko Kneckt |  | 05/14/09 | Closed | "The Awake Window field is 2 octets in length and contain the Awake Window length in TUs." Why not to use ms or us as units (or tens or hundreds of). | As in comment. | Reject | The unit of TU is used in ATIM Window and the same units in Awake and ATIM Windows should be easy to understand by the most of the readers. | Reject. The unit of TU is used in ATIM Window and the same units in Awake and ATIM Windows should be easy to understand by the most of the readers. |  | Done | 147 | NC
972 | Erceg, Vinko | Broadcom | 11B.2.3.1.2 | 101 | 36 | TR | Y | 101 | 36 | T | 11B.2.3.1.2 | Security | S-SAE |  |  | 11-09/754r3 | 07/16/09 | Closed | "Generation of rand and mask should be normative." | Please provide normative requirements. | Counter | Will be resolved by resolution of CID 412 Resolved by submission https://mentor.ieee.org/802.11/dcn/09/11-09-0754-04-000s-resolving-sae-comments.doc | Counter. Will be resolved by resolution of CID 412 Resolved by submission https://mentor.ieee.org/802.11/dcn/09/11-09-0754-04-000s-resolving-sae-comments.doc |  | Done | 147 | 3.03
973 | Erceg, Vinko | Broadcom | 11B.2.3.1.2 | 101 | 37 | TR | Y | 101 | 37 | T | 11B.2.3.1.2 | Security | S-SAE |  |  | 11-09/754r3 | 07/16/09 | Closed | "Construction of commit message should be normative." | Please provide normative requirements. | Counter | Will be resolved by resolution of CID 412 Resolved by submission https://mentor.ieee.org/802.11/dcn/09/11-09-0754-04-000s-resolving-sae-comments.doc | Counter. Will be resolved by resolution of CID 412 Resolved by submission https://mentor.ieee.org/802.11/dcn/09/11-09-0754-04-000s-resolving-sae-comments.doc |  | Done | 147 | 3.03
974 | Erceg, Vinko | Broadcom | 11B.2.3.1.4 | 101 | 57 | TR | Y | 101 | 57 | T | 11B.2.3.1.4 | Security | S-SAE |  |  | 11-09/754r3 | 07/16/09 | Closed | "Construction of confirm message should be normative." | Please provide normative requirements. | Counter | Will be resolved by resolution of CID 412 Resolved by submission https://mentor.ieee.org/802.11/dcn/09/11-09-0754-04-000s-resolving-sae-comments.doc | Counter. Will be resolved by resolution of CID 412 Resolved by submission https://mentor.ieee.org/802.11/dcn/09/11-09-0754-04-000s-resolving-sae-comments.doc |  | Done | 147 | 3.03
975 | Stacey, Robert | Intel Corporation | 7.1.2 | 9 | 16 | TR | Y | 9 | 16 | T | 7.1.2 | General | G-Frame |  |  | 11-09/968r0 969r0 | 09/22/09 | Closed | It is not clear how the presence of the Mesh Control field is signalled. Traditionally, the frames are self defining meaning that it can be parsed without context information. The Mesh Control field seems to violate this principle, being present by virtue of transmitter being a Mesh STA (i.e. some capability). | Make the frame self defining. Signal the presence of the Mesh Control field in the frame carrying it. | Counter | Although the legacy STA may not interpret the existence of the Mesh Control field, 1 bit indicator for the existence of Mesh Control field is defined in QoS header. See submission https://mentor.ieee.org/802.11/dcn/09/11-09-0969-00-000s-general-frameformat-comment-resolution-text.doc | Counter. Although the legacy STA may not interpret the existence of the Mesh Control field, 1 bit indicator for the existence of Mesh Control field is defined in QoS header. See submission https://mentor.ieee.org/802.11/dcn/09/11-09-0969-00-000s-general-frameformat-comment-resolution-text.doc |  | Done | 147 | 3.04
976 | Stacey, Robert | Intel Corporation | 9.9.1.6 | 75 | 13 | TR | Y | 75 | 13 | T | 9.9.1.6 | MAC | M-QoSSTA |  | Youko Omori | 11-09/1176r1 | 11/18/09 | Closed | Are mesh STA and QoS STA functionality mutually exclusive? Why not define a mesh STA as a STA that includes QoS STA functionality. QoS functionality was carefully designed not to burdensome and the optional mainly for legacy compatibility reasons. We should try to carry forward functions as much as possible to avoid too many permutations of STA functionality. | Define a mesh STA as including QoS STA functionality (perhaps in the Definitions section). That way it would only be necessary to mention QoS STA in all QoS related text. | Counter | Resolved by https://mentor.ieee.org/802.11/dcn/09/11-09-1176-01-000s-qos-sta-comment-resolution-text.doc | Counter. Resolved by https://mentor.ieee.org/802.11/dcn/09/11-09-1176-01-000s-qos-sta-comment-resolution-text.doc |  | Done | 147
1096 | Roy, Richard |  | 5.2.12.2 | 5 | 61 | TR | Y | 5 | 61 | T | 5.2.12.2 | General | G-Architecture |  |  | 11-09/977r0 978r0 | 09/22/09 | Closed | Text reads: "Effectively, this means that an MBSS appears functionally equivalent to a link from the perspective of other networks and higher layer protocols." Links are implicitly defined in 802.11 as existing between two STAs. As such, they can not be "functionally equivalent to" a set of STAs in a basic service set of any kind, mesh or otherwise. It seems the intent is to describe MAC layer mesh services as transparent to all layers above the MAC, i.e. as a form of MAC bridging (forwardsing at the MAC sublayer). | Rewrite the paragraph so the meaning is clearer. | Counter | The text is updated. See submission https://mentor.ieee.org/802.11/dcn/09/11-09-0978-00-000s-general-arch-def-comment-resolution-text.doc | Counter. The text is updated. See submission https://mentor.ieee.org/802.11/dcn/09/11-09-0978-00-000s-general-arch-def-comment-resolution-text.doc |  | Done | 147 | 3.04
1098 | Roy, Richard |  | 7.1.3.1.3 | 10 | 25 | TR | Y | 10 | 25 | T | 7.1.3.1.3 | General | G-Frame |  |  | 11-09/968r0 969r0 | 09/22/09 | Closed | Text in table 7-2 reads: "A data frame using the four-address MAC header format, including but not limited to mesh data frames. In an MBSS, this bit combination indicates the presence of the Mesh Control information." It appears that the only indication that the Mesh Control subfield is present as the first few octets in the body field is having both ToDS and FromDS bits in the frame control field set to one. If this is the case, then there would appear to be no way to distinguish "normal" four-addresss format data frames from four address format mesh data frames. The only conclusion would then be that ALL four address data frames with ToDS and FromDS both one must be mesh data frames. If this is the case, this is not backward compatible and not a good idea. Note if the thinking is that this only applies to "STAs in mesh mode" or something similar, in 802.11, STAs don't have modes or states (other than power save which is not relevant for this discussion), links do. In particfualr, a mesh STA should be able to forward mesh traffic as well as engage in four-address data exhanges with other STAs or APs "simultaneously", and it would seem that this amendment as written would not allow this. | If the analysis is correct, the restriction of ToDS an FromDS = 1 implying a mesh data frame and therefore the presence of the mesh control field in the body of the data frame should be removed. Perhaps a solution could be to define a new data subtype (1101 may be available), or perhaps create a new frame type (11 is still available). | Reject | TGs still try to use the existing QoS data frame subtypes for the convenience. The draft spec is modified so that the Mesh Control field existence can be distinguished by referring 1 bit indicator in the QoS Control field. See submission https://mentor.ieee.org/802.11/dcn/09/11-09-0969-00-000s-general-frameformat-comment-resolution-text.doc | Reject. TGs still try to use the existing QoS data frame subtypes for the convenience. The draft spec is modified so that the Mesh Control field existence can be distinguished by referring 1 bit indicator in the QoS Control field. See submission https://mentor.ieee.org/802.11/dcn/09/11-09-0969-00-000s-general-frameformat-comment-resolution-text.doc |  | Done | 147 | 3.04
3109 | Ecclesine, Peter | Cisco Systems | 11.9.7.2a | 166 | 9 | TR | Y | 166 | 9 | T | 11.9.7.2a | MAC | M-CS |  | Ashish | 11-10/547r0 | 20100520 | Closed | P802.11s_Draft 5 alters MBSS Extended Channel Switching, so the scope of the changed text raises the issue of how to operate in Brazil or China or any country whose regulatory classes are not in Annex J. This comment is essentially CID 2113 of LB 160, asking to extend the regulatory class definitions to allow regulatory specific rules and channel specification to be used in all countries where IEEE 802.11 can be used. This comment is requesting Annex J to be extended to cover all regulatory rules, i.e., some generic mechanism for describing channels (regulatory class,channel number pairs) outside the US/EU/JP. 802.11mb Draft3.0 shows a global table for use in any regulatory domain for 802.11 channel switching and operation. | Apply the resolution contained in submission 11-10-210-07 to P802.11s_Draft5.0 for the next draft. | Counter | P802.11-rev-mb3.0d has already incorporated the submission 11-10-210-07. Given that 11s may be finished before 11m, please incoporate the submission https://mentor.ieee.org/802.11/dcn/10/11-10-0210-08-000m-lb160-cid-2113-proposed-resolution.doc | Counter. P802.11-rev-mb3.0d has already incorporated the submission 11-10-210-07. Given that 11s may be finished before 11m, please incoporate the submission https://mentor.ieee.org/802.11/dcn/10/11-10-0210-08-000m-lb160-cid-2113-proposed-resolution.doc |  | Done | 161 | 5.01
3276 | Wentink, Menzo | Qualcomm | 7.1.3.5.10 | 19 | 44 | TR | Y | 19 | 44 | T | 7.1.3.5.10 | General | G-Frame |  | Kazuyuki | 11-10/538r2 | 20100520 | Closed | Adding the proposed mesh entry to the QoS Control field implies that the parsing of the QoS Control field has now become dependent on the MAC addresses earlier in the MAC header. I am not sure if this is a good idea. Also not because future amendments may add other MAC address specific parsing, based on this precedent. | Find a different way to add the newly proposed bits to the MAC header, so that the presence of the bits does not depend on the MAC address. In fact, it would be great if other amendments also got access to the currently useless bits 8-15 of the QoS Control field. | Reject | header fields: As we can see in table 7-4 in the base standard, parsing of the QoS Control field has been dependent on the transmitter even before TGs amendment. Also, it is believed that the TGs does not change the rationale of the QoS control field parsing. APs or STAs in an IBSS process QoS Control field of the received data frame assuming that the frame is transmitted by non-mesh, non-HC STA. STAs in an infrastructure BSS process QoS Control field of the received data frame assuming that the frame is transmitted by an AP (STA with HC) of the BSS. These legacy STAs do not need to perform additional check routine as they do not communicate with mesh STAs. Mesh STAs can process the QoS Control field of the received data frame assuming that the frame is transmitted by a mesh STA. as they do not communicate with non-mesh STAs. | Reject. header fields: As we can see in table 7-4 in the base standard, parsing of the QoS Control field has been dependent on the transmitter even before TGs amendment. Also, it is believed that the TGs does not change the rationale of the QoS control field parsing. APs or STAs in an IBSS process QoS Control field of the received data frame assuming that the frame is transmitted by non-mesh, non-HC STA. STAs in an infrastructure BSS process QoS Control field of the received data frame assuming that the frame is transmitted by an AP (STA with HC) of the BSS. These legacy STAs do not need to perform additional check routine as they do not communicate with mesh STAs. Mesh STAs can process the QoS Control field of the received data frame assuming that the frame is transmitted by a mesh STA. as they do not communicate with non-mesh STAs. |  | Done | 161 | NC
3277 | Wentink, Menzo | Qualcomm | 7.1.3.6.3 | 20 | 32 | TR | Y | 20 | 32 | T | 7.1.3.6.3 | General | G-Frame |  | Kazuyuki | 11-10/538r2 | 20100520 | Closed | iven that the Mesh Control field is part of the frame body anyway, it might as well be preceded by an Ethertype that announces its presence. This way you don't have to announce the field through the QoS Control field. | In Annex U, define a new Protocol value for the 890d Ethertype and use it to announce any mesh related headers. The convention for the new 890d protocol should be that the original LLC header follows immediately after the mesh information. | Reject | header fields: As illustrated in the figure in Annex Y.1 (Clarification of Mesh Data frame format), LLC/SNAP header is preceded by the Mesh Control field. Actually, LLC/SNAP header is a part of the MSDU, but Mesh Control field is not. It will become difficult to use Ethertype field in the SNAP header to signal the presence of Mesh Control field. It is believed that the QoS control field can signal it in much simpler fashion. | Reject. header fields: As illustrated in the figure in Annex Y.1 (Clarification of Mesh Data frame format), LLC/SNAP header is preceded by the Mesh Control field. Actually, LLC/SNAP header is a part of the MSDU, but Mesh Control field is not. It will become difficult to use Ethertype field in the SNAP header to signal the presence of Mesh Control field. It is believed that the QoS control field can signal it in much simpler fashion. |  | Done | 161 | NC
3278 | Wentink, Menzo | Qualcomm | 7.2.3 | 24 | 52 | TR | Y | 24 | 52 | T | 7.2.3 | General | G-Frame |  | Kazuyuki | 11-10/538r2 | 20100520 | Closed | According to rule 3, the A3 field of mesh frames is set to the BSSID and to A2. | Clarify which value is contained in A3. | Counter | Clarification: Replace "3) If the STA is a mesh STA, the Address 3 field is set to Address 2." with "3) If the STA is a mesh STA, the BSSID value is set to the same value as Address 2 (TA)." | Counter. Clarification: Replace "3) If the STA is a mesh STA, the Address 3 field is set to Address 2." with "3) If the STA is a mesh STA, the BSSID value is set to the same value as Address 2 (TA)." |  | Done | 161 | 5.01
3279 | Wentink, Menzo | Qualcomm | 7.1.3.5.2 | 18 | 44 | TR | Y | 18 | 44 | T | 7.1.3.5.2 | MAC | M-PM |  | Jarkko | 11-10/508r3 | 20100520 | Closed | "The mesh STA uses the subfield" - insert EOSP between "the" and "subfield". | As in comment. | Accept | Change the sentence to read: "The mesh STA uses the EOSP subfield to indicate the end of the current peer service period (PSP) in which it operates as the transmitter." | Accept. Change the sentence to read: "The mesh STA uses the EOSP subfield to indicate the end of the current peer service period (PSP) in which it operates as the transmitter." |  | Done | 161 | 5.01
3280 | Wentink, Menzo | Qualcomm | 7.1.3.5.2 | 18 | 44 | TR | Y | 18 | 44 | T | 7.1.3.5.2 | MAC | M-PM |  | Jarkko | 11-10/508r3 | 20100520 | Closed | "in which it operates as the transmitter" - typically both STAs in a service period act as a transmitter, for Data or ACK frames. | Clarify. | Counter | It is valid point that the receiver in the service period may send ACK and block ack frames. Change the text that describes the operation of the transmitter and the receiver in the service period. Change the following text in page 18, line 44: "The mesh STA uses the subfield to indicate the end of the current peer service period (PSP) in which it operates as the transmitter. The mesh STA sets the EOSP subfield" to:" The mesh STA uses the subfield to indicate the end of the current peer service period (PSP) in which it operates as the owner." Change the following text in page 263, line 61:"One mesh STA operates as transmitter in peer service period, transmits frames and initiates the termination of the peer service period. The other mesh STA operates as receiver in peer service period and receives the frames." to:" One mesh STA operates as the owner in the peer service period. It obtains TXOPs in order to transmit MMPDUs or MPDUS to the recipient in the peer service period. Furthermore, the mesh STA initiates the termination of the peer service period. The other mesh STA operates as the recipient in the peer service period and does not obtain TXOPs for transmitting MPDUs or MMPDUs to the owner of the peer service period." Change in figure s58 the: " Mesh STA is transmitter in the peer service period" to:" Mesh STA is the owner in the peer service period" Change in figure s58 the: " Mesh STA is receiver in the peer service period" to:" Mesh STA is the recipient in the peer service period" Change table s66: " The transmitter of the trigger frame is the transmitter in the peer service period." to: " The transmitter of the trigger frame is the owner in the peer service period." Change table s66:"Both mesh STAs are transmitters in a peer service period." to:" Both mesh STAs are owners in a peer service period." Change table s66:" The receiver of the trigger frame is the transmitter in the peer service period." to: "The receiver of the trigger frame is the owner in the peer service period." Change p.265 line 20 11C.13.10.3: "During the peer service period, the transmitter of the peer service period and peer mesh STA shall operate in Awake state." to: " During the peer service period, the owner and the recipient of the peer service period shall operate in the Awake state." Change p.265 line 25 11C.13.10.3:" Reverse Direction Grant (RDG) shall not be used when the receiver of the TXOP operates in light or deep sleep mode and is not a transmitter in service period toward the transmitter in the TXOP." to: " Reverse Direction Grant (RDG) shall not be used when the receiver of the TXOP operates in light or deep sleep mode and is not an owner in the peer service period toward the holder of the TXOP." Change p.265, line 32 11C.13.10.4: "The peer service period is terminated after a successfully acknowledged QoS Null or Mesh Data frame with the EOSP bit set to 1 from the transmitter of the peer service period." to: "The peer service period is terminated after a successfully acknowledged QoS Null or Mesh Data frame with the EOSP bit set to 1 from the owner of the peer service period." Change p.265, line 56 11C.13.11: " The MCCAOP owner is the transmitter during the scheduled peer service period. The MCCAOP responder is the receiver during the scheduled peer service period." to:" The MCCAOP owner is the owner during the scheduled peer service period. The MCCAOP responder is the recipient during the scheduled peer service period." Change p.265, line 56 11C.13.11: " The scheduled peer service period continues until it is successfully terminated by acknowledged QoS Null or Mesh Data frame with set EOSP bit from transmitter to receiver as described in 11C.13.10 (Peer service periods)." to: " The scheduled peer service period continues until it is successfully terminated by the acknowledged QoS Null or Mesh Data frame with the EOSP bit set to 1 from the owner of the peer service period to the recipient of the peer service period as described in 11C.13.10 (Peer service periods). | Counter. It is valid point that the receiver in the service period may send ACK and block ack frames. Change the text that describes the operation of the transmitter and the receiver in the service period. Change the following text in page 18, line 44: "The mesh STA uses the subfield to indicate the end of the current peer service period (PSP) in which it operates as the transmitter. The mesh STA sets the EOSP subfield" to:" The mesh STA uses the subfield to indicate the end of the current peer service period (PSP) in which it operates as the owner." Change the following text in page 263, line 61:"One mesh STA operates as transmitter in peer service period, transmits frames and initiates the termination of the peer service period. The other mesh STA operates as receiver in peer service period and receives the frames." to:" One mesh STA operates as the owner in the peer service period. It obtains TXOPs in order to transmit MMPDUs or MPDUS to the recipient in the peer service period. Furthermore, the mesh STA initiates the termination of the peer service period. The other mesh STA operates as the recipient in the peer service period and does not obtain TXOPs for transmitting MPDUs or MMPDUs to the owner of the peer service period." Change in figure s58 the: " Mesh STA is transmitter in the peer service period" to:" Mesh STA is the owner in the peer service period" Change in figure s58 the: " Mesh STA is receiver in the peer service period" to:" Mesh STA is the recipient in the peer service period" Change table s66: " The transmitter of the trigger frame is the transmitter in the peer service period." to: " The transmitter of the trigger frame is the owner in the peer service period." Change table s66:"Both mesh STAs are transmitters in a peer service period." to:" Both mesh STAs are owners in a peer service period." Change table s66:" The receiver of the trigger frame is the transmitter in the peer service period." to: "The receiver of the trigger frame is the owner in the peer service period." Change p.265 line 20 11C.13.10.3: "During the peer service period, the transmitter of the peer service period and peer mesh STA shall operate in Awake state." to: " During the peer service period, the owner and the recipient of the peer service period shall operate in the Awake state." Change p.265 line 25 11C.13.10.3:" Reverse Direction Grant (RDG) shall not be used when the receiver of the TXOP operates in light or deep sleep mode and is not a transmitter in service period toward the transmitter in the TXOP." to: " Reverse Direction Grant (RDG) shall not be used when the receiver of the TXOP operates in light or deep sleep mode and is not an owner in the peer service period toward the holder of the TXOP." Change p.265, line 32 11C.13.10.4: "The peer service period is terminated after a successfully acknowledged QoS Null or Mesh Data frame with the EOSP bit set to 1 from the transmitter of the peer service period." to: "The peer service period is terminated after a successfully acknowledged QoS Null or Mesh Data frame with the EOSP bit set to 1 from the owner of the peer service period." Change p.265, line 56 11C.13.11: " The MCCAOP owner is the transmitter during the scheduled peer service period. The MCCAOP responder is the receiver during the scheduled peer service period." to:" The MCCAOP owner is the owner during the scheduled peer service period. The MCCAOP responder is the recipient during the scheduled peer service period." Change p.265, line 56 11C.13.11: " The scheduled peer service period continues until it is successfully terminated by acknowledged QoS Null or Mesh Data frame with set EOSP bit from transmitter to receiver as described in 11C.13.10 (Peer service periods)." to: " The scheduled peer service period continues until it is successfully terminated by the acknowledged QoS Null or Mesh Data frame with the EOSP bit set to 1 from the owner of the peer service period to the recipient of the peer service period as described in 11C.13.10 (Peer service periods). |  | Done | 161 | 5.01
3281 | Wentink, Menzo | Qualcomm | 7.1.3.1.6 | 17 | 61 | ER | Y | 17 | 61 | E | 7.1.3.1.6 | MAC | M-PM |  | Jarkko | 11-10/508r3 | 20100520 | Closed | "The value of this field together with Mesh Power Save Level subfield" - the article "the" is missing between "with" and "Mesh". This happens in many places in this draft. | Review the draft and add missing articles wherever needed. | Counter | Change the sentence to read: "The value of this field together with the Mesh Power Save Level subfield..." | Counter. Change the sentence to read: "The value of this field together with the Mesh Power Save Level subfield..." |  | Done | 161 | 5.01
3282 | Wentink, Menzo | Qualcomm | 7.2.3.1 | 25 | 19 | TR | Y | 25 | 19 | T | 7.2.3.1 | MAC | M-QoS |  | Jarkko | 11-10/640r0 | 20100520 | Closed | If dot11QoSOptionImplemented and dot11MeshActivated are true then the EDCA Parameter Set element is both present and not present. | Clarify. | Counter | Similar to CID 3128. Change the sentence in page 25 lines 19-24 to read: " The EDCA Parameter Set element is present when dot11QosOptionImplemented is true, and dot11MeshActivated is false, and the QoS Capability element is not present. " | Counter. Similar to CID 3128. Change the sentence in page 25 lines 19-24 to read: " The EDCA Parameter Set element is present when dot11QosOptionImplemented is true, and dot11MeshActivated is false, and the QoS Capability element is not present. " |  | Done | 161 | 5.01
3283 | Wentink, Menzo | Qualcomm | 7.2.3.1 | 25 | 25 | TR | Y | 25 | 25 | T | 7.2.3.1 | MAC | M-QoS |  | Jarkko | 11-10/640r0 | 20100520 | Closed | If dot11QoSOptionImplemented and dot11MeshActivated are true then the QoS Capability element is both present and not present. | Clarify. | Counter | Similar to CID 3129. Change the sentence in page 25, lines 25-29 to read: "The QoS Capability element is present if dot11QosOption-Implemented is true, and dot11MeshActivated is false, and EDCA Parameter Set element is not present. | Counter. Similar to CID 3129. Change the sentence in page 25, lines 25-29 to read: "The QoS Capability element is present if dot11QosOption-Implemented is true, and dot11MeshActivated is false, and EDCA Parameter Set element is not present. |  | Done | 161 | 5.01
3284 | Wentink, Menzo | Qualcomm | 7.2.3.1 | 25 | 19 | TR | Y | 25 | 19 | T | 7.2.3.1 | MAC | M-QoS |  | Jarkko | 11-10/640r0 | 20100520 | Closed | I assume that a mesh STA does not need to include the EDCA Parameter Set element because there will be no STAs associated with the mesh STA. But this does not seem to be explained anywhere, or I may have missed it. | Please clarify. | Counter | Correct, the EDCA parameter set is not needed, because the mesh STA operates only with default parameters. | Counter. Correct, the EDCA parameter set is not needed, because the mesh STA operates only with default parameters. |  | Done | 161 | NC
3285 | Wentink, Menzo | Qualcomm | 9.9a.3.1 | 111 | 39 | TR | Y | 111 | 39 | T | 9.9a.3.1 | MAC | M-MCCA |  | Guido/Dee | 11-10/501r3, 502r3 | 20100520 | Closed | The use of MCCA may imply long interruptions at a mesh STA, due to the self-imposed NAV. This may have a significant impact on the jitter in a mesh network, even though the overall throughput might increase because of it. Is there really not something better to resolve the mesh specific channel access issues? | Please clarify. | Reject | The simulations on MCCA, as in https://mentor.ieee.org/802.11/dcn/07/11-07-0356-00-000s-mda-sims-with-interference.ppt, have shown that MCCA reduces the number of collisions in an MBSS, as is generally the case with reservations mechanisms. This by itself is known to reduce jitter. Also, the more deterministic, predictable, behavior of MCCA gives rise to fixed delays, which again reduces jitter. The second part of the comment does not contain sufficient direction for technical change. | Reject. The simulations on MCCA, as in https://mentor.ieee.org/802.11/dcn/07/11-07-0356-00-000s-mda-sims-with-interference.ppt, have shown that MCCA reduces the number of collisions in an MBSS, as is generally the case with reservations mechanisms. This by itself is known to reduce jitter. Also, the more deterministic, predictable, behavior of MCCA gives rise to fixed delays, which again reduces jitter. The second part of the comment does not contain sufficient direction for technical change. |  | Done | 161 | NC
3286 | Wentink, Menzo | Qualcomm | 9.9a.3.10.1 | 117 | 54 | TR | Y | 117 | 54 | T | 9.9a.3.10.1 | MAC | M-MCCA |  | Guido/Dee | 11-10/501r3, 502r3 | 20100520 | Closed | "The values of the retry counters are copied to temporary storage and reset to 0." | Please clarify why this is needed and whether this will introduce a risk of introducing duplicates. If it is not strictly needed, then remove this requirement. | Accept | Implemented in Contribution https://mentor.ieee.org/802.11/dcn/10/11-10-0502-03-000s-mcca-resolutions-text.doc | Accept. Implemented in Contribution https://mentor.ieee.org/802.11/dcn/10/11-10-0502-03-000s-mcca-resolutions-text.doc |  | Done | 161 | 5.01
4028 | Bumiller, George | Research In Motion | 8 |  |  | TR | Y |  |  | T | 8 | Security | S-Base |  | Dan | 11-10/726r3 | 20100715 | Closed | The draft makes the use of SAE authentication mandatory when the STA and the RSNA-capable peer support SAE authentication. I do not wish it to replace PSK, but have no issue with SAE being a possible (i.e. optional) authentication method. | Change "support SAE" to "advertise SAE", and other similar changes/ | Counter | Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc | Counter. Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc |  |  | 165
4029 | Bumiller, George | Research In Motion | 8.1.3 | 79 | 26 | TR | Y | 79 | 26 | T | 8.1.3 | Security | S-Base |  | Dan | 11-10/726r3 | 20100715 | Closed | SAE can be an option for password-based authentication, but should not be mandatory. | In 2): First sentence: change "support" to "advertise" [one instance]. Second sentence: change "support" to "advertise" [two instances]. | Counter | Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc | Counter. Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc |  |  | 165
4030 | Bumiller, George | Research In Motion | 8.1.3 | 79 | 53 | TR | Y | 79 | 53 | T | 8.1.3 | Security | S-Base |  | Dan | 11-10/726r3 | 20100715 | Closed | SAE can be an option for password-based authentication, but should not be mandatory. | In 2): First sentence: change "support" to "advertise" [one instance]. Second sentence: change "support" to "advertise" [two instances]. | Counter | Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc | Counter. Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc |  |  | 165
4031 | Bumiller, George | Research In Motion | 8.4.7 | 100 | 63 | TR | Y | 100 | 63 | T | 8.4.7 | Security | S-Base |  | Dan | 11-10/726r3 | 20100715 | Closed | clairfy [use terminology in keeping with above changes] | change "SAE capable STA' to "SAE advertising STA" | Counter | Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc | Counter. Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc |  |  | 165
4032 | Bumiller, George | Research In Motion | 8.4.7 | 100 | 65 | TR | Y | 100 | 65 | T | 8.4.7 | Security | S-Base |  | Dan | 11-10/726r3 | 20100715 | Closed | clarify | change third sentence of paragraph "A STA that does not…" to "A STA may use PSK authentication." | Counter | Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc | Counter. Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc |  |  | 165
4107 | Montemurro, Michael | Research in Motion | 8.1.3 | 79 | 26 | TR | Y | 79 | 26 | T | 8.1.3 | Security | S-Base |  | Dan | 11-10/726r3 | 20100715 | Closed | I agree that SAE could be an option for password based authentication. However I disagree that a STA that supports SAE "shall" use SAE for authentication. | Replace 2) with the following: If the STA and the RSNA-capable peer advertise SAE authentication the STA shall invoke SAE authentication and establish a PMK. If either the STA or the RSNA-capable peer does not advertise SAE but advertise the alternate form of PSK authentication (see 5.8.2.2 (Alternate Operations with PSK)) it may It shall invoke Open System authentication and use the PSK as the PMK with the alternate form of PSK authentication. | Counter | Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc | Counter. Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc |  |  | 165
4108 | Montemurro, Michael | Research in Motion | 8.1.3 | 79 | 53 | TR | Y | 79 | 53 | T | 8.1.3 | Security | S-Base |  | Dan | 11-10/726r3 | 20100715 | Closed | I agree that SAE could be an option for password based authentication. However I disagree that a STA that supports SAE "shall" use SAE for authentication. | Replace 2) with the following: If the STA and the RSNA-capable peer advertise SAE authentication the STA shall invoke SAE authentication and establish a PMK. If either the STA or the RSNA-capable peer does not advertise SAE but advertise the alternate form of PSK authentication. | Counter | Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc | Counter. Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc |  |  | 165
4109 | Montemurro, Michael | Research in Motion | 8.4.7 | 100 | 63 | TR | Y | 100 | 63 | T | 8.4.7 | Security | S-Base |  | Dan | 11-10/726r3 | 20100715 | Closed | SAE should be used when its advertised by the peer STA in an IBSS | Replace "an SAE capable STA" with "a STA advertising SAE" | Counter | Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc | Counter. Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc |  |  | 165
4110 | Montemurro, Michael | Research in Motion | 8.4.7 | 100 | 65 | TR | Y | 100 | 65 | T | 8.4.7 | Security | S-Base |  | Dan | 11-10/726r3 | 20100715 | Closed | Clarify PSK authentication behaviour. | Replace the sentence beginning with "A STA that does not…" with "A STA may use PSK authentication by sending a 4-Way Handshake Message 1 to the target STA." | Counter | Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc | Counter. Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc |  |  | 165
4111 | Montemurro, Michael | Research in Motion | 8.4.7 | 101 | 4 | TR | Y | 101 | 4 | T | 8.4.7 | Security | S-Base |  | Dan | 11-10/726r3 | 20100715 | Closed | I agree with the sentiment, but not the text as written. | Replace the sentence beginning with "PSK PMKIDs …." with " | Counter | Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc | Counter. Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc |  |  | 165
4112 | Montemurro, Michael | Research in Motion | 8.4.7 | 101 | 8 | TR | Y | 101 | 8 | T | 8.4.7 | Security | S-Base |  | Dan | 11-10/726r3 | 20100715 | Closed | The paragraph and the lettered items provide key assumptions and should not be removed. | Restore the text including the item list that has been remobed; modify item a) to include SAE authentication; restroe item b) | Counter | Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc | Counter. Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc |  |  | 165
4113 | Montemurro, Michael | Research in Motion | 8.4.1.2.1 | 98 | 65 | TR | Y | 98 | 65 | T | 8.4.1.2.1 | Security | S-Base |  | Dan | 11-10/726r3 | 20100715 | Closed | SAE should be an optional authentication method. | Replace the sentence beginning with "A STA wishing..." with "A STA wishing to perform Std IEEE 802.1X-2004 authentication shall chose Open System authentication. A STA wishing to perform secure password-based, or PSK, authentication shall choose SAE authentication or an alternate method of authentication with a PSK which also uses Open System authentication. It is recommended that SAE security be used since the alternatvie PSK method has security vulnerabilities. | Counter | Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc | Counter. Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc |  |  | 165
4114 | Montemurro, Michael | Research in Motion | 8.4.1.2.1 | 99 | 11 | TR | Y | 99 | 11 | T | 8.4.1.2.1 | Security | S-Base |  | Dan | 11-10/726r3 | 20100715 | Closed | SAE or the Alternative PSK method could be used for authentication. | Replace the changes to the sentence beginning with "SAE authentication provides…" with "SAE authentication and the alternative PSK authentication provide mutual authentication and derivation of a PMK. If Open System authentication is chosen instead, | Counter | Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc | Counter. Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc |  |  | 165
4115 | Montemurro, Michael | Research in Motion | 8.4.1.2.1 | 99 | 57 | TR | Y | 99 | 57 | T | 8.4.1.2.1 | Security | S-Base |  | Dan | 11-10/726r3 | 20100715 | Closed | It's the AP's Autheniticator which retains the PMK, not the AP. | Restore the modified text. | Counter | Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc | Counter. Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc |  |  | 165
4116 | Myles, Andrew | Cisco | 8.4.1.2.1 | 99 | 2 | TR | Y | 99 | 2 | T | 8.4.1.2.1 | Security | S-Base |  | Dan | 11-10/726r3 | 20100715 | Closed | The text states that "A STA wishing to perform secure password-based, or PSK, authentication shall choose SAE authentication." This has the effect of deprecating PSK, which is beyond the scope TGs. | Modify this "shall" so that the use of SAE is an option | Counter | Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc | Counter. Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc |  |  | 165
4117 | Myles, Andrew | Cisco | 8.4.1.2.2 | 99 | 2 | TR | Y | 99 | 2 | T | 8.4.1.2.2 | Security | S-Base |  | Dan | 11-10/726r3 | 20100715 | Closed | The test states, "A STA wishing to perform secure password-based, or PSK, authentication shall choose SAE authentication. An alternate method of authentication with a PSK which also uses Open System authentication has security vulnerabilities and should only be used if SAE authentication is not possible" However, these two sentence are contradictory is that teh first says SAE "shall" be used and teh second says alternate methods are allowed. It is also no clear when SAE authentication is "not possible" | Remove conradiction by making SAE an option | Counter | Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc | Counter. Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc |  |  | 165
4118 | Ptasinski, Henry | Broadcom | 8.1.3 | 78 | 26 | TR | Y | 78 | 26 | T | 8.1.3 | Security | S-Base |  | Dan | 11-10/726r3 | 20100715 | Closed | Normative changes to ESS behavior are out of scope. | Remove normative changes to ESS behavior. | Counter | Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc | Counter. Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc |  |  | 165
4119 | Ptasinski, Henry | Broadcom | 8.1.3 | 78 | 53 | TR | Y | 78 | 53 | T | 8.1.3 | Security | S-Base |  | Dan | 11-10/726r3 | 20100715 | Closed | Normative changes to IBSS behavior are out of scope. | Remove normative changes to IBSS behavior. | Counter | Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc | Counter. Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc |  |  | 165
4120 | Ptasinski, Henry | Broadcom | 8.4.1.2.1 | 99 | 2 | TR | Y | 99 | 2 | T | 8.4.1.2.1 | Security | S-Base |  | Dan | 11-10/726r3 | 20100715 | Closed | Normative changes to ESS behavior are out of scope. | Remove normative changes to ESS behavior. | Counter | Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc | Counter. Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc |  |  | 165
4121 | Ptasinski, Henry | Broadcom | 8.4.7 | 100 | 62 | TR | Y | 100 | 62 | T | 8.4.7 | Security | S-Base |  | Dan | 11-10/726r3 | 20100715 | Closed | Normative changes to IBSS behavior are out of scope. | Remove normative changes to IBSS behavior. | Counter | Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc | Counter. Resolved by the adoption of https://mentor.ieee.org/802.11/dcn/10/11-10-0726-03-000s-password-auth-comment-resolution.doc |  |  | 165
4162 | Stephenson, Dave | Cisco | 11.1.3.2.1 | 169 | 38 | ER | Y | 169 | 38 | E | 11.1.3.2.1 | General | G-Editor |  |  | 11-10/725r5 | 20100715 | Closed | The text shown in this paragraph does not accurately reflect the text from 802.11u-d8.0. Therefore, this text is incorrect. | Correct the baseline text in 11s-d6 to reflect 11u. | Accept |  | Accept. |  |  | 165
4163 | Stephenson, Dave | Cisco | Intro | iii | 12 | ER | Y | iii | 12 | E | Intro | General | G-Editor |  |  | 11-10/725r5 | 20100715 | Closed | The text states that the draft is based on IEEE P802.11-REVmb D3.01. The problem is that 802.11mb-d3.01 does not yet contain any of the 802.11p, 802.11z, 802.11v or 802.11u amendments. Because of this, the 11s draft can't be properly evaluated. | Base the text of 802.11s on the proper set of amendments. | Counter | Change the text to describe that this draft standard is based on 802.11-2007 revised by REVmb, including amendment by P802.11p, P802.11z, P802.11u, and P802.11v. | Counter. Change the text to describe that this draft standard is based on 802.11-2007 revised by REVmb, including amendment by P802.11p, P802.11z, P802.11u, and P802.11v. |  |  | 165
4164 | Stephenson, Dave | Cisco | 11.1.3.2.1 | 169 | 64 | TR | Y | 169 | 64 | T | 11.1.3.2.1 | MAC | M-PM |  | Jarkko | 11-10/848r3,858r2 | 20100715 | Closed | The text states "In an MBSS, STAs may not be awake at any given time and respond to probe requests." This is confusing. How can a STA that is not awake respond to a probe request? | Fix the text. | Counter | The text is contradistionary and should be improved. Change the text to read: "In an MBSS, STAs may not be awake at any given time to respond to probe requests." | Counter. The text is contradistionary and should be improved. Change the text to read: "In an MBSS, STAs may not be awake at any given time to respond to probe requests." |  |  | 165
4166 | Stephenson, Dave | Cisco | 5.2.13.5.7 | 10 | 11 | ER | Y | 10 | 11 | E | 5.2.13.5.7 | General | G-General |  |  | 11-10/725r5 | 20100715 | Closed | The text states "When a mesh STA tries to switch the operating channel …" is confusing. What does "try" mean in this context? | Delete the word "try". | Counter | Replace "tries to switch" with "switches". | Counter. Replace "tries to switch" with "switches". |  |  | 165
4167 | Stephenson, Dave | Cisco | 5.2.13.5.10 | 10 | 47 | ER | Y | 10 | 47 | E | 5.2.13.5.10 | RFI | R-MeshGate |  | Michael/Guenael | 11-10/897r1 | 20100715 | Closed | The section heading is "Interworking with external networks"; however the 802.11u amendment is already using this terminology. | Select different terminology that doesn't collide with existing amendments. | Counter | Change heading into "Interworking with the DS" see also CID 4141 | Counter. Change heading into "Interworking with the DS" see also CID 4141 |  |  | 165
4168 | Stephenson, Dave | Cisco | 5.4.1.1 | 11 | 50 | TR | Y | 11 | 50 | T | 5.4.1.1 | General | G-General |  | Guido | 11-10/868r0 | 20100715 | Closed | The text states "A mesh BSS can form an entire DS or a part of a DS using the WM, as shown in Figure s1 (Example MBSS containing mesh STAs, mesh gates, APs, and portals)." However, figure s1 shows the DS as distinct from a mesh DS. | Align the figure and the text. | Reject | Please see 802.11-2007 or 802.11REVmb 4.0. These documents describe the DS as a logical concept: "The architectural component used to interconnect infrastructure BSSs is the DS." The DS operates over the Distribution System Medium (DSM): "IEEE Std 802.11 logically separates the WM from the distribution system medium (DSM). Each logical medium is used for different purposes, by a different component of the architecture. The IEEE 802.11 definitions neither preclude, nor demand, that the multiple media be either the same or different." When APs use Ethernet (802.3) to interconnect, the Ethernet is used as one DSM. When APs interconnect through a mesh BSS, the mesh BSS works as the DSM for the APs. Figure s1 shows a mixture of DSMs. Two mesh BSSs, a non-802.11 LAN, and three infrastructure BSSs integrate. The mesh BSSs and the non-802.11 LAN may be used as a DSM. Through the Distribution System Media, two portals, and APs 13, 17, and 18, and mesh gates 1, 2, 8, and 9 interconnect. As a logical concept that spans between all of them, the DS integrates all of the aforementioned devices and their attached LANs into a single 802 LAN. Although we understand the desire of the commenter, we do not agree with the intention of the comment. Since the DS is a logical concept that works over the DSM the picture shows only one potential point of view. | Reject. Please see 802.11-2007 or 802.11REVmb 4.0. These documents describe the DS as a logical concept: "The architectural component used to interconnect infrastructure BSSs is the DS." The DS operates over the Distribution System Medium (DSM): "IEEE Std 802.11 logically separates the WM from the distribution system medium (DSM). Each logical medium is used for different purposes, by a different component of the architecture. The IEEE 802.11 definitions neither preclude, nor demand, that the multiple media be either the same or different." When APs use Ethernet (802.3) to interconnect, the Ethernet is used as one DSM. When APs interconnect through a mesh BSS, the mesh BSS works as the DSM for the APs. Figure s1 shows a mixture of DSMs. Two mesh BSSs, a non-802.11 LAN, and three infrastructure BSSs integrate. The mesh BSSs and the non-802.11 LAN may be used as a DSM. Through the Distribution System Media, two portals, and APs 13, 17, and 18, and mesh gates 1, 2, 8, and 9 interconnect. As a logical concept that spans between all of them, the DS integrates all of the aforementioned devices and their attached LANs into a single 802 LAN. Although we understand the desire of the commenter, we do not agree with the intention of the comment. Since the DS is a logical concept that works over the DSM the picture shows only one potential point of view. |  |  | 165
4169 | Stephenson, Dave | Cisco | 5.4.3.1 | 12 | 9 | TR | Y | 12 | 9 | T | 5.4.3.1 | General | G-Editor |  |  | 11-10/725r5 | 20100715 | Closed | Open authentication is not defined. | Change to "Open system authentication" | Accept |  | Accept. |  |  | 165

## Statistics
Overall Summary | Total | LB147 | LB159 | LB161 | LB165
Total Comments: | 77 | 38 | 0 | 12 | 27
Editorial Comments: | 8 | 3 | 0 | 1 | 4
Technical Comments: | 69 | 35 | 0 | 11 | 23
Total Comments: | 77 | 38 | 0 | 12 | 27
General | 19 | 11 | 0 | 3 | 5
MAC | 20 | 10 | 0 | 9 | 1
RFI | 4 | 3 | 0 | 0 | 1
Security | 34 | 14 | 0 | 0 | 20
G-Architecture | 2 | 2 | 0 | 0 | 0
G-Def | 1 | 1 | 0 | 0 | 0
G-Editor | 5 | 2 | 0 | 0 | 3
G-Frame | 9 | 6 | 0 | 3 | 0
G-General | 2 | 0 | 0 | 0 | 2
M-CC | 1 | 1 | 0 | 0 | 0
M-CS | 1 | 0 | 0 | 1 | 0
M-MCCA | 4 | 2 | 0 | 2 | 0
M-General | 2 | 2 | 0 | 0 | 0
M-PM | 7 | 3 | 0 | 3 | 1
M-QoS | 3 | 0 | 0 | 3 | 0
M-QoSSTA | 2 | 2 | 0 | 0 | 0
R-LM | 2 | 2 | 0 | 0 | 0
R-MeshGate | 1 | 0 | 0 | 0 | 1
R-Portal | 1 | 1 | 0 | 0 | 0
S-Base | 20 | 0 | 0 | 0 | 20
S-General | 6 | 6 | 0 | 0 | 0
S-IPR | 1 | 1 | 0 | 0 | 0
S-SAE | 7 | 7 | 0 | 0 | 0
Total: | 77 | 38 | 0 | 12 | 27

## Rev. History
Revisision | Date | Notes / Summary of Changes
r0 | 2010-07-15 | Initial revision
r0 | 2010-07-15 | Statistics are calculated