## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: 11-10/1051r5
Venue Date: | September 2010
First Author: | Michael Montemurro, Research in Motion
Subject: | Resolution of comments received during Internal Review of D0.01
Full Date: | 2010-09-13
Author(s): | Michael Montemurro
Research in Motion
Mississauga, ON. Canada
email: mmontemurro@rim.com
Abstract:
This spreadsheet is a working document showing comments and resolutions from the TGae Task Group internal review.

## TGae D0.01 Review Comments
Project # P802.11ae/D0.01, Internal Comment Resolution
CID | Name or person submitting comment, (by Editor) | Clause Number. Provided by Commenter. | Page Number. Provided by Commenter. | Line Number. Provided by Commenter. | Type of Comment (T) Technical, (E) Editorial. Provided by Commenter. | Comment | Proposed Change | Resolution | Comment Group Number | Technical Issue Number | Addressed in Draft | Major Clause | Notes
1 | Michael Montemurro | General |  |  | E | Need to update clause numbers to conform with 11mbD5.0 | As in comment. | Accept. |  |  | 0.02
2 | Michael Montemurro | General |  |  | E | We probably don't want to number the body of the draft using roman numerals. | Change page numbering as needed. | Accept. |  |  | 0.03 |  | Assigned to Henry
3 | Michael Montemurro | General |  |  |  | Change all references to "multicast" to "group addressed" | As in comment. | Accept in principle. Change the Broadcast/Multicast to Group Addressed. Change unicast to individually addressed. Change figures as appropriate. |  |  | 0.03 |  | Assigned to Henry
4 | Michael Montemurro | General |  |  | T | There are no MLME primitives. | We might need to add some | Accept with submission of 11-10/1140r0 |  |  |  |  | Submission Required. Mike
5 | Michael Montemurro | General |  |  | T | Missing Annex D | Add one and define mib variables used in this draft. | Reject. The definition exists.
6 | Michael Montemurro | General |  |  | T | Default Management frame priorities missing | Add default management frame priorities. | Accept |  |  |  |  | Submission Required. Document 11-10/997r2 by Santosh.
7 | Santosh Pandey | General |  |  | T | Technical clarifications to MFQ are required. | Incorporate changes given in document 11-10/997r1. | Accept |  |  |  |  | Submission Required. Document 11-10/997r2 by Santosh.
8 | Mark Hamilton | General | NA | NA | T | I think this has already been agreed, but just to be sure: simplify dot11MgmtFrameQoSPolycActivated, dot11MFQImplemented and dot11MFQEnabled into a single MIB attribute (dot11MFQImplemented). Or, if there is a clear need to enable/disable this feature via external management, a dot11MFQActivated could be used, but I don't see the need for that, and the PICS would imply this is not meant to be turned off. | Change the text to just use dot11MFQImplemented. | Accept |  |  |  |  | Submission Required. Document 11-10/997r2 by Santosh.
9 | Mark Hamilton | A.4.3 | xxvi | 0 | T | Really? This feature is magically now required of all QoS (etc) STAs, including the existing ones? I don't think you can do that. Also, I think CF15 (use of the 3GHz band) is not what you meant, and I'm not sure what it was that was meant. | Change the PICS statement for TGae to be 'O'. Fix the CF depdendcies for this feature. | Accept |  |  |  |  | Submission Required. Document 11-10/997r3 by Santosh.
10 | Matthew Fischer | 9.1.3.1 | xxi | 34 | T | added sentence is not quite formal enough | Change "If dot11MgmtFrameQoSPolicyActivated is true for a STA, the STA shall send management frames as described in 11.24.2 (Managmement frame QoS policy configuration procedures)." to "If dot11MgmtFrameQoSPolicyActivated is true for a STA, the STA shall send each management frame using an access category as determined by the rules in 11.24.2 (Managmement frame QoS policy configuration procedures)." | Accept in Principle. Change the sentence to: "If dot11MgmtFrameQoSPolicyActivated is true for a STA, the STA shall send each management frame using an access category as described in 11.24.2 (Managmement frame QoS policy configuration procedures)." |  |  | 3
11 | Mark Hamilton | 9.1.3.1 | xxi | 10 | T | The text references a subclause called "Management Frame QoS Policy configuration procedures" to define how an MFQ STA sends management frames. (The subclause reference, like many others, has an explicit number, but the draft only has "ae1-style" placeholders, by the way. I assume this is a reference to 11.ae1.2. These need to be corrected.) But, that subclause isn't really very defniitive about how management frames are transmitted. The previous subclause would be a better reference. | Refer to "Management Frame QoS implementation dependencies" instead. | Accept |  |  |  |  | Submission required. Document 11-10/997r3 by Santosh.
12 | Mark Hamilton | 7.4.ae1.5 | xx | 10 | T | There is no Dialog Token in the MFQ Policy Config Delete frame. | Detele the paragraph describing the Dialog Token. | Accept.
13 | Mark Hamilton | 7.4.ae1.4 | xx | 2 | T | (This really applies to 11.ae1.2.3, but this is the first occurance.) Current text in Notes for 'Reject' Status Code says, "… and the requesting STA shall not retry the same request." I assume this applies only to the same requested STA. And, does it have any time function, or is this forever? It appears (from 11.ae1.2.3) that Config Request/Response happens only within the context of an association - how about for the lifetime of the association? | Change last phrase to, "… and the requesting STA shall not retry the same request within the lifetime of the association between the requesting and responding STAs." | Accept in principle. |  |  |  |  | Submission required. Santosh to create a separate submission.
14 | Michael Montemurro | 7.4.3.ae1 | 15 | 1 | T | It would be good to add a cross-reference to a normative clause. | Add the following sentence to the paragraph before the sentence beginning with See Figure….: "The use of the Mangament Frame QoS Policy element is given in clause 11.ae1. | Accept in Principle. Make the change on page xv, line 3, 7.3.2.ae1 of draft 0.01. |  |  | 0.03
15 | Michael Montemurro | 7.4.121 | 17 | 3 | T | I believe we would want Management Frame QoS Policy to be a Public Action frame, not just an Action frame. | Move this clause under the Public Action Frame clause and create a parallel clause in the "Protected dual of public action" clause. | Accept |  |  |  |  | Submission required. Santosh.
16 | Matthew Fischer | 7.3.2.ae1.1 | xvi | 8 | T | Group decided that MCAST MGMT frames would not be subject to modified priority. I.e. MCAST MGMT frames should be transmitted using default baseline priority of AC_VO. | Remove all references to MCAST field "M" in this subclause - change M bit in priority definition field to reserved. | Accept in principle |  |  |  |  | Submission required. TBD. Matt/Santosh.
17 | Michael Montemurro | 7.3.2.ae1.1 | 15 | 10 | T | All references in this subclause to TID should be actually AC. | Replace TID with AC throughout this clause, and anywhere else in the draft where appropriate. | Acceot |  |  | 0.03 |  | Submission required. Henry.
18 | Michael Montemurro | 7.3.2.ae1.1 | 16 | 5 | T | I don't believe we need Multicast as part of the MFQ policy | Make B3 reserved and remove the paragraph on lines 5-6. | Accept |  |  |  |  | Same as comment 16.
19 | Michael Montemurro | 7.3.2.27 | 15 | 1 | T | Do we really need MFQCapability? | If not, remove it. | Accept |  |  |  |  | Submission required. Document 11-10/997r2 by Santosh.
20 | Michael Montemurro | 7.3.2.27 | 15 | 1 | T | MFQImplemented would be set when dot11MFQImplemented is set to true. | Replace the description with "Set to 1 when dot11MFQImplemented is set to true. Otherwise set to 0. | Accept.
21 | Mark Hamilton | 7.2.3.9 | xiv | 1 | T | The MFQ Policy element needs only be present in Probe Responses if the probing STA is MFQ capable. The probing STA signals this through the Extended Capabilities element and the new MFQ bit(s) there. | Add to the end of the Notes, "… and the MFQ capability bit is set in the Extended Capabilities element in the associated Probe Request frame." | Accept in Principle. |  |  |  |  | Submission required. Document 11-10/997r2 by Santosh.
22 | Mark Hamilton | 7.2.3.6 | xiii | 9 | E | In the Notes of Table 7-12, an "is" is missing. | Change to "… if dot11MgmtFrameQoSPolicyActivated is true …" | Accept. |  |  | 0.03
23 | Mark Hamilton | 7.2.3.6 | xiii | 9 | E | This table is for Reassociation. The "Re" got lost in a couple places. | Change "Association Request" and "Association Response" to say "Reassociation" | Accept. |  |  | 0.03
24 | Mark Hamilton | 7.2.3.5 | xiii | 7 | E | In the Notes of Table 7-11, an "is" is missing. | Change to "… if dot11MgmtFrameQoSPolicyActivated is true …" | Accept. |  |  | 0.03
25 | Yongho Seok | 7.1.3.4.1 | xii | When the Sequence control 21-22 | T | When the IMFQ frame is encrypted, the sequence number field of AAD Construction is masked to 0. Access Category field of the sequence number field shall not be masked to 0. Also, the priority field of Nonce Construction shall be set to Access Category field of sequence number field of IMFQ frame. | AAD Construction and Nonce Construction for IMFQ frame shall be changed as the comment. | Accept with submission of 11-10/1142r0 |  |  | 0.03 |  | Jouni to investigate.
26 | Michael Montemurro | 7.1.3.4.1 | 12 | 14 | T | Just checking, is it "dot11MFQImplemented" or "dot11MFQActivated" | Change as appropriate. | Accept in principle |  |  |  |  | Submission required. Document 11-10/997r2 by Santosh.
27 | Mark Hamilton | 7.1.3.4.1 | xii | 7 | E | Typo | Change "of" to "as" | Accept. |  |  | 0.03
28 | Mark Hamilton | 7.1.3.4.1 | xii | 16 | E | Wording is confusing. | Change phrase to, "the most recently received Extended Capability Information element from the STA corresponding to the RA of the frame to be transmitted indicated that the RA STA is a QoS STA and has the value of 1 in the MFQImplemented field." | Accept in Principle. Change "RA STA" to "the STA whose MAC address matches the RA" |  |  | 0.03
29 | Mark Hamilton | 7.1.3.4.1 | xii | 22 | E | This figure is really confusing, since it is a 12-bit field within the 16-bit field, and B0 is really B4. It would be better to show the entire 16-bit field, for clarity | Change Figure 7-1ae1 to be a 16-bit field, "Sequence Control field in IMFQ frames", and show the full 16-bit field including the Fragment Number | Accept in Principle. Number the bit fields from B4 to B15, and change the name to Sequence Number Sub-field. |  |  | 0.03
30 | Michael Montemurro | 6.1.1.0a | 12 | 3 | T | Only QoS STA's that support MFQ differentiate MMPDU delivery | Change "QoS STA's differentiate" to "QoS STA's that support MFQ differentiate". | Accept. |  |  | 0.03
31 | Mark Hamilton | 6.1.1.0a | xii | 4 | T | MMPDU priority is independent of BSS membership status, yes, but it is dependent on the negotiated policy with the receiving STA. | Add to the end of the last sentence of 6.1.1.0a, ", and based on the MFQ policy negotiated with the receiving STA." | Accept in Principle. Add the folliwing sentence at the end of the paragraph: "Differentiation is based on the current MFQ policy at the transmitting STA." |  |  | 0.03
32 | Mark Hamilton | 5.4.5.ae1 | Xi | 21 | T | Two points: 1) an MFQ STA only applies these new rules to management frame transmissions to destination STAs that are known to be MFQ STAs also; 2) MFQ policies are actually negotiated between the communicating STAs through the Query/Config methods, since this is introductory text, it is useful to describe this as a negotiation, I think. | Change sentence to, "A QoS STA that supports MFQ transmits management frames to another MFQ STA at priorities as defined by the MFQ policy configured on that STA negotiated between the STAs." | Accept in Principle. Change the sentence to "A QoS STA that supports MFQ transmits management frames to another STA that supports MFQ at priorities as defined by the MFQ policy negotiated between the STAs or at priorities as defined by the default MFQ policy when no negotiation has been completed between the STAs." Delete from "Generally" to the end of the paragraph. |  |  | 0.03
33 | Matthew Fischer | 11.ae1.3 | xxv | 16 | T | Language needs clarifying edits | Make changes as indicated for this subclause in doc 11-10-0972r0. | Accept |  |  |  |  | Submission required. Document 11-10/997r2 by Santosh.
34 | Matthew Fischer | 11.ae1.3 | xxv | 29 | T | Which subfield? | Clarify the reference for the instance of "This subfield" | Accept |  |  |  |  | Submission required. Document 11-10/997r2 by Santosh.
35 | Mark Hamilton | 11.ae1.3 | xxiv | 38 | E | Formatting details like zero padding belong in the (former) clause 7. | Move the sentence, "This subfield is zero padded to complete any incomplete octet." to subclause 7.3.2.ae1.1. | Accept |  |  |  |  | Submission required. Document 11-10/997r3 by Santosh.
36 | Mark Hamilton | 11.ae1.3 | xxiv | 40 | E | Clarity that this is another option, in addition to the options just described at length. | Add "also" to the last sentence of this paragraph: "The Priority Definition Field also may be used to indicate priority of a single management frame." | Accept. |  |  | 0.03
37 | Mark Hamilton | 11.ae1.2.4 | xxiv | 21 | T | The delete procedure needs to delete all configuration done by either end of the pair, or this gets really confusing, and implementations get complicated. Also, to say that policy configuration changes were done by using the MFQ policy configuration mechanism is redundant. | Change the second sentence of this subclause by replacing "requested by the requesting STA" with "negotiated between the STAs". Delete the phrase "… using the MFQ policy configuration mechansim" through to the end of the sentence. In the last setence (last line), replace "sent by the responding STA" to "exchanged by the STAs, per 11.ae1.2.1 or 11.ae1.2.2." | Accept in principle. Make the changes with the exception of adding ", per 11.ae1.2.1 or 11.ae1.2.2". |  |  | 0.03
38 | Matthew Fischer | 11.ae1.2.3 | xxiv | 36 | T | language needs clarification - in particular, what happens when expected responses do not occur? What happens in case of a transmitted request without a subsequent response? How long does a STA wait for a response? What does it do after waiting for the response for that time? | Make changes as indicated for this subclause in doc 11-10-0972r0. | Accept. |  | Discuss |  |  | Submission required. Document 11-10/997r3 by Santosh.
39 | Matthew Fischer | 11.ae1.2.3 | xxiv | 51 | T | The sentence says "associated" - but we are talking about IBSS - what gives? | Clarify what is supposed to happen. Are STAs in infrastructure supposed to be sending these things or not? Earlier language said no - this language contradicts the earlier language. Clarify and eliminate the contradiction. See also lines mentioning actions on the part of the AP. | Accept in Principle. |  | Discuss |  |  | Submission required. Document 11-10/997r3 by Santosh.
40 | Mark Hamilton | 11.ae1.2.3 | xxiv | 11 | E | Missing "the" | Insert "the" : "… then the configuration change is rejected." | Accept. |  | Discuss | 0.03 |  | Propose Accept
41 | Mark Hamilton | 11.ae1.2.3 | xxiv | 15 | E | A STA sending a configuration request to its AP is non-specific. | Change "The" to "An" : "An assocaited MFQ STA may send …" | Accept |  | Discuss | 0.03 |  | Propose Accept
42 | Mark Hamilton | 11.ae1.2.3 | xxiv | 13 | T | See the comment on subclause 7.4.ae1.4, about the duration of the prohibition to try a configuration change request again. | Make a parallel change to the changes (if any) in 7.4.ae1.4. | Accept in Principle. Config reject frame has been deleted. |  | Discuss |  |  | Submission required. Document 11-10/997r3 by Santosh. See CID 13
43 | Matthew Fischer | 11.ae1.2.2 | xxiv | 26 | T | If an MFQ STA that receives an MFQ Policy Query Request does not have the policy, then WHAT? | Add behavior for case discussed. | Reject. An MFQ STA always has a policy. It will at least have the default policy. |  | Discuss
44 | Matthew Fischer | 11.ae1.2.2 | xxiv | 26 | T | language needs clarification | Make changes as indicated for this subclause in doc 11-10-0972r0. | Accept |  | Discuss |  |  | Propose Accept
45 | Matthew Fischer | 11.ae1.2.2 | xxiv | 26 | T | Why is this information not available in the beacon? And what if there is a mixed IBSS where some of the STAs are MFQ and some are not? Why would both MFQ STAs not already have a copy of the policy? Doesn’t a STA that is new to the IBSS adopt the existing policy at join time from the older members of the IBSS? So how can there be a question about a STA having the policy or not? Which STA has precedence when there is more than one policy floating around, or, if this is done correctly, then should this case never arise? | Provide clear answers to the questions and modify the behavior according to the answers. See for example, the giant table in 10.3.2.2.2 and the behavorial requirements found in 11.1.4 | Accept in Principle. |  | Discuss |  |  | There is no MFQ policy advertised in the IBSS beacon. STA's would use the default MFQ policy and could modify the policy using Policy Config Request/Response on a per-link basis. Santosh to address this comment in Document 11-10/997r3.
46 | Matthew Fischer | 11.ae1.2.1 | xxiii | 49 | T | missing complete case coverage | The text in this first paragraph does not cover all cases. Make it cover all cases. Describe what should happen in all cases. | Accept |  | Discuss |  |  | Submission required. Document 11-10/997r3 by Santosh.
47 | Matthew Fischer | 11.ae1.2.1 | xxiv | 1 | T | language is not precise | Make changes as indicated for this subclause in doc 11-10-0972r0. | Accept in Principle |  | Discuss |  |  | Submission required. Document 11-10/997r3 by Santosh.
48 | Matthew Fischer | 11.ae1.2.1 | xxiii | 49 | T | What about STA-STA IMFQ transmissions? | Please clarify the rules for transmission of STA-STA IMFQ frames. | Accept in Principle. |  | Discuss |  |  | Submission required. Document 11-10/997r3 by Santosh.
49 | Mark Hamilton | 11.ae1.2.1 | xxiii | 20 | T | The first contact for a STA with an AP might be via a Probe Request/Response. | Change the first sentence of this paragraph to, "Aps advertise the partial management frame QoS policy in Beacon frames, and the complete management frame QoS policy is in Probe Responses." Change all the rest of the sentences in this paragraph and the next paragraph, to add "or Probe Response" everywhere it says "Beacon frame". | Accept. |  | Discuss |  |  | Submission required. Document 11-10/997r3 by Santosh.
50 | Mark Hamilton | 11.ae1.2.1 | xxiii | 32 | T | The three bullets here leave it unspecified what happens to multicast management frames that do not cross multiple ESSs. I'm not sure what it even means for a frame to be "across multiple ESS" - is this supposed to be multiple BSS, perhaps? I think recent discussion has concluded that all multicast management frames will use legacy methods, anyway. | Change this third bullet to say, "All multicast management frames shall be transmitted at AC_VO priority." | Accept in principle. Change the sentence to "All group addressed management frames shall be transmitted at the default MFQ policy. See Table 10-ae2." |  | Discuss |  |  | Discussion
51 | Michael Montemurro | 11.ae1.2 | 23 | 9 | E | Remove "to each other" from the end of the last sentence. It isn't needed. | As in comment. | Accept. |  |  | 0.03
52 | Matthew Fischer | 11.ae1.1 | xxiii | 24 | T | wrong verb | change "transmit" to "assign an Access Category to each" - change "frames" to "frame" - change "priorities" to "priority assignments" | Accept in Principle. |  |  |  |  | Submission required. Document 11-10/997r3 by Santosh.
53 | Matthew Fischer | 11.ae1.1 | xxiii | 35 | T | wrong adjective | change "definition of different management frames" to "assignments of different management frames" | Accept.
54 | Mark Hamilton | 11.ae1.1 | xxii | 32 | E | Recommend a slight reorganization of this subclause and the next. Have one sub-clause that says how management frames are transmitted, based on the currently configured MFQ policy. Have a seaprate sub-clause, exclusively for how the MFQ policy is configured and reconfigured. | Rename 11.ae1.1 to delete the word "dependencies" (this has more than just the dependencies, anyway). Move the second sentence of 11.ae1.2 to 11.ae1.1. (Actually, this sentence seems to be redundant, and could just be deleted, instead.) Move lines 27-32 of 11.ae1.2.1 to 11.ae1.1, as an "ESS case" paragraph. Move the last sentence of 11.ae1.2.2, first paragraph to 11.ae1.1, as an "IBSS case" paragraph. Move the last sentence of 11.ae1.2.2 (a standalone paragraph) to 11.ae1.2.1. Change language in 11.ae1.2 and its subclauses to say things to the effect of "the MFQ policy is configured to be x" rather than talking about how management frames are sent. Let 11.ae1.1 say that management frames are sent, according to the current policy. | Reject. This change requires a submission. No submission has been submitted. |  |  |  |  | Needs a submission.
55 | Mark Hamilton | 11.ae1.1 | xxii | 33 | E | First sentence of this subcluase is redundant and circular, given the definition of MFQ STA. | Delete the first sentence of the subclause. | Accept.
56 | Mark Hamilton | 11.ae1.1 | xxii | 38 | T | Use normative language in this subclause, to set the requirements for the format defined in (former) clause 7. | Change "is" to "shall be" | Accept.
57 | Mark Hamilton | 11.ae1.1 | xxiii | 3 | T | What does this sentence mean: "The specific priority definition of different management frames within a MFQ policy is beyond the scope of this document."? Is this trying to say that the choice of the priority is beyond the scope? | Clarify this sentence. | Accept in Principle. See CID 53.
58 | Michael Montemurro | 11.a2.2.4 | 24 | 18 | T | When MFQ Policy Configuration is used, I believe we need a token to identify the policy config request to the appropriate policy can be deleted. | Define a policy identifier and add it to the MFQ Policy Config Request/Response/Delete frame definitions. The initiating STA would set the Policy identifier (which would have to be unique for the STA pair). | Accept in Principle. The Config Delete frame has been removed so the policy is simply overwritten. |  |  |  |  | Submission required. Document 11-10/997r3 by Santosh.
1.01
1.01
1.01
1.01
1.01
1.02
1.01
1.02
1.01
1.02
1.02
1.01
1.02
1.02
1.02
1.02
1.02
1.02
1.01
1.03
1.01
1.03
1.03
1.02
1.02
1.03
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.02
1.01
1.02
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.02
1.02
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.02
1.02
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.02
1.02
1.02
1.02
1.02
1.02
1.02
1.02
1.02
1.02
1.02
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
1.01
755 | [10 empty] | 1.01
756 | [10 empty] | 1.01
757 | [10 empty] | 1.01
758 | [10 empty] | 1.01
759 | [10 empty] | 1.01
760 | [10 empty] | 1.01
761 | [10 empty] | 1.01
762 | [10 empty] | 1.01
763 | [10 empty] | 1.01
764 | [10 empty] | 1.01
765 | [10 empty] | 1.01
766 | [10 empty] | 1.01
767 | [10 empty] | 1.01
767 | [10 empty] | 1.01
768 | [10 empty] | 1.01
769
770
771 | [10 empty] | 1.01
772 | [10 empty] | 1.01
773 | [10 empty] | 1.01
774 | [10 empty] | 1.01
775 | [10 empty] | 1.01
776 | [10 empty] | 1.01
777 | [10 empty] | 1.01
778 | [10 empty] | 1.01
779 | [10 empty] | 1.01
780 | [10 empty] | 1.01
781 | [10 empty] | 1.01
782 | [10 empty] | 1.01
783 | [10 empty] | 1.01
784 | [10 empty] | 1.01
785 | [10 empty] | 1.01
786 | [10 empty] | 1.01
787 | [10 empty] | 1.01
788 | [10 empty] | 1.01
789 | [10 empty] | 1.01
790 | [10 empty] | 1.01
791 | [10 empty] | 1.01
792 | [10 empty] | 1.01
793 | [10 empty] | 1.01
794 | [10 empty] | 1.01
795 | [10 empty] | 1.01
796 | [10 empty] | 1.01
797 | [10 empty] | 1.02
798 | [10 empty] | 1.02
799 | [10 empty] | 1.02
800 | [10 empty] | 1.02
801
802 | [10 empty] | 1.02
803 | [10 empty] | 1.02
804 | [10 empty] | 1.02
805 | [10 empty] | 1.02
806 | [10 empty] | 1.01
807 | [10 empty] | 1.01
808
809 | [10 empty] | 1.01
810 | [10 empty] | 1.01
811 | [10 empty] | 1.01
812 | [10 empty] | 1.01
813 | [10 empty] | 1.01
814 | [10 empty] | 1.01
815
816 | [10 empty] | 1.01
817 | [10 empty] | 1.01
818 | [10 empty] | 1.01
819 | [10 empty] | 1.01
820 | [10 empty] | 1.01
821 | [10 empty] | 1.01
822 | [10 empty] | 1.01
823 | [10 empty] | 1.01
824 | [10 empty] | 1.01
825 | [10 empty] | 1.01
826 | [10 empty] | 1.01
827 | [10 empty] | 1.01
828 | [10 empty] | 1.01
829 | [10 empty] | 1.01
830 | [10 empty] | 1.01
831 | [10 empty] | 1.01
832 | [10 empty] | 1.01
833
834 | [10 empty] | 1.01
835 | [10 empty] | 1.01
836 | [10 empty] | 1.01
837 | [10 empty] | 1.01
838 | [10 empty] | 1.01
839 | [10 empty] | 1.01
840 | [10 empty] | 1.01
841 | [10 empty] | 1.01
842 | [10 empty] | 1.02
843 | [10 empty] | 1.02
844 | [10 empty] | 1.02
845 | [10 empty] | 1.02
846 | [10 empty] | 1.02
847 | [10 empty] | 1.01
848 | [10 empty] | 1.02
849 | [10 empty] | 1.02
850 | [10 empty] | 1.02
851 | [10 empty] | 1.02
852 | [10 empty] | 1.02
853 | [10 empty] | 1.01
854 | [10 empty] | 1.03
855 | [10 empty] | 1.01
856 | [10 empty] | 1.01
857 | [10 empty] | 1.01
858 | [10 empty] | 1.01
859 | [10 empty] | 1.01
860 | [10 empty] | 1.01
861 | [10 empty] | 1.01
862 | [10 empty] | 1.01
863 | [10 empty] | 1.01
864 | [10 empty] | 1.01
865 | [10 empty] | 1.01
866 | [10 empty] | 1.01
867 | [10 empty] | 1.01
868 | [10 empty] | 1.01
869 | [10 empty] | 1.01
870 | [10 empty] | 1.01
871 | [10 empty] | 1.01
872 | [10 empty] | 1.01
873 | [10 empty] | 1.01
874 | [10 empty] | 1.01
875 | [10 empty] | 1.01
876 | [10 empty] | 1.01
877 | [10 empty] | 1.01
878 | [10 empty] | 1.01
879 | [10 empty] | 1.01
880 | [10 empty] | 1.01
881 | [10 empty] | 1.01
882 | [10 empty] | 1.01
883 | [10 empty] | 1.02
884 | [10 empty] | 1.01
885 | [10 empty] | 1.01
886 | [10 empty] | 1.01
887 | [10 empty] | 1.01
888 | [10 empty] | 1.01
889 | [10 empty] | 1.01
890 | [10 empty] | 1.01
891 | [10 empty] | 1.01
892 | [10 empty] | 1.01
893 | [10 empty] | 1.01
894 | [10 empty] | 1.01
895
896 | [10 empty] | 1.01
897 | [10 empty] | 1.01
898 | [10 empty] | 1.01
899 | [10 empty] | 1.01
900
901 | [10 empty] | 1.01
902 | [10 empty] | 1.01
903 | [10 empty] | 1.01
904 | [10 empty] | 1.01
905 | [10 empty] | 1.01
906 | [10 empty] | 1.01
907 | [10 empty] | 1.01
908 | [10 empty] | 1.01
909 | [10 empty] | 1.01
910 | [10 empty] | 1.01
911 | [10 empty] | 1.02
912 | [10 empty] | 1.02
913 | [10 empty] | 1.01
914 | [10 empty] | 1.02
915 | [10 empty] | 1.02
916 | [10 empty] | 1.02
917 | [10 empty] | 1.02
918 | [10 empty] | 1.02
919 | [10 empty] | 1.02
920 | [10 empty] | 1.02
921 | [10 empty] | 1.02
922 | [10 empty] | 1.02
923 | [10 empty] | 1.02
924 | [10 empty] | 1.01
925 | [10 empty] | 1.01
926 | [10 empty] | 1.01
927 | [10 empty] | 1.01
928 | [10 empty] | 1.01
929
930 | [10 empty] | 1.01
931 | [10 empty] | 1.01
932 | [10 empty] | 1.03
933 | [10 empty] | 1.01
934 | [10 empty] | 1.01
935 | [10 empty] | 1.01
936 | [10 empty] | 1.01
937 | [10 empty] | 1.01
938 | [10 empty] | 1.01
939 | [10 empty] | 1.01
940 | [10 empty] | 1.01
941 | [10 empty] | 1.01
942 | [10 empty] | 1.01
943 | [10 empty] | 1.01
944 | [10 empty] | 1.02
945 | [10 empty] | 1.01
946 | [10 empty] | 1.02
947 | [10 empty] | 1.02
948 | [10 empty] | 1.03
949 | [10 empty] | 1.01
950 | [10 empty] | 1.01
951
952 | [10 empty] | 1.01
953 | [10 empty] | 1.01
954 | [10 empty] | 1.01
955 | [10 empty] | 1.01
956 | [10 empty] | 1.01
957 | [10 empty] | 1.01
958 | [10 empty] | 1.01
959 | [10 empty] | 1.02
960 | [10 empty] | 1.01
961 | [10 empty] | 1.01
962 | [10 empty] | 1.01
963 | [10 empty] | 1.02
964 | [10 empty] | 1.02
965 | [10 empty] | 1.02
966 | [10 empty] | 1.02
967 | [10 empty] | 1.01
968 | [10 empty] | 1.01
969 | [10 empty] | 1.01
970 | [10 empty] | 1.01
971 | [10 empty] | 1.01
972 | [10 empty] | 1.03
973 | [10 empty] | 1.02
974 | [10 empty] | 1.02
975 | [10 empty] | 1.01
976 | [10 empty] | 1.01
977 | [10 empty] | 1.01
978 | [10 empty] | 1.01
979 | [10 empty] | 1.02
980 | [10 empty] | 1.01
980 | [10 empty] | 1.02
982 | [10 empty] | 1.01
983 | [10 empty] | 1.02
984 | [10 empty] | 1.01
985 | [10 empty] | 1.02
986 | [10 empty] | 1.02
987 | [10 empty] | 1.01
988 | [10 empty] | 1.01
989 | [10 empty] | 1.01
990 | [10 empty] | 1.01
991
992 | [10 empty] | 1.01
993 | [10 empty] | 1.01
994 | [10 empty] | 1.01
995
996 | [10 empty] | 1.01
997 | [10 empty] | 1.01
998 | [10 empty] | 1.01
999 | [10 empty] | 1.01
1000 | [10 empty] | 1.02
1001 | [10 empty] | 1.01
1002 | [10 empty] | 1.01
1003 | [10 empty] | 1.01
1004 | [10 empty] | 1.02
1005 | [10 empty] | 1.01
1006 | [10 empty] | 1.02
1007 | [10 empty] | 1.02
1008
1009 | [10 empty] | 1.01
1010
1011
1012 | [10 empty] | 1.03
1013 | [10 empty] | 1.03
1014
1015 | [10 empty] | 1.02
1016 | [10 empty] | 1.02
1017 | [10 empty] | 1.02
1018 | [10 empty] | 1.02
1019 | [10 empty] | 1.02
1020 | [10 empty] | 1.02
1021 | [10 empty] | 1.02
1022 | [10 empty] | 1.02
1023 | [10 empty] | 1.02
1024
1025 | [10 empty] | 1.01
1026 | [10 empty] | 1.01
1027 | [10 empty] | 1.01
1028 | [10 empty] | 1.03
1029
1030
1031 | [10 empty] | 1.01
1032 | [10 empty] | 1.02
1033 | [10 empty] | 1.01
1034 | [10 empty] | 1.01
1035 | [10 empty] | 1.01
1036 | [10 empty] | 1.01
1037 | [10 empty] | 1.03
1038 | [10 empty] | 1.01
1039
1040 | [10 empty] | 1.01
1041 | [10 empty] | 1.01
1042 | [10 empty] | 1.02
1043 | [10 empty] | 1.01
1044
1045 | [10 empty] | 1.01
1046 | [10 empty] | 1.01
1047 | [10 empty] | 1.01
1048
1049 | [10 empty] | 1.01
1050 | [10 empty] | 1.01
1051 | [10 empty] | 1.01
1052 | [10 empty] | 1.01
1053 | [10 empty] | 1.01
1054 | [10 empty] | 1.01
1055 | [10 empty] | 1.01
1056 | [10 empty] | 1.02
1057
1058 | [10 empty] | 1.01
1059 | [10 empty] | 1.01
1060
1061
1062 | [10 empty] | 1.01
1063 | [10 empty] | 1.01
1064 | [10 empty] | 1.01
1065
1066
1067
1068 | [10 empty] | 1.01
1069
1070 | [10 empty] | 1.02
1071
1072 | [10 empty] | 1.01
1073 | [10 empty] | 1.01
1074 | [10 empty] | 1.02
1075 | [10 empty] | 1.02
1076 | [10 empty] | 1.01
1077
1078 | [10 empty] | 1.01
1079 | [10 empty] | 1.01
1080 | [10 empty] | 1.02
1081
1082 | [10 empty] | 1.01
1083 | [10 empty] | 1.01
1084 | [10 empty] | 1.01
1084
1085 | [10 empty] | 1.01
1085
1086 | [10 empty] | 1.01
1087 | [10 empty] | 1.01
1090 | [10 empty] | 1.01
1091 | [10 empty] | 1.01
1092
1093
1094 | [10 empty] | 1.01
1095 | [10 empty] | 1.01
1096
1097
1098
1099
1100 | [10 empty] | 1.02
1101 | [10 empty] | 1.02
1102 | [10 empty] | 1.02
1103 | [10 empty] | 1.01
1104
1105
1106 | [10 empty] | 1.02
1107 | [10 empty] | 1.01
1108
1109
1110
1111 | [10 empty] | 1.01
1112
1113
1114
1115
1116
1117 | [10 empty] | 1.02
1118 | [10 empty] | 1.02
1119 | [10 empty] | 1.02
1120 | [10 empty] | 1.02
1121 | [10 empty] | 1.01
1122 | [10 empty] | 1.01
1123 | [10 empty] | 1.01
1124
1125
1126
1127
1128
1129 | [10 empty] | 1.02
1130
1131
1132 | [10 empty] | 1.02
1133 | [10 empty] | 1.01
1134
1135
1136
1137 | [10 empty] | 1.01
1138
1139
1140
1141
1142
1143 | [10 empty] | 1.02
1144 | [10 empty] | 1.02
1145 | [10 empty] | 1.02
1146 | [10 empty] | 1.02
1147 | [10 empty] | 1.01
1148 | [10 empty] | 1.01
1149 | [10 empty] | 1.01
1150
1151
1152
1153
1154 | [10 empty] | 1.02
1155 | [10 empty] | 1.02
1156 | [10 empty] | 1.01
1157 | [10 empty] | 1.01
1158 | [10 empty] | 1.01
1159 | [10 empty] | 1.01
1160 | [10 empty] | 1.01
1161 | [10 empty] | 1.01
1162 | [10 empty] | 1.01
1163 | [10 empty] | 1.02
1164
1165
1166 | [10 empty] | 1.02
1167
1168 | [10 empty] | 1.01
1169
1170 | [10 empty] | 1.01
1171 | [10 empty] | 1.01
1172 | [10 empty] | 1.02
1173 | [10 empty] | 1.02
1174
1175 | [10 empty] | 1.02
1176 | [10 empty] | 1.02
1177
1178 | [10 empty] | 1.02
1179 | [10 empty] | 1.02
1180 | [10 empty] | 1.02
1181 | [10 empty] | 1.02
1182
1183 | [10 empty] | 1.02
1184 | [10 empty] | 1.02
1185
1186 | [10 empty] | 1.02
1187 | [10 empty] | 1.01
1188 | [10 empty] | 1.01
1189
1190
1191
1192
1193
1194
1195
1196
1197
1198
1199
1200
1201
1202
1203
1204
1205
1206 | [10 empty] | 1.01
1207
1208
1209 | [10 empty] | 1.01
1210