## Slide 1: TGac Proposed Timeline Changes
Date: 2010-09-15
Authors:

## Slide 2: Abstract
This submission proposes changes to the current TGac Timeline to reflect current progress

## Slide 3: TGac Current Timeline
The current timeline doesn’t reflect the current progress
Need to define a more realistic timeline
2009
2010
2011
2012
2013
J
M
M
J
S
N
J
M
M
J
S
N
J
M
M
J
S
N
J
M
M
J
S
N
J
M
M
J
S
N
D1.0
WG Letter ballot
Sponsor ballot

## Slide 4: Proposed Changes
Draft 1.0 is to be ready by May 2011 for WG Letter Ballot
  Versions of the draft (e.g. D0.1) may be available earlier
WG Letter Ballot is extended to 20 months, which seems to be close to the current WG average [1].
2009
2010
2011
2012
2013
J
M
M
J
S
N
J
M
M
J
S
N
J
M
M
J
S
N
J
M
M
J
S
N
J
M
M
J
S
N
D1.0
WG Letter ballot
Sponsor ballot

## Slide 5: TGac New Timeline
Jan
Mar
May
July
Sept
Nov
Jan
Mar
May
July
Sept
Nov
Jan
Mar
May
July
Sept
Nov
2011
2012
2013
D1.0
WG LB starts
D2.0
Recirc
D3.0
Recirc
D4.0
Recirc
D5.0
Sponsor Ballt Starts
D6.0
Recirc
D7.0
Recirc
Form Sponsor ballot pool

## Slide 6: Straw Poll
Do you agree to change the current TGac Timeline as indicated in slide 4 of this presentation.

## Slide 7: References
[1] 11-07-1952-14-0000, “Non-Procedural Letter Ballot Results”