## GENERAL
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
294 | Hart, Bria | 164 | 1 | 7.3.2 | General | General | T | Y |  |  | 7.3.2 |  | D |  |  |  | Where are 11aa capability bits advertised? | Add | DISAGREE (General: 2010-09-25 08:17:07Z) 11aa capabilities are advertised in Extended Capability IE. See Cl. 7.3.2.27. | General | GENERAL | [5 empty] | 2010-09-25 08:17 | General
140 | Fischer, Matthew | 164 | 1 | General |  |  | T | Y |  |  | General |  | P |  |  |  | Throughout this document, there are instances the use of "may" that are incorrect, in that their use describes a possible event, and not a permission to act in a certain way. The only allowed use of "may" in this amendment is as permission to act in a certain way. | Locate all uses of "may" in the amendment draft - replace any that refer to a possible event that is not a permission to act with "might" | AGREE IN PRINCIPLE (General: 2010-09-25 09:33:13Z) 5.2.12.4 (p4.7): "may" -> "can" 9.10.10 (p43.5): "may" -> "might" 9.10.10 (p43.38): "may" -> "might" 10.3.aa71.6.4 (p61.15): "may be available" -> "is provided" 11.4.1 (p70.20): "An Intra-Access Category Priority element may be associated with a TS. The" -> "If an Intra-Access Category Priority element is associated with a TS, the" 11.22.15.2.2 (p73.21): "may choose to ignore the DMS Response frame, or to initiate" -> "may ignore the DMS Response frame, or initiate" 11.22.15.2.2 (p73.24): "Group membership detection may be achieved via IGMP snooping" -> "IGMP snooping can be used to establish group membership" 11.22.15.2.2 (p73.30): "may" -> "might" 11.aa24.1 (p81.11), second occurance: "The Access Factor may be calculated from the summation of the QLoads" -> "An implementation might calculate the Access Factor from the sum of the QLoads" 11.aa24.1 (p81.33), second occurance: "The HCCA Access Factor may be calculated from the summation of the HCCA Peak values" -> "An implementation might calculate the HCCA Access Factor from the sum of the HCCA Peak values" 11.aa24.2 (p82.18): "may" -> "might" | General | GENERAL | [5 empty] | 2010-09-25 09:34 | General
138 | Fischer, Matthew | 164 | 1 | General |  |  | T | Y |  |  | General | [5 empty] | Throughout this document, there are instances of formal requirements and recommendations - e.g. sentences that include "shall", "should", "may" - and many of these are repeating existing formal descriptions of behavior. All of such sentences must be removed, as the duplication of formally described behavior is not allowed in the specification, or at least, ill-advised. | Remove all redundant formal behavioral statements to avoid repeating existing behavioral requirements and recommendations - please note that existing baseline plus all oustanding approved amendments and any amendments that are expected to complete before this amendment must be examined for such precedents. |  | General | GENERAL |  | Agree -- Defer till all comments are resolved and a corresponding 11aa Draft is generated. A full review of the draft will reveal repetitions that need removal. |  |  |  | 2010-09-25 09:32 | General
545 | Hunter, David | 164 | 1 | 3.aa3 | 2 | 36 | E | Y | 2 | 36 | 3.aa3 |  | P |  |  |  | "where" usually refers to location. This same change is needed for most applications of "where" in this document. | Replace "where" with "in which". | AGREE IN PRINCIPLE (General: 2010-09-25 11:57:58Z) New text reads (changes due to CID #72, #71, #616). NO additional changes required: "3.aa2 All-Active/Any power save (Any-PS): Power Management delivery method for group addressed frames whereby group addressed frame are transmitted when all associated non-access point (non-AP) stations (STAs) are in Active mode or after a delivery time indication message (DTIM) beacon if any associated non-AP station (STA) is in power save (PS) mode." | General | GENERAL | [5 empty] | 2010-09-25 12:00 | General
542 | Hunter, David | 164 | 1 | 1.2 | 2 | 8 | T | Y | 2 | 8 | 1.2 |  | P |  |  |  | The length and detail of this item are not in keeping with those of the other items in this list. | Replace the comma on line 8 with a period and delete the rest of the item, leaving: "-- Defines mechanisms to improve video streaming performance while maintaining data and voice performance." | AGREE IN PRINCIPLE (General: 2010-09-25 11:50:49Z) Replace P2L7-12 with: "Defines mechanisms to improve video streaming performance while maintaining data and voice performance. The mechanisms defined include support for graceful degradation of audio video streams when there is insufficient channel capacity, increased robustness in overlapping BSS environments, Intra-access category prioritization, improved link reliability and low jitter characteristics for group addressed audio video streams, and interworking with relevant 802.1AVB mechanisms (802.1Qat, 802.1Qav, 802.1AS)." | General | GENERAL | [5 empty] | 2010-09-27 09:10 | General
557 | Hunter, David | 164 | 1 | 5.2.12.1 | 3 | 33 | T | Y | 3 | 33 | 5.2.12.1 |  | P |  |  |  | It is not clear whether RAVS includes all three functions listed in the subclauses, or not. | After this sentence add "Robust AV streaming includes three functions: more reliable groupcast, stream classification service and overalapping BSS management." | AGREE IN PRINCIPLE (General: 2010-09-25 12:05:17Z) Delete Cl. 5.2.12.1. Move the paragraph "Robust Audio Video Streaming enables …" to Cl. 5.2.12. With this change it will be clear that all subclauses under 5.2.12 describe 11aa features. | General | GENERAL |  | Delete Cl. 5.2.12.1. Move the paragraph "Robust Audio Video Streaming enables …" to Cl. 5.2.12. With this change it will be clear that all subclauses under 5.2.12 describe 11aa features. |  |  |  | 2010-09-27 09:19 | General
556 | Hunter, David | 164 | 1 | 5.2.12.1 | 3 | 32 | T | Y | 3 | 32 | 5.2.12.1 | 251 | P |  |  |  | 802.11 already transports audio and video streams, So robust AV streaming is not disttinguished from normal 802.11 operations. | Insert "with greater reliability" after "802.11". | AGREE IN PRINCIPLE (General: 2010-09-25 12:01:05Z) | General | GENERAL |  | See CID #251 for suggested alternates. |  |  |  | 2010-09-27 09:16 | General
251 | Hart, Bria | 164 | 1 | 5.2.12.1 | 3 | 32 | T | Y | 3 | 32 | 5.2.12.1 |  | P |  |  |  | "RAVS enables AV streams to be transported" is an over-claim; this can be done without 11aa | "RAVS enables AV streams to be transported" => "RAVS improves the transport of AV streams" | AGREE IN PRINCIPLE (General: 2010-09-25 08:16:17Z) Suggested text choices: (a) Replace P3L47-48 with "Robust Audio Video Streaming improves audio video streaming performance over 802.11 for consumer and enterprise applications." -- however the question "improvement over what?" could be asked. (b) Replace P3L47-48 with "Robust Audio Video Streaming provides mechanisms to meet the needs of consumer and enterprise applications that stream audio video content over 802.11." (c) Replace P3L47-48 with "Robust Audio Video Streaming provides mechanisms that enhance the quality of service of audio video streaming over 802.11 for consumer and enterprise applications." | General | GENERAL |  | Suggested text choices: (a) Replace P3L47-48 with "Robust Audio Video Streaming improves audio video streaming performance over 802.11 for consumer and enterprise applications." -- however the question "improvement over what?" could be asked. (b) Replace P3L47-48 with "Robust Audio Video Streaming provides mechanisms to meet the needs of consumer and enterprise streaming applications that stream audio video content over 802.11." |  |  |  | 2010-09-27 09:23 | General
693 | Stephens, Adrian | 164 | 1 | 7.2.1.7.3 | 7 | 32 | E | N | 7 | 32 | 7.2.1.7.3 | [5 empty] | The word "through" is ideosyncratically American. The word "to" is equivalent and not objectionally ideosyncratic. Unfortunately the IEEE-SA editors don't grok this and will insert this word in your editing instructions. I can live with that, but not in the text of the standard itself. | Replace "through" with "to" where used in the context "a through b". | AGREE IN PRINCIPLE (EDITOR: 2010-07-14 03:50:38Z) Change "consists of octets numbered P1 through P2" to "consists of octets numbered P1 to P2" | General | GENERAL |  | AGREE IN PRINCIPLE (EDITOR: 2010-07-14 03:50:38Z) Change "consists of octets numbered P1 through P2" to "consists of octets numbered P1 to P2" |  |  |  | 2010-09-27 09:19 | General
458 | Hart, Bria | 164 | 1 | 9.2.4 | 36 | 17 | T | Y | 36 | 17 | 9.2.4 |  | A |  |  |  | Rather than deleting and rewriting so much text, can we achieve the same with with change instructions? For instance, the comma in "MMPDU, when SLRC" is actually an "OR" comma, and this meaning has been lost in the rewrite | Try | AGREE (General: 2010-09-25 11:46:22Z) There are no changes to Cl. 9.2.4 in TGaa anymore. | General | GENERAL | [5 empty] | 2010-09-25 11:47 | General
216 | Gong, Michelle | 164 | 1 | 9.9.3.2 | 40 | 35-36 | T | Y | 40 |  | 9.9.3.2 |  | A |  |  |  | All the management procedures including this one are triggered by SME. It does not need to be explicitly stated. A STA means either a client STA or an AP STA. Both a client STA and an AP STA have SME. Simply stating "SME" does not differentiate an AP from a client. | Remove "or explicitly requested by the SME." | AGREE (General: 2010-09-25 08:15:34Z) Agree. The text that this comment is on is no longer part of TGaa (See CID #215). | General | GENERAL | [5 empty] | 2010-09-25 08:16 | General
114 | Ecclesine, Peter | 164 | 1 | 11.22.15.2.1 | 72 | 33 | T | Y | 72 | 33 | 11.22.15.2.1 |  | P |  |  |  | Add dot11MRGActivated and Make the use of MRG contingent on dot11MRGActivated being true. (Look at 11.10 for this kind of specification). | Should have two MIB variables - Implemented and Activated, not one. | AGREE IN PRINCIPLE (General: 2010-09-25 09:27:45Z) Add a new MIB variable dot11MRGActivated and replace all occurrences of dot11MRGImplemented in Cl. 7, Cl.9 and Cl.11 with dot11MRGActivated. dot11MRGActivated OBJECT-TYPE SYNTAX TruthValue MAX-ACCESS read-only STATUS current DESCRIPTION “This is a control variable. It is written by the SME or external management entity. Changes take effect for the next MLME-START.request primitive or MLME-JOIN.request primitive This attribute, when TRUE, indicates that the station implementation supports the more reliable groupcast service and that this has been activated.” DEFVAL { true } ::= { dot11StationConfigEntry aa? } | General | GENERAL | [5 empty] | 2010-09-27 09:28 | General
113 | Ecclesine, Peter | 164 | 1 | 11.22.15.1 | 72 | 23 | T | Y | 72 | 23 | 11.22.15.1 |  | A |  |  |  | Add dot11RobustAVStreamingActivated, and change this reference to be dot11RobustAVStreamingImplemented (see p88 line 25) | Should have two MIB variables - Implemented and Activated, not one. Use Activated in 11.aa23. | AGREE (General: 2010-09-25 09:04:06Z) Add dot11RobustAVStreamingActivated after dot11RobustAVStreamingImplemented in Annex-A. Also add the following description for dot11RobustAVStreamingActivated after the description for dot11RobustAVStreamingImplement in Annex-A: dot11RobustAVStreamingActivated OBJECT-TYPE SYNTAX TruthValue MAX-ACCESS read-write STATUS current DESCRIPTION "This is a control varia It is written by an external management entity when any of the MIB variables doAVSxxxxActivated is set to tr Changes take effect with the next MLME-START.request primitive or MLME-JOIN.request primitive. This attribute, when true, indicates that one or more of the dot11RAVS Activated Capabilities MIB attributes (dot11RAVSxxxActivated), listed in 7.3.2.27 (Extended Capabilities Information element), are set to true. A STA may use the defined Robust AV Streaming procedures if this attribute is true." DEFVAL { false } ::= { dot11StationConfigEntry aa2 } Consider renaming dot11SCSActivated and similar MIB entries to dot11RAVSSCSActivated. Replace dot11RobustAVStreamingEnabled with dot11RobustAVStreamingActivated in Cl.7, Cl.9 and Cl.11. Since dot11RobustACStreamingActivated is aa2 now, shift all other (existing) RobustAVStreaming MIB entry dot11StationConfigEntry by 1. | General | GENERAL | [5 empty] | 2010-09-27 09:29 | General
112 | Ecclesine, Peter | 164 | 1 | 11.23aa | 78 | 45 | T | Y | 78 | 45 | 11.23aa |  | D |  |  |  | As 802.11n is specified for unlicensed bands where interference must be accepted from all licensed services, and 11aa uses 11n PHY, it is only possible to offer More Robust AV Streaming, BECAUSE ROBUSTNESS COMES FIRST FROM THE RADIO, not the MAC protocol. If this protocol were put on .11g radios in 2.4 GHz band at a hotspot, noone would call the result robust AV streaming. | Change the name of this serivce to More Robust AV Streaming, in keeping with MRG and operation in shared frequency bands. | DISAGREE (General: 2010-09-25 08:28:37Z) Robustness derived from the 802.11 PHY is a given for all applications running over 802.11. A/V streaming applications have additional requirements which can be satisfied using one or more mechanisms defined in 802.11. The term "robust" used to describe 802.11aa is akin to that used for 802.11 security (RSNA), where 802.11i mechanisms render robust security. The proposed change "more robust …" automatically generates another comment -- "more relative to what"? | General | GENERAL | [5 empty] | 2010-09-25 08:34 | General
370 | Hart, Bria | 164 | 1 | A.4.23 | 84 | 22 | T | Y | 84 | 22 | A.4.23 |  | P |  |  |  | MRG should be dependent on 11n also; ditto DEI is dependent on 11n | Fix | AGREE IN PRINCIPLE (General: 2010-09-25 09:36:45Z) In A.4.23 Robust AVT Extensions: Change the status column of AVT2 to (CF16 and CFaa): M Add a new row AVT4.3 DEI 11.aa.23.2 (CF16 and AVT4):M | General | GENERAL | [5 empty] | 2010-09-25 11:45 | General

## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-10/1184r0
Venue Date: | July 2010
First Author: | Alex Ashley (NDS Ltd)
Subject: | LB164 General Comment Spreadsheet
Full Date: | 2010-07-11
Author(s): | Alex Ashley
NDS Ltd
One London Road, Staines, Middlesex, TW18 4EX, UK
Phone: +44 1784 848770
Fax:
email: aashley at nds dot com
Abstract:
Comments from individual comment spreadsheets from LB164 voters in the general category.