## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-10/01434r7
Venue Date: | January 2011
First Author: | Jon Rosdahl, (CSR)
Subject: | GEN Adhoc Sponsor Ballot Comment Resolutions
Full Date: | 2011-01-20
Author(s): | Jon Rosdahl
10871 N 5750 W
Highland, UT 84003
+1-801-492-4023
jrosdahl@ieee.org
Abstract:
This spreadsheet contains a set of proposed resolutions to the General AdHoc comments for Sponsor Ballot for the first sponsor ballot of P802.11Revmb.
As comments are resolved, they are moved to the Editor and out of this file.

## Revision History
Revision | Comments
R0 | Initial pass on the General Adhoc Comments. Initial proposed resolutions included. Proposed resolutions from the Telecon on Dec 3 applied. -- see Proposed Dec 3 tab.
R1 | Proposed resolutions from January Interim Monday PM2 timeslot -- See Gen Motion 1 tab. Withdrawn tab added for CID 10154.
R2 | 2 comments that were agreed to on Monday PM2 were missed in Gen Motion 1 Tab… Added to new Gen motion 2 Tab. The last 4 comments that MAC AdHoc had left to resolve were transferered to Gen AdHoc one of those comments moved to Operation class. Proposals for 18 comments included to prep for Tues Eve Discussion.
R3 | Motion to accept Gen Motion 1, Gen Motion 2 and Proposed Dec 3 Tab passed, comments moved to Editor. Proposed Resolutions prepared and moved to Gen Motion 3 and Gen Motion 4 Tab in the Tues Evening session.
R4 | comment resolutions for Wed added to Gen Motion 5.
R5 | Added Gen Motion 6 for comments from Thurs AM1
R6 | added Gen Motion 7 which has all but the PHY comments ready for motion. PHY comments covered in spearate motion and will be in R7 of the spreadsheet.
R7 | All Gen AdHoc comments ready for motion in repective tabs.

## HT PHY
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
10152 | Kim, Youhan | 1000 | 6 | 17.3.9.7.3 | 1049 | 22 | T | Y | 1049.22 | 22 | 17.3.9.7.3 |  | P | Vinko |  |  | Receivers are designed to be able to received signal with non-flat spectrum since it has to deal with multipath channels anyhow. The current spectral flatness requirement puts unecessary constraint on the TX design without much benefit. | Change +/- 2 dB on line 22 to +/- 4 dB. Change +2/-4 dB on line 23 to +4/-6 dB. | AGREE IN PRINCIPLE (GEN: 2011-01-20 23:56:44Z) incorporate the text changes as indicated in https://mentor.ieee.org/802.11/dcn/11/11-11-0159-02-000m-revmb-sb-spectral-mask-cids-proposed-resolutions.doc | GEN | HT PHY | Ready for motion |  |  |  |  | 2011-01-20 23:57 | GEN
10153 | Kim, Youhan | 1000 | 6 | 19.3.20.1 | 1181 | 39 | T | Y | 1181.39 | 39 | 19.3.20.1 |  | P | Vinko |  |  | 802.11a has -40 dBr mask requirement and works just fine. The -45 dBr requirement in this subclause only puts more constraint on the TX chain design without much benefit. | Change -45 dBr on line 39(p.1181), line 4 (p.1182), and Figures 19-17 and 19-18 to -40 dBr. | AGREE IN PRINCIPLE (GEN: 2011-01-20 23:56:44Z) incorporate the text changes as indicated in https://mentor.ieee.org/802.11/dcn/11/11-11-0159-02-000m-revmb-sb-spectral-mask-cids-proposed-resolutions.doc | GEN | HT PHY | Ready for motion |  |  |  |  | 2011-01-20 23:59 | GEN
10093 | Hansen, Christopher | 1000 | 6 | 19.3.20.1 | 1181 | 39 | T | Y | 1181.39 | 39 | 19.3.20.1 |  | P | Vinko |  |  | TX mask limit is too strict. The values currently specified impose excessive constraints on implementations. Existing 802.11a systems are built with a less stringent mask of -40 dBr. These systems have not suffered from problematic interference in the field. | Change - 45 dBr in this subclause to - 40 dBr. Text and diagrams. | AGREE IN PRINCIPLE (GEN: 2011-01-20 23:56:44Z) incorporate the text changes as indicated in https://mentor.ieee.org/802.11/dcn/11/11-11-0159-02-000m-revmb-sb-spectral-mask-cids-proposed-resolutions.doc | GEN | HT PHY | Ready for motion |  |  |  |  | 2011-01-20 23:59 | GEN
10087 | Ptasinski, Henry | 1000 | 6 | 19.3.20.1 | 1181 | 39 | G | Y | 1181.39 | 39 | 19.3.20.1 |  | P | Vinko |  |  | The transmit mask limit of -45dBr at 30MHz offset is unnecessarily restrictive, and is inconsistent with the limits specified for the OFDM phy. | Change the -45dBr requirement to -40dBr throughout this subclause. | AGREE IN PRINCIPLE (GEN: 2011-01-20 23:56:44Z) incorporate the text changes as indicated in https://mentor.ieee.org/802.11/dcn/11/11-11-0159-02-000m-revmb-sb-spectral-mask-cids-proposed-resolutions.doc | GEN | HT PHY | Ready for motion |  |  |  |  | 2011-01-20 23:58 | GEN
10028 | Fischer, Matthew | 1000 | 6 | 19.3.20.1 | 1181 | 39 | T | Y | 1181.39 | 39 | 19.3.20.1 |  | P | Vinko |  |  | TX mask limit should be softened. The strictness currently specified is not needed and imposes excessive constraints on designs. Existing 802.11a systems are built with a softer specification of -40 dBr and have not been shown to suffer from excessive interference issues in the field. | Change - 45 dBr wherever it occurs in this subclause to - 40 dBr, including text and diagrams. | AGREE IN PRINCIPLE (GEN: 2011-01-20 23:56:44Z) incorporate the text changes as indicated in https://mentor.ieee.org/802.11/dcn/11/11-11-0159-02-000m-revmb-sb-spectral-mask-cids-proposed-resolutions.doc | GEN | HT PHY | Ready for motion |  |  |  |  | 2011-01-20 23:58 | GEN
10077 | Perahia, Eldad | 1000 | 6 | 19.3.20.1 | 1181 | 56 | T | N | 1181.5601 | 56 | 19.3.20.1 |  | P | Vinko |  |  | 11a has a mask level of -40dBr. This was tightened to -45dBr. This results in lower Tx power to meet mask, reducing range of 11n. Furthermore, 11ac is planning to change back to -40dBr. | change -45dBr to -40dBr for 20 and 40 MHz masks | AGREE IN PRINCIPLE (GEN: 2011-01-20 23:56:44Z) incorporate the text changes as indicated in https://mentor.ieee.org/802.11/dcn/11/11-11-0159-02-000m-revmb-sb-spectral-mask-cids-proposed-resolutions.doc | GEN | HT PHY | Ready for motion |  |  |  |  | 2011-01-20 23:58 | GEN
10078 | Perahia, Eldad | 1000 | 6 | 19.3.20.2 | 1182 | 38 | T | N | 1182.38 | 38 | 19.3.20.2 |  | P | Vinko |  |  | such a tight spectral flatness spec is not necessary. First of all, the spec doesn't even apply to transmit beamforming. Second, the only possible impact of relaxing the spectral flatness would be a small increase in delay spread which would not have a measurable impact on PER. Relaxing the spectral flatness spec allows for shaping of the spectrum to better meet out of band emissions, which would increase Tx power at the band edges. | Change values to those proposed in 11ac: 20MHz: +4/-4dB for subcarriers +/- 1-16 and +4/-6dB for outer subcarriers. 40MHz: +4/-4dB for subcarriers +/- 2-42 and +4/-6dB for outer subcarriers. | AGREE IN PRINCIPLE (GEN: 2011-01-20 23:56:44Z) incorporate the text changes as indicated in https://mentor.ieee.org/802.11/dcn/11/11-11-0159-02-000m-revmb-sb-spectral-mask-cids-proposed-resolutions.doc | GEN | HT PHY | Ready for motion |  |  |  |  | 2011-01-20 23:58 | GEN
10070 | Perahia, Eldad | 1000 | 6 | 17.3.9.7.3 | 1182 | 38 | T | N | 1182.38 | 38 | 17.3.9.7.3 |  | P | Vinko |  |  | such a tight spectral flatness spec is not necessary. The only possible impact of relaxing the spectral flatness would be a small increase in delay spread which would not have a measurable impact on PER. Relaxing the spectral flatness spec allows for shaping of the spectrum to better meet out of band emissions, which would increase Tx power at the band edges. | Change values to those proposed in 11ac for 20MHz: +4/-4dB for subcarriers +/- 1-16 and +4/-6dB for outer subcarriers. | AGREE IN PRINCIPLE (GEN: 2011-01-20 23:56:44Z) incorporate the text changes as indicated in https://mentor.ieee.org/802.11/dcn/11/11-11-0159-02-000m-revmb-sb-spectral-mask-cids-proposed-resolutions.doc | GEN | HT PHY | Ready for motion |  |  |  |  | 2011-01-20 23:58 | GEN
10155 | Kim, Youhan | 1000 | 6 | 19.3.20.2 | 1182 | 43 | T | Y | 1182.4301 | 43 | 19.3.20.2 |  | P | Vinko |  |  | Receivers are designed to be able to received signal with non-flat spectrum since it has to deal with multipath channels anyhow. The current spectral flatness requirement puts unecessary constraint on the TX design without much benefit. | Change +/- 2 dB on lines 43, 50 and 58 to +/- 4 dB. Change +2/-4 dB on lines 44, 52 and 59 to +4/-6 dB. | AGREE IN PRINCIPLE (GEN: 2011-01-20 23:56:44Z) incorporate the text changes as indicated in https://mentor.ieee.org/802.11/dcn/11/11-11-0159-02-000m-revmb-sb-spectral-mask-cids-proposed-resolutions.doc | GEN | HT PHY | Ready for motion |  |  |  |  | 2011-01-20 23:58 | GEN
10092 | Hansen, Christopher | 1000 | 6 | 19.3.20.2 | 1182 | 43 | T | Y | 1182.4301 | 43 | 19.3.20.2 |  | P | Vinko |  |  | TX spectral flatness limits are too strict. The values currently specified impose excessive constraints on implementations. | Change +/- 2 dB to +/- 4 dB - throughout the subclause. Change +2/-4 dB to +4/-6 dB throughout the subclause. | AGREE IN PRINCIPLE (GEN: 2011-01-20 23:56:44Z) incorporate the text changes as indicated in https://mentor.ieee.org/802.11/dcn/11/11-11-0159-02-000m-revmb-sb-spectral-mask-cids-proposed-resolutions.doc | GEN | HT PHY | Ready for motion |  |  |  |  | 2011-01-20 23:58 | GEN
10027 | Fischer, Matthew | 1000 | 6 | 19.3.20.2 | 1182 | 43 | T | Y | 1182.4301 | 43 | 19.3.20.2 |  | P | Vinko |  |  | TX spectral flatness limits should be softened. The strictness currently specified is not needed and imposes excessive constraints on designs. | Change +/- 2 dB wherever it occurs in this subclause to +/- 4 dB. Change +2/-4 dB to +4/-6 dB wherever it occurs in this subclause. | AGREE IN PRINCIPLE (GEN: 2011-01-20 23:56:44Z) incorporate the text changes as indicated in https://mentor.ieee.org/802.11/dcn/11/11-11-0159-02-000m-revmb-sb-spectral-mask-cids-proposed-resolutions.doc | GEN | HT PHY | Ready for motion |  |  |  |  | 2011-01-20 23:58 | GEN
10086 | Ptasinski, Henry | 1000 | 6 | 19.3.20.2 | 1182 | 44 | T | Y | 1182.4399 | 44 | 19.3.20.2 |  | P | Vinko |  |  | The transmit spectral flatness requirements are unnecessarily burdensome to implementations. | Change all +2/-4 dB requirements in this clause to +4/-6 dB. Change all +-2 dB requirements in this clause to +-4 dB. | AGREE IN PRINCIPLE (GEN: 2011-01-20 23:56:44Z) incorporate the text changes as indicated in https://mentor.ieee.org/802.11/dcn/11/11-11-0159-02-000m-revmb-sb-spectral-mask-cids-proposed-resolutions.doc | GEN | HT PHY | Ready for motion |  |  |  |  | 2011-01-20 23:58 | GEN

## Gen Motion 7
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
10045 | Fischer, Matthew | 1000 | 6 | 8.1 | 227 | 12 | T | Y | 227.12 | 12 | 8.1 |  | D | Matthew Fischer |  |  | Is this true: "All STAs shall be able to validate every received frame using the frame check sequence (FCS) and to interpret certain fields from the MAC headers of all frames." I.e. does it apply to frames with a protocol version field set to an value that is unknown by the receiver? I.e. is this effectively, a restriction that when the protocol version field is non-zero, the new formats of the frames with the non-zero protocol version field will also have a 4-octet FCS value that uses CRC32? | Clarify. | DISAGREE (GEN: 2011-01-20 23:00:42Z) The Commentor does not clarify what would be need to resolve the issue. The commentor may bring more detail in a submission at a later time. | GEN | Gen Motion 7 | Ready for motion |  |  |  |  | 2011-01-20 23:10 | GEN
10021 | Adachi, Tomoko | 1000 | 6 | 8.3.1.8 | 252 | 1 | T | Y | 252.01 | 1 | 8.3.1.8 |  | P | Adrian Stephens |  |  | The BAR Ack Policy subfield is not used for immediate nor HT-immediate BA operation. The STA that receives a BAR under immediate (including the HT-immediate) BA policy won't return an ACK but a BA. | Add a sentence that, for immediate and HT-immediate BA operation, the BAR Ack Policy subfield is reserved. | AGREE IN PRINCIPLE (GEN: 2011-01-20 22:55:26Z) Agree in principle. Replace: “The BAR Ack Policy subfield of the BAR Control field has the meaning shown in Table 8-14 (BAR Ack Policy subfield).” at 252.01 with: “For BlockAckReq frames sent under Delayed and HT-Delayed agreements the BAR Ack Policy subfield of the BAR Control field has the meaning shown in Table 8-14 (BAR Ack Policy subfield). For BlockAckReq frames sent under other types of agreement, the BAR Ack Policy subfield is reserved.” | GEN | Gen Motion 7 | Ready for motion | Agree in principle. Replace: “The BAR Ack Policy subfield of the BAR Control field has the meaning shown in Table 8-14 (BAR Ack Policy subfield).” at 252.01 with: “For BlockAckReq frames sent under Delayed and HT-Delayed agreements the BAR Ack Policy subfield of the BAR Control field has the meaning shown in Table 8-14 (BAR Ack Policy subfield). For BlockAckReq frames sent under other types of agreement, the BAR Ack Policy subfield is reserved.” |  |  |  | 2011-01-20 22:56 | GEN
10022 | Adachi, Tomoko | 1000 | 6 | 8.3.1.9 | 255 | 1 | T | Y | 255.01 | 1 | 8.3.1.9 |  | P | Adrian Stephens |  |  | The BA Ack Policy subfield is not used for immediate nor HT-immediate BA operation. The STA that receives a BA under immediate (including the HT-immediate) BA policy won't return an ACK. | Add a sentence that, for immediate and HT-immediate BA operation, the BA Ack Policy subfield is reserved. | AGREE IN PRINCIPLE (GEN: 2011-01-20 22:56:23Z) Agree in principle. Replace: “The BA Ack Policy subfield of the BA Control field has the meaning shown in Table 8-16 (BA Ack Policy subfield).” at 255.01 with: “For BlockAck frames sent under Delayed and HT-Delayed agreements the BA Ack Policy subfield of the BA Control field has the meaning shown in Table 8-16 (BA Ack Policy subfield). For BlockAck frames sent under other types of agreement, the BA Ack Policy subfield is reserved.” | GEN | Gen Motion 7 | Ready for motion | propose: Agree in principle. Replace: “The BA Ack Policy subfield of the BA Control field has the meaning shown in Table 8-16 (BA Ack Policy subfield).” at 255.01 with: “For BlockAck frames sent under Delayed and HT-Delayed agreements the BA Ack Policy subfield of the BA Control field has the meaning shown in Table 8-16 (BA Ack Policy subfield). For BlockAck frames sent under other types of agreement, the BA Ack Policy subfield is reserved.” |  |  |  | 2011-01-20 22:57 | GEN
10049 | Fischer, Matthew | 1000 | 6 | 8.4.1.11 | 286 | 16 | T | Y | 286.16 | 16 | 8.4.1.11 |  | D | Matthew Fischer |  |  | There's something odd with the description of action frames. Action field in this description of the action frame has a category subfield and an action details subfield. Later on, families of action frames are described as having a family-named Action field. There is no mention of the action details field within the descriptions of the families of frames. In the individual frame descriptions, the distinction between the category and action details is not discussed at all. | Not certain of how to fix this. At first, I thought that if you modify the table in 8.4.1.11, things would become a bit more straightforward. E.g. suggest changing the heading "Meaning" to be "Action details contents" and then for each row of the table, use the family action name to fill in the entry for this column. E.g. "QoS Action field" - but this does not fix the overall problem. The "action details" field in 8.4.1.11 does NOT include the Category, but the description for each frame includes category. So it seems like category is included twice, even though the family description does NOT say that the contents is the "action details" field, which is, i am certain, the reason why you are still able to sleep well at night. | DISAGREE (GEN: 2011-01-20 22:57:58Z) The CRC is not certain how to resolve this. The commentor may bring more detail in a submission at a later time. | GEN | Gen Motion 7 | Ready for motion |  |  |  |  | 2011-01-20 23:00 | GEN
10143 | Malinen, Jouni | 1000 | 6 | 8.4.2.2 | 307 | 65 | T | Y | 307.65 | 65 | 8.4.2.2 |  | D |  |  |  | The SSID is a value between 1 and 32 arbitrary octets without any definition on the encoding. While this is enough for the protocol to function, it can result in user inconvenience and even interoperability issue when non-ASCII characters are used in the SSID. As a de facto standard, ASCII characters seem to be shown by more or less all implementation. However, encoding of non-ASCII characters varies depending on implementation and even locality of the device in some cases. At least ISO/IEC 8859-2 (Latin-2), UTF-8, and GB2312 have been used in deployed implementation. When the AP and non-AP STAs do not agree with encoding, the UIs are likely to show "incorrect" values and make it difficult for users to enter the SSID. While it is not feasible to fix all the issues with deployed systems, it would be good to be able to help in this area for future products by defining a mechanism to indicate which encoding is used for SSID. I would propose UTF-8 to be used for this. | Add a new Extended Capabilities element value in 8.4.2.29, Table 8-88: Information=UTF-8 SSID, Notes: The SSID in this BSS uses UTF-8 encoding. Add following text to the end of 8.4.2.2: "When UTF-8 SSID capability is set to 1 in Extended Capabilities element in the frame that includes the SSID element, the SSID is encoded using UTF-8. | DISAGREE (GEN: 2011-01-20 22:50:56Z) Normative behaviour must be described for the addition of the Extended Capabilities element value. How the SSID is originally set would also need additional requirements described in order to make the requested change. | GEN | Gen Motion 7 | Ready for motion | GEN: 2011-01-20 22:49:59Z - Proposed Resolution….AGREE IN PRINCIPLE (GEN: 2011-01-20 22:40:43Z)Add a new Extended Capabilities element value in 8.4.2.29, Table 8-88: Information=UTF-8 SSID, Notes: The SSID in this BSS is interpreted using UTF-8 encoding. Add the following text to the end of 8.4.2.2: "When UTF-8 SSID capability is set to 1 in Extended Capabilities element in the frame that includes the SSID element, the SSID is interpreted using UTF-8 encoding. The TG decided that more description was needed and addition information when the SSID was set to be a complete solution. Therefore the TG will decline this CID for now. |  |  |  | 2011-01-20 22:53 | GEN
10447 | Hunter, David | 1000 | 6 | C.3 | 1557 | 33 | T | Y | 1557.33 | 33 | C.3 |  | P | Trish Gerdon |  |  | 802.1F is scheduled for IEEE administrative withdrawal in December 2010. Why is it being referenced in these MIB variable definitions? | Lines 33, 51: Either find a substitute for this reference or delete these MIB variables. | AGREE IN PRINCIPLE (GEN: 2011-01-20 23:11:02Z) Add a footnote that the 802.1F standard has been withdrawn. | GEN | Gen Motion 7 | Ready for motion | Proposed Resolution if we don't hear back from Trish… Disagree -- an updated reference has not been identified. GEN: 2011-01-19 22:51:41Z - Trish will check for a valid reference. Suggest that we remove the MIB entries for 802.1F. Response from Trish: Here is what I found out about 802.1F-2003. Our records show that it was reaffirmed in 2004 and withdrawn in 2010. There hasn't been a replacement of the standard. However if you want to reference the document you can, but you will need to put a footnote that the standard has been withdrawn. Let me know if you need anything else. Tricia Patricia A. Gerdon Manager, Technical Program Development |  |  |  | 2011-01-20 23:12 | GEN

## gen Motion 6
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
10149 | Vlantis, George | 1000 | 6 | 8.5.7.5 | 441 | 1 | T | Y | 441.01 | 1 | 8.5.7.5 |  | P |  |  |  | Formerly CID 4093 in LB163 (11k "Link Measurement Report Frame Format" is missing mandatory Incapable Bit): On, page 687, line 42, subclause 10.11.11 "Link Measurement", paragraph 2 states "If dot11RMLinkMeasurementActivated is false in an AP receiving a Link Measurement Request, it shall ignore the request and return a Link Measurement Report with the Incapable bit in the Measurement Report Mode field set to 1. " However, Figure 8-215 "Link Measurement Report frame body format" on page 441, line 1, subclause 8.5.75 "Link Measurement Report Frame Format" lacks the required "Measurement Report" information element, defined in 8.4.2.24.1, page 340-341, Figures 8-110 and 8-111. The "Measure Report" IE contains the required "Measurement Report Mode" octet and the "Incapable Bit" (B1) . We have communicated with some of the participants in 802.11k, and it appears to be an oversight. There are a fews ways to fix this: either add the IE or add the "Measurement Report Mode" octet to the "Link Measurement Report frame body format". Naturally some text will have to be added to subclause 8.5.7.5 to describe the inclusion of this IE or octet, as well as changing Figure 8-215. | The Recommended Changes from the previous LB163 recommended. "Either add the 'Measurement Report' IE (or the 'Measurement Report Mode' octet) to the definition of the "Link Measure Report frame body format" in Figure 8-215 and the associated subclause 8.5.7.5 and 10.11.11 descriptions." These recommendations were rejected because the IE has a name-space clash (which can fixed by defining a new IE) or the recommendation to add the bit to the Link Measure Rport frame body format was rejected due to legacy implementations. Therefore, the alternative that remains is to add a definition of a newly-named IE with the "Incapable Bit" to 8.5.7.5. Legacy implementations (that could not have implemented the "Incapabile Bit" feature) will not be affected and the "Incapable Bit" feature will be supported according to 10.11.11, with a reference to this new IE. (I should also note that the "Ad-Hoc Notes" column of the resolution spreadsheet for LB163, i.e. 11-09-0706, indicates a similar solution to CID 4093, although the Resolution column chose to reject the comment for the stated reasons.) | AGREE IN PRINCIPLE (GEN: 2011-01-20 17:18:01Z) -- CID 10118 has made the following change: "delete "and return a Link Measurement Report with the Incapable bit in the Measurement Report Mode field set to 1"" | GEN | gen Motion 6 | Ready for motion |  |  |  |  | 2011-01-20 17:21 | GEN
10050 | Fischer, Matthew | 1000 | 6 | 8.5.8.2 | 444 | 50 | T | Y | 444.5 | 50 | 8.5.8.2 |  | D |  |  |  | Not just this subclause, but everywhere in the public action frames, it is rather disturbing to see a "public action" field and a "public action" frame. | Change the name of one of these to avoid confusion. | DISAGREE (GEN: 2011-01-20 17:34:32Z) The full action field description is in each frame to assist the reader to understand the overall frame format without having to reference back several layers of hierarchy. | GEN | gen Motion 6 | Ready for motion |  |  |  |  | 2011-01-20 17:37 | GEN
10051 | Fischer, Matthew | 1000 | 6 | 8.5.8.2 | 446 | 46 | T | Y | 446.46 | 46 | 8.5.8.2 |  | D |  |  |  | Reason result code appears in more than one frame, yet it has a different meaning in each frame. Is thi s the new convention? Sounds confusing. | check all reason and result and status code fields of each action frame and determine whether there will be confusion by virtue of the shared names among various frames which assign different meanings to the fields - possible deconfusination strategies include renaming each field so that each has a unique name | DISAGREE (GEN: 2011-01-20 17:44:25Z) There are "Reason Result Code field values" tables for each of the DSE frame definitions. The values are defined uniquely to the specific frame. This was the design choice made in 11y amendment. This is not a new convention. This is not ambiguous. | GEN | gen Motion 6 | Ready for motion |  |  |  |  | 2011-01-20 17:49 | GEN
10091 | Hansen, Christopher | 1000 | 6 | 5 | 1143 |  | E | Y | 1143 |  | 5 |  | D |  |  |  | Mathematical description for signals at each subcarrier k is not consistent. Sometimes it uses subindex, H_k, but sometimes it uses parenthesis, H(k). We have to unify the format. Since 11ac may use the subscript as a user index, especially for H (channel), Q (steering) and V (beamforming), subcarrier index for those matrices is better to be expressed with parenthesis. The list of changes is as follows | - 19.3.9.4.5 replace Q_k with Q(k) in Eq. (19-21) - 19.3.9.4.6 replace Q_k with Q(k) in figures/equations/text - 19.3.9.5.3 replace Q_k with Q(k) in Eq. (19-28) - 19.3.9.5.4 replace Q_k with Q(k) in Eq. (19-29) to Eq.(19-31). In (19-30), it should be Q(k+32) or Q(k-32) - 19.3.11.11.2 replace Q_k with Q(k), V_k with V(k) and H_eff with H_eff(k) in figures/equations/text - 19.3.11.11.3 to 19.3.11.11.5 replace Q_k with Q(k) in Eq. (19-58) to Eq.(19-60). In (19-60), it should be Q(k+32) or Q(k-32) - 19.3.12.1 replace Q_k with Q(k), x_k with x(k), y_k with y(k), H_k with H(k), in figures/equations/text - 19.3.12.2 replace all "subscript k" with "(k)" for H, H_AB, H_BA, Q_A, Q_B, A_RX, A_TX, K_A, K_B et. al. - 19.3.12.3.1 replace Q_k with Q(k), V_k with V(k) and Heff,k with Heff(k) - 19.3.12.3.2 replace Q_k with Q(k), - 19.3.12.3.3 to 19.3.12.3.6 replace Q_k with Q(k) | DISAGREE (GEN: 2011-01-20 17:05:51Z) Describing Mathematical equations in a consistent manner is important. The proposed changes do not seem to resolve the inconsistencies in the draft, and would not make the resultant equations easier to read. | GEN | gen Motion 6 | Ready for motion | EDITOR: 2010-11-12 00:04:18Z - Transferred to GEN |  |  |  | 2011-01-20 17:08 | GEN
10062 | Sakoda, Kazuyuki | 1000 | 6 | C.3 | 1382 | 16 | T | N | 1382.16 | 16 | C.3 |  | D |  |  |  | dot11AuthenticationAlgorithms table enumeration starts with value of 1, whereas Authentication Algorithm Number defined in 8.4.1.1 starts with 0. This difference causes different number assignment for an authentication algorithm. This is confusing. It should be better to align the assinged number for each authentication algorithm. | Propose to change enumeration in the dot11AuthenticationAlgorithmsTable starting from zero, so that the assigned value becomes identical to the Authentication Algorithm Number in 8.4.1.1. | DISAGREE (GEN: 2011-01-20 16:46:45Z) MIB enumerations cannot start at zero. A Change in clause 8.4.1.1 values would cause an interoperability issue. | GEN | gen Motion 6 | Ready for motion | GEN: 2011-01-20 16:46:22Z - MIB enumerations cannot start at zero. GEN: 2011-01-18 02:06:13Z This may cause an interoperability issue. Changing in 8.4.1.1 is the over the air values, and the MIB variable would cause a difference in definition. Current thought is not to change. |  |  |  | 2011-01-20 16:49 | GEN
10063 | Sakoda, Kazuyuki | 1000 | 6 | C.3 | 1382 | 64 | T | N | 1382.64 | 64 | C.3 |  | D |  |  |  | dot11AuthenticationAlgorithm integer definition starts with value of 1, whereas Authentication Algorithm Number defined in 8.4.1.1 starts with 0. This difference causes different number assignment for an authentication algorithm. This is confusing. It should be better to align the assinged number for each authentication algorithm. | Propose to change integer definition in the dot11AuthenticationAlgorithm to become starting from zero, so that the assigned value becomes identical to the Authentication Algorithm Number in 8.4.1.1. | DISAGREE (GEN: 2011-01-20 16:46:45Z) MIB enumerations cannot start at zero. A Change in clause 8.4.1.1 values would cause an interoperability issue. | GEN | gen Motion 6 | Ready for motion | This may cause an interoperability issue. Changing in 8.4.1.1 is the over the air values, and the MIB variable would cause a difference in definition. Current thought is not to change. |  |  |  | 2011-01-20 16:49 | GEN
10125 | Worstell, Harry | 1000 | 6 | C | 1482 | 34 | T | Y | 1482.34 | 34 | C |  | D | Mark Hamilton |  |  | entries in Dot11RMNeighborReportEntry are documented as status variables, but the MAX-ACCESS is read-write or read-create. This is inconsistent. | These entries should be written by an external management entity or the SME, so the MAX-ACCESS is correct. Fix the description. | DISAGREE (GEN: 2011-01-20 16:53:11Z) "status" variable is the best fit given the current set of descriptors in use by 802.11 MIB. | GEN | gen Motion 6 | Ready for motion | Proposed Resolution: AGREE IN PRINCIPLE (GEN: 2011-01-19 05:30:10Z) - Change description of all of these MIB variables to "This is a control variable. It is written by an external management entity or by the SME. Changes take effect as soon as practical in the implementation. Proposed Resolution from https://mentor.ieee.org/802.11/dcn/10/11-10-1329-01-000m-misc-resolutions.xls proposed resolution: Change description of all of these MIB variables to "This is a control variable. It is written by an external management entity or by the SME. Changes take effect as soon as practical in the implementation. |  |  |  | 2011-01-20 16:54 | GEN
10169 | Ecclesine, Peter | 1000 | 6 | D.1 | 1632 | 14 | T | Y | 1632.14 | 14 | D.1 |  | A | Micheal Montemurro |  |  | IndoorOnlyBehavior is defined and used only where "location of operation must be 'indoors' as defined in the regulatory domain." It is not a specified behavior in any band without radar regulatory requirements, and should be removed from the standard as all stations that will be allowed to operate in those bands will meet such regulatory requirements. | Remove all references to IndoorOnlyBehavior, both in Annex D and Annex E. | AGREE (GEN: 2011-01-20 16:42:59Z) | GEN | gen Motion 6 | Ready for motion | agree -- Mike to check with Rich. |  |  |  | 2011-01-20 16:43 | GEN
10168 | Ecclesine, Peter | 1000 | 6 | D.1 | 1633 | 39 | T | Y | 1633.39 | 39 | D.1 |  | A | Michael Montemurro |  |  | DFS_50_100_Behavior is defined and used only "where radiolocation radar is primary, and station operation has in-service monitoring requirements". It is not a specified behavior in any band without radar regulatory requirements, and should be removed from the standard as all stations that will be allowed to operate in those bands will meet such regulatory requirements. | Remove all references to DFS_50_100_Behavior, both in Annex D and Annex E. | AGREE (GEN: 2011-01-20 16:43:25Z) | GEN | gen Motion 6 | Ready for motion | agree -- Mike to check with Rich |  |  |  | 2011-01-20 16:44 | GEN
10110 | Rosdahl, Jon | 1000 | 6 |  | 1636 |  | T | Y | 1636 |  |  |  | P |  |  |  | the Public Safety channels are listed in opposite order of channel spacing between Tables E-1 and E-4, but the cross references between global operating class and non-global operating class are not correspondingly reversed. It is not clear whether the operating class or cross reference should be swapped to fix this issue. | correct the order to match appropriately. | AGREE IN PRINCIPLE (GEN: 2011-01-20 16:15:48Z) Table E-1 Changes: Row 6 and 7 change from 101 to 103 in the second column. Row 10 and 11 change from 103 to 101 in the second column. Table E-4 Changes: Row 101 Change from E-1-6, 7 to E-1-10, 11 Row 103 Change from E-1-10, 11 to E-1-6, 7 Row 103 Delete the "k" from the Channel Set Column entry. | GEN | gen Motion 6 | Ready for motion | Agree -- change Table E-1 Class 10 and 11 to cross index into table 101 in E-4. Global/local references in both tables are swapped…. Table E-1 Changes: Row 6 and 7 change from 101 to 103 in the second column. Row 10 and 11 change from 103 to 101 in the second column. Table E-4 Changes: Row 101 Change from E-1-6, 7 to E-1-10, 11 Row 103 Change from E-1-10, 11 to E-1-6, 7 Row 103 Delete the "k" from the Channel Set Column entry. |  |  |  | 2011-01-20 16:17 | GEN
10002 | Song, Jae-Hyung | 1000 | 6 | Annex E.1 | 1636 | 1 | T | Y | 1636.01 | 1 | Annex E.1 |  | D |  |  |  | There are a number of duplicated operating classes in the U.S., with same global operating class, starting frequency, channel spacing, channel set and behavior limits set. See operating class pairs <6,7>, <8, 9>, and <10, 11>. It seems unnecessary to have duplicated operating classes with same parameters. | Modify Table E-1 (Operating Classes in the United States) to have a single operating class for a specific combination of parameters. If there is a specific reason to have different operating classes having same parameters, then clarify the reason. | DISAGREE (GEN: 2011-01-20 16:18:30Z) The reason that there are operating classes that seem to be duplicative is historic. We cannot combine the classes as they did have some diferential emmissions masks when the table was originally created. When we removed Transmit behaviours from the tables, the operationg classes look identical. | GEN | gen Motion 6 | Ready for motion |  |  |  |  | 2011-01-20 16:24 | GEN
10170 | Ecclesine, Peter | 1000 | 6 | E.1 | 1636 | 14 | T | Y | 1636.14 | 14 | E.1 |  | A |  |  |  | DynamicFrequencySelectionBehavior is required by US regulation for operation in UNII-2 bands, and should should be removed from the standard as all stations that will be allowed to operate in those bands will meet such regulatory requirements. | Remove DynamicFrequencySelectionBehavior from behavior limits sets of Operating Classes 2, 4, 23, 24, 28 and 29 in Table E-1. | AGREE (GEN: 2011-01-20 16:26:20Z) Remove "DynamicFrequencySelectionBehavior" from behavior limits sets of Operating Classes 2, 4, 23, 24, 28 and 29 in Table E-1. | GEN | gen Motion 6 | Ready for motion |  |  |  |  | 2011-01-20 16:27 | GEN
10174 | Ecclesine, Peter | 1000 | 6 | E.1 | 1638 | 16 | T | Y | 1638.16 | 16 | E.1 |  | A |  |  |  | TransmitPowerControlBehavior is required by EU regulation for operation in 5.15-5.725 GHz bands, and should should be removed from the standard as all stations that will be allowed to operate in those bands will meet such regulatory requirements. | Remove TransmitPowerControlBehavior from behavior limits sets of Operating Classes 1, 2, 3, 5, 6, 7, 8, 9 and 10 in Table E-2. | AGREE (GEN: 2011-01-20 16:27:06Z) Remove "TransmitPowerControlBehavior" from behavior limits sets of Operating Classes 1, 2, 3, 5, 6, 7, 8, 9 and 10 in Table E-2. | GEN | gen Motion 6 | Ready for motion |  |  |  |  | 2011-01-20 16:28 | GEN
10171 | Ecclesine, Peter | 1000 | 6 | E.1 | 1638 | 21 | T | Y | 1638.21 | 21 | E.1 |  | A |  |  |  | DynamicFrequencySelectionBehavior is required by EU regulation for operation in 5.25-5.725 GHz bands, and should should be removed from the standard as all stations that will be allowed to operate in those bands will meet such regulatory requirements. | Remove DynamicFrequencySelectionBehavior from behavior limits sets of Operating Classes 2, 3, 6, 7, 9, 10 and 17 in Table E-2. | AGREE (GEN: 2011-01-20 16:27:41Z) Remove "DynamicFrequencySelectionBehavior" from behavior limits sets of Operating Classes 2, 3, 6, 7, 9, 10 and 17 in Table E-2. | GEN | Gen Motion 6 | Ready for motion |  |  |  |  | 2011-01-20 16:28 | GEN
10003 | Song, Jae-Hyung | 1000 | 6 | Annex E.1 | 1639 | 28 | T | Y | 1639.28 | 28 | Annex E.1 |  | D |  |  |  | There are a number of duplicated operating classes in Japan, with same global operating class, starting frequency, channel spacing, channel set and behavior limits set. See operating classes <2, 4>, <3, 5, 6>, <7, 9>, <8, 10, 11>, <12, 14>, <13, 15>, <16, 18>, <17, 19, 20>, <21, 23>, <22, 24>, <25, 27>, <26, 28, 29>, <46, 48>, <47, 49, 50>, <51, 53>, and <52, 54, 55> It seems unnecessary to have duplicated operating classes with same parameters. | Modify Table E-3 (Operating Classes in Japan) to have a single operating class for a specific combination of parameters. If there is a specific reason to have different operating classes having same parameters, then clarify the reason. | DISAGREE (GEN: 2011-01-20 16:18:30Z) The reason that there are operating classes that seem to be duplicative is historic. We cannot combine the classes as they did have some diferential emmissions masks when the table was originally created. When we removed Transmit behaviours from the tables, the operationg classes look identical. | GEN | Gen Motion 6 | Ready for motion |  |  |  |  | 2011-01-20 16:25 | GEN
10175 | Ecclesine, Peter | 1000 | 6 | E.1 | 1641 | 50 | T | Y | 1641.5 | 50 | E.1 |  | A |  |  |  | TransmitPowerControlBehavior is required by Japanese regulation for operation in 5.15-5.725 GHz bands, and should should be removed from the standard as all stations that will be allowed to operate in those bands will meet such regulatory requirements. | Remove TransmitPowerControlBehavior from behavior limits sets of Operating Classes 32, 34, 37, 39, 42, 44 and 58 in Table E-3. | AGREE (GEN: 2011-01-20 16:28:52Z) Remove TransmitPowerControlBehavior from behavior limits sets of Operating Classes 32, 34, 37, 39, 42, 44 and 58 in Table E-3. | GEN | Gen Motion 6 | Ready for motion |  |  |  |  | 2011-01-20 16:30 | GEN
10172 | Ecclesine, Peter | 1000 | 6 | E.1 | 1641 | 51 | T | Y | 1641.51 | 51 | E.1 |  | A |  |  |  | DynamicFrequencySelectionBehavior is required by Japanese regulation for operation in 5.25-5.725 GHz bands, and should should be removed from the standard as all stations that will be allowed to operate in those bands will meet such regulatory requirements. | Remove DynamicFrequencySelectionBehavior from behavior limits sets of Operating Classes 32, 33, 34, 35, 37, 38, 39, 40, 42, 43, 44, 45 and 58 in Table E-3. | AGREE (GEN: 2011-01-20 16:30:42Z) - Remove "DynamicFrequencySelectionBehavior" from behavior limits sets of Operating Classes 32, 33, 34, 35, 37, 38, 39, 40, 42, 43, 44, 45 and 58 in Table E-3. | GEN | Gen Motion 6 | Ready for motion |  |  |  |  | 2011-01-20 16:31 | GEN
10109 | Rosdahl, Jon | 1000 | 6 |  | 1645 | 21 | T | Y | 1645.21 | 21 |  |  | A |  |  |  | in Table E-4 global operating class 84 lists E-3-46,47,48,49,50 as some of the equivalent non-global operating classes. Presumably these should not be listed here; they are correctly listed against global operating class 104 lower down the same table. | remove the incorrect references. | AGREE (GEN: 2011-01-20 16:38:57Z) Remove from Table E-4 global operating class 84 entries in Non-Global operating Class(es): "E-3-46,47,48,49,50" | GEN | Gen Motion 6 | Ready for motion |  |  |  |  | 2011-01-20 16:41 | GEN
10173 | Ecclesine, Peter | 1000 | 6 | E.1 | 1645 | 31 | T | Y | 1645.3101 | 31 | E.1 |  | A |  |  |  | DynamicFrequencySelectionBehavior is required by each regulatory domain's regulations for operation in 5.25-5.725 GHz bands, and should should be removed from the standard as all stations that will be allowed to operate in those bands will meet such regulatory requirements. | Remove DynamicFrequencySelectionBehavior from behavior limits sets of Operating Classes 118, 119, 120, 121, 122 and 123 in Table E-4. | AGREE (GEN: 2011-01-20 16:40:42Z) Remove "DynamicFrequencySelectionBehavior" from behavior limits sets of Operating Classes 118, 119, 120, 121, 122 and 123 in Table E-4. | GEN | gen Motion 6 | Ready for motion |  |  |  |  | 2011-01-20 16:41 | GEN
10176 | Ecclesine, Peter | 1000 | 6 | E.1 | 1646 | 50 | T | Y | 1646.5 | 50 | E.1 |  | A |  |  |  | TransmitPowerControlBehavior is required by each regulatory domain's regulations for operation in 5.15-5.725 GHz bands, and should should be removed from the standard as all stations that will be allowed to operate in those bands will meet such regulatory requirements. | Remove TransmitPowerControlBehavior from behavior limits sets of Operating Classes 118, 119, 120, 121, 122 and 123 in Table E-4. | AGREE (GEN: 2011-01-20 16:41:24Z) Remove TransmitPowerControlBehavior from behavior limits sets of Operating Classes 118, 119, 120, 121, 122 and 123 in Table E-4. | GEN | Gen Motion 6 | Ready for motion |  |  |  |  | 2011-01-20 16:42 | GEN

## Gen Motion 5
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
10111 | Rosdahl, Jon | 1000 | 6 |  |  |  | T | Y |  |  |  |  | P |  |  |  | sometimes the spec says "MPDU or MMPDU". This doesn't really make sense: an MPDU is a MAC frame (which may contain all or a part of an MSDU or MMPDU), while an MMPDU is the lump of data exchanged between two MLMEs. Maybe they mean "MSDU or MMPDU"? It's all rather messy, with the advent of A-MSDUs and A-MPDUs. | change "MPDU or MMPDU" to the appropriate use of MPDU or if it is an MLME exchange MMPDU | AGREE IN PRINCIPLE (GEN: 2011-01-20 01:29:51Z) - change any "MPDU or MMPDU" as follows: 488.60: "frame containing all or part of an MSDU or MMPDU" 488.60: reword " ... response to the transmission of a frame containing all or part of an MSDU or MMPDU," 489.01: "frame containing all or part of an MSDU or MMPDU" 824.11: reword "... the reception of frames containing all or part of an MSDU or MMPDU". | GEN | Gen Motion 5 | Ready for motion | EDITOR: 2010-11-12 00:01:57Z Transferred to GEN |  |  |  | 2011-01-20 01:31 | GEN
10105 | Rosdahl, Jon | 1000 | 6 |  |  |  | T | Y |  |  |  |  | P |  |  |  | in some places the text talks about "QoS parameters" and in others "access category". Is there a subtle difference between the two -- perhaps something to do with whether the frames actually go into a per-AC queue or not? If there isn't a difference, it might be better to use consistent (and clear) wording. | Use either QoS Parameter or "access category" consistently one or the other if possible. | AGREE IN PRINCIPLE (GEN: 2011-01-20 01:40:36Z) D6.04 546.29: Change "QoS Parameters" to "EDCA Parameters" D6.04 721.60 replace : "The AP uses the parameters in the TCLAS elements to filter the MSDUs belonging to this TS so that they can be delivered with the QoS parameters that have been set up for the TS." with "The AP uses the parameters in the TCLAS elements to filter the MSDUs belonging to this TS for delivery as part of the TS." | GEN | Gen Motion 5 | Ready for motion | D6.04 546.29: Change "QoS Parameters" to "EDCA Parameters" D6.04 721.60 replace : "The AP uses the parameters in the TCLAS elements to filter the MSDUs belonging to this TS so that they can be delivered with the QoS parameters that have been set up for the TS." with "The AP uses the parameters in the TCLAS elements to filter the MSDUs belonging to this TS for delivery as part of the TS." |  |  |  | 2011-01-20 01:41 | GEN
10455 | Kenney, John | 1000 | 6 |  | 9.3.2.11 |  | T | N | 0 | 0 | 9.3.2.11 |  | P |  |  |  | (Post ballot comment). Consider clause 9.3.2.11 on duplicate frame detection (was 9.2.9 in 802.11-2007). Two paragraphs have been added. Those two paragraphs are shown below, along with the paragraph that they precede, which was not changed from the 2007 text. Non-QoS STAs, as well as QoS STAs operating as non-QoS STAs because they are in a non-QoS BSS or non-QoS IBSS, assign sequence numbers, to management frames and data frames (QoS subfield of the Subtype field is set to 0), from a single modulo-4096 counter, starting at 0 and incrementing by 1 for each MSDU or MMPDU. QoS STAs associated in a QoS BSS maintain one modulo-4096 counter, per TID, per unique receiver (specified by the Address 1 field of the MAC header). Sequence numbers for QoS data frames are assigned using the counter identified by the TID subfield of the QoS Control field of the frame, and that counter is incremented by 1 for each MSDU belonging to that TID. Sequence numbers for management frames, QoS data frames with a group address in the Address 1 field, and all non-QoS data frames sent by QoS STAs are assigned using an additional single modulo-4096 counter, starting at 0 and incrementing by 1 for each MSDU or MMPDU. Sequence numbers for QoS (+)Null frames may be set to any value. The sequence number, for management frames and for data frames with the QoS subfield of the Subtype field set to 0, is generated by the transmitting STA as an incrementing sequence of integers. In a QoS STA, the sequence numbers for QoS (+)data frames are generated by different counters for each TID and receiver pair and shall be incremented by one for each new MSDU or A-MSDU corresponding to the TID/receiver pair. My concern is that the cases covered by the two new paragraphs do not include a QoS STA communicating outside the context of a BSS (or more specifically, a STA with dot11OCBEnabled equal to true). I have a feeling the cases in these two paragraphs are intended to be exhaustive: • Non-QoS STAs • QoS STAs operating as non-QoS STAs because they are in a non-QoS BSS or non-QoS IBSS • QoS STAs associated in a QoS BSS But, they aren't exhaustive, because they don't include the dot11OCBEnabled = true case, for which the QoS STA is not a member of a BSS at all. This is one relatively minor instance, but my larger concern is two-fold: • this type of omission might pop up in many places where text was modified in REVmb in an attempt to correct an error in, or provide clarity to, the 2007 text. Assuming people from TGp weren't involved in much of what has gone into REVmb thus far, it would be an easy oversight to make. • this type of omission will be hard to detect without a line-by-line reading of the 2000+ page document, since there is nothing 11p-specific in this clause and thus it is not likely to receive attention from anyone hoping to verify that 11p has been correctly integrated. I just happened to notice because TGae made further modifications to this clause. Note that the 2007 text did not require 11p-specific language because the phrase "for management frames and for data frames with the QoS subfield of the Subtype field set to 0" covers frames sent by STAs in a BSS and by STAs communicating outside of a BSS. [As an aside, I'm also confused about the intended relationship between the two new paragraphs and the retained 3rd paragraph (unchanged from 2007). The third paragraph seems to cover the same cases, in aggregate, as the first two, but with some contradictory statements. For example, a management frame transmitted by a QoS STA in a QoS BSS is covered by paragraph #2 (per TID and per receiver sequence numbers) and by paragraph #3 (no mention of per TID or per receiver seq. numbers). I wonder if the third paragraph was intended to be deleted and replaced by the two new ones?] [Another aside. There may be another sense in which the two new paragraphs are not exhaustive, if I understand them. The case of a QoS STA in a QoS iBSS does not appear to be covered.] | Modifying the two new paragraphs to cover the dot11OCBEnabled=true case is probably easy, but finding other places where similar modifications are required may be tough. In preparing the 11p amendment we did as thorough a job as we could of finding places where 11p-specific qualifications needed to be added. | AGREE IN PRINCIPLE (GEN: 2011-01-19 23:27:02Z) Change (D6.0) 486.51 "QoS STAs associated in a QoS BSS maintain one modulo-4096" to "A STA operating as a QoS STA maintains one module-4096" and There's also a minor fix-up: "or A-MSDU" needs to be added after MSDU at (D6.0) 486.55 and (D60) 486.58 | GEN | Gen Motion 5 | Ready for motion | Proposed Resolution: Change "QoS STAs associated in a QoS BSS maintain one modulo-4096" to "A STA operating as a QoS STA maintains one module-4096" and There's also a minor fix-up: "or A-MSDU" needs to be added after MSDU at (D6.0) 486.55 and (D60) 486.58 ---------- To Discuss: do we attempt to fix 2nd aside or not? If we do, then I suggest we delete the para at 486.61. There's also a minor fix-up: "or A-MSDU" needs to be added after MSDU at 486.55 and 486.58. Disagree. The cited text: "The sequence number, for management frames and for data frames with the QoS subfield of the Subtype field set to 0, is generated by the transmitting STA as an incrementing sequence of integers." suffices to determine the sequence number for dot11OCBEnabled=true STAs. In this case, STAs have no knowledge of whether a peer is a QoS STA or not, or indeed any other capability information. As such it can use only mandatory features. The paragraphs cited as new by the commenter were, in fact, moved from 7.1.3.4.1 as part of an exercise to move behavioural description out of the frame format section. So the commenter's concern in this particular case is concerned, .11p had the chance to address this particular concern when writing the amendment. TGmb has conducted a review process with the former members of TGp to resolve conflict arising from changes made in TGmb and TGp. Former members of TGp who are in the sponsor ballot pool have further and continuing chances to address any remaining issues. To respond to the first aside, there is overlap between the functionality specified at 486.45 + 486.51 (the moved content) versus 486.61 (the original 9.3.2.11 content). The two are not inconsistent and no changes are proposed. To respond to the second aside, the commenter wrongly assumes a QoS BSS is an infrastructure BSS. This is not the case - witness the definition: "quality of service (QoS) basic service set (BSS): A BSS that provides the QoS facility.". |  |  |  | 2011-01-19 23:28 | GEN
10205 | Hunter, David | 1000 | 6 | 4.8 | 60 | 22 | E | Y | 60.22 | 22 | 4.8 |  | A |  |  |  | The Data Link Layer encompasses more than just the MAC. | Delete the line segment above "Data Link Layer" (indicating that the DLL extends up, above the MAC). | AGREE (GEN: 2011-01-19 23:30:30Z) - | GEN | Gen Motion 5 | Ready for motion | EDITOR: 2010-11-12 00:00:51Z Transferred to GEN. |  |  |  | 2011-01-19 23:31 | GEN
10066 | shi, yang | 1000 | 6 | 1.3 | 91 | 9 | E | N | 91.09 | 9 | 1.3 |  | A |  |  |  | The line only talks about the data frame protection while the protection of management frame is missed. |  | AGREE (GEN: 2011-01-20 01:04:31Z) - Add " and MAC management information" after "user information" at 2.09 | GEN | Gen Motion 5 | Ready for motion | EDITOR: 2010-11-12 00:02:36Z Transferred to GEN |  |  |  | 2011-01-20 01:05 | GEN
10065 | shi, yang | 1000 | 6 | 3.1 | 93 | 25 | E | N | 93.25 | 25 | 3.1 |  | D |  |  |  | Suggest to add definition of management frame, control frame and data frame, since these conceptions are important. |  | DISAGREE (GEN: 2011-01-20 01:05:41Z) - These are not terms, but names of frames. They are fully described in Clause 8. It is not necessary to provide an entry in the definitions for every named frame type. | GEN | Gen Motion 5 | Ready for motion | EDITOR: 2010-11-12 00:02:58Z - Transferred to GEN |  |  |  | 2011-01-20 01:06 | GEN
10081 | Stanley, Dorothy | 1000 | 6 | 8.4.1.1 | 277 | 59 | T | Y | 277.59 | 59 | 8.4.1.1 |  | P | Dan Harkins |  |  | there should be an authentication algorithm number that is "reserved for private use among consenting parties". | make 65535 or another designated value to indicate "private use". How the parties mutually consent to interpret its use is outside the scope of the standard but use of a vendor-specific AKM (advertised in beacons and probe responses) would indicate ability to do "something". What that "something" is is out of scope. It would be better if 32768-65535 (i.e. top bit=1) were "private use" but I'd be happy with a single authentication algorithm. Change from "Authentication algorithm number = 2: Fast BSS Transition All other values of authentication number are reserved." to "Authentication algorithm number = 2: Fast BSS Transition Authentication algorithm number = 65535: Private Use (use of the value is agreed to by mechanisms outside the scope of the standard) All other values of authentication number are reserved." | AGREE IN PRINCIPLE (GEN: 2011-01-19 21:49:29Z) Change from "Authentication algorithm number = 2: Fast BSS Transition All other values of authentication number are reserved." to "Authentication algorithm number = 2: Fast BSS Transition Authentication algorithm number = 65535: Vendor Specific use: (use of the value implies that a Vendor Specific IE is included with more information) All other values of authentication number are reserved." Also add an entry to dot11AuthenticationAlgorithm in the MIB for the Vendor Specific use. Also update the descriptions. | GEN | Gen Motion 5 | Ready for motion | Proposed Resolution: AGREE IN PRINCIPLE (GEN: 2011-01-19 04:05:33Z) Change from "Authentication algorithm number = 2: Fast BSS Transition All other values of authentication number are reserved." to "Authentication algorithm number = 2: Fast BSS Transition Authentication algorithm number = 65535: Experimental Private Use (use of the value is agreed to by mechanisms outside the scope of the standard) All other values of authentication number are reserved." The idea is that the Authentication Algorithim number is to be Vendor Specific Algorithm value that would have the specifics include the IE later in the frame. Naming of the bit would be better to be Vendor Specific Use. There would be a required Vendor Specific IE included when the Vendor Specific algorthim is used. Suggestion: Vendor Specific use: (use of the value implies that a Vendor Specific IE is included with more information) Proposed resolution 2: Change from "Authentication algorithm number = 2: Fast BSS Transition All other values of authentication number are reserved." to "Authentication algorithm number = 2: Fast BSS Transition Authentication algorithm number = 65535: Vendor Specific use: (use of the value implies that a Vendor Specific IE is included with more information) All other values of authentication number are reserved." |  |  |  | 2011-01-19 22:06 | GEN
10334 | Hunter, David | 1000 | 6 | 9.29.2 | 599 | 65 | T | Y | 599.65 | 65 | 9.29.2 |  | P |  |  |  | NOTE paragraphs are informative, and thus must contain no standards requirements terms (shall/should/may). | Replace "should" with "need to". | AGREE IN PRINCIPLE (GEN: 2011-01-20 01:09:07Z) - Replace: "These sounding PPDUs should be sent within a single TXOP." with "These sounding PPDUs need to be sent within a single TXOP in order to minimize the change in the channel during this procedure." | GEN | Gen Motion 5 | Ready for motion | EDITOR: 2010-12-14 15:56:10Z - I think turning this into "need to be" is stronger than necessary. Basically you get better data on which to base a decision if the channel has not evolved significantly between sounding PPDUs. I'm not sure how to word this. One option is to delete the cited sentence and let the reader go figure. Transferring to GEN. |  |  |  | 2011-01-20 01:09 | GEN
10345 | Hunter, David | 1000 | 6 | 10.2.1.2 | 616 | 28 | E | Y | 616.28 | 28 | 10.2.1.2 |  | D |  |  |  | The group of management frames that are bufferable seems to be fairly clearly delimited in the defintion in 3.2. But so far I haven't been able to find such a delimitation in the text -- where it needs to be. | Include the list of bufferable management frames in this section (where the term "bufferable management frames" is first used). At least duplicate the list given in 3.2; but it would be much better to add a note explaining why other management frames are not bufferable. | DISAGREE (GEN: 2011-01-20 01:11:13Z) - The definition in 3.2 is normative, duplication here would be unnecessary and harmful. Note to the commenter - the discussion on what types of management frame should be buffered was lengthy. It is inappropriate to reproduce the justification of those types in the standard. | GEN | Gen Motion 5 | Ready for motion | EDITOR: 2010-12-13 09:28:28Z Bill's resolution: Reject, the definition is normative. This doesn't respond to the idea of adding an explanatory note. Creating content is not an editorial function, so transferring to GEN. |  |  |  | 2011-01-20 01:12 | GEN
10399 | Hunter, David | 1000 | 6 | 11.5.1.3 | 769 | 4 | E | Y | 769.04 | 4 | 11.5.1.3 |  | P |  |  |  | "Pre-authentication" is not defined anywhare in this document | Either define "pre-authentication" or delete this sentence and the definition containing that term on page 4. | AGREE IN PRINCIPLE (GEN: 2011-01-20 01:14:05Z) - Preauthentication is defined in 11.4.8.2. However, additional introductory material may make this more accessible. Add an introductory para in 11.4.8.2: "Preauthentication allows a STA to perform RSN authentication with an AP prior to attempting (re)association. This can reduce the time that the IEEE 802.1X port is not valid." | GEN | Gen Motion 5 | Ready for motion | Bills resolution: Preauthentication is defined in 11.4.8.2. I have sympathy with the commenter. While defining how to do preauthentication, there is no statement as to what it is or is trying to achieve. I recommend adding an introductory para in 11.4.8.2: "Preauthentication allows a STA to authenticate with multiple APs prior to attempting (re)association. This can reduce the time that the IEEE 802.1X port is not valid." As the Editor does not create content, passing to GEN. |  |  |  | 2011-01-20 01:16 | GEN
10082 | Stanley, Dorothy | 1000 | 6 | 11.5.2 | 779 | 44 | T | Y | 779.44 | 44 | 11.5.2 |  | A | Dan Harkins | 11-10/1071r1 |  | The key descriptor version is extraneous, makes use of new hash algorithms very problematic, and is an impediment to use of Vendor-Specific OUIs for AKMs. | accept the recommendations in 11-10/1071r1 | AGREE (GEN: 2011-01-19 22:14:56Z) | GEN | Gen Motion 5 | Ready for motion |  |  |  |  | 2011-01-19 22:16 | GEN
10410 | Hunter, David | 1000 | 6 | 11.5.4.6 | 795 | 27 | T | Y | 795.27 | 27 | 11.5.4.6 |  | P |  |  |  | NOTE paragraphs are informative, and thus must contain no standards requirements terms (shall/should/may). | Replace "should log an error and deauthenticate the peer" with "directs that an error be logged an the peer deauthenticated." | AGREE IN PRINCIPLE (GEN: 2011-01-20 01:17:36Z) - Replace: "NOTE 1—If the RSN element check for Message 2 or Message 3 fails, IEEE Std 802.1X-2004 should log an error and deauthenticate the peer." with "If the RSN element check for Message 2 or Message 3 fails, the SME should log an error and deauthenticate the peer." | GEN | Gen Motion 5 | Ready for motion | EDITOR: 2010-12-16 10:01:49Z This may actually need to be turned into a normative statement. Certainly the proposed resolution is wrong, because IEEE Std 802.1X-2004 directs nothing about the response to RSN element checks. Transferring to MAC. |  |  |  | 2011-01-20 01:20 | GEN
10411 | Hunter, David | 1000 | 6 | 11.5.4.6 | 795 | 29 | T | Y | 795.29 | 29 | 11.5.4.6 |  | P |  |  |  | NOTE paragraphs are informative, and thus must contain no standards requirements terms (shall/should/may). | Replace "should check that" with "checks that, ". | AGREE IN PRINCIPLE (GEN: 2011-01-20 01:23:36Z) -- delete note 2. | GEN | Gen Motion 5 | Ready for motion | EDITOR: 2010-12-16 10:03:46Z It looks to me like this should be a normative statement, not a note. Transferring to MAC. TBD - what to do if check fails. Principle. Replace: "NOTE 2—The Supplicant should check that if the RSN element specified a pairwise cipher suite, then the 4-Way Handshake did specify to configure the temporal key portion of the PTK into the IEEE 802.11 STA." with "The Supplicant should check that if the RSN element specified a pairwise cipher suite, then the 4-Way Handshake did specify to configure the temporal key portion of the PTK into the IEEE 802.11 STA. If the check fails then ???." |  |  |  | 2011-01-20 01:24 | GEN
10135 | Worstell, Harry | 1000 | 6 | 11.5.4.8 | 796 | 1 | E | N | 796.01 | 1 | 11.5.4.8 |  | D |  |  |  | generic picture for a station should be updated to 21st century | make a iPhone; also at 800.45 | DISAGREE (GEN: 2011-01-20 01:24:49Z) - Disagree. The standard is agnostic about the type of device that represents a STA. A change to any other identifiable type of user equipment (e.g. cellphone, set-top-box/TV, vending machine, sports shoe/sneaker, T-shirt ...) will be equally inapplicable to the remaining types of user equipment, so no benefit would be gained by making that change. | GEN | Gen Motion 5 | Ready for motion | EDITOR: 2010-12-13 10:05:30Z The editor is unwilling to take a position on which image most accurately represents our concept of a "Station". Embedding a picture of an iPhone would raise interesting questions of copyright that I would prefer to avoid. Assigning to GEN, so the group can make a decision as to which picture most accurately represents a generic STA. |  |  |  | 2011-01-20 01:25 | GEN
10414 | Hunter, David | 1000 | 6 | 11.5.7.3 | 812 | 40 | T | Y | 812.4 | 40 | 11.5.7.3 |  | P |  |  |  | NOTE paragraphs are informative, and thus must contain no standards requirements terms (shall/should/may). | Replace "should be" with "are". | AGREE IN PRINCIPLE (GEN: 2011-01-20 01:26:13Z) - Remove "NOTE 1-" | GEN | Gen Motion 5 | Ready for motion | EDITOR: 2010-12-16 10:05:11Z If this statement is not made elsewhere normatively, then perhaps this note should be a normative statement. Transferring to MAC. |  |  |  | 2011-01-20 01:27 | GEN
10415 | Hunter, David | 1000 | 6 | 11.5.7.3 | 812 | 42 | T | Y | 812.42 | 42 | 11.5.7.3 |  | P |  |  |  | NOTE paragraphs are informative, and thus must contain no standards requirements terms (shall/should/may). | Replace "should be" with "are". | AGREE IN PRINCIPLE (GEN: 2011-01-20 01:26:44Z) - Remove "NOTE 2-" | GEN | Gen Motion 5 | Ready for motion | EDITOR: 2010-12-16 10:05:11Z If this statement is not made elsewhere normatively, then perhaps this note should be a normative statement. Transferring to MAC. |  |  |  | 2011-01-20 01:28 | GEN
10088 | Fischer, Matthew | 1000 | 6 | 17.3.9.3 | 1049 | 21 | T | Y | 1049.21 | 21 | 17.3.9.3 |  | D |  |  |  | TX mask limits include an absolute value. This specification is not correct, and is also too stringent. It is not correct because the subbands of allowed operation in different regulatory domains have different absolute limits and this is not reflected by the single absolute limit that is provided. Secondly, the combination of an absolute and a relative limit is not correctly specified - the mask should be specified as requiring the device to meet the higher of the two values, relative and absolute. Same problems for 10 and 5 MHz masks. | Respecify to account for the errors indicated, either listing the absolute limits for each subband and regulatory domain, for example, -30dBm/MHz in the USA 5.15 - 5.25 GHz subband based on the 40mW limit -> 16dBm => 3dBm/MHz minus 40 dBr => -37 dBm/MHz --- and change the AND between the relative and absolute specs to be a "the higher of the two limits" - or more simply, drop the absolute limits - Also make similar changes to 10 and 5 MHz masks. | DISAGREE (GEN: 2011-01-20 01:00:15Z) 11a, 11n and now 11ac are consistent in specifying these numbers, so that changes to 11n only are not necessary or desirable. This change would significantly increase the noise floor with the mask relaxation. | GEN | Gen Motion 5 | Ready for motion |  |  |  |  | 2011-01-20 02:37 | GEN
10079 | Perahia, Eldad | 1000 | 6 | 19.3.11.4 | 1152 | 39 | T | N | 1152.39 | 39 | 19.3.11.4 |  | P |  |  |  | The sentence "When the BCC FEC encoder is used, a single encoder is used, except that two encoders shall be used when the selected MCS has a PHY rate greater than 300 Mb/s. To determine whether to use one or two BCC FEC encoders, the rate is calculated based on the use of an 800 ns GI." is confusing and irrelevant. Clause 19.6 has "shalls" specifying how many encoders to use based on the data rate. | Replace these sentences with "When the BCC FEC encoder is used, refer to clause 19.6 for the number of encoders to use." | AGREE IN PRINCIPLE (GEN: 2011-01-20 01:57:21Z) replace in (6.04) 1262.40 "except that two encoders shall be used when" with "except that two encoders are used when" add a reference to the end of this sentence to clause 19.6. | GEN | Gen Motion 5 | Ready for motion |  |  |  |  | 2011-01-20 01:59 | GEN
10089 | Fischer, Matthew | 1000 | 6 | 19.3.20.1 | 1181 | 39 | T | Y | 1181.39 | 39 | 19.3.20.1 |  | D |  |  |  | TX mask limits include an absolute value. This specification is not correct, and is also too stringent. It is not correct because the subbands of allowed operation in different regulatory domains have different absolute limits and this is not reflected by the single absolute limit that is provided. Secondly, the combination of an absolute and a relative limit is not correctly specified - the mask should be specified as requiring the device to meet the higher of the two values, relative and absolute. See similar problems for 40 MHz mask. | Respecify to account for the errors indicated, either listing the absolute limits for each subband and regulatory domain, for example, -30dBm/MHz in the USA 5.15 - 5.25 GHz subband based on the 40mW limit -> 16dBm => 3dBm/MHz minus 40 dBr => -37 dBm/MHz --- and change the AND between the relative and absolute specs to be a "the higher of the two limits" - or more simply, drop the absolute limits - Also make similar changes to 40 MHz mask. | DISAGREE (GEN: 2011-01-20 01:00:15Z) 11a, 11n and now 11ac are consistent in specifying these numbers, so that changes to 11n only are not necessary or desirable. This change would significantly increase the noise floor with the mask relaxation. | GEN | Gen Motion 5 | Ready for motion | copy resolution to proposal to 10088. |  |  |  | 2011-01-20 02:37 | GEN
10080 | Stephens, Adrian | 1000 | 6 | Annex C |  |  | T | Y | 1350 | 1 | C |  | A |  |  |  | Compile the MIB and resolve any compilation errors | As in comment | AGREE (GEN: 2011-01-19 05:23:00Z) The MIB has been compiled. | GEN | Gen Motion 5 | Ready for motion | proposed resolution from https://mentor.ieee.org/802.11/dcn/10/11-10-1329-01-000m-misc-resolutions.xls . = Accept |  |  |  | 2011-01-19 22:42 | GEN
10009 | Landt, Jeremy | 1000 | 6 | Annex D | 1630 | 1 | T | Y | 1630.01 | 1 | Annex D |  | D |  |  |  | Draft is not the result of rollup of Std 802.11-2007 and published amendments. Technical information has been eliminated. | Replace Draft P802.11-REVmb/D6.0 Annex D with Std 802.11-2007 Annex I as ammended by approved amendments, restoring deleted text, tables and figures. | DISAGREE (GEN: 2011-01-19 22:52:54Z) Draft P802.11-Revmb/D6.0 contained the results from the TGmb maintainance on Std 802.11-2007 as well as the roll-up of 11k, r, y, w, and n. Published amendments will be rolled in as they become available in recirculations. Annex I and J were combined, and duplication of regulatory rules were removed. | GEN | Gen Motion 5 | Ready for motion | decline - Draft P802.11-Revmb/D6.0 contained the results from the TGmb maintainance on Std 802.11-2007 as well as the roll-up of 11k, r, y, w, and n. 11p, z, v, and u will be rolled in as they become available in recirculations. Annex I an J were combined, and duplication of regulatory rules were removed. |  |  |  | 2011-01-19 22:55 | GEN
10010 | Landt, Jeremy | 1000 | 6 | Annex E | 1635 | 1 | T | Y | 1635.01 | 1 | Annex E |  | D |  |  |  | Draft is not the result of rollup of Std 802.11-2007 and published amendments. Technical information has been eliminated. | Replace Draft P802.11-REVmb/D6.0 Annex E with Std 802.11-2007 Annex J as ammended by approved amendments, restoring deleted text, tables and figures. | DISAGREE (GEN: 2011-01-19 22:55:14Z) Draft P802.11-Revmb/D6.0 contained the results from the TGmb maintainance on Std 802.11-2007 as well as the roll-up of 11k, r, y, w, and n. Published amendments will be rolled in as they become available in recirculations. Annex I and J were combined, and duplication of regulatory rules were removed. | GEN | Gen Motion 5 | Ready for motion | decline - Draft P802.11-Revmb/D6.0 contained the results from the TGmb maintainance on Std 802.11-2007 as well as the roll-up of 11k, r, y, w, and n. 11p, z, v, and u will be rolled in as they become available in recirculations. Annex I an J were combined, and duplication of regulatory rules were removed. |  |  |  | 2011-01-19 22:56 | GEN
10140 | Fischer, Matthew | 1000 | 6 | Q.4 | 2000 | 47 | T | Y | 2000.47 | 47 | Q.4 |  | P |  |  |  | Each of the sequences described for explicit NDP in this subclause contradict the normative text description for NDP sequences found in 9.30.1, where the control response frame for and NDPA frame always precedes the NDP transmission. | swap the order of NDP transmission and control response transmission in each described sequence for the explicit case of NDP transmission | AGREE IN PRINCIPLE (GEN: 2011-01-20 02:01:28Z) incorporate the changes in https://mentor.ieee.org/802.11/dcn/11/11-11-0170-01-000m-revmb-sb-ndp-sequence-cids-proposed-resolution.doc. | GEN | Gen Motion 5 | Ready for motion |  |  |  |  | 2011-01-20 02:05 | GEN
10156 | Kim, Youhan | 1000 | 6 | Q.4 | 2000 | 53 | T | Y | 2000.53 | 53 | Q.4 |  | P |  |  |  | According to Clause 9.30.1 (p. 603, line 44-47), NDP is sent after receiving ACK if the NDP announcement was sent in a packet requiring immediate response. However, the example in Q.4 (p. 2000, line 53) shows that the sequence of NDPA(normal-ack)-->NDP-->ACK. This is incorrect. Same comment applies to lines 59 and 65. | Delete lines 53, 59 and 65. Then add new examples which show the sequence of NDPA-->ACK/BA-->NDP-->Feedback. | AGREE IN PRINCIPLE (GEN: 2011-01-20 02:01:28Z) incorporate the changes in https://mentor.ieee.org/802.11/dcn/11/11-11-0170-01-000m-revmb-sb-ndp-sequence-cids-proposed-resolution.doc. | GEN | Gen Motion 5 | Ready for motion |  |  |  |  | 2011-01-20 02:04 | GEN

## Gen Motion 4
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
10116 | Rosdahl, Jon | 1000 | 6 |  | 1172 | 29 | T | Y | 1172.29 | 29 |  |  | D |  |  |  | 19.3.12.2 - The text is 'STA B sends the quantized estimates of H(tilde)_AB,k to STA A'. The normal interpretation of Figure 20-15 is that H(tilde)_AB,k includes the imbalances in transmit and receive chains at STA A and STA B and the over the air channel and that it does not include spatial mapping. This is further supported by the text on page 1269 Line 6 which states that 'The relationship between the baseband-to-baseband channel, H(tilde)_AB,k, and the over-the-air channel, H_AB,k, is shown in Equation (20-64)'. - On page 592 Line 54 the text is 'The calibration responder shall not remove the spatial mapping from the CSI to be fed back to the initiator of the frame exchange.' I cannot see how these statements can be made to agree, with any amount of stretching the meanings of words and figures: in one case the channel matrix that is quantised and fed back to STA A does not include the spatial mapping and in the other case it does. (See CID 3082) Notes indicate that CID 3082 was pointing out a correct issue, but was rejected without the specific text to change. Note that in 19.3.12.2 the text is 'STA B sends the quantized estimates of H(tilde)_AB,k to STA A'. This is an unambiguous statement, but it is incorrect since VK's comment [Email exchange documented in CID 3082] confirms that H(tilde)_AB,k does not include the spatial mapping. So this section clearly instructs the implementer of STA B to send to STA A CSI feedback that does not include the spatial mapping. This is plain wrong. Section 19.3.12.2 should be modified to show clearly that H(tilde)_AB,k includes the transmitter's spatial mapping. | changes to section 20.3.12.1 are: - Figure 20-15 to also show the spatial mapping matrix for sounding Q_A [at STA A], Q_B [at STA B]. - Statement o 'STA B sends the quantized estimates of H(tilde)_AB,k to STA A' [802.11mb-d6.0, p1172, line 29] to be changed to o 'STA B sends the quantized estimates of H(tilde)_AB,k*Q_A,k to STA A' | DISAGREE (GEN: 2011-01-19 05:12:41Z) The clause is informative, and the sentence "Spatial mapping matrices QA, k and QB, k are assumed to be identity matrices here for simplicity of illustration." This applies to both the figure and to the following example equations. The note cited in 19.3.12.2 is "NOTE—When a non-identity matrix is used for QA, k, STA A is responsible for accounting for the spatial mapping in its local channel estimate as well as in the quantized CSI fed back since the channel feedback received in step c) is actually H ˜AB k , QA k and not ˜AB, k. Furthermore, since QB, k is defined in 19.3.13.3 (Sounding PPDU for calibration), additional steps can be taken in STA A to remove the effect of QB, k when computing the correction matrix KA, k." STA A is responsible for accounting for the spatial mapping, as well as, the quantized CSI feedback. No change is needed. | GEN | Gen Motion 4 | Ready for motion | The note cited in 19.3.12.2 is "NOTE—When a non-identity matrix is used for QA, k, STA A is responsible for accounting for the spatial mapping in its local channel estimate as well as in the quantized CSI fed back since the channel feedback received in step c) is actually H ˜AB k , QA k and not ˜AB, k. Furthermore, since QB, k is defined in 19.3.13.3 (Sounding PPDU for calibration), additional steps can be taken in STA A to remove the effect of QB, k when computing the correction matrix KA, k." STA A is responsible for accounting for the spatial mapping, as well as, the quantized CSI feedback. No change is needed. Well, it’s not such a big deal, at least the notes went in. However, it is disappointing to see that the ‘group’ goes to extreme lengths to avoid accepting they are/were wrong. In order to avoid changing a figure and an equation to make them clear/correct they have chosen to add two notes that effectively say “all the description here of how calibration works is deliberately misleading since for the sake of simplicity [here read “for the sake of not admitting we made a mistake”] we assume that Q_A,k and Q_B,k are identity matrices.” This is not benefitting the quality of the standard. With regard to the formulation of the note “When a non-identity matrix is used for QA, k …” -- in fact, the only case where STA A [the calibration initiator] could use an identity matrix for QA, k is the case where it has only one antenna [see 19.3.13.3], which would never happen in practice since in this case STA A requires no calibration. Andrei |  |  |  | 2011-01-20 22:39 | GEN

## Gen Motion 3
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
10108 | Rosdahl, Jon | 1000 | 6 |  |  |  | T | Y |  |  | 8.4.2.37 |  | D |  |  |  | 8.4.2.37 QoS Capability element, states: "The QoS Capability element contains a number of subfields that are used to advertise optional QoS capabilities at a QoS STA. The QoS Capability element is present in Beacon frames that do not contain the EDCA Parameter Set element and in (Re)Association Request frames." Section 9.2.4.2 HCF contention-based channel access (EDCA), states: "A QoS STA shall update its MIB values of the EDCA parameters within an interval of time equal to one beacon interval after receiving an updated EDCA parameter set. QoS STAs update the MIB attributes and store the EDCA Parameter Set update count value in the QoS Info field. An AP may change the EDCA access parameters by "changing the EDCA Parameter Set element in the Beacon frame, Probe Response frame, and (Re)Association Response frame." However, the AP should change them only rarely. A QoS STA shall use the EDCA Parameter Set Update Count Value subfield in the QoS Capability element of all Beacon frames to determine whether the STA is using the current EDCA Parameter Values. If the EDCA Parameter Set update count value in the QoS Capability element is different from the value that has been stored, the QoS STA shall query the updated EDCA parameter values by sending a Probe Request frame to the AP." Hence 1. An AP may change the EDCA access parameters by changing the EDCA Parameter Set element in the Beacon frame (see point 3) 2. EDCA Parameter Set Update Count Value subfield in the QoS Capability element of all Beacon frames, BUT 3. The QoS Capability element is present in Beacon frames that do not contain the EDCA Parameter Set element This seems inconsistent. | Reconcile the inconsitency. | DISAGREE (GEN: 2011-01-19 03:57:26Z) The QoS Capability element is in Beacon Frames without the EDCA Parameter Set. Because it does include the EDCA Parameter Set update count, then the beacon is able to indicate which EDCA Paramenter set is currently in use. This makes the Beacon consistent in indicating which EDCA information is current. | GEN | Gen Motion 3 | Ready for motion | Disagree -- The QoS Capability element is in Beacon Frames without the EDCA Parameter Set. Because it does include the EDCA Parameter Set update count, then the beacon is able to indicate which EDCA Paramenter set is currently in use. This makes the Beacon consistent in indicating which EDCA information is current. |  |  |  | 2011-01-19 03:58 | GEN
10020 | Mccann, Stephen | 1000 | 6 | 8.4.2.1 | 305 | 25 | T | N | 305.25 | 25 | 8.4.2.1 |  | D |  |  |  | Why is the maximum length of the TCLAS element (and others) 257 octets? This can be a difficult size to implement. | Either change the maximum size to 256 or perhaps provide a footnote explaiing why it is 257. | DISAGREE (GEN: 2011-01-19 04:13:02Z) There are 5 instances of 257 in the .11/2007 revision, including this cited example. Changing this would cause interoperability issues. | GEN | Gen Motion 3 | Ready for motion | Propose disagree: There are 5 instances of 257 in the .11/2007 revision, including this cited example. Changing this would cause interoperability issues. |  |  |  | 2011-01-19 04:13 | GEN
10016 | Mccann, Stephen | 1000 | 6 | 8.4.2.37 | 389 | 12 | T | N | 389.12 | 12 | 8.4.2.37 |  | D |  |  |  | Why is the length field in Figure 8-160 shown as "Length(1)". I'm not sure what the "(1)" refers to. Same issue in Figure 8-77 P315L30, Figure 8-86 P319L60, Figure 8-141 P377L35 and a few others. | Possibly remove the "(1)" from the length field in the figure. | DISAGREE (GEN: 2011-01-19 04:37:12Z) - The value of the field is being specified. | GEN | Gen Motion 3 | Ready for motion | Propose Agree in Principle: in D6.04: 371.55, (figure 8-77), 442.48 (Figure 8-152), 442.57 (Figure 8-153), 444.12 (Figure 8-157), and 445.41 (Figure 8-160), remove the Extraneous "(1)" in the figure. The length of the field is below the figure in each case. |  |  |  | 2011-01-19 04:39 | GEN
10031 | Fischer, Matthew | 1000 | 6 | 9.3.2.11 | 487 | 1 | T | Y | 487.01 | 1 | 9.3.2.11 |  | P | Matthew Fischer | 11-11/138r0 |  | The cache-filling descriptions are lacking. There is no discrimination here for what goes into any given cache, but there should be. | Change the cache-filling instructions such that the first cache mentioned is only used for non-QOS receptions by any STA and the second cache is only used for QOS receptions by QoS STAs. E.g. "The receiving STA shall keep a cache of recently received <Address 2, sequence-number, fragment-number> tuples." becomes something like this: "The receiving STA shall keep a cache of recently received <Address 2, sequence-number, fragment-number> tuples from non-QoS MSDUs." In order to make the rejection text work properly, both caches are going to need a label as well. I suggest non-QoS duplicate cache and QoS duplicate cache and then use the appropriate reference wherever the noun cache is currently employed in this subclause. | AGREE IN PRINCIPLE (GEN: 2011-01-19 03:43:38Z) Incorporate the changes in https://mentor.ieee.org/802.11/dcn/11/11-11-0138-00-000m-receive-buffer-operations-cid-10031-10032.docx. | GEN | Gen Motion 3 | Ready for motion | Submission Required. |  |  |  | 2011-01-19 03:53 | GEN
10032 | Fischer, Matthew | 1000 | 6 | 9.3.2.11 | 487 | 12 | T | Y | 487.12 | 12 | 9.3.2.11 |  | P | Matthew Fischer | 11-11/138r0 |  | The rejection instructions are not correct. The caching instructions do not exclude the QoS STA in filling the first cache, but the rejection instructions do exclude it. This means that QoS STAs will not correctly check for duplicates that are not QoS MSDUs. Note that the second sentence of the rejection checking paragraph includes "also" but the first sentence explicitly excluded "QoS STA" - so why is "also" used? I believe that "also" is correct, which means that the entire paragraph needs some work and so does the preceding paragraph because the cached information for non-QoS MSDUs seems to get lost by QoS STAs. | I believe that the paragraph should read as follows: "A STA shall reject as a duplicate frame any non-QoS frame in which the Retry bit in the Frame Control field is 1 and that matches an <Address 2, sequence-number, fragment-number> tuple of an entry in the non-QoS cache. A receiver QoS STA shall also reject as a duplicate frame any QoS frame in which the Retry bit in the Frame Control field is 1 and that matches an <Address 2, TID, sequence-number, fragment-number> tuple of an entry in the QoS cache." | AGREE IN PRINCIPLE (GEN: 2011-01-19 03:52:46Z) Incorporate the changes in https://mentor.ieee.org/802.11/dcn/11/11-11-0138-00-000m-receive-buffer-operations-cid-10031-10032.docx. | GEN | Gen Motion 3 | Ready for motion | Submission required. |  |  |  | 2011-01-19 03:55 | GEN
10071 | Perahia, Eldad | 1000 | 6 | 17.3.11 | 1056 | 23 | T | N | 1056.23 | 23 | 17.3.11 |  | P |  |  |  | 17.3.2.2 d) states that string is extended by at least 6 bits. Then e) says to scramble. J.1.1 i) add pad bits, j) scramble. 17.3.11 pg 1056, line 53 "padded prior to scrambling". Fig 17-17 conflicts with all the above, which shows bit padding added after scrambling. | fix figure | AGREE IN PRINCIPLE (GEN: 2011-01-19 04:42:57Z) move padding prior to scrambling in the cited figure. Move the "Bit Padding if Needed" block to after the "Tail Bit" after the PSDU block. | GEN | Gen Motion 3 | Ready for motion | Propose: Agree in Principle, move padding prior to scrambling in the cited figure. |  |  |  | 2011-01-19 04:46 | GEN
10072 | Perahia, Eldad | 1000 | 6 | 17.3.12 | 1058 | 27 | T | N | 1058.27 | 27 | 17.3.12 |  | P |  |  |  | Fig 17-19 makes it appear that the pad bits are not part of the scrambing and coding. However in the transmit flow, the padding comes before the scrambling and coding. | fix figure such that pad bits are part of C-PSDU | AGREE IN PRINCIPLE (GEN: 2011-01-19 04:46:33Z) Move the "Bit Removing if Needed" block to after the "Tail bit" block after the PSDU in figure 17-19. | GEN | Gen Motion 3 | Ready for motion | Propose: Agree in Principle, move padding prior to scrambling in the cited figure. |  |  |  | 2011-01-19 04:49 | GEN
10073 | Perahia, Eldad | 1000 | 6 | 19 | 1109 | 1 | T | N | 1109.01 | 1 | 19 |  | D |  |  |  | renumbering clause 20 to 19 will confuse me forever. I won't be able to keep straight which is 11g and which is 11n | change 11g back to 19 and 11n back to 20. | DISAGREE (GEN: 2011-01-19 04:49:08Z) Clause numbers change over time as the standard is amended and revised. | GEN | Gen Motion 3 | Ready for motion | Decline -- Clause numbers change over time as the standard is amended and revised. |  |  |  | 2011-01-19 04:49 | GEN
10075 | Perahia, Eldad | 1000 | 6 | 19.3.22 | 1189 | 50 | T | N | 1189.5 | 50 | 19.3.22 |  | A |  |  |  | bit padding is before scambling and encoding | fix figures 19-20 and 19-21, accordingly | AGREE (GEN: 2011-01-19 05:14:17Z) Editor to See CID 10071 and 10072. | GEN | Gen Motion 3 | Ready for motion | Agree |  |  |  | 2011-01-19 05:16 | GEN
10076 | Perahia, Eldad | 1000 | 6 | 19.3.23 | 1193 | 14 | T | N | 1193.14 | 14 | 19.3.23 |  | A |  |  |  | Fig 19-23 makes it appear that the pad bits are not part of the scrambing and coding. However in the transmit flow, the padding comes before the scrambling and coding. | fix figure such that pad bits are part of C-PSDU | AGREE (GEN: 2011-01-19 05:15:41Z) Editor to See CID 10071 and 10072. | GEN | Gen Motion 3 | Ready for motion | Agree |  |  |  | 2011-01-19 05:16 | GEN
10074 | Perahia, Eldad | 1000 | 6 | 19.4.3 | 1202 | 51 | T | N | 1202.51 | 51 | 19.4.3 |  | P |  |  |  | N_sym is already defined in 19-32 for BCC and 19-41for LDPC. The same definition should not be in multiple spots | Replace Eq 19-95 with a reference to 19-32 and 19-41 | AGREE IN PRINCIPLE (GEN: 2011-01-19 05:21:48Z) Delete Eq 19-95 and change the text for N_SYM with the following: N_SYM is defined in Equation (19-32) for BCC and Equation (19-41) for LDPC. | GEN | Gen Motion 3 | Ready for motion | Proposed: Agree in Principle: Delete Eq 19-95 and change the text for N_SYM with the following: N_SYM is defined in Equation (19-32) for BCC and Equation (19-41) for LDPC. |  |  |  | 2011-01-19 05:22 | GEN

## MAC Motion D
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
10054 | Fischer, Matthew | 1000 | 6 | 9.3.2.8.1 | 483 | 39 | T | Y | 483.39 | 39 | 9.3.2.8.1 |  | A |  |  |  | Incorrect wording. This text is describing a CTS 2 SELF that occurs before the full exchange. Certainly, this text should allow the AP to continue only if the medium is IDLE. Note, as an example, a PIFS vs IDLE transmission rule is used inside of the box above the text in another case. | Change the existing sentence to read: "The AP may continue a PIFS after the CTS, only if the CS mechanism (see 9.3.2.2 (CS mechanism)) indicates that the medium is IDLE at the TxPIFS slot boundary (defined in 9.3.7 (DCF timing relations)) following the transmission of the CTS." | AGREE (MAC: 2010-11-09 22:27:29Z) | GEN | MAC Motion D | Ready for motion | This changes busy to idle in the cited text. It looks as if "idle" should be used. |  |  |  | 2011-01-19 22:42 | GEN
10034 | Fischer, Matthew | 1000 | 6 | 9.18.5 | 525 | 37 | T | Y | 525.37 | 37 | 9.18.5 |  | P |  |  |  | The text says that if a "STA parsing a Country element finds a First Channel Number or Operating Class field with a reserved value, the STA shall ignore the remainder of the Country element" - this seems like overkill. Only first channel number would be expected to cause a new format of the subfields to be introduced and thereby cause a parsing problem for STAs unaware of the new format. Reserved operating classes should be simply ignored. | Delete the text "or Operating Class field" | AGREE IN PRINCIPLE (MAC: 2010-11-10 23:59:51Z) - Change "finds a First Channel Number or Operating Class field with a reserved value" to "finds a invalid First Channel Number field or Operating Class field with a value that is reserved" | GEN | MAC Motion D | Ready for motion | Propose Accept. |  |  |  | 2011-01-19 06:47 | EDITOR
10115 | Rosdahl, Jon | 1000 | 6 |  | 628 |  | T | Y | 628 |  |  |  | P |  |  |  | The text in 10.3 has some inconsistencies as documented in 11-10-0728r2. | use 11-10/826 to correct the issues identified. | AGREE IN PRINCIPLE (MAC: 2011-01-18 00:23:21Z) Adopt the changes indicated in document 11-10/1364 | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 23:01 | GEN
10094 | Hamilton, Mark | 1000 | 6 | 10.3 | 628 | 58 | T | Y | 628.58 | 58 | 10.3 |  | P |  |  |  | It needs to be clarified in this subclause which actions labeled as "STA shall" are really "MLME shall" and which are "SME shall" | See changes proposed in 10/0728r2 | Accept in Principle. Adopt the changes given in https://mentor.ieee.org/802.11/dcn/10/11-10-1364-01-000m-subclause-10-3-clean-up-proposal.docx. | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10095 | Hamilton, Mark | 1000 | 6 | 10.3 | 628 | 58 | T | Y | 628.58 | 58 | 10.3 |  | P |  |  |  | It is unclear what "appropriate reason code" implies in this subclause Use the reason code delivered via the various .request primitives. | See changes proposed in 10/0728r2 | Accept in Principle. Adopt the changes given in https://mentor.ieee.org/802.11/dcn/10/11-10-1364-01-000m-subclause-10-3-clean-up-proposal.docx. | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10096 | Hamilton, Mark | 1000 | 6 | 10.3 | 628 | 58 | T | Y | 628.58 | 58 | 10.3 |  | P |  |  |  | Several bullet list items in this subsection are impossible to understand. | See changes proposed in 10/0728r2 | Accept in Principle. Adopt the changes given in https://mentor.ieee.org/802.11/dcn/10/11-10-1364-01-000m-subclause-10-3-clean-up-proposal.docx. | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10097 | Hamilton, Mark | 1000 | 6 | 10.3 | 628 | 58 | T | Y | 628.58 | 58 | 10.3 |  | P |  |  |  | The architectural model is blurred in this sub-clause. It is not clear: 1) how memory of a previous failed SA Query procedure is retained, and whether this is in the MLME or SME; 2) whether the sending of the protected disassociation frame is an action of the MLME or SME. It is likely the latter, but it is expressed as though it were the former. | See changes proposed in 10/0728r2 | Accept in Principle. Adopt the changes given in https://mentor.ieee.org/802.11/dcn/10/11-10-1364-01-000m-subclause-10-3-clean-up-proposal.docx. | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10098 | Hamilton, Mark | 1000 | 6 | 10.3 | 628 | 58 | T | Y | 628.58 | 58 | 10.3 |  | P |  |  |  | Text in this sub-clause assumes the SME can see the contents of the Reassociation response frame, which is not true. | See changes proposed in 10/0728r2 | Accept in Principle. Adopt the changes given in https://mentor.ieee.org/802.11/dcn/10/11-10-1364-01-000m-subclause-10-3-clean-up-proposal.docx. | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10099 | Hamilton, Mark | 1000 | 6 | 10.3 | 628 | 58 | T | Y | 628.58 | 58 | 10.3 |  | P |  |  |  | 10.3.2.2 and 10.3.2.3 say the PTKSA gets deleted at 802.11 Authentication. 802.11 Authentication has nothing to do with the PTKSA | See changes proposed in 10/0826r5 | Accept in Principle. Adopt the changes given in https://mentor.ieee.org/802.11/dcn/10/11-10-1364-01-000m-subclause-10-3-clean-up-proposal.docx. | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10100 | Hamilton, Mark | 1000 | 6 | 10.3 | 628 | 58 | T | Y | 628.58 | 58 | 10.3 |  | P |  |  |  | Authentication failure does not change state (at either STA) even if not MFP (this is e.g. to avoid DoS between auth and asoc where an attacker keeps injecting fake broken auth frames while you're trying to get associated so you can engage MFP). Authentication success takes you from state 1 to state 2 but does not take you down from state 3 or 4 to state 2, even if not MFP. This is for protection against open system authentication attack (in MFP especially), by not going from state 3 or 4 down if authentication requested or even succeeds. | See changes proposed in 10/0826r5 | Accept in Principle. Adopt the changes given in https://mentor.ieee.org/802.11/dcn/10/11-10-1364-01-000m-subclause-10-3-clean-up-proposal.docx. | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10102 | Hamilton, Mark | 1000 | 6 | 10.3 | 628 | 58 | T | Y | 628.58 | 58 | 10.3 |  | P |  |  |  | Failure to (re)assoc on STA does not change state or delete keys in FT case. On tx of (re)assoc on STA if not FT then drop keys and go to state 3 if in state 4 (you have to drop keys if MFP so can be ready for 4WH). Failure to (re)assoc on AP does not change state or delete keys on FT case or MFP case (to avoid DOS). On rx of (re)assoc on AP if not FT or MFP then AP has to drop keys and go to state 3 if in state 4. On successful (re)assoc on AP if MFP then AP drops keys and goes to state 3 if in state 4 -- no action on failure. Successful (re)assoc if in state 4 without FT or MFP therefore takes you back to state 3 (or lower -- see next point) and you have to redo the 4WH. Failed (re)assoc without FT or MFP does not change state. | See changes proposed in 10/0826r5 | Accept in Principle. Adopt the changes given in https://mentor.ieee.org/802.11/dcn/10/11-10-1364-01-000m-subclause-10-3-clean-up-proposal.docx. | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10008 | Stephens, Adrian | 1000 | 6 | 10.3 | 628 | 58 | T | Y | 628.58 | 58 | 10.3 |  | P |  |  |  | 1. We have two separate variables in 10.3.1, but state elsewhere is treated as an enumeration. 2. The state machine cannot be localized to either the SME or the MLME. Some of its transitions respond to events known only within the MLME and some to events known only within the SME. Having a state machine split over two architectural entities in this way implies the existence of communications not documented in the MLME-SAP. The distinction between states 3 and 4 has no effect on the operation of the MAC or MLME, and therefore serves no purpose. The experiment post D1.0 of REVmb to "clarify" this state has had the opposite effect and should be deemed a failed experiment. 3. The location of the state variable and the responsibility for maintaining it are not defined. 4. Given that the state variable is located in one or other of the MLME or SME, there is no interface to allow this variable to be read from the other architectural entity. 5. Some of the text is impenetrable and needs to be restructured (e.g. 10.3.3.3 bullet c). I am lumping these comments together because I believe they need to be considered together. | 1. Replace two state variables with an enumeration 2. Remove the distinction between states 3 and 4 within the MAC and MLME. 3. Indicate that the state variable sits in the MLME and is maintained by the MLME and update language to reflect this. 4. Add an MLME interface to export the MLME state variable (read-only) 5. Restructure impenetrable text to improve readability, e.g. by adding sub-bullets inside longwinded list items. | Accept in Principle. Adopt the changes given in https://mentor.ieee.org/802.11/dcn/10/11-10-1364-01-000m-subclause-10-3-clean-up-proposal.docx. | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10104 | Hamilton, Mark | 1000 | 6 | 10.3 | 628 | 58 | T | Y | 628.58 | 58 | 10.3 |  | P |  |  |  | The descriptions of the transitions from State 3 to State 4 do not make it clear which entity (SME or MLME) writes to the state variable (it needs to be MLME to not have more than one writer), nor how the MLME has enough information to know when to do this transtion. The architectural model for MAC state (which is said to be maintained by MLME) and the 802.1X state, is confusing in this regard. This makes FT transition very hard to understand as well. | See changes proposed in 10/0826r5 | Accept in Principle. Adopt the changes given in https://mentor.ieee.org/802.11/dcn/10/11-10-1364-01-000m-subclause-10-3-clean-up-proposal.docx. | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10103 | Hamilton, Mark | 1000 | 6 | 10.3 | 628 | 58 | T | Y | 628.58 | 58 | 10.3 |  | P |  |  |  | The transitions from states 3 and 4 to state 2 for unsuccessful (re)association are not true at an AP. Doing this transition at an AP opens a denial-of-service attack -- a rogue STA sending failing (re)association requests on behalf of a target STA causes the AP to put the target STA back into state 2 and deny it service. | See changes proposed in 10/0826r5 | Accept in Principle. Adopt the changes given in https://mentor.ieee.org/802.11/dcn/10/11-10-1364-01-000m-subclause-10-3-clean-up-proposal.docx. | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10084 | Stanley, Dorothy | 1000 | 6 | 10.3 | 629 | 4 | T | Y | 629.04 | 4 | 10.3 |  | D |  |  |  | Restore the 3 state model, as there are layering issues that cannot be accurately represented currently. | As in comment. | DISAGREE (MAC: 2011-01-18 00:31:41Z) - Adopt the changes given in https://mentor.ieee.org/802.11/dcn/10/11-10-1364-01-000m-subclause-10-3-clean-up-proposal.docx. | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10144 | Malinen, Jouni | 1000 | 6 | 10.3 | 629 | 10 | T | N | 629.1 | 10 | 10.3 |  | D |  |  |  | Introduction of the new "State 4" makes description of MLME unnecessarily complex. While a description of combinations of MLME State and IEEE 802.1X Controlled Port may indeed be useful as an introduction to RSN, it does not look necessary for describing MLME behavior in normative text. | Consider reverting the introduction of State 4 to simplify MLME state description in 10.3. | DISAGREE (MAC: 2011-01-18 00:32:36Z) Adopt the changes given in https://mentor.ieee.org/802.11/dcn/10/11-10-1364-01-000m-subclause-10-3-clean-up-proposal.docx. | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10126 | Worstell, Harry | 1000 | 6 | 10.3.1 | 629 | 33 | T | Y | 629.33 | 33 | 10.3.1 |  | P |  |  |  | The transitions from states 3 and 4 to state 2 for unsuccessful (re)association are not true at an AP. Doing this transition at an AP opens a denial-of-service attack -- a rogue STA sending failing (re)association requests on behalf of a target STA causes the AP to put the target STA back into state 2 and deny it service. | It is not possible to show a simple transition that covers both the non-AP STA and AP case, as the behavior is different. Either qualify the label on both Unsuccessful (re)association transitions by including "at a non-AP STA", or delete the two transitions completely from the figure (as it is better to be silent than to say something incorrect). | AGREE IN PRINCIPLE (MAC: 2011-01-18 00:33:31Z) - Adopt the changes given in https://mentor.ieee.org/802.11/dcn/10/11-10-1364-01-000m-subclause-10-3-clean-up-proposal.docx. | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10127 | Worstell, Harry | 1000 | 6 | 10.3.2.3 | 632 | 5 | T | Y | 632.05 | 5 | 10.3.2.3 |  | P |  |  |  | The text inserted in D4.0 "The STA shall be set to state 1" is incorrect, and leads to an denial-of-service attack. The statement conflicts with the correct statement on page 632 line 10, where the state value is left unchanged. This case was analyzed in 11-10/0390r0. | delete list item (b)(2). List item (b)(1) should be incorporated into (b), and made conditional on a successful ResultCode. | Accept in Principle. Adopt the changes given in https://mentor.ieee.org/802.11/dcn/10/11-10-1364-01-000m-subclause-10-3-clean-up-proposal.docx. | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10101 | Hamilton, Mark | 1000 | 6 | 10.3.2.3 | 632 | 5 | T | Y | 632.05 | 5 | 10.3.2.3 |  | P |  |  |  | The inserted text "The STA shall be set to state 1" is incorrect, and leads to an denial-of-service attack. | See changes proposed in 10/0826r5 | Accept in Principle. Adopt the changes given in https://mentor.ieee.org/802.11/dcn/10/11-10-1364-01-000m-subclause-10-3-clean-up-proposal.docx. | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10145 | Malinen, Jouni | 1000 | 6 | 10.3.2.3 | 632 | 22 | T | Y | 632.22 | 22 | 10.3.2.3 |  | P |  |  |  | The authentication procedure steps e and f seem to open a denial-of-service issue in FT and MFP cases (which provide protection for this). There is no real authentication in Open System authentication algorithm, so anyone could easily drop the association if these rules were used at an AP. | Limit steps e and f to apply only if FT or MFP are not used (like step b is already doing). | Accept in Principle. Adopt the changes given in https://mentor.ieee.org/802.11/dcn/10/11-10-1364-01-000m-subclause-10-3-clean-up-proposal.docx. | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10119 | Worstell, Harry | 1000 | 6 | 10.3.3.2 | 634 | 5 | T | Y | 634.05 | 5 | 10.3.3.2 |  | P |  |  |  | Line 5 uses the phrase "if RSNA establishment is required" and line 26 "if policy within the SME requires secure communication". | make them the same | Accept in Principle. Adopt the changes given in https://mentor.ieee.org/802.11/dcn/10/11-10-1364-01-000m-subclause-10-3-clean-up-proposal.docx. | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10177 | Ecclesine, Peter | 1000 | 6 | 10.10.1 | 669 | 17 | T | N | 669.17 | 17 | 10.10.1 |  | P |  |  |  | The ECS general text should describe the situation where some receiving STAs do not support ECS, and both channel switch and ECS are being transmitted. The procedures that do so are in 10.10.3. | Add text to end of second paragraph "When an AP is switching to a different channel and some STAs do not support Extended Channel Switch, then both the Extended Channel Switch Announcement and the Channel Switch Announcement elements and frames may be used." | AGREE IN PRINCIPLE (MAC: 2010-11-11 22:36:03Z) - "When an AP is switching to a different channel and one or more of its associated STAs do not support Extended Channel Switch, then both the Extended Channel Switch Announcement and the Channel Switch Announcement elements and frames may be used." | GEN | MAC Motion D | Resolved |  |  |  |  | 2011-01-19 06:47 | EDITOR
10060 | Fischer, Matthew | 1000 | 6 | 10.11.9.1 | 678 | 6 | T | Y | 678.06 | 6 | 10.11.9.1 |  | P |  |  |  | In this subclause, I see the term "beacon report element" yet there is no such thing as a beacon report element. | I believe that an appropriate fix would be to change the instances of beacon report element to beacon report. Examine the document to determine if other report fields are mistakenly labeled as elements in the subclauses that describe the report functions, and if so, correct them as well. | AGREE IN PRINCIPLE (MAC: 2010-11-11 22:29:34Z) Replace all occurences of "Beacon Report element" with "Beacon Report" | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10059 | Fischer, Matthew | 1000 | 6 | 10.11.9.1 | 678 | 6 | T | Y | 678.06 | 6 | 10.11.9.1 |  | P |  |  |  | Describe how the operating class is determined by the STA sending a beacon report - in particular, in the case when a received beacon does not contain operating class information. | Provide a description of how the operating class field is to be filled in when the received beacon does not provide the information that would normally be entered into that field. | AGREE IN PRINCIPLE (MAC: 2010-11-10 21:06:31Z) In 8.4.2.56, reference of the description of the use of this element is an incomplete list: needs to add 10.11.9.1. In 10.11.9.1 on page 680, remove the last three sentences from the paragraph at line 1. In 10.11.9.1 on page 678, insert the following paragraph after the first paragraph: "If the requested Beacon Measurement Report includes the Supported operating classes element, channel number, operating class, and/or reported frame information for that any measurement may be included in the beacon report; otherwise these fields shall be set to 255 in the beacon report. The STA shall use the Reporting Detail specified in the measurement request to determine the data to be included in the measurement report. If the STA has no beacon information available then the STA may either refuse the request or send an empty Beacon Report. and the received Beacon that is used to populate the fields of this element does not contain | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 23:01 | GEN
10151 | Vlantis, George | 1000 | 6 | 10.15.1 | 698 | 59 | T | Y | 698.59 | 59 | 10.15.1 |  | P |  |  |  | This sentence is unclear. It would be a lot more straightforward if the text first stated that each FC STA must support the Coexistence Management frame. | Replace this paragraph with: "An FC STA shall support 20/40 BSS Coexistence Management, so as a result an FC HT STA that transmits a frame containing an Extended Capabilities element shall set the 20/40 BSS Coexistence Management Support field of this element to 1." | AGREE IN PRINCIPLE (MAC: 2010-11-11 22:40:32Z) - Replace cited paragraph with the following: "An FC STA shall support 20/40 BSS Coexistence Management. NOTE -- An FC HT STA that transmits a frame containing an Extended Capabilities element sets the 20/40 BSS Coexistence Management Support field of this element to 1." | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10069 | shi, yang | 1000 | 6 | 11.3.1 | 817 | 6 | G | N | 728.06 | 6 | 11.3.1 |  | P |  |  |  | Suggest to point out that BIP is a integrity protocol for management frame | This standard defines two RSNA data confidentiality and integrity protocols: TKIP and CCMP. This standard defines one integrity protocol for management frame: BIP. | AGREE IN PRINCIPLE (MAC: 2010-11-11 23:45:58Z) - Change "This standard defines one integrity protocol: BIP." to "This standard defines one integrity protocol for management frames: BIP." | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10395 | Hunter, David | 1000 | 6 | 11.5.1.2 | 768 | 44 | T | Y | 768.44 | 44 | 11.5.1.2 |  | P |  |  |  | Both K and B are used extensively in the following equations, but both remain undefined. | Define K and B in this line. | AGREE IN PRINCIPLE (MAC: 2010-11-11 22:46:23Z) - insert "K is a key; B is a variable length string" | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10398 | Hunter, David | 1000 | 6 | 11.5.1.2 | 768 | 47 | T | Y | 768.47 | 47 | 11.5.1.2 |  | P |  |  |  | What are 'K', 'A' and 'B' in this equation? Is 'K' a 256-bit key derivation key, as noted in page 775? | Define 'K', 'A' and 'B' in the material immediately following this equation. | AGREE IN PRINCIPLE (MAC: 2010-11-11 22:46:27Z) - insert "K is a key; B is a variable length string" at line 44. Note that this is the same resolution as CID 10395 | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10401 | Hunter, David | 1000 | 6 | 11.5.1.3 | 769 | 41 | T | Y | 769.41 | 41 | 11.5.1.3 |  | D |  |  |  | The MIB variable dot1xAuthTxPeriod is not defined in the MIB annex, nor anywhere else for that matter. | Either define dot1xAuthTxPeriod or delete "+ dot1xAuthTxPeriod" from this line. | DISAGREE (MAC: 2010-11-11 22:47:35Z) - dot1xAuthTxPeriod is defined in IEEE Std 802.1X-2004, which is already cited as a normative reference. | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10406 | Hunter, David | 1000 | 6 | 11.5.1.4 | 770 | 58 | T | Y | 770.58 | 58 | 11.5.1.4 |  | P |  |  |  | This is the first mention of "GMK" in the text, but nothing tells us where the GMK comes from. | Insert a description of the origin of the GMK -- hopefully earlier than this requirement that it "may be reinitialized". | AGREE IN PRINCIPLE (MAC: 2010-11-11 22:57:35Z) - Change "Any group master key (GMK) may be reinitialized" to "A group master key (GMK) is an auxiliary key that may be used to derive a group temporal key (GTK)." at the cited location. | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10124 | Worstell, Harry | 1000 | 6 | 11.5.2 | 779 | 33 | T | Y | 779.33 | 33 | 11.5.2 |  | A |  |  |  | Key Descriptor Version is three bits, 0-2, not just bit 0 | move "B2" to be over the Key Descriptor Version | AGREE (MAC: 2010-11-11 23:43:02Z) - | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10120 | Worstell, Harry | 1000 | 6 | 12.9.3.1 | 863 | 54 | T | Y | 863.54 | 54 | 12.9.3.1 |  | A |  |  |  | SETKEYS (PTK) should be SETKEYS (Pairwise) | as in comment | AGREE (MAC: 2010-11-11 23:49:33Z) - | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10121 | Worstell, Harry | 1000 | 6 | 12.9.3.1 | 864 | 23 | T | Y | 864.23 | 23 | 12.9.3.1 |  | A |  |  |  | SETKEYS (PTK) should be SETKEYS (Pairwise) | as in comment | AGREE (MAC: 2010-11-11 23:50:04Z) - | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10122 | Worstell, Harry | 1000 | 6 | 12.9.5.1 | 868 | 49 | T | Y | 868.49 | 49 | 12.9.5.1 |  | A |  |  |  | SETKEYS (PTK) should be SETKEYS (Pairwise) | as in comment | AGREE (MAC: 2010-11-11 23:50:57Z) - | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR
10123 | Worstell, Harry | 1000 | 6 | 12.9.5.1 | 869 | 27 | T | Y | 869.27 | 27 | 12.9.5.1 |  | A |  |  |  | SETKEYS (PTK) should be SETKEYS (Pairwise) | as in comment | AGREE (MAC: 2010-11-11 23:53:28Z) | GEN | MAC Motion D | Ready for motion |  |  |  |  | 2011-01-19 06:47 | EDITOR

## Withdrawn
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
10180 | Ecclesine, Peter | 1000 | 6 | 9.18.5 | 525 | 40 | T | Y | 525.4 | 40 | 9.18.5 |  | U | Peter Ecclesine |  |  | This text is missing the description of a BSS where more than one operating class is in use because of HT or other reasons. Expand this paragraph to refer to a hierarchy of operating classes, i.e., from oldest legacy to HT, and provisions for changing channels or transmit power when multiple operating classes are in use. | Describe 20/40 operation with operating classes in this clause by references to other clauses. | UNRESOLVABLE (GEN: 2011-01-19 17:59:22Z) Comment withdrawn by commentor 2011-01-19. | GEN | Withdrawn | Ready for motion | Submission required? |  |  |  | 2011-01-19 18:00 | GEN