## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-11/0279r1
Venue Date: | March 2011
First Author: | Jon Rosdahl (CSR)
Title: | GEN Adhoc Recirc-1 Sponsor Ballot Comment Resolutions
Full Date: | 2011-03-01
Author(s): | Name(s) | Jon Rosdahl
| Affiliation | CSR
| Address | 10871 N 5750 W, Highland, Utah
| Phone: | 801-492-4023
Fax:
| email: | jrosdahl@ieee.org
Abstract:
Proposed Resolutions for comments received on Draft 7.0 during the 1st recirculation ballot.
Rev 0 has 62 comments assigned to the Gen AdHoc, and as the comments are resolved they are assigned back to the Editor, and so this file will shrink.
Rev 1 updates the proposed resolutions -- created topical tabs.

## Revision History
Revision | Comments
R0 | Initial pass on the General Adhoc Comments. Initial proposed resolutions included.
R1 | Feedback from technical Editor on 20 CIDs. Updated AdHoc Proposal Tabs by comment subject group added

## General
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
11061 | Fischer, Matthew | 1001 | 7 | 4.2.3 | 37 | 52 | T | N | 37.52 | 52 | 4.2.3 | [5 empty] | Item e) incorrect use of "may" | Change "may" to "might" |  | GEN | General | Proposed | Propose Agree |  |  |  | 2011-03-04 14:00 | GEN
11087 | Ptasinski, Henry | 1001 | 7 | 4.3.12 | 50 | 21 | T | Y | 50.21 | 21 | 4.3.12 | [5 empty] | Once a TDLS link is setup with a peer, all data frames to the peer must be sent using the direct path. | Change "have the option of transmitting frames" to "transmit frames" |  | GEN | General | Proposed | Propose Agree |  |  |  | 2011-03-02 17:59 | GEN
11213 | Hunter, David | 1001 | 7 |  |  |  | G | Y | 259.65 | 65 | 6.4.5.2 | [5 empty] | In SB1 it was pointed out that there is a difference of capitalizatonss and concatenations of the primitive names. The CRC response was that changing was too much work without benefit. But this standard depends on consistency in indicating types of names. So it is not unimportant to be consistent. | If no one else has time to work on this, it appears that I will not have a job after March 31, so I will have the time to buy a copy of FrameMaker, learn how to use it, and make the changes sometime in April. P.S., the implementer of this standard doesn't care about how hard it is to integrate amendments that had been erroneously approved by the WG. |  | GEN | General | Proposed | GEN: 2011-03-04 13:06:57Z - Propose: Disagree - Related comments are 11211 (Editor, disagree); 11213 (Gen) and 11215 (MAC). The proposed resolution for 11211 reads: DISAGREE (EDITOR: 2011-02-22 10:39:51Z) - There is no particular rule observable in the draft about whether these parameters should be lower case, InitialCaps, UPPER_CASE_WITH_UNDERSCORES, or something else. The IEEE-SA has no such rule, and the material cited has been through multiple rounds of IEEE-SA professional editing, from which we may determine that they do not regard such consistency to be necessary. While it is the commenter's preference to strive for consistency, the material cited is not incorrect and transgresses no IEEE-SA rule of style. Further, the substantial number of changes to be made would open up much of Clause 6 to further comment. |  |  |  | 2011-03-04 14:02 | GEN
11021 | Stephens, Adrian | 1001 | 7 | Annex S | 2099 | 12 | T | Y | 2099.1201 | 12 | S | [5 empty] | Editor's Note: I challenge whether this should be informative. Any item required for interoperability should surely be normative. And payload type and format would appear to meet this description. | Change Annex to normative and re-order as necessary. |  | GEN | General | Proposed | Propose Agree in principle…also delete pages 2100-2104 as they are blank. |  |  |  | 2011-03-04 14:02 | GEN

## Intro
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
11128 | Struik, Rene | 1001 | 7 | 2 | 2 |  | T | N | 2 |  | 2 | [5 empty] | (E) Clause 2, p. 2: The NIST hash function standard FIPS Pub 180-2 is out of date and has been superseded by FIPS Pub 180-3 (and even FIPS Pub 180-4 by February 11, 2011, although the latter seems to be a draft still up for comment). Suggested remedy: Update reference. |  |  | GEN | Intro | Proposed | Propose Agree in principle, (there is no stated proposed change) and update reference as noted in the comment. |  |  |  | 2011-03-04 14:00 | GEN
11060 | Fischer, Matthew | 1001 | 7 | 3.1 | 4 | 49 | T | N | 4.49 | 49 | 3.1 | [5 empty] | Which AP? Use of the definitive article preceding AP leaves the reader hanging. | Either include a precedent for the article, or change to an indefinite article. |  | GEN | Intro | Proposed | propose Agree in Principle, and change "the" to "a" at cited location. |  |  |  | 2011-03-04 14:00 | GEN
11082 | Ptasinski, Henry | 1001 | 7 | 3.1 | 14 | 1 | T | Y | 14.01 | 1 | 3.1 | [5 empty] | Definitions for peer U-APSD (and related) are inconsistent with definitions for peer PSM (and related). | Add "tunneled direct-link setup (TDLS)" to the beginning of all the peer U-APSD definitions, or delete "tunneled direct-link setup (TDLS)" from the beginning of all the peer PSM definitions. |  | GEN | Intro | Proposed | Propose Agree in Principle --Add "tunneled direct-link setup (TDLS)" to the beginning of all the peer U-APSD definitions, and where used later in the draft. |  |  |  | 2011-03-04 14:00 | GEN
11083 | Ptasinski, Henry | 1001 | 7 | 3.1 | 21 | 10 | G | Y | 21.1 | 10 | 3.1 | [5 empty] | Definition should be reworded for clarity | Change to "bufferable management frame: A Probe Response that is sent in an IBSS in response to a unicast Probe Request frame, and any Action, Disassociation, or Deauthentication frame." |  | GEN | Intro | Proposed | GEN: 2011-03-04 13:10:13Z - Propose Agree |  |  |  | 2011-03-04 14:00 | GEN
11085 | Ptasinski, Henry | 1001 | 7 | 3.1 | 21 | 20 | T | Y | 21.17 | 20 | 3.1 | [5 empty] | Definitions should not be hidden inside other definitions. | Delete "A non-bufferable MMPDU is an MMPDU that is not a bufferable MMPDU." |  | GEN | Intro | Proposed | Propose Agree (actual line number is 17) |  |  |  | 2011-03-04 13:32 | GEN
11077 | Montemurro, Michael | 1001 | 7 | 3.2 | 21 | 21 | T | Y | 21.21 | 21 | 3.2 | [5 empty] | Bufferable Units should contain A-MPDU's as well. In general, there is no specification for how A-MPDU's are treated when used for PS delivery of buffered frames. | Add A-MPDU's to the definition. At the time of my review, most of the changes would be addressed by adding A-MPDU to the BU definition. |  | GEN | Intro | Proposed | GEN: 2011-03-04 13:32:02Z - Propose Disagree. Buffering is of "things that can be fragmented", which is above MPDUs, which is above A-MPDUs in our layer cake. GEN: 2011-03-01 - propose Agree |  |  |  | 2011-03-04 13:32 | GEN
11084 | Ptasinski, Henry | 1001 | 7 | 3.1 | 22 | 52 | T | Y | 22.52 | 52 | 3.1 | [5 empty] | A TDLS DFS owner should not be included in the definition of "independent basic service set (IBSS) dynamic frequency selection (DFS) owner (IDO) station" since TDLS is not IBSS. | Delete "independent basic service set (IBSS)" from the beginning of the definition. |  | GEN | Intro | Proposed | Propose Agree |  |  |  | 2011-03-04 12:52 | GEN
11086 | Ptasinski, Henry | 1001 | 7 | 3.3 | 33 | 5 | T | Y | 33.05 | 5 | 3.3 | [5 empty] | "peer U-APSD" is inconsistent with "TDLS peer PSM" | Make the two consistent - either add "TDLS" to "peer U-APSD", or delete "TDLS" from "TDLS peer PSM". |  | GEN | Intro | Proposed | GEN: 2011-03-04 13:32:50Z - The ad-hoc proposed resolution is non-responsive as it addresses a separate issue. Proposed resolution: Agree in principle. Globally change peer U-APSD to "TDLS peer U-APSD". GEN: 2011-03-01 - Proposed to see CID 11082 for resolution. |  |  |  | 2011-03-04 13:34 | GEN

## Operating Classes
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
11111 | Ecclesine, Peter | 1001 | 7 | E.1 | 1729 | 14 | T | Y | 1729.14 | 14 | E.1 | [5 empty] | Since TransmitPowerControlBehavior and DynamicFrequencyControlBehavior are required by Regulations in the 5 GHz band, there is no normative reason to require it in Table E-2 Operating Class 16. | In Table E-2 Operating Class 16, remove TransmitPowerControlBehavior and DynamicFrequencyControlBehavior. |  | GEN | Operating Classes | Proposed | propose Agree |  |  |  | 2011-03-02 16:49 | GEN
11110 | Ecclesine, Peter | 1001 | 7 | E.1 | 1729 | 50 | T | Y | 1729.5 | 50 | E.1 | [5 empty] | Since CS4msBehavior is required by Japanese regulations in unlicensed operation, there is no normative reason to require it in Table E-3 Operating Classes in Japan. | Remove all references to CS4msBehavior in Table E-3. |  | GEN | Operating Classes | Proposed | propose Agree |  |  |  | 2011-03-02 16:49 | GEN
11123 | Ecclesine, Peter | 1001 | 7 | E.2.2 | 1738 | 2 | T | Y | 1738.02 | 2 | E.2.2 | [5 empty] | 802.11y-2008 requires the use of CCA-ED, TPC, DFS and CS-4ms for operation in 3650 MHz band, but the requirement to use CS-4ms is not stated in E.2.2 in normative text. Insert sentence "No station can transmit for more than 4 ms without carrier sensing, whether transmitting fragments or frames, unless it is controlled by another STA." Annex D Table D-2 CS4ms-Behavior is thus redundantly stating a normative requirement. Its existence in the standard adds no value. | Remove all references to CS4msBehavior, both in Annex D and Annex E. |  | GEN | Operating Classes | Proposed | propose Agree |  |  |  | 2011-03-02 16:49 | GEN

## OFDM PHY
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
11056 | Kim, Youhan | 1001 | 7 | 17.3.9.7.3 | 1153 | 22 | T | Y | 1153.22 | 22 | 17.3.9.7.3 | [5 empty] | CIDs 10070 and 10152 for the previous ballot on D6.0 had a resolution of "AGREE IN PRINCIPLE (GEN: 2011-01-20 23:56:44Z) incorporate the text changes as indicated in https://mentor.ieee.org/802.11/dcn/11/11-11-0159-02-000m-revmb-sb-spectral-mask-cids-proposed-resolutions.doc". However, 0159-02 erroneously missed the necessary changes required in section 17.3.9.7.3. Copying from the previous ballot comment - "Receivers are designed to be able to received signal with non-flat spectrum since it has to deal with multipath channels anyhow. The current spectral flatness requirement puts unecessary constraint on the TX design without much benefit." Please note that similar changes have been accepted in the previous ballot for Section 19.3.20.2. Not changing Section 17.3.9.7.3 will result in different spectral flatness requirement for 11a and 11n devices. | Change +/- 2 dB on line 22 to +/- 4 dB. Change +2/-4 dB on line 23 to +4/-6 dB. |  | GEN | OFDM PHY | Proposed | Propose Agree |  |  |  | 2011-03-02 18:38 | GEN
11024 | Stephens, Adrian | 1001 | 7 | 17.3.9.7.3 | 1153 | 22 | T | Y | 1153.22 | 22 | 17.3.9.7.3 | [5 empty] | This is a pile on to CID 10152. That comment proposed relaxing the spectral flatness requirement, and was marked 'AGREE IN PRINCIPLE (GEN: 2011-01-20 23:56:44Z) incorporate the text changes as indicated in https://mentor.ieee.org/802.11/dcn/11/11-11-0159-02-000m-revmb-sb-spectral-mask-cids-proposed-resolutions.doc'. However the cited document contained no editing instructions to this subclause, and is therefore non-responsive. | Make the change as proposed by the commenter in CID 10152: "Change +/- 2 dB on line 22 to +/- 4 dB. Change +2/-4 dB on line 23 to +4/-6 dB." (references are to page 1049 of D6.0). |  | GEN | OFDM PHY | Proposed | Propose Agree |  |  |  | 2011-03-02 18:38 | GEN

## MLME - Primitives
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
11001 | Stephens, Adrian | 1001 | 7 | 6.3.7.5.2 | 111 | 21 | T | Y | 111.21 | 21 | 6.3.7.5.2 |  |  | Adrian Stephens |  |  | Editor's Note: There is no clear 1:1 mapping between these values and the Status Code values. This field is supposed to determine the contents of the Status Code field of the Associate Response frame. There are codes above that appear to have no counterpart in Table 8-35, and there are Status Codes there related to association that have no counterpart here. | Add a "name" column to the Status Code definitions, review all Clause 6 parameters that are intended to map into a Status Code field value and populate name column in Status Code definition where there is a clear match with an existing Status Code description. Reserve new Status Code entries for any such unmatched Clause 6 parameter, inventing new names or descriptions as appropriate. |  | GEN | MLME - Primitives | Submission | GEN: 2011-03-04 13:37:50Z - Propose Agree, but a submission should be prepared. |  |  |  | 2011-03-04 13:41 | GEN
11002 | Stephens, Adrian | 1001 | 7 | 6.3.8.5.2 | 120 | 23 | T | Y | 120.23 | 23 | 6.3.8.5.2 | [5 empty] | Editor's Note: List does not match "refused" list in confirm | Copy ResultCode enumation list from .confirm primitive. |  | GEN | MLME - Primitives | Proposed | Propose Agree |  |  |  | 2011-03-02 18:03 | GEN
11045 | Malinen, Jouni | 1001 | 7 | 6.3.9.1.3 | 122 | 39 | T | N | 122.39 | 39 | 6.3.9.1.3 | [5 empty] | The language used to describe MLME-DISASSOCIATE.request and MLME-DISASSOCIATE.confirm primitives seems to indicate that this mechanism is used only by a non-AP STA to disassociate from an AP. However, these primitives are used by an AP to initiate disassociation with a non-AP STA, too. For example, 10.3.3.8 (page 719 line 7) describes such use. It would be clearer to not use AP specific language in the description of the disassociation primitives and to make them a bit more consistent with the deauthentication primitives in this sense. | Replace "SME for a STA to establish disassociation with an AP" with "SME for a STA to establish disassociation with a peer STA. (line 39). Replace "a specific peer MAC entity that is within an AP" with "a specific peer MAC entity" (line 54). Replace "a specified peer MAC entity that is within an AP" with "a specified peer MAC entity" (page 123 line 15). |  | GEN | MLME - Primitives | Proposed | GEN: 2011-03-04 13:40:43Z - Propose Agree in Principle; The suggested wording is poor, and introduces the problemmatic "peer". Replace "SME for a STA to establish disassociation with an AP" with "SME for a STA to disassociate from a STA with which it has an association. (line 39). Replace "a specific peer MAC entity that is within an AP" with "a specific MAC entity" (line 54). Replace "a specified peer MAC entity that is within an AP" with "a specified MAC entity" (page 123 line 15). GEN: 2011-03-01 - Propose Agree |  |  |  | 2011-03-04 13:42 | GEN
11212 | Hunter, David | 1001 | 7 |  |  |  | G | Y | 136.6 | 60 | 6.3.14.2.2 | [5 empty] | In SB1 it was pointed out that there is a difference of concatenations of the parameter names. The CRC response was that changing was too much work without benefit. But this standard depends on consistency in indicating types of names. So it is not unimportant to be consistent. | If no one else has time to work on this, it appears that I will not have a job after March 31, so I will have the time to buy a copy of FrameMaker, learn how to use it, and make the changes sometime in April. P.S., the implementer of this standard doesn't care about how hard it is to integrate amendments that had been erroneously approved by the WG. |  | GEN | MLME - Primitives | Proposed | Propose Disagree: "Related comments are 11211 (Editor, disagree); 11213 (Gen) and 11215 (MAC). The proposed resolution for 11211 reads: DISAGREE (EDITOR: 2011-02-22 10:39:51Z) - There is no particular rule observable in the draft about whether these parameters should be lower case, InitialCaps, UPPER_CASE_WITH_UNDERSCORES, or something else. The IEEE-SA has no such rule, and the material cited has been through multiple rounds of IEEE-SA professional editing, from which we may determine that they do not regard such consistency to be necessary. While it is the commenter's preference to strive for consistency, the material cited is not incorrect and transgresses no IEEE-SA rule of style. Further, the substantial number of changes to be made would open up much of Clause 6 to further comment." |  |  |  | 2011-03-04 12:54 | GEN
11088 | Ptasinski, Henry | 1001 | 7 | 6.3.42.2.2 | 232 | 56 | G | Y | 222.56 | 56 | 6.3.42.2.2 | [5 empty] | Description of resultcode is circular and doesn't make sense. | Change to "Reports the outcome of an MLME-GETTSFTIME.request" |  | GEN | MLME - Primitives | Proposed | proposed: agree with proposed change Note, adjusted page to 222.56 |  |  |  | 2011-03-04 12:56 | GEN
11089 | Ptasinski, Henry | 1001 | 7 | 6.3.42.2.2 | 232 | 59 | G | Y | 222.59 | 59 | 6.3.42.2.2 | [5 empty] | Description of TSFtime should indicate that it is conditionally present. | Change to "Optional. The value of the TSF timer if the ResultCode is SUCCESS." |  | GEN | MLME - Primitives | Proposed | Proposed: Agree in Principle --To fit in with our style should say: "The value of the TSF timer. Present only if ResultCode is SUCCESS." Note, adjusted page to 222.59 |  |  |  | 2011-03-04 12:56 | GEN
11091 | Ptasinski, Henry | 1001 | 7 | 6.3.43.1.4 | 235 | 51 | G | Y | 226.5 | 51 | 6.3.43.1.4 | [5 empty] | What happens to the frame after it's generated? This text is inconsistent with other clauses. | Add "The STA then attempts to transmit the frame to the STA(s) indicated by the PeerMACAddress parameter." |  | GEN | MLME - Primitives | Proposed | GEN: 2011-03-04 12:58:40Z - Page reference should be 226.50. Propose Agree in Principle: Replace cited sentence with: "Upon the receipt of this primitive, the MLME attempts to transmit a Timing Advertisement frame to the specified MAC address, using the procedures defined in 10.21." GEN: 2011-03-01 - check cited location does not match clause number |  |  |  | 2011-03-04 13:09 | GEN
11093 | Ptasinski, Henry | 1001 | 7 | 6.3.44.2.2 | 229 | 20 | G | Y | 229.2 | 20 | 6.3.44.2.2 | [5 empty] | TDLS discovery requests can only be sent to unicast addresses. | Change valid range for DestinationAddress to "Any valid individual MAC address." |  | GEN | MLME - Primitives | Proposed | Propose Agree |  |  |  | 2011-03-02 18:05 | GEN
11094 | Ptasinski, Henry | 1001 | 7 | 6.3.44.4.4 | 230 | 47 | G | Y | 230.47 | 47 | 6.3.44.4.4 | [5 empty] | Wishy-washy requirement. | Change "the SME should operate" to "the SME shall operate" or "the SME operates". |  | GEN | MLME - Primitives | Proposed | Propose: Agree in Principle - Change "the SME should operate" to "the SME operates". |  |  |  | 2011-03-02 18:06 | GEN
11095 | Ptasinski, Henry | 1001 | 7 | 6.3.45.1.2 | 233 | 31 | T | Y | 233.31 | 31 | 6.3.45.1.2 | [5 empty] | A timeout parameter with a valid range of only "0" doesn't seem to be very useful. And the tdls setup procedure timeout is handled in the SME anyway, isn't it? | Delete the TDLSResponseTimeout parameter. |  | GEN | MLME - Primitives | Proposed | GEN: 2011-03-04 12:56:52Z - Propose Agree -- The protocol in 10.22.4 cites a MIB variable as providing a value for the timeout, so this parameter is unused. Remove the cited parameter. GEN: 2011-03-01 - Propose Agree, or Agree in Principle and include a valid range other than"0" |  |  |  | 2011-03-04 13:00 | GEN
11096 | Ptasinski, Henry | 1001 | 7 | 6.3.45.2.2 | 234 | 13 | T | Y | 234.13 | 13 | 6.3.45.2.2 | [5 empty] | The BSS membership of a TDLS peer is a determination that is made in the SME (e.g. by using the tdls discovery procedures). | Delete NOT_IN_SAME_BSS from the valid range of ResultCode. |  | GEN | MLME - Primitives | Proposed | Propose Agree |  |  |  | 2011-03-02 18:10 | GEN
11090 | Ptasinski, Henry | 1001 | 7 | 6.3.43.1.1 | 234 | 13 | T | Y | 234.13 | 13 | 6.3.43.1.1 | [5 empty] | Need some additional punctuation. | Change to "to transmit timing and, optionally, higher layer information." |  | GEN | MLME - Primitives | Proposed | Proposed Aggree. Note, this should have been classified editorial. |  |  |  | 2011-03-04 12:58 | GEN
11097 | Ptasinski, Henry | 1001 | 7 | 6.3.45.3.4 | 235 | 4 | G | Y | 235.04 | 4 | 6.3.45.3.4 | [5 empty] | Wishy-washy requirement. | Change "the SME should operate according" to either "the SME shall operate according" or "the SME operates according". |  | GEN | MLME - Primitives | Proposed | Propose Agree in Principle-Change "the SME should operate according" to "the SME operates according". |  |  |  | 2011-03-02 18:18 | GEN
11092 | Ptasinski, Henry | 1001 | 7 | 6.3.43.2.2 | 236 | 7 | G | Y | 236.07 | 7 | 6.3.43.2.2 | [5 empty] | Valid range for ResultCode is incomplete. | Add TIMEOUT and UNSPECIFIED_FAILURE, at least. |  | GEN | MLME - Primitives | Proposed | GEN: 2011-03-04 13:00:20Z - Propose Disagree. This is an abstract interface, not an implementation one. There is no protocol associated with getting the value of the TSF timer that could cause any kind of failure. Either the STA supports this or it does not. In the case that it does not, this interface does not exist, and the SME does not attempt to use it. GEN: 2011-03-01 - propose Agree, but are there other codes needed here? |  |  |  | 2011-03-04 13:01 | GEN
11099 | Ptasinski, Henry | 1001 | 7 | 6.3.45.6.4 | 237 | 4 | G | Y | 237.04 | 4 | 6.3.45.6.4 | [5 empty] | Wishy-washy requirement. | Change "should operate" to either "shall operate" or "operates". |  | GEN | MLME - Primitives | Proposed | Propose Agree in Principle-Change "the SME should operate according" to "the SME operates according". |  |  |  | 2011-03-02 18:18 | GEN
11100 | Ptasinski, Henry | 1001 | 7 | 6.3.45.7.2 | 237 | 35 | G | Y | 237.35 | 35 | 6.3.45.7.2 | [5 empty] | Timeout is unnecessary. | Delete TDLSResonseTimeout parameter. |  | GEN | MLME - Primitives | Proposed | GEN: 2011-03-04 13:01:43Z - Propose Agree GEN: 2011-03-01 - Resolution should match resolution from CID 11095 |  |  |  | 2011-03-04 13:03 | GEN
11101 | Ptasinski, Henry | 1001 | 7 | 6.3.45.9.4 | 239 | 4 | G | Y | 239.04 | 4 | 6.3.45.9.4 | [5 empty] | Wishy-washy requirement. | Chane "should operate" to either "shall operate" or "operates." |  | GEN | MLME - Primitives | Proposed | Propose Agree in Principle-Change "the SME should operate according" to "the SME operates according". |  |  |  | 2011-03-02 18:30 | GEN
11098 | Ptasinski, Henry | 1001 | 7 | 6.3.45.4.2 | 245 | 34 | G | Y | 245.34 | 34 | 6.3.45.4.2 | [5 empty] | Timeout is unnecessary. Termination of the setup procedure is done in the SME. | Delete TDLSResponseTimeout parameter. |  | GEN | MLME - Primitives | Proposed | GEN: 2011-03-04 13:01:43Z - Propose Agree in principle: There is no protocol in 10.22 that relates to a timeout of the TDLS Setup Confirm, this has to be an error, because there must be a way for the protocol to terminate. However, related language in 10.22.4 uses the value of a MIB variable, not a timeout parameter. Delete the parameter at the cited location. Add at line 802.22: "A TDLS responder STA that transmits a TDLS Setup Response frame and that does not receive a matching TDLS Setup Confirm frame within a dot11TDLSResponseTimeout shall delete the TDLS link." GEN: 2011-03-01 - Resolution should match resolution from CID 11095 and 11100 |  |  |  | 2011-03-04 13:05 | GEN
11103 | Ptasinski, Henry | 1001 | 7 | 6.3.49 | 252 | 3 | G | Y | 252.03 | 3 | 6.3.49 | [5 empty] | These primitives do not signal tdls setup. | Change "support the signaling of tunneled direct-link setup" to something more appropriate. |  | GEN | MLME - Primitives | Proposed | GEN: 2011-03-04 13:05:21Z - Propose Agree in Principle - Change cited sentence to "The following MLME primitives support the management of TDLS Peer PSM." |  |  |  | 2011-03-04 13:06 | GEN

## MLME - Association
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
11011 | Stephens, Adrian | 1001 | 7 | 10.3.3.2 | 714 | 10 | T | Y | 714.1 | 10 | 10.3.3.2 | [5 empty] | Editor's Note: The previous statement would appear to conflict with the possible existence of a TimeoutInterval element in the response frame. The point is that the AP may generate a "... rejected temporarily" with a timeout Interval element specifying a value more or less than 2s. In this case the behaviour should be guided by the Timeout Interval element, not a fixed 2s. | In the last sentence of the previous para, add "and the Association Response frame does not include a Timout Interval element with Timout Interval Type equal to 3" before the first comma. Add a new sentence to end of para: "If the status code indicates the association failed and the Association Response frame contains a Timeout Interval element with Timout Interval Type equal to 3, the SME shall not issue an MLMEASSOCIATE. request primitive for the same AP until the period specified in the Timeout Interval element has elapsed." |  | GEN | MLME - Association | Proposed | Propose Agree |  |  |  | 2011-03-02 18:33 | GEN
11012 | Stephens, Adrian | 1001 | 7 | 10.3.3.3 | 714 | 24 | T | Y | 714.24 | 24 | 10.3.3.3 | [5 empty] | Editor's Note: The following does not make clear whether this event transits the MLME interface or not. Ditto comment in 10.3.3.5 | Change "AP" to "MLME" at line 27. |  | GEN | MLME - Association | Proposed | Propose Agree |  |  |  | 2011-03-02 18:33 | GEN
11071 | Malinen, Jouni | 1001 | 7 | 10.3.3.3 | 714 | 46 | T | Y | 714.46 | 46 | 10.3.3.3 | [5 empty] | The conditions in step (d) do not cover the exception from (d) (6) to allow the consecutive SAQuery procedures to be skipped. | Add a new condition to the end of step (d): ", and an earlier, timed out SA Query procedure with the non-AP STA has not allowed a new association process to be started without an additional SA Query procedure". |  | GEN | MLME - Association | Proposed | Propose Agree |  |  |  | 2011-03-02 18:34 | GEN
11080 | Fischer, Matthew | 1001 | 7 | 10.3.3.3 | 715 | 6 | G | N | 715.06 | 6 | 10.3.3.3 | [5 empty] | There are still some problems with the SA query behavior. | For example, maybe: Replace 6) with: 6) If an MLME-SAQuery.confirm primitive with an outstanding transaction identifier is notreceived within dot11AssociationSAQueryMaximumTimeout period, the SME shall issue a MLME-DISASSOCIATE.request primitive addressed to the STA with Reason Code "Previous Authentication no longer valid", after which the SME shall delete the old SA. Delete the last paragraph ("In case ...") in the clause, and move the note after 6. Maybe the "after which ..." part is unnecessary. It may be handled in the MLME-DISASSOCIATE.request. Note that other subclauses around here have problems as well and need similar changes. |  | GEN | MLME - Association | Discuss |  |  |  |  | 2011-03-02 18:34 | GEN
11013 | Stephens, Adrian | 1001 | 7 | 10.3.3.3 | 715 | 6 | T | Y | 715.06 | 6 | 10.3.3.3 | [5 empty] | Editor's Note: The following item effectively modifies the condition shown in bullet d). As such it conflicts with that condition. Ditto comment in 10.3.3.5 | There are perhaps two ways of fixing this, either by adding a condition to bullet d), ("and an SAQuery has not completed successfully within a timeout") or by adding an item 7) that describes how to respond to an MLME-ASSOCIATE.indication. |  | GEN | MLME - Association | Discuss |  |  |  |  | 2011-03-02 18:34 | GEN
11081 | Ptasinski, Henry | 1001 | 7 | 10.3.3.3 | 715 | 11 | T | Y | 715.11 | 11 | 10.3.3.3 | [5 empty] | The SME can't allow the association process at this point, as it already rejected the association request in d)1). | Make the following changes: a. Replace 6) with: 6) If an MLME-SAQuery.confirm primitive with an outstanding transaction identifier is notreceived within dot11AssociationSAQueryMaximumTimeout period, the SME shall issue a MLME-DISASSOCIATE.request primitive addressed to the STA with Reason Code "Previous Authentication no longer valid". b. Delete the last paragraph ("In case ...") in the clause c. and move the note after 6). d. Make the same changes in clause 10.3.3.5. |  | GEN | MLME - Association | Discuss |  |  |  |  | 2011-03-02 18:35 | GEN
11014 | Stephens, Adrian | 1001 | 7 | 10.3.3.3 | 715 | 47 | T | Y | 715.47 | 47 | 10.3.3.3 | [5 empty] | Editor's Note: Although the exact meaning of "failed SA Query procedure" is not clear, the following statement appears to conflict with "...with an outstanding transaction identifier is not received within dot11AssociationSAQueryMaximumTimeout period, the SME shall allow the association process to be started without starting an additional SA Query procedure." (line14) Ditto comment in 10.3.3.5 | Resolve the conflict |  | GEN | MLME - Association | Discuss |  |  |  |  | 2011-03-02 18:35 | GEN
11072 | Malinen, Jouni | 1001 | 7 | 10.3.3.3 | 715 | 48 | T | Y | 715.48 | 48 | 10.3.3.3 | [5 empty] | The Editor's Note here points out an unclear "failed SA Query produre" term and a possible conflict with an earlier description. I can agree with the first part, but I'm not sure I understood where exactly the conflict is. This additional requirement does not mean that the new association process would be prevented in any way. This is used to notify the non-AP STA with which there is an active SA that the association is dropped. In normal case, this protected Disassociation frame would not actually be received by the non-AP STA since it is indeed in the process of associating here. However, should this be an attack situation where the attacker managed to make the SA Query fail, this frame would be a notification for the real STA that association was lost. While I do not exactly agree with this being necessary functionality, it was added in 802.11w and at this point, the best approach would be to make sure that the goal of this functionality can be understood. This special case would require an action from the AP within the step (g) in the sequence above. As such, it would be good to move this text there. | Remove lines 53 through 59 (paragraph and NOTE). Modify item (g) above on line 23: Replace 'defined in 6.3.7.5.2. If the Result Code is SUCCESS, the association identifier' with 'defined in 6.3.7.5.2. If the ResultCode is SUCCESS, and the SME has an existing SA with the non-AP STA, and an SA Query procedure with that non-AP STA has failed to receive a valid response, then the SME shall send an MLME-DISASSOCIATE.request primitive to the STA with Reason Code "Previous Authentication no longer valid" (NOTE--This MLME-DISASSOCIATE.request generates a protected Disassociation frame addressed to the STA). If the ResultCode is SUCCESS, the association identifier'. |  | GEN | MLME - Association | Discuss |  |  |  |  | 2011-03-02 18:35 | GEN
11015 | Stephens, Adrian | 1001 | 7 | 10.3.3.4 | 716 | 31 | T | Y | 716.31 | 31 | 10.3.3.4 | [5 empty] | Editor's Note: Possible conflict with TimeoutInterval element in following para. Ditto comment in 10.3.3.5 | In the last sentence of the following para, add "and the Reassociation Response frame does not include a Timout Interval element with Timout Interval Type equal to 3" before the first comma. Add a new sentence to end of para: "If the status code indicates the reassociation failed and the Reassociation Response frame contains a Timeout Interval element with Timout Interval Type equal to 3, the SME shall not issue an MLME-REASSOCIATE. request primitive for the same AP until the period specified in the Timeout Interval element has elapsed." |  | GEN | MLME - Association | Proposed | Propose Agree |  |  |  | 2011-03-02 18:36 | GEN
11075 | Malinen, Jouni | 1001 | 7 | 10.3.3.5 | 717 | 9 | T | Y | 717.09 | 9 | 10.3.3.5 | [5 empty] | The conditions in step (c) do not cover the exception from (c) (6) to allow the consecutive SAQuery procedures to be skipped. | Add a new condition to the end of step (c): ", and an earlier, timed out SA Query procedure with the non-AP STA has not allowed a new association process to be started without an additional SA Query procedure". |  | GEN | MLME - Association | Proposed | Proposed Agree |  |  |  | 2011-03-02 18:37 | GEN
11074 | Malinen, Jouni | 1001 | 7 | 10.3.3.5 | 718 | 9 | T | Y | 718.09 | 9 | 10.3.3.5 | [5 empty] | The "failed SA Query procedure" term is a bit vague and this paragraph is not really in the best location since it applies to a specific step during the procedure described above. This special case would require an action from the AP within the step (g) in the sequence above (or just before this step). As such, it would be good to move this text there. | Remove lines 9 through 15 (paragraph and NOTE). Add a new step (g) into the procedure above (page 717 line 47) and update letters for remaining items accordingly: 'g) If the ResultCode is SUCCESS, and the SME has an existing SA with the non-AP STA, and an SA Query procedure with that non-AP STA has failed to receive a valid response, then the SME shall send an MLME-DISASSOCIATE.request primitive to the STA with Reason Code "Previous Authentication no longer valid". NOTE--This MLME-DISASSOCIATE.request generates a protected Disassociation frame addressed to the STA.' |  | GEN | MLME - Association | Discuss |  |  |  |  | 2011-03-02 18:37 | GEN

## MLME
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
11023 | Stephens, Adrian | 1001 | 7 | General |  |  | T | Y |  |  | General |  |  | Adrian Stephens |  |  | In discussions following the .11p roll-in, I believe we came to an improved understanding of the .request/.confirm/.indication/.response mechanism. Excluding those primitives that have a purely local effect, I think there are two types of service: asynchronous and synchronous. In the asynchronous case, the originator has no knowlege of whether the primitive reached the peer, and whether it had any effect on that peer. In the synchronous case, the originator knows whether the primitive reached the peer or not, and, in the successful case, that the peer has taken any necessary action and returned some kind of response. We have a number of services that try and provide a half-way house. These provide a "transmit status", but don't close the loop with the remote peer. In my opinion such .confirms are useless. They tell you something, but that something is not useful. They don't tell you whether the peer SME received the request (it could be discarded in the MLME for a number of reasons), or if it received it, whether any action taken by the peer has completed. Another issue is that of "Invalid Parameters". Given that the SME and MLME both equally know what is valid and what is not, there are no circumstances under which the SME should generate a request that results in locally-generated "Invalid parameters". | Remove any .confirms that are always locally generated and containing nothing more than a transmit status or "invalid parameters". Remove from other .confirms any locally generated "invalid parameters" status values. |  | GEN | MLME | Submission |  |  |  |  | 2011-03-04 12:47 | GEN
11240 | Hamilton, Mark | 1001 | 7 |  |  |  | T | Y | 104.6 | 60 | 6.3.7.2.2 | [5 empty] | In RSN Description, it should limit (to match the .indication): "Only one pairwise cipher suite and only one authenticated key suite are allowed in the RSN element." | Add this sentence, and make the nouns ("suites") singular. Also in 6.3.8.2.2, and 6.3.8.4.2. |  | GEN | MLME | Proposed | GEN: 2011-03-04 13:36:33Z - Propose Agree in Principle - Make proposed change, but "allowed" should be "present" for WG802.11 style consistency. GEN: 2011-03-01 - Propose Agree |  |  |  | 2011-03-04 13:38 | GEN
11239 | Hamilton, Mark | 1001 | 7 |  |  |  | T | Y | 104.6 | 60 | 6.3.7.2.2 | [5 empty] | "A description of the cipher suites and AKM suites supported in the BSS." How about supported by the STA? Or, really, it is each suite as selected by the STA. | Change "supported in the BSS" to "selected by the STA". In 6.3.7.4.2, change it to "selected by the STA that is requesting association." Similarly in 6.3.8.2.2 and 6.3.8.4.2. |  | GEN | MLME | Proposed | Propose Agree |  |  |  | 2011-03-02 18:01 | GEN
11241 | Hamilton, Mark | 1001 | 7 |  |  |  | T | Y | 159.62 | 62 | 6.3.24.1.4 | [5 empty] | "Once it is specified that a data frame is protected to or from a MAC address, this is reset by the MLMESETPROTECTION.request primitive. The MLME-SETPROTECTION.request primitive deletes the state by specifying None." - Huh? | (I think this is what it means) Change text to, "If it was previously specified that data frames are protected to or from the specified MAC address, the MLME-SETPROTECTION.request primitive wil reset the prior setting. The MLME-SETPROTECTION.request can be used to delete a protection state by specifying a ProtectType of None." |  | GEN | MLME | Proposed | Propose Agree |  |  |  | 2011-03-02 18:04 | GEN

## MIB & PICS
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
11236 | Hamilton, Mark | 1001 | 7 |  |  |  | T | Y | 1331.4399 | 44 | B.3.1 | [5 empty] | This paragraph needs to be updated for new sectoins that have been added, although it seems not very useful anyway. | Just delete this paragraph. |  | GEN | MIB & PICS | Proposed | Propose Agree |  |  |  | 2011-03-04 14:04 | GEN
11073 | Stephens, Adrian | 1001 | 7 | B.3.1 | 1331 | 44 | T | Y | 1331.4399 | 44 | B.3.1 | [5 empty] | The list "at least one of" was supposed to ennumerate the PHY alternatives, but was not updated by .11n, and "spectrum management" is hardly an alternative PHY. | Move spectrum management out of the list, and ensure the list includes all the PHYs. |  | GEN | MIB & PICS | Proposed | Propose Agree in principle, Spectrum management is not a PHY, and delete the paragraph. |  |  |  | 2011-03-04 14:05 | GEN
11042 | Malinen, Jouni | 1001 | 7 | C.3 | 1470 | 31 | T | N | 1470.3101 | 31 | C.3 | [5 empty] | The name of the MLME-SCAN.request parameter for SSID is not "DesiredSSID" as mentioned here; it is "SSID" (see 6.3.3.2.2 on page 86). While this text did not change in D7.0, this comment is somewhat related to an open comment CID 10143 from the previous ballot. I found the mismatch when searching for a MIB variable to set the SSID for an BSS. Alas, it looks like we do not have one for that purpose, but we did have this one with an incorrect description for scanning. | Replace "DesiredSSID parameter" with "SSID parameter". |  | GEN | MIB & PICS | Proposed | Propose to agree. |  |  |  | 2011-03-04 14:04 | GEN

## Regulatory
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
11109 | Ecclesine, Peter | 1001 | 7 | D.1 | 1710 | 31 | T | Y | 1710.3101 | 31 | D.1 | [5 empty] | Since the removal of emissions limits sets, LicensedBaseSTABehavior and MobileSTABehavior are defined without any normative requirements. Their existence in the standard adds no value. | Remove all references to LicensedBaseSTABehavior and MobileSTABehavior, both in Annex D and Annex E. |  | GEN | Regulatory | Proposed | proprose agree |  |  |  | 2011-03-02 16:41 | GEN
11112 | Ecclesine, Peter | 1001 | 7 | D.1 | 1719 | 15 | T | Y | 1719.15 | 15 | D.1 | [5 empty] | TransmitPowerControlBehavior is defined without any normative requirements. Its existence in the standard adds no value. The normative statement for the use of Transmit Power Control in the 3.65 GHz band is at E.2.2, page 1737 line 65. | Remove all remaining references to TransmitPowerControlBehavior, both in Annex D and Annex E. |  | GEN | Regulatory | Proposed | propose agree |  |  |  | 2011-03-02 16:42 | GEN
11113 | Ecclesine, Peter | 1001 | 7 | D.1 | 1719 | 19 | T | Y | 1719.1899 | 19 | D.1 | [5 empty] | DynamicFrequencySelectionBehavior is defined without any normative requirements. Its existence in the standard adds no value. The normative statement for the use of Transmit Power Control in the 3.65 GHz band is at E.2.2, page 1738 line 1. | Remove all remaining references to DynamicFrequencySelectionBehavior, both in Annex D and Annex E. |  | GEN | Regulatory | Proposed | propose agree (the paragraph in the right colum, on page 1719 line 20 includes a reference to 11.9 which does not exist either.) |  |  |  | 2011-03-02 16:46 | GEN
11108 | Ecclesine, Peter | 1001 | 7 | D.1 | 1719 | 23 | T | Y | 1719.23 | 23 | D.1 | [5 empty] | IBSSRestrictionsBehavior is defined and used only "where an IBSS is required to communicate with a licensed operator or agent designated by regulatory authorities." It is not a specified behavior in any band without such regulatory requirements, and should be removed from the standard as all stations that will be allowed to operate in those bands will meet such regulatory requirements. | Remove all references to IBSSRestrictionsBehavior, both in Annex D and Annex E. |  | GEN | Regulatory | Proposed | propose agree |  |  |  | 2011-03-02 16:46 | GEN
11106 | Ecclesine, Peter | 1001 | 7 | D.1 | 1719 | 36 | T | Y | 1719.36 | 36 | D.1 | [5 empty] | PublicSafetyBehavior is defined without any normative requirements. Its existence in the standard adds no value. | Remove all references to PublicSafetyBehavior, both in Annex D and Annex E. |  | GEN | Regulatory | Proposed | propose agree |  |  |  | 2011-03-02 16:47 | GEN
11107 | Ecclesine, Peter | 1001 | 7 | D.1 | 1720 | 6 | T | Y | 1720.0601 | 6 | D.1 | [5 empty] | Since the removal of emissions limits sets, RegisteredSTABehavior and DependentSTABehavior are defined without any normative requirements. Their existence in the standard adds no value. | Remove all references to RegisteredSTABehavior and DependentSTABehavior, both in Annex D and Annex E. |  | GEN | Regulatory | Proposed | propose agree |  |  |  | 2011-03-02 16:48 | GEN
11105 | Ecclesine, Peter | 1001 | 7 | D.1 | 1720 | 49 | T | Y | 1720.49 | 49 | D.1 | [5 empty] | The NOTE in footnote c is not correct because US Government facilities, including radiolocation facilities, are not regulated by the FCC. | Change NOTE by deleting "and three radiolocation facilities" |  | GEN | Regulatory | Proposed | propose agree |  |  |  | 2011-03-02 16:48 | GEN
11127 | Ecclesine, Peter | 1001 | 7 | D.2.5 | 1724 | 1 | T | Y | 1724.01 | 1 | D.2.5 | [5 empty] | 802.11y-2008 requires the use of CCA-ED, TPC, DFS and CS-4ms for operation in 3650 MHz band, but other frequency bands may require OFDM PHY CCA-ED behavior. Generalize Annex D.2.5 CCA-ED threshold to remove 3.65-3.7 GHz band, and restate the 802.11y requirement in normative text in E.2.2. In E.2.2 page 1738 after list item 'DFS' , insert dashed list item "CCA-ED (D.2.5 CCA-ED threshold)". In D.2.5 change start of first sentence from "For operation in the 3.65-3.7 GHz band, ..." to "For OFDM PHY operation in specific bands, ..." | per comment |  | GEN | Regulatory | Discuss |  |  |  |  | 2011-03-02 19:14 | GEN