## Slide 1: IEEE 802.11ah Timeline Projection
Date: 2012-05-17
Authors:

## Slide 2: Abstract
IEEE 802.11ah timeline. This document gets updated as milestones are met.

## Slide 3: Use TGac as guide to internal task group ballot
First/Last motion
Use Cases
Chnl Mdls
Func Req
Spec Frm
Use Cases
Chnl Mdls
Func Req
Spec Frm
JAN
MAR
MAY
JUL
SEP
NOV
JAN
MAR
MAY
JUL
SEP
NOV
JAN
TGac
TGah
Sub groups formed

## Slide 4: Forecasted IEEE 802.11ah timeline
Internal Task Group Ballot : November 2012
Initial Letter Ballot : March 2013
Initial Sponsor Ballot : March 2014
EC Approval : January 2015
Revcom Approval : March 2015