## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-11/1245r0
Venue Date: | Sept 2011
First Author: | Brian Hart, Cisco Systems
Subject: | LB178 MU comments - TGac D1.0
Full Date: | 2011-09-18
Author(s): |  | Brian Hart | Robert Stacey | Sameer Vermani
| Company | Cisco Systems | Apple | Qualcomm
Address
Phone:
Fax:
| email: | brianh@cisco.com | rjstacey@gmail.com | svverman@qualcomm.com
Abstract:
This document contains working update on comments assigned to the MUAd Hoc for the TGac P802.11ac/D1.0 and their resolution.

## Revision History
Revision | Date | History
0 | 2011-09-18 | Evolution of 11/1057 with MU-2011-07-19-PM2 and now adding MU-Seoul-20110913-20110916
1

## MU-Seoul-20110913-20110916
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
2562 | Hunter, David | 178 | 1 | 6.4.7.1 | 14 | 64 | T | Y | 14.64 | 64 | 6.4.7.1 |  | P | Brian |  |  | It is not clear what a "user" of a PPDU is. Does this mean "transmitting STA"? | Replace "user" with "transmitting STA" or define "user of a PPDU". If "user" is replaced, that change needs to be made throughout the draft text. | AGREE IN PRINCIPLE (MU: 2011-09-14 02:34:01Z) - Accept in principle. See 11/1128r1 | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-14 02:39 | MU
2797 | Lindskog, Erik | 178 | 1 | 8.4.1.38 | 33 | 50 | T | Y | 33.5 | 50 | 8.4.1.38 |  | P | Joonsuk |  |  | The packing rules are not specified | Say something like "No padding is present between angles, even if they correspond to different subcarriers. The last angle is followed with zero pad to make the VHT Compressed Beamforming Report field an integer number of octets in size.". Perhaps an example could be given | AGREE IN PRINCIPLE (MU: 2011-09-15 08:09:11Z) - See 11/1206r1 | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-15 08:09 | MU
3673 | van Zelst, Allert | 178 | 1 | 8.4.1.38 | 39 | 20 | T | N | 39.2 | 20 | 8.4.1.38 |  | P | Joonsuk |  |  | Ns is 468, but the number of indices is 476, it seems that only 8 pilot tones are skipped whereas 160 MHz has 16 pilot tones. | Also skip [+/-25 +/-53 +/-89 +/-117] | AGREE IN PRINCIPLE (MU: 2011-09-15 08:09:29Z) - See 11/1206r1 | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-15 08:10 | MU
2667 | Kim, Youhan | 178 | 1 | 8.4.1.38 | 39 | 20 | T | Y | 39.2 | 20 | 8.4.1.38 |  | P | Joonsuk |  |  | Subcarriers +-25, +-53, +-89 and +-117 are also pilot subcarriers in 160 MHz. | Delete +-25, +-53, +-89 and +-117 from the list. Also, add +-25, +-53, +-89 and +-117 to the list of pilot subcarriers. | AGREE IN PRINCIPLE (MU: 2011-09-15 08:13:47Z) - See 11/1206r1 | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-15 08:14 | MU
3171 | Perahia, Eldad | 178 | 1 | 8.4.1.38 | 42 | 30 | T | N | 42.3 | 30 | 8.4.1.38 |  | P | Joonsuk |  |  | be more specific about "feedback with BW=20MHz". | change to "feedback with Channel Width subfield of VHT MIMO Control field equal to 20 MHz". Do the same change for 40, 80, and 160 MHz | AGREE IN PRINCIPLE (MU: 2011-09-15 08:09:41Z) - See 11/1206r1 | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-15 08:10 | MU
2160 | Chu, Liwen | 178 | 1 | 8.4.1.38 | 42 | 30 | T | Y | 42.3 | 30 | 8.4.1.38 |  | P | Joonsuk |  |  | It is not clear what is "feedback with BW=10MHz". Is it "the width of the channel in which a measurement was made"? Is it "the width of the transmission"? | Clarify it. | AGREE IN PRINCIPLE (MU: 2011-09-15 08:07:48Z) - See 11/1206r1 | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-15 08:08 | MU
2279 | Fischer, Matthew | 178 | 1 | 8.4.1.39 | 42 | 61 | T | Y | 42.61 | 61 | 8.4.1.39 | 2660 | P | Joonsuk |  |  | More detail description is necessary Delta_SNR on how to represent it with 4 bits. For example, if Delta_SNR > 7 dB, it needs to represent it with 7. And if Delta_SNR < -8dB, it should be -8 in the report field. | need to submit contribution | AGREE IN PRINCIPLE (MU: 2011-09-15 08:08:10Z) - See 11/1206r1 | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-15 08:08 | MU
2798 | Lindskog, Erik | 178 | 1 | 8.4.1.39 | 43 | 14 | T | Y | 43.14 | 14 | 8.4.1.39 |  | P | Joonsuk |  |  | The packing rules are not specified | Say something like "No padding is present between delta SNRs, even if they correspond to different subcarriers.". Perhaps an example could be given | AGREE IN PRINCIPLE (MU: 2011-09-15 08:08:32Z) - See 11/1206r1 | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-15 08:09 | MU
2950 | LU, KAIYING | 178 | 1 | 9.30.5 | 92 | 42 | T | Y | 92.42 | 42 | 9.30.5 |  | A | Yong Liu, Tianyu Wu |  |  | Since a VHT Compressed Beamforming frame may be split into segments, when the beamformer fails to receive some of the segments, it should be clarified if segments correctly received could be considered as a valid response to the NDPA or Beamforming Report Poll. | Suggest to modify as follows:A VHT Compressed Beamforming frame sent received as a response to the NDPA, or at least one segment received as a response to the NDPA when the VHT Compressed Beamforming frame is segmented ,SIFS time after the NDP, is considered a valid response to the NDPA in the terms used in 9.19.2.4 (Multiple frame transmission in an EDCA TXOP).When a NDPA is the first frame in a TXOP , receiving at least one of the VHT Compressed Beamforming frame segments is considered that the TXOP has been obtained by the beamformer. | AGREE (MU: 2011-09-14 04:30:37Z) - Modify the spec text as suggested in 11/1193r2 | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-15 04:45 | MU
3306 | Rosdahl, Jon | 178 | 1 | 9.30.5 | 92 | 45 | T | Y | 92.45 | 45 | 9.30.5 |  | P | Yong Liu, Tianyu Wu |  |  | If the intent is that segmentation is only used if necessary, this needs to be specified | Say something like "If a VHT Compressed Beamforming frame would result in an MMPDU that does not exceed the maximum MPDU length, the VHT Compressed Beamforming Report field and MU Exclusive report field shall be sent in the same MPDU." | AGREE IN PRINCIPLE (MU: 2011-09-15 02:55:57Z) - SAME AS CID2816 | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-15 02:56 | MU
3307 | Rosdahl, Jon | 178 | 1 | 9.30.5 | 92 | 45 | T | Y | 92.45 | 45 | 9.30.5 |  | P | Yong Liu, Tianyu Wu |  |  | The beamformer and beamformee's maximum MPDU length may differ. Which is used? | Say something like "beamformer's maximum MPDU length capability" and add a "NOTE--The beamformee might therefore have to be able to transmit a bigger MPDU than it is capable of receiving." | AGREE IN PRINCIPLE (MU: 2011-09-15 02:56:27Z) - 1) SAME AS 2817 2) The NOTE is not necessarily true since a BFmee can set its BFming capabilities and Feedback parameters to ensure the Feedback frame length is always shorter than its max receiving MPDU length. No need to specify this. | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-15 02:57 | MU
2817 | Lindskog, Erik | 178 | 1 | 9.30.5 | 92 | 45 | T | Y | 92.45 | 45 | 9.30.5 |  | P | Yong Liu, Tianyu Wu |  |  | The beamformer and beamformee's maximum MPDU length may differ. Which is used? | Say something like "beamformee's maximum MPDU transmission length capability" | AGREE IN PRINCIPLE (MU: 2011-09-15 02:55:29Z) - 1) There is no transmission length capability; 2) Change to beamformer’s maximum MPDU length capability Refer to doc: 11/1191r1 | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-15 02:56 | MU
2816 | Lindskog, Erik | 178 | 1 | 9.30.5 | 92 | 45 | T | Y | 92.45 | 45 | 9.30.5 |  | P | Yong Liu, Tianyu Wu |  |  | If the intent is that segmentation is only used if necessary, this needs to be specified | Clarify | AGREE IN PRINCIPLE (MU: 2011-09-15 02:54:24Z): Add a rule: A VHT Compressed Beamforming frame shall be transmitted in a single MPDU unless the frame would result in an MMPDU that exceeds the beamformer’s maximum MPDU length capability. Refer to doc: 11/1191r1 | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-15 02:55 | MU
3305 | Rosdahl, Jon | 178 | 1 | 9.30.5 | 92 | 47 | T | Y | 92.47 | 47 | 9.30.5 |  | A | Yong Liu, Tianyu Wu |  |  | If it doesn't fit, then it can't not be split | Change "may" to "shall" | AGREE (MU: 2011-09-15 02:57:37Z) - Same as CID2815 | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-15 02:58 | MU
2815 | Lindskog, Erik | 178 | 1 | 9.30.5 | 92 | 47 | T | Y | 92.47 | 47 | 9.30.5 | 3305 | A |  |  |  | If it doesn't fit, then it can't not be split | Change "may" to "shall" | AGREE (MU: 2011-09-15 02:57:08Z) - Change “may” to “shall” | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-15 02:57 | MU
3359 | Rosdahl, Jon | 178 | 1 | 9.30.5 | 92 | 48 | T | Y | 92.48 | 48 | 9.30.5 |  | P | Yong Liu, Tianyu Wu |  |  | If the report is split up, may it be split up into any number from 2 to 8 segments, or must the number of segments be minimised? | Clarify | AGREE IN PRINCIPLE (MU: 2011-09-15 02:59:18Z) - Same as CID 2869. | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-15 02:59 | MU
2869 | Lindskog, Erik | 178 | 1 | 9.30.5 | 92 | 48 | T | Y | 92.48 | 48 | 9.30.5 | 3359 | P |  |  |  | If the report is split up, may it be split up into any number from 2 to 8 segments, or must the number of segments be minimised? | Clarify | AGREE IN PRINCIPLE (MU: 2011-09-15 02:59:03Z) - Add a rule that all segments except for the last one shall have a max MPDU length. Refer to doc: 11/1191r1 | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-15 02:59 | MU
2906 | Lindskog, Erik | 178 | 1 | 9.30.5 | 92 | 50 | T | Y | 92.5 | 50 | 9.30.5 |  | D | Yong Liu, Tianyu Wu |  |  | Is the beamformee allowed to return the segments out-of-order, i.e. with Remaining Segments set to 4,2,1,0,3, say? | Clarify | DISAGREE (MU: 2011-09-15 02:59:29Z) - Up to implementation. Can be out of order. No need to specify | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-15 03:00 | MU
2895 | Lindskog, Erik | 178 | 1 | 9.30.5 | 92 | 60 | T | Y | 92.6 | 60 | 9.30.5 |  | D | Yong Liu, Tianyu Wu |  |  | Is there any restriction as to when the re-poll is to be performed? | Clarify -- do you have to use PIFS recovery? | DISAGREE (MU: 2011-09-15 02:59:54Z) - BFmer has the freedom to decide whether and when to repoll. No need to specify. | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-15 03:00 | MU
3386 | Rosdahl, Jon | 178 | 1 | 9.30.5 | 92 | 60 | T | Y | 92.6 | 60 | 9.30.5 |  | D | Yong Liu, Tianyu Wu |  |  | Is there any restriction as to when the re-poll is to be performed? | Clarify | DISAGREE (MU: 2011-09-15 02:59:41Z) - Same as CID2895. | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-15 03:00 | MU
2905 | Lindskog, Erik | 178 | 1 | 9.30.5 | 92 | 64 | T | Y | 92.64 | 64 | 9.30.5 |  | D | Yong Liu, Tianyu Wu |  |  | If the beamformer does receive the segment with FS set, is it still allowed to request retransmission assuming there are 8 segments? | Clarify | DISAGREE (MU: 2011-09-15 03:00:07Z) - It is not disallowed. No need to specify. | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-15 03:00 | MU
3388 | Rosdahl, Jon | 178 | 1 | 9.30.5 | 93 |  | T | Y | 93 |  | 9.30.5 |  | P | Yong Liu, Tianyu Wu |  |  | What if the Segment Retx Bitmap has bits set for segments which don't exist (e.g. b7 is set by there were only 7 segments)? | Clarify | AGREE IN PRINCIPLE (MU: 2011-09-15 03:00:23Z) - Same as 2897 | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-15 03:00 | MU
2897 | Lindskog, Erik | 178 | 1 | 9.30.5 | 93 |  | T | Y | 93 |  | 9.30.5 |  | P | Yong Liu, Tianyu Wu |  |  | What if the Segment Retx Bitmap has bits set for segments which don't exist (e.g. b7 is set but there were only 7 segments)? | Clarify | AGREE IN PRINCIPLE (MU: 2011-09-15 03:00:34Z) - Add “if the indicated segments present” Refer to doc: 11/1191r1 | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-15 03:01 | MU
2819 | Lindskog, Erik | 178 | 1 | 9.30.5 | 93 | 6 | T | Y | 93.06 | 6 | 9.30.5 | 3309 | P |  |  |  | This does not allow a STA to not provide a report, contrary to 91.64 | Say something like "or by sending a VHT Compressed Beamforming frame without including the VHT Compressed Beamforming Report field and the MU Exclusive Beamforming Report field" | AGREE IN PRINCIPLE (MU: 2011-09-15 03:01:18Z) - Clarify that in this case, the BFmee intends to send a non-null FB frame. Refer to doc: 11/1191r1 | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-15 03:01 | MU
3768 | Yee, James | 178 | 1 | 9.30.5 | 93 | 6 | T | N | 93.06 | 6 | 9.30.5 |  | P | Yong Liu, Tianyu Wu |  |  | In the retransmission of segments by the beamformee, the beamformee should be allowed to retransmit no segments by setting the Remaining Segments field to all ones in the VHT MIMO Control field. This will indicate to the beamformer that the beamformee does support retransmission in this exchange. Editorially, this paragraph does not clearly describe what the beamformee needs to do. Is it being required to transmit a VHT Compressed Beamforming frame with the described segment information? | Clarify as suggested. | AGREE IN PRINCIPLE (MU: 2011-09-15 03:00:53Z) - 1) Agree that BFmee should be allowed to send Null FB if it does not have any FB available; 2) However, BFmee shall not reject a retransmission request by sending a Null FB. Clarify that in this case, the BFmee intends to send a non-null FB frame. Refer to doc: 11/1191r1 | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-15 03:01 | MU
3309 | Rosdahl, Jon | 178 | 1 | 9.30.5 | 93 | 6 | T | Y | 93.06 | 6 | 9.30.5 |  | P | Yong Liu, Tianyu Wu |  |  | This does not allow a STA to not provide a report, contrary to 91.64 | Say something like "or by sending a VHT Compressed Beamforming frame without including the VHT Compressed Beamforming Report field and the MU Exclusive Beamforming Report field" | AGREE IN PRINCIPLE (MU: 2011-09-15 03:01:07Z) - Same as CID2819. | MU | MU-Seoul-ad-hoc-20110913-20110916 | [5 empty] | 2011-09-15 03:01 | MU

## MU-2011-07-19-PM2
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3548 | Stephens, Adrian | 178 | 1 | 8.3.1.12 | 27 | 33 | T | N | 27.33 | 33 | 8.3.1.12 |  | D | Illsoo | 11/1025r0 |  | I suspect that the segment retransmission bitmap is not useful without a reference to a specific instance of feedback. This would ensure that the STA hasn't updated its local estimate and revised feedback between sending an initial full feedback and then being polled for missed segments. | Put a sounding sequence number in this frame. | DISAGREE (MU: 2011-07-20 15:29:38Z) See 11/1025r0 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:30 | MU
3284 | Rosdahl, Jon | 178 | 1 | 8.3.1.12 | 27 | 51 | T | Y | 27.51 | 51 | 8.3.1.12 |  | D | Illsoo | 11/1025r0 |  | See comment on page 33 line 12--"What does "the remaining segment number" mean?" , but is the intent really that b0 is set to ask for retransmission of the last segment, then b1 for the penultimate one, and so on? This is somewhat counterintuitive | Add a Note, maybe? | DISAGREE (MU: 2011-07-20 15:24:33Z). The segment indication rule with Segment Retransmission Bitmap field is defined with no ambiguity in the current spec text. There is no need to change or add texts as long as the rule is clearly defined. See 11/1025r0 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:25 | MU
2794 | Lindskog, Erik | 178 | 1 | 8.3.1.12 | 27 | 51 | T | Y | 27.51 | 51 | 8.3.1.12 |  | D | Illsoo | 11/1025r0 |  | See previous CID, but is the intent really that b0 is set to ask for retransmission of the last segment, then b1 for the penultimate one, and so on? This is somewhat counterintuitive | Add a Note, maybe? | DISAGREE (MU: 2011-07-20 15:24:02Z). The segment indication rule with Segment Retransmission Bitmap field is defined with no ambiguity in the current spec text. There is no need to change or add texts as long as the rule is clearly defined. See 11/1025r0 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:26 | MU
3066 | Merlin, Simone | 178 | 1 | 9.30.5 | 27 | 55 | T | Y | 27.55 | 55 | 9.30.5 |  | P | Yong Liu, Tianyu Wu | 11/961r2 |  | Beamforming Report Poll frame can carry HT control field in HT format with the NDP Announcement set to 1, or with the TRQ set to 1; these cases give origin to ambiguous frame exchange definitions and potential collisions; Other functionalities indicated by the HTC-VHT are not relevant to the VHT sounding protocol. In order to maintain a well defined VHT sounding protocol the HT Control field in the HT format should not be sent in a Beamforming Report Poll frame | Add a rule: "HTControl field in the HT format shall not be present in an Beamforming Report Poll Frame" | AGREE IN PRINCIPLE (MU: 2011-07-20 15:40:54Z)See CID 3099 resolution. | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:41 | MU
2804 | Lindskog, Erik | 178 | 1 | 8.4.1.37 | 32 | 29,35,41 | T | Y | 32 |  | 8.4.1.37 |  | P | Joonsuk | 11/1026r1 |  | "in a matrix" is rather wishy-washy; ditto "a measurement" | Clarify: what matrix and measurement? | AGREE IN PRINCIPLE (MU: 2011-07-20 16:02:35Z) - Resolved by CID 2666 for ‘matrix’ part. For ‘measurement’ part, Agreed that it is confusing. See 11/1026r1 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 16:08 | MU
3294 | Rosdahl, Jon | 178 | 1 | 8.4.1.37 | 32 | 29,35,41 | T | Y | 32 |  | 8.4.1.37 |  | P | Joonsuk | 11/1026r1 |  | "in a matrix" is rather wishy-washy; ditto "a measurement" | Clarify what matrix and measurement? | AGREE IN PRINCIPLE (MU: 2011-07-20 16:15:36Z) - Duplicate of CID 2804 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 16:16 | MU
2002 | Aboul-Magd, Osama | 178 | 1 | 8.4.1.37 | 32 | 11-13 | T | N | 32 |  | 8.4.1.37 |  | A | Joonsuk | 11/1026r1 |  | B18-B23 carries the sounding sequence number (the last 6 bits of the sounding sequence field) not the sounding sequence filed (which is 8-bit long) | change "sounding sequence" to "Sounding sequence number" in Figure 8-ac8 and Table 8-ac4 on page 33. | AGREE (MU: 2011-07-20 15:58:24Z) - Current words are confusing. See 11/1026r1 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 16:06 | MU
3042 | Malinen, Jouni | 178 | 1 | 8.4.1.37 | 32 | 14 | T | Y | 32.14 | 14 | 8.4.1.37 |  | A | Joonsuk | 11/1026r1 |  | Reserved fields B16..B17 in Figure 8-ac8 are claimed to be 4 bits in size. | Replace "4" with "2" as the length of the Reserved field in Figure 8-ac8. | AGREE (MU: 2011-07-20 16:03:35Z) - See 11/1026r1 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 16:04 | MU
3771 | Zhang, Hongyuan | 178 | 1 | 8.4.1.37 | 32 | 14 | T | N | 32.14 | 14 | 8.4.1.37 |  | A | Joonsuk | 11/1026r1 |  | Reserved Subfield is 2 bits | Change to 2 bits | AGREE (MU: 2011-07-20 16:03:52Z) - See 11/1026r1 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 16:04 | MU
2666 | Kim, Youhan | 178 | 1 | 8.4.1.37 | 32 | 30 | T | Y | 32.3 | 30 | 8.4.1.37 |  | P | Joonsuk | 11/1026r1 |  | a matrix' is ambiguous. Same comment on P32L35 | Change 'a matrix' to 'the compressed beamforming matrix' | AGREE IN PRINCIPLE (MU: 2011-07-20 15:59:40Z) - See 11/1026r1 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 16:00 | MU
3668 | van Zelst, Allert | 178 | 1 | 8.4.1.37 | 32 | 30 | T | N | 32.3 | 30 | 8.4.1.37 |  | P | Joonsuk | 11/1026r1 |  | "Indicates the number of columns, Nc, in a matrix minus one" -> in what matrix? | Clarify by changing to "in a beamforming matrix" | AGREE IN PRINCIPLE (MU: 2011-07-20 16:00:09Z) - See 11/1026r1 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 16:00 | MU
3669 | van Zelst, Allert | 178 | 1 | 8.4.1.37 | 32 | 35 | T | N | 32.35 | 35 | 8.4.1.37 |  | P | Joonsuk | 11/1026r1 |  | "Indicates the number of rows, Nr, in a matrix minus one" -> in what matrix? | Clarify by changing to "in a beamforming matrix" | AGREE IN PRINCIPLE (MU: 2011-07-20 16:00:24Z) - See 11/1026r1 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 16:00 | MU
2793 | Lindskog, Erik | 178 | 1 | 8.4.1.37 | 33 | 12 | T | Y | 33.12 | 12 | 8.4.1.37 |  | A | Joonsuk | 11/1025r0 |  | What does "the remaining segment number" mean? | "the number of segments following this segment (not necessarily in the A-MPDU in which the segment is carried, however)"? | AGREE (MU: 2011-07-20 15:20:58Z) The sentence needs to be clarified. See 11/1025r0 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:21 | MU
3283 | Rosdahl, Jon | 178 | 1 | 8.4.1.37 | 33 | 12 | T | Y | 33.12 | 12 | 8.4.1.37 |  | A | Joonsuk | 11/1025r0 |  | What does "the remaining segment number" mean? | "the number of segments following this segment"? | AGREE (MU: 2011-07-20 15:23:05Z) - The sentence needs to be clarified. See 11/1025r0 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:23 | MU
3251 | Reuss, Edward | 178 | 1 | 8.4.1.37 | 33 | 20 | T | Y | 33.2 | 20 | 8.4.1.37 |  | D | Joonsuk | 11/1026r1 |  | For the phrase ", the field is set to all ones", shouldn't the field be set to "Reserved"? Do we have a standard assignment for Reserved fields? Why does this clause explicitly specify this reserved field is set set to all ones? | Change this field to follow the standard behaviour for a reserved field. | DISAGREE (MU: 2011-07-20 16:11:55Z) - : Need to define bits when it is not used. Setting all ones is clear to set and it would not be used for other purpose. | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 16:12 | MU
3043 | Malinen, Jouni | 178 | 1 | 8.4.1.37 | 33 | 27 | T | N | 33.27 | 27 | 8.4.1.37 |  | D | Joonsuk | 11/1026r1 |  | Table 8-ac4 does not include the Reserved subfield. While this is not really used now, it would be better to explicitly define how it is to be set and ignored to allow for future extensions. | Add following row to Table 8-ac4: “Reserved ¦ Set to 0 on transmission. Ignored on reception.” | DISAGREE (MU: 2011-07-20 16:04:26Z) - No need for subscription on ‘reserved’. | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 16:09 | MU
3252 | Reuss, Edward | 178 | 1 | 8.4.1.37 | 33 | 34 | T | Y | 33.34 | 34 | 8.4.1.37 |  | D | Joonsuk | 11/1026r1 |  | For the phrase "Sounding Sequence are reserved and set to 0", shouldn't the field be set to "Reserved"? Do we have a standard assignment for Reserved fields? Why does this clause explicitly specify this reserved field is set to all zeros? | Change this field to follow the standard behaviour for a reserved field. | DISAGREE (MU: 2011-07-20 16:14:50Z) - Duplicate of CID 3251 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 16:15 | MU
2744 | Kudo, Riichi | 178 | 1 | 8.4.1.38 | 36 | 38 | T | Y | 36.38 | 38 | 8.4.1.38 |  | P | Joonsuk | 11/1026r1 |  | Whether pilot subcarriers are included in the calculation of averaged SNR or NOT is not clear. | Please clarify. | AGREE IN PRINCIPLE (MU: 2011-07-20 16:00:50Z) - Resolved by CID 2027. | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 16:07 | MU
2027 | Asai, Yusuke | 178 | 1 | 8.4.1.38 | 36 | 38 | T | Y | 36.38 | 38 | 8.4.1.38 |  | A | Joonsuk | 11/1026r1 |  | "averaged over subcarriers" is not clear. It is seemed that pilot subcarriers are not used to calculate the average SNR of each space-time stream because V matrices corresponding to pilot subcarriers are not included in VHT compressed beamforming report field; however, there is no definition to identify whether pilot subcarriers are included or not to calculate the average SNR. | Please clarify the subcarriers which are used for average SNR calculation. If only data subcarriers are used for calculation of SNR, change "averaged over subcarriers" to "averaged over all data subcarriers". | AGREE (MU: 2011-07-20 15:59:10Z) - Current words are confusing. See 11/1026r1 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 16:07 | MU
3172 | Perahia, Eldad | 178 | 1 | 8.4.1.39 | 42 | 45 | T | N | 42.45 | 45 | 8.4.1.39 |  | P | Joonsuk | 11/1026r1 |  | Feedback Type values are 0 or 1 | change "MU" to "1 indicating MU" | AGREE IN PRINCIPLE (MU: 2011-07-20 16:05:08Z) - Better to describe it with the specific meaning that it is a feedback for MU. However, we’d better change the description on Feedback type in Table 8-ac4 since we don’t really use SU-BF or MU-BF in the text. See 11/1026r1 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 16:10 | MU
3173 | Perahia, Eldad | 178 | 1 | 8.4.1.39 | 42 | 51 | T | N | 42.51 | 51 | 8.4.1.39 |  | P | Joonsuk | 11/1026r1 |  | what is Ng'? | please clarify | AGREE IN PRINCIPLE (MU: 2011-07-20 16:05:41Z) - Resolved by CID 2800 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 16:06 | MU
2800 | Lindskog, Erik | 178 | 1 | 8.4.1.39 | 42 | 51 | T | Y | 42.51 | 51 | 8.4.1.39 |  | P | Joonsuk | 11/1026r1 |  | Spurious prime after "Ng" | Delete the prime after "Ng" | AGREE IN PRINCIPLE (MU: 2011-07-20 16:03:00Z) - Ng’ description is new and missing the description. Since it is not mentioned anywhere else, we may remove Ng’ in the text.. See 11/1026r1 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 16:09 | MU
3290 | Rosdahl, Jon | 178 | 1 | 8.4.1.39 | 42 | 51 | T | Y | 42.51 | 51 | 8.4.1.39 |  | P | Joonsuk | 11/1026r1 |  | Spurious prime after "Ng" | Delete the prime after "Ng+G82" | AGREE IN PRINCIPLE (MU: 2011-07-20 16:16:13Z) - Duplicate of CID 2800 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 16:16 | MU
3194 | Ponnampalam, Vish | 178 | 1 | 8.4.1.39 | 45 | 3-36 | T | N | 45 |  | 8.4.1.39 |  | P | Joonsuk | 11/1026r1 |  | Second column of table is Ng not Ng'. As such valid values for Ng are 1,2 and 4. | as per comment | AGREE IN PRINCIPLE (MU: 2011-07-20 16:10:19Z) - See 11/1026r1 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 16:10 | MU
3455 | Shi, Wei | 178 | 1 | 8.4.1.39 | 45 | 12,26,34 | T | Y | 45 |  | 8.4.1.39 |  | P | Joonsuk | 11/1026r1 |  | Ng for 160MHz appears to be incorrect. | I think they should be 1,2 and 4 respectively. | AGREE IN PRINCIPLE (MU: 2011-07-20 16:11:26Z) - See 11/1026r1 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 16:11 | MU
2280 | Fischer, Matthew | 178 | 1 | 8.4.1.39 | 45 | 1 | T | Y | 45.01 | 1 | 8.4.1.39 | 2661 | P | Joonsuk | 11/1026r1 |  | Table 8-ac11 for 160MHz, Ng needs to be 1,2 and 4, Not 2,4 and 8, to be consistent with BW=20/40/80MHz | change it as recommended | AGREE IN PRINCIPLE (MU: 2011-07-20 16:10:52Z) - See 11/1026r1 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 16:11 | MU
2661 | Kim, Joonsuk | 178 | 1 | 8.4.1.39 | 45 | 1 | T | Y | 45.01 | 1 | 8.4.1.39 |  | P | Joonsuk | 11/1026r1 |  | Table 8-ac11 for 160MHz, Ng needs to be 1,2 and 4, Not 2,4 and 8, to be consistent with BW=20/40/80MHz | change it as recommended | AGREE IN PRINCIPLE (MU: 2011-07-20 16:11:15Z) - See 11/1026r1 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 16:11 | MU
3195 | Ponnampalam, Vish | 178 | 1 | 8.4.1.39 | 46 | 3-46 | T | N | 46 |  | 8.4.1.39 |  | P | Joonsuk | 11/1026r1 |  | Second column of table is Ng not Ng'. As such valid values for Ng are 1,2 and 4. | as per comment | AGREE IN PRINCIPLE (MU: 2011-07-20 16:10:37Z) - See 11/1026r1 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 16:11 | MU
3099 | Merlin, Simone | 178 | 1 | 9.30.5 | 90 | 24 | T | Y | 90.24 | 24 | 9.30.5 |  | P | Yong Liu, Tianyu Wu | 11/961r2 |  | Sounding protocol shall use VHT NDP only. | modify: "A beamformer shall initiate a sounding feedback sequence by sending an NDPA frame followed by an NDP frame after a SIFS." to "A beamformer shall initiate a sounding feedback sequence by sending an NDPA frame followed by an VHT NDP frame after a SIFS." | AGREE IN PRINCIPLE (MU: 2011-07-20 15:33:54Z)Please see the change in 11/0961r2 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:39 | MU
2891 | Lindskog, Erik | 178 | 1 | 9.30.5 | 90 | 42 | T | Y | 90.42 | 42 | 9.30.5 | 3382 | D |  | 11/961r2 |  | So an NDPA may contain multiple STA Infos even if the FT is SU, as long as all the STAs are MU-capable? | Clarify | DISAGREE (MU: 2011-07-20 15:43:44Z)Ans: Yes | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:44 | MU
3382 | Rosdahl, Jon | 178 | 1 | 9.30.5 | 90 | 42 | T | Y | 90.42 | 42 | 9.30.5 |  | D | Yong Liu, Tianyu Wu | 11/961r2 |  | So an NDPA may contain multiple STA Infos even if the FT is SU, as long as all the STAs are MU-capable? | Clarify | DISAGREE (MU: 2011-07-20 15:44:00Z)Ans: Yes | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:44 | MU
2893 | Lindskog, Erik | 178 | 1 | 9.30.5 | 90 | 61 | T | Y | 90.61 | 61 | 9.30.5 | 3384 | D |  | 11/961r2 |  | How does the beamformer know how big the VHT Compressed Beamforming frames will be (so that it knows whether they will fit in the TXOP Limit)? What happens if they don't fit (especially in the case of a single beamformee)? | Clarify | DISAGREE (MU: 2011-07-20 15:47:28Z)Ans: It is BFmer’s responsibility to leave sufficient time in the TXOP for BFmee to send the BFming report. BFmee does not need to check the TXOP limit. If the BFming report exceeds the max PPDU duration, the BFmee shall send a Null report back. | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:48 | MU
3384 | Rosdahl, Jon | 178 | 1 | 9.30.5 | 90 | 61 | T | Y | 90.61 | 61 | 9.30.5 |  | D | Yong Liu, Tianyu Wu | 11/961r2 |  | How does the beamformer know how big the VHT Compressed Beamforming frames will be (so that it knows whether they will fit in the TXOP Limit)? What happens if they don't fit (especially in the case of a single beamformee)? | Clarify | DISAGREE (MU: 2011-07-20 15:47:51Z)See CID 2893 resolution | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:48 | MU
3459 | Shi, Wei | 178 | 1 | 9.30.5 | 91 | 64-65 | T | Y | 91 |  | 9.30.5 |  | D | Yong Liu, Tianyu Wu | 11/961r2 |  | My understanding here is that if a beamformee has no stored compressed beamforming report after receiving a beamforming report poll then it does not have to include the compressed beamforming report field. Why does this not apply to receiving a NDP? As far as I can see, this is the same as a MU capable beamformee receiving a beamforming report poll for the first time. | I would recommend allowing this for receiving a NDP too. | DISAGREE (MU: 2011-07-20 15:50:44Z)1) If a BFmee receives both NDPA and NDP correctly, it shall prepare for a BFming report, and send the report SIFS after NDP or a Poll frame (based on NDPA indication). 2) If a BFmee does not receive either NDPA or NDP correctly, it does not know whether or when to send a Null BFming report after NDP. It is also not a good practice for BFmee to transmit anything when receiving a failed NDPA or NDP. 3) However, if the BFmee receives a Poll frame correctly, it knows exactly when to send a Null BFming report. | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:51 | MU
3778 | Zhang, Hongyuan | 178 | 1 | 9.30.5 | 91 | 1~27 | T | N | 91 |  | 9.30.5 |  | P | Yong Liu, Tianyu Wu | 11/961r2 |  | For better clarity, it should be mandatotory that an VHT NDPA (i.e. the NDPA MAC format follows 8.3.1.11) has to be followed by an VHT NDP, and an HT NDPA (using HT Control Field) has to be followed by an HT NDP. The mixture between VHT and HT NDPA/NDP are not allowed | Add appropriate language to reflect the constraints as in the comment. | AGREE IN PRINCIPLE (MU: 2011-07-20 15:39:47Z) See CID 3099 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:40 | MU
3676 | van Zelst, Allert | 178 | 1 | 9.30.5 | 91 | 32 | T | N | 91.32 | 32 | 9.30.5 |  | P | Yong Liu, Tianyu Wu | 11/961r2 |  | It is not clear if "Rx MCS map in the VHT Supported MCS set field" refers to that of the beamformer or beamformee | add "of the corresponding beamformee" to the end of the sentense. | AGREE IN PRINCIPLE (MU: 2011-07-20 15:42:03Z)See CID 2684 resolution | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:42 | MU
2684 | Kim, Youhan | 178 | 1 | 9.30.5 | 91 | 32 | T | Y | 91.32 | 32 | 9.30.5 |  | P | Yong Liu, Tianyu Wu | 11/961r2 |  | Whose 'Rx MCS map' does this refer to? | Please clarify. | AGREE IN PRINCIPLE (MU: 2011-07-20 15:41:33Z)Please see the change in 11/0961r2 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:42 | MU
3065 | Merlin, Simone | 178 | 1 | 9.30.5 | 91 | 33 | T | Y | 91.33 | 33 | 9.30.5 |  | P | Yong Liu, Tianyu Wu | 11/961r2 |  | NDPA frame can carry HT control field in HT format with the NDP Announcement set to 1, or with the TRQ set to 1; these cases give origin to ambiguous frame exchange definitions and potential collisions; Other functionalities indicated by the HTC-VHT are not relevant to the VHT sounding protocol. In order to maintain a well defined VHT sounding protocol the HT Control field in the HT format should not be sent in NDPA | Add a rule: "HTControl field in the HT format shall not be present in an NDPA Frame" | AGREE IN PRINCIPLE (MU: 2011-07-20 15:40:12Z)See CID 3099 resolution | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:41 | MU
3399 | Seok, Yongho | 178 | 1 | 9.30.5 | 91 | 41 | T | Y | 91.41 | 41 | 9.30.5 |  | D | Yong Liu, Tianyu Wu | 11/961r2 |  | According to 9.30.6, TXVECTOR CH_BANDWIDTH of an NDP frame shall be set to the same value as the TXVECTOR CH_BANDWIDTH of an NDP frame preceeding it. Thus "The TXVECTOR parameter CH_BANDWIDTH of the VHT Compressed Beamforming frame shall be set to indicate a bandwidth not wider than that indicated in the RXVECTOR parameter CH_BANDWIDTH of the received NDP frame" could be better changed to "~ of the received NDPA frame" | Change "~ of the received NDP frame" to "~ of the received NDPA frame" | DISAGREE (MU: 2011-07-20 15:42:29Z)BFming report frame is sent immediately after receiving NDP. It is better to refer to the BW of NDP. | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:43 | MU
3414 | Seok, Yongho | 178 | 1 | 9.30.5 | 91 | 41 | T | Y | 91.41 | 41 | 9.30.5 | 308 | D |  | 11/961r2 |  | According to 9.30.6, TXVECTOR CH_BANDWIDTH of an NDP frame shall be set to the same value as the TXVECTOR CH_BANDWIDTH of an NDP frame preceeding it. Thus "The TXVECTOR parameter CH_BANDWIDTH of the VHT Compressed Beamforming frame shall be set to indicate a bandwidth not wider than that indicated in the RXVECTOR parameter CH_BANDWIDTH of the received NDP frame" could be better changed to "~ of the received NDPA frame" | Change "~ of the received NDP frame" to "~ of the received NDPA frame" | DISAGREE (MU: 2011-07-20 15:42:55Z)See CID 3399 resolution. | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:43 | MU
2956 | LU, KAIYING | 178 | 1 | 9.30.5 | 91 | 43 | T | Y | 91.43 | 43 | 9.30.5 |  | A | Yong Liu, Tianyu Wu | 11/961r2 |  | If the Individual/group bit in TA field of the the Beamformer Report Poll frame equals to 1 , the beamformee shall force the individual/Group bit of the TA field to 0 before matching with the MAC address of the beamformer. | A beamformee that receives an NDPA from a beamformer with which it is associated or with which it has an established DLS or TDLS session and that contains the beamformee’s AID in the AID subfield of a STA Info field that is not the first STA Info field shall transmit its VHT Compressed Beamforming frame after receiving a Beamforming Report Poll with RA matching its MAC address and TA with the Individual/Group bit forced to 0 matching the MAC address of the beamformer. | AGREE (MU: 2011-07-20 15:44:46Z)Change text as suggested. Please see the change in 11/0961r1 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:45 | MU
3665 | SUN, BO | 178 | 1 | 9.30.5 | 91 | 43 | T | Y | 91.43 | 43 | 9.30.5 | 737 | A |  | 11/961r2 |  | If the Individual/group bit in TA field of the the Beamformer Report Poll frame equals to 1 , the beamformee shall force the individual/Group bit of the TA field to 0 before matching with the MAC address of the beamformer. | A beamformee that receives an NDPA from a beamformer with which it is associated or with which it has an established DLS or TDLS session and that contains the beamformee’s AID in the AID subfield of a STA Info field that is not the first STA Info field shall transmit its VHT Compressed Beamforming frame after receiving a Beamforming Report Poll with RA matching its MAC address and TA with the Individual/Group bit forced to 0 matching the MAC address of the beamformer. | AGREE (MU: 2011-07-20 15:45:35Z)See CID 2956 resolution | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:46 | MU
2944 | LU, KAIYING | 178 | 1 | 9.30.5 | 91 | 55 | T | Y | 91.55 | 55 | 9.30.5 |  | A | Yong Liu, Tianyu Wu | 11/961r2 |  | A VHT STA that sends a VHTcompressed beamforming frame in response to a non-HT or non-HT duplicate format frame with the Individual/Group bit in the TA field equal to 1, shall set the I/G bit inthe RA field of the response frame to "0" | modify in p91/l55 "...not wider than that indicated by the RXVECTOR parameter CH_BANDWIDTH of the Beamforming Report Poll frame. Note that the RA field of the VHT Compressed Beamforming frame shall be set to the MAC address obtained from the TA field of the NDPA frame or the Beamforming Report Poll frame to which this VHT Compressed Beamforming frame is a response with the Individual/Group bit in the RA field set to 0. ". | AGREE (MU: 2011-07-20 15:45:51Z)Change text as suggested. Please see the change in 11/0961r2 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:46 | MU
3641 | SUN, BO | 178 | 1 | 9.30.5 | 91 | 55 | T | Y | 91.55 | 55 | 9.30.5 | 725 | A |  | 11/961r2 |  | A VHT STA that sends a VHTcompressed beamforming frame in response to a non-HT or non-HT duplicate format frame with the Individual/Group bit in the TA field equal to 1, shall set the I/G bit inthe RA field of the response frame to "0" | modify in p91/l55 "...not wider than that indicated by the RXVECTOR parameter CH_BANDWIDTH of the Beamforming Report Poll frame. Note that the RA field of the VHT Compressed Beamforming frame shall be set to the MAC address obtained from the TA field of the NDPA frame or the Beamforming Report Poll frame to which this VHT Compressed Beamforming frame is a response with the Individual/Group bit in the RA field set to 0. ". | AGREE (MU: 2011-07-20 15:46:15Z)See CID 2944 resolution. | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:46 | MU
2820 | Lindskog, Erik | 178 | 1 | 9.30.5 | 91 | 61 | T | Y | 91.61 | 61 | 9.30.5 | 3310 | D |  | 11/961r2 |  | What if it violates something else, like the TXOP Limit on AC_VO? | Clarify | DISAGREE (MU: 2011-07-20 15:46:49Z)Ans: It is BFmer’s responsibility to leave sufficient time in the TXOP for BFmee to send the BFming report. BFmee does not need to check the TXOP limit. | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:47 | MU
3310 | Rosdahl, Jon | 178 | 1 | 9.30.5 | 91 | 61 | T | Y | 91.61 | 61 | 9.30.5 |  | D | Yong Liu, Tianyu Wu | 11/961r2 |  | What if it violates something else, like the TXOP Limit on AC_VO? | Clarify | DISAGREE (MU: 2011-07-20 15:47:06Z)See CID 2820 resolution. | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:47 | MU
3645 | SUN, BO | 178 | 1 | 9.30.5 | 91 | 64 | T | Y | 91.64 | 64 | 9.30.5 | 729 | D |  | 11/961r2 |  | it is also true When the beamformee does not have any stored VHT compressed beamforming report after receiving an NDPA. | change the sentence as "the beamformee does not have any stored VHT Compressed Beamforming Report after receiving a Beamforming Report Poll frame or an NDPA frame." | DISAGREE (MU: 2011-07-20 15:51:34Z)See CID 3459 resolution. | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:52 | MU
2948 | LU, KAIYING | 178 | 1 | 9.30.5 | 91 | 64 | T | Y | 91.64 | 64 | 9.30.5 |  | D | Yong Liu, Tianyu Wu | 11/961r2 |  | it is also true When the beamformee does not have any stored VHT compressed beamforming report after receiving an NDPA. | change the sentence as "the beamformee does not have any stored VHT Compressed Beamforming Report after receiving a Beamforming Report Poll frame or an NDPA frame." | DISAGREE (MU: 2011-07-20 15:51:05Z)See CID 3459 resolution. | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:51 | MU
3460 | Shi, Wei | 178 | 1 | 9.30.5 | 93 | 11-12 | T | Y | 93 |  | 9.30.5 |  | D | Yong Liu, Tianyu Wu | 11/961r2 |  | Why is this restriction in place? If a beamformer has a group of SU only beamformees then it has to a NDPA-NDP to each beamformee and this is inefficient. | Please clarify. | DISAGREE (MU: 2011-07-20 15:52:10Z) - Ans: this restriction is to allow a SU only BFmee not to support BFming report fragmentation and polling, thus simplifying designs. | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:52 | MU
2272 | Edgar, Richard | 178 | 1 | 9.30.5 | 93 | 11 | T | Y | 93.11 | 11 | 9.30.5 |  | D | Yong Liu, Tianyu Wu | 11/961r2 |  | "A beamformer shall not transmit a Beamforming Report Poll frame to a SU only beamformee unless it has received at least one segment of the VHT Compressed Beamforming frame from the beamformee." This rule does not make sense - it would mean that the beamformer cannot normally poll SU only beamformees using the 'sounding protocol with more than one beamformee' of Figure 9-ac2. | Remove statement "A beamformer shall not transmit a Beamforming Report Poll frame to a SU only beamformee unless it has received at least one segment of the VHT Compressed Beamforming frame from the beamformee." | DISAGREE (MU: 2011-07-20 15:52:45Z) - See CID 3460 resolution | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:53 | MU
2877 | Lindskog, Erik | 178 | 1 | 9.30.6 | 93 | 21 | T | Y | 93.21 | 21 | 9.30.6 | 3367 | A |  | 11/961r2 |  | 63 even if the NDPA is addressed to a mesh STA (compare Table 22-10 and 8.5.16.3)? | Clarify | AGREE (MU: 2011-07-20 15:53:17Z) - Please see the change in 11/0961r2 | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:53 | MU
3367 | Rosdahl, Jon | 178 | 1 | 9.30.6 | 93 | 21 | T | Y | 93.21 | 21 | 9.30.6 |  | A | Kaiying | 11/961r2 |  | 63 even if the NDPA is addressed to a mesh STA (compare Table 22-10 and 8.5.16.3)? | Clarify | AGREE (MU: 2011-07-20 15:53:38Z) - See CID 2877 resolution | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:54 | MU
3656 | SUN, BO | 178 | 1 | 9.30.6 | 93 | 22 | T | Y | 93.22 | 22 | 9.30.6 | 733 | A |  | 11/961r2 |  | GROUP_ID in the NDP PPDU should be the same as the associated NDPA frame. The current text for setting GROUP_ID in the NDP PPDU when the associated NDPA frame addressed to a mesh STA is not consistent with the GROUP_ID in the associated NDPA frame. P143 table 22-10, In an NDP PPDU, the Group ID is set according to 9.30.6(Transmission of a VHT NDP). P93, Line 22 "GROUP_ID set to 0 if the associated NDPA frame is addressed to an AP; otherwise, set to 63." However for an NDPA addressed to an AP or to a mesh STA, it is defined as P143 table 22-10, "In a SU VHT PPDU, if the PPDU carries MPDU(s)addressed to an AP or to a mesh STA, the Group ID field is set to 0, otherwise it is set to 63." | GROUP_ID set to 0 if the associated NDPA frame is addressed to an AP or to a mesh STA; otherwise, set to 63. | AGREE (MU: 2011-07-20 15:54:22Z) - See CID 2877 resolution | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:54 | MU
2952 | LU, KAIYING | 178 | 1 | 9.30.6 | 93 | 22 | T | Y | 93.22 | 22 | 9.30.6 |  | A | Kaiying | 11/961r2 |  | GROUP_ID in the NDP PPDU should be the same as the associated NDPA frame. The current text for setting GROUP_ID in the NDP PPDU when the associated NDPA frame addressed to a mesh STA is not consistent with the GROUP_ID in the associated NDPA frame. P143 table 22-10, In an NDP PPDU, the Group ID is set according to 9.30.6(Transmission of a VHT NDP). P93, Line 22 "GROUP_ID set to 0 if the associated NDPA frame is addressed to an AP; otherwise, set to 63." However for an NDPA addressed to an AP or to a mesh STA, it is defined as P143 table 22-10, "In a SU VHT PPDU, if the PPDU carries MPDU(s)addressed to an AP or to a mesh STA, the Group ID field is set to 0, otherwise it is set to 63." | GROUP_ID set to 0 if the associated NDPA frame is addressed to an AP or to a mesh STA; otherwise, set to 63. | AGREE (MU: 2011-07-20 15:54:05Z) - See CID 2877 resolution | MU | MU-2011-07-19-PM2 | [5 empty] | 2011-07-20 15:54 | MU

## GroupID
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
2118 | Chambelin | 178 | 1 |  | general |  | T | Y | [5 empty] | osama |  |  | As the specification of the GroupID is not completely clear, would it be possible to use TPC per STA in a GroupID ? |  |  | MU | GroupID | [5 empty] | 2011-09-01 14:21 | MU
3360 | Rosdahl, Jon | 178 | 1 | 9 | missing | missing | T | Y |  |  | 9 |  |  | Illsoo, Wei Shi |  |  | The way group ID management is performed is not described | Describe it |  | MU | GroupID | [5 empty] | 2011-06-30 16:58 | MU
2278 | Fischer, Matthew | 178 | 1 | 7.3.4.5 | 16 | 21 | T | Y | 16.21 | 21 | 7.3.4.5 | 2659 |  |  |  |  | two out of 64 GroupID are reserved for special purpose, SU or BCAST. Valid number of GroupID for MU is 62, not 64 | Change '64' to '62'. Add proper explanation if necessary |  | MU | GroupID | [5 empty] | 2011-06-30 01:55 | <not set>
2119 | Chambelin, Philippe | 178 | 1 | 8.5.16.3 | 62 | 65 | T | Y | 62.65 | 65 | 8.5.16.3 |  |  | Illsoo |  |  | Where is the definition or the specification on how to assign STAs to a specific GroupID or another one ? If no definition exists, please specify the way to make the assignement of a STA to a GroupID. |  |  | MU | GroupID | [5 empty] | 2011-06-30 15:21 | MU
2120 | Chambelin, Philippe | 178 | 1 | 8.5.16.3 | 62 | 65 | T | Y | 62.65 | 65 | 8.5.16.3 |  |  | Illsoo |  |  | How to assign the number of streams from the NSTS of a STA, relatively to the AP capabilities (Total NSTS) and the capabilities of the other STAs in the GroupID as well as the number of streams already assigned to these STAs ? Please specify. |  |  | MU | GroupID | [5 empty] | 2011-06-30 15:21 | MU
2121 | Chambelin, Philippe | 178 | 1 | 8.5.16.3 | 62 | 65 | T | Y | 62.65 | 65 | 8.5.16.3 |  |  | Illsoo |  |  | How to assign a STA to a GroupId in an OBSS case ? | Define an interference metric and use it to select the best GroupID. |  | MU | GroupID | [5 empty] | 2011-06-30 15:21 | MU
2004 | Aboul-Magd, Osama | 178 | 1 | 8.5.16.3 | 63 | 27-42 | T | N | 63 |  | 8.5.16.3 |  |  | Illsoo |  |  | The definition of the Group ID Management frame is not consistent with the definitions of other management frames in IEEE 802.11. | The Membership Status Array and the User Position Array need to be included in Clause 8.4.1 as management frame fields. Table 8-ac18 needs to be updated to show that the "Membership Status Array" and the "User Position Array" are fields, and Figure 8-ac20 maybe deleted. |  | MU | GroupID | [5 empty] | 2011-06-30 15:21 | MU
2625 | Kakani, Naveen | 178 | 1 | 8.5.16.3 | 63 | 1 | T | Y | 63.01 | 1 | 8.5.16.3 |  |  | Illsoo |  |  | The Group ID Management frame should be capable to indicate that the STA is not member of any group. Currently the frame may indicate that the STA is member of one or more groups, i.e. it is not possible to indicate that the STA is not member of any group. | Please explicitly state that Group ID Management frame may indicate that the STA is not member of any group. |  | MU | GroupID | [5 empty] | 2011-06-30 15:21 | MU
2610 | Kafle, Padam | 178 | 1 | 8.5.16.3 | 63 | 1 | T | N | 63.01 | 1 | 8.5.16.3 |  |  | Illsoo |  |  | The Group ID Management frame should be capable to indicate that the STA is not a member of any group. Currently the frame may indicate that the STA is member of one or more groups, i.e. It is not possible to indicate that the STA is not member of any group. | Please explicitly state that Group ID Management frame may indicate that the STA is not member of any group. |  | MU | GroupID | [5 empty] | 2011-06-30 15:21 | MU
3700 | Varshney, Prabodh | 178 | 1 | 8.5.16.3 | 63 | 1 | T | Y | 63.01 | 1 | 8.5.16.3 |  |  | Illsoo |  |  | The Group ID Management frame should be capable to indicate that the STA is not member of any group. Currently the frame may indicate that the STA is member of one or more groups, i.e. It is not possible to indicate that the STA is not member of any group. | Please explicitly state that Group ID Management frame may indicate that the STA is not member of any group. |  | MU | GroupID | [5 empty] | 2011-06-30 15:21 | MU
2730 | Kneckt, Jarkko | 178 | 1 | 8.5.16.3 | 63 | 1 | T | Y | 63.01 | 1 | 8.5.16.3 | 3700 |  |  |  |  | The Group ID Management frame should be capable to indicate that the STA is not member of any group. Currently the frame may indicate that the STA is member of one or more groups, i.e. It is not possible to indicate that the STA is not member of any group. | Please explicitly state that Group ID Management frame may indicate that the STA is not member of any group. |  | MU | GroupID | [5 empty] | 2011-06-30 02:13 | <not set>
3401 | Seok, Yongho | 178 | 1 | 8.5.16.3 | 63 | 4 | T | Y | 63.04 | 4 | 8.5.16.3 |  |  | Illsoo |  |  | In Figure 8-ac20, the subfields for Group IDs 0 and 63 are meaningless, since they are for SU transmissions. Furthermore, STA position subfields for each of Group IDs having subfield 0 are not only meaningless, but also causing the ambiguity, because reserved bits are overlapped to one of STA position subfields. | Change "~ and a 16 octet User Position Array field (indexed by the Group ID) consisting of a 2 bit User Position subfield for each of the 64 Group IDs ~" to "~ and a variable octet User Position Array field (indexed by the Group ID having subfield 1) consisting of a 2 bit User Position subfield for each of the Group IDs having subfield 1". In Figure 8-ac20, change "16 octets" to "Variable", and modify the figure accordingly. |  | MU | GroupID | [5 empty] | 2011-06-30 15:21 | MU
3416 | Seok, Yongho | 178 | 1 | 8.5.16.3 | 63 | 4 | T | Y | 63.04 | 4 | 8.5.16.3 | 310 |  |  |  |  | In Figure 8-ac20, the subfields for Group IDs 0 and 63 are meaningless, since they are for SU transmissions. Furthermore, STA position subfields for each of Group IDs having subfield 0 are not only meaningless, but also causing the ambiguity, because reserved bits are overlapped to one of STA position subfields. | Change "~ and a 16 octet User Position Array field (indexed by the Group ID) consisting of a 2 bit User Position subfield for each of the 64 Group IDs ~" to "~ and a variable octet User Position Array field (indexed by the Group ID having subfield 1) consisting of a 2 bit User Position subfield for each of the Group IDs having subfield 1". In Figure 8-ac20, change "16 octets" to "Variable", and modify the figure accordingly. |  | MU | GroupID | [5 empty] | 2011-06-30 02:13 | <not set>
2663 | Kim, Joonsuk | 178 | 1 | 8.5.16.3 | 63 | 30 | T | Y | 63.3 | 30 | 8.5.16.3 |  |  | Illsoo |  |  | Figure 8-ac20, GroupID 0 and 63 are used for special purpose (SU or BCAST). This management frame is used for MU operation, so no valid data in this frame. | Reserve it (2 bits in the first 8 octets and 4 bits in next 16 octets) |  | MU | GroupID | [5 empty] | 2011-06-30 15:21 | MU
2282 | Fischer, Matthew | 178 | 1 | 8.5.16.3 | 63 | 30 | T | Y | 63.3 | 30 | 8.5.16.3 | 2663 |  |  |  |  | Figure 8-ac20, GroupID 0 and 63 are used for special purpose (SU or BCAST). This management frame is used for MU operation, so no valid data in this frame. | Reserve it (2 bits in the first 8 octets and 4 bits in next 16 octets) |  | MU | GroupID | [5 empty] | 2011-06-30 02:13 | <not set>
3402 | Seok, Yongho | 178 | 1 | 8.5.16.3 | 64 | 20 | T | Y | 64.2 | 20 | 8.5.16.3 |  |  | Illsoo |  |  | In Figure 8-ac20, the subfields for Group IDs 0 and 63 are meaningless, since they are for SU transmissions. Furthermore, STA position subfields for each of Group IDs having subfield 0 are not only meaningless, but also causing the ambiguity, because reserved bits are overlapped to one of STA position subfields. | Delete the sentence "If the Membership Status subfield for a Group ID is set to 0 (meaning the STA is not a member of that group), then the corresponding User Position subfield in the User Position Array field is reserved." |  | MU | GroupID | [5 empty] | 2011-06-30 15:21 | MU
3417 | Seok, Yongho | 178 | 1 | 8.5.16.3 | 64 | 20 | T | Y | 64.2 | 20 | 8.5.16.3 | 311 |  |  |  |  | In Figure 8-ac20, the subfields for Group IDs 0 and 63 are meaningless, since they are for SU transmissions. Furthermore, STA position subfields for each of Group IDs having subfield 0 are not only meaningless, but also causing the ambiguity, because reserved bits are overlapped to one of STA position subfields. | Delete the sentence "If the Membership Status subfield for a Group ID is set to 0 (meaning the STA is not a member of that group), then the corresponding User Position subfield in the User Position Array field is reserved." |  | MU | GroupID | [5 empty] | 2011-06-30 02:14 | <not set>
2191 | Dehghan, Hossein | 178 | 1 | 8.5.16.3 | 64 | 21 | T | N | 64.21 | 21 | 8.5.16.3 |  |  | Illsoo |  |  | No value is specified for reserved field values |  |  | MU | GroupID | [5 empty] | 2011-06-30 15:21 | MU
2005 | Aboul-Magd, Osama | 178 | 1 | 8.5.16.3 | 64 | 24 | T | N | 64.24 | 24 | 8.5.16.3 |  |  | Illsoo |  |  | Group ID 0 and 63 are reserved. Need to clarify the use of Group ID 0 and 63 | Indicate that Group ID 0 is reserved for transmissions to AP and Group ID 63 is reserved for downlink SU transmissions |  | MU | GroupID | [5 empty] | 2011-06-30 15:21 | MU

## Feedback
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
2262 | Edgar, Richard | 178 | 1 | ` | 32 | 1 | T | Y | 32.01 | 1 | ` |  |  | Wei Shi |  |  | Limiting feedback to compressed V precludes low-complexity implementations at stations with a low number of antennas. For 1-antenna stations, the benefit of compressing the V feedback versus simply quantising the V feedback per 20.3.12.2.4 is small. Furthermore, limiting beamforming feedback to a single method greatly increases the risk of unavoidable 'essential IP' being asserted in that respect. | Add a clause to allow [single-antenna] stations to transmit the VHT beamforming report using noncompressed beamforming feedback per 20.3.12.2.4. Add a table similar to Table 8-ac7, describing the VHT Non Compressed Beamforming Report field. |  | MU | Feedback |  | Possible resolution presented in 11/935r0. |  |  |  | 2011-07-14 14:49 | MU
2868 | Lindskog, Erik | 178 | 1 | 8.4.1.37 |  |  | T | Y | 32.04 |  | 8.4.1.37 | 3358 |  |  |  |  | What is the beamformee flexibility in filling in the VHT MIMO Control? May it choose what values it wants to use for Nr? [For Nc only if SU or it doesn't have as many antennas as requested (9.30.5); yes for Grouping (8.4.1.38, 23.3.11.2), Codebook Info (23.3.11.2); no for Feedback Type (9.30.5), Channel Width (9.30.5).] | Clarify |  | MU | Feedback | [5 empty] | 2011-06-30 03:54 | <not set>
3358 | Rosdahl, Jon | 178 | 1 | 8.4.1.37 |  |  | T | Y | 32.4 |  | 8.4.1.37 |  |  | Yong |  |  | What is the beamformee flexibility in filling in the VHT MIMO Control? May it choose what values it wants to use for Nr? [For Nc only if SU or it doesn't have as many antennas as requested (9.30.5); yes for Grouping (8.4.1.38, 23.3.11.2), Codebook Info (23.3.11.2); no for Feedback Type (9.30.5), Channel Width (9.30.5).] | Clarify |  | MU | Feedback | [5 empty] | 2011-09-15 07:55 | MU
3469 | Shi, Wei | 178 | 1 | 8.4.1.38 | 33 | All | T | Y | 33 |  | 8.4.1.38 |  |  | Wei Shi |  |  | It seems to me that there is a bit of overhead in compressing a feedback matrix at a beamformee. For a single- or two-antenna beamformee compressing the feedback matrix may not be very beneficial. Non-compressed beamforming seems like a viable option certainly for a beamformee with a small receive antenna set. Also, a VHT STA includes HT functionality and in HT non-compressed beamforming is an option. | Please allow non-compressed beamforming as an option. |  | MU | Feedback |  | Possible resolution presented in 11/935r0. Will present again at July session for strawpolls. |  |  |  | 2011-07-14 14:48 | MU
3510 | Stacey, Robert | 178 | 1 |  | 33 | 4 | T | Y | 33.04 | 4 |  | 232 |  |  |  |  | Don't use shall in the frame formats section. This normative statement belongs in 9.30.5. Also, note that there are three flavors of report: null, su and mu. Any statement about format needs to account for null. | State that this field reflects value in NDPA. Statements regarding format of the VHT Compressed Beamforming frame can be made in 8.5.16.2. |  | MU | Feedback | [5 empty] | 2011-06-30 04:08 | <not set>
3476 | Stacey, Robert | 178 | 1 |  | 33 | 4 | T | Y | 33.04 | 4 | 8.4.1.37 |  |  | Robert |  |  | Don't use shall in the frame formats section. This normative statement belongs in 9.30.5. Also, note that there are three flavors of report: null, su and mu. Any statement about format needs to account for null. | State that this field reflects value in NDPA. Statements regarding format of the VHT Compressed Beamforming frame can be made in 8.5.16.2. |  | MU | Feedback | [5 empty] | 2011-09-01 14:34 | MU
3670 | van Zelst, Allert | 178 | 1 | 8.4.1.37 | 33 | 18 | T | N | 33.18 | 18 | 8.4.1.37 |  |  | Joonsuk |  |  | "In case of a VHT Compressed Beamforming frame not carrying the Compressed Beamforming Report field, the field is set to all ones." -> this option is not clear from 8.5.16.2 VHT Compressed Beamforming frame format. | Add to 8.5.16.2 that the Compressed Beamforming Report field can be "not present". |  | MU | Feedback | [5 empty] | 2011-06-30 17:09 | MU
3169 | Perahia, Eldad | 178 | 1 | 8.4.1.37 | 33 | 32 | T | N | 33.32 | 32 | 8.4.1.37 |  |  | Joonsuk |  |  | Why would a VHT Compressed Beamforming frame carry a Compressed Beamforming Report field? Isn't Compressed Beamforming frame only used in HT, in which case a VHT Compressed Beamforming frame would never carry a Compressed Beamforming Report field? Assuming it was a typo and it should have been VHT Compressed Beamforming Report field, why would a VHT Compressed Beamforming frame not carry a VHT Compressed Beamforming Report field? | please clarify |  | MU | Feedback | [5 empty] | 2011-06-30 17:09 | MU
3287 | Rosdahl, Jon | 178 | 1 | 8.4.1.38 | 33 | 50 | T | Y | 33.5 | 50 | 8.4.1.38 |  |  | Joonsuk |  |  | The packing rules are not specified | Say something like "No padding is present between angles, even if they correspond to different subcarriers. The last angle is followed with zero pad to make the VHT Compressed Beamforming Report field an integer number of octets in size." |  | MU | Feedback | [5 empty] | 2011-06-30 17:09 | MU
2957 | Luo, Yi | 178 | 1 | 8.4.1.38 | 36 | 32-57 | T | Y | 36 |  | 8.4.1.38 |  |  | Yi Luo |  |  | The structure of the VHT compressed beamforming report field is not adequate due to the big difference of SNRs among channels. | Redefine the structure of the VHT compressed beamforming report field for each 20MHz. Details of the proposed text change are presented in our contribution. |  | MU | Feedback | [5 empty] | 2011-07-12 20:53 | MU
3411 | Seok, Yongho | 178 | 1 | 8.4.11.38 | 42 | 30,34,38 | T | Y | 42 |  | 8.4.1.38 | 305 |  |  |  |  | The phases "feedback with BW=20MHz", "feedback with BW=40MHz", and "feedback with BW=80MHz" are not clear. | Rewrite the sentences with the defined term "Channel Width" in VHT MIMO Control field. |  | MU | Feedback | [5 empty] | 2011-06-30 03:54 | <not set>
3396 | Seok, Yongho | 178 | 1 | 8.4.11.38 | 42 | 30,34,38 | T | Y | 42.3 |  | 8.4.1.38 |  |  | Brian |  |  | The phases "feedback with BW=20MHz", "feedback with BW=40MHz", and "feedback with BW=80MHz" are not clear. | Rewrite the sentences with the defined term "Channel Width" in VHT MIMO Control field. |  | MU | Feedback | [5 empty] | 2011-09-01 14:32 | MU
2660 | Kim, Joonsuk | 178 | 1 | 8.4.1.39 | 42 | 61 | T | Y | 42.61 | 61 | 8.4.1.39 |  |  | Joonsuk |  |  | More detail description is necessary Delta_SNR on how to represent it with 4 bits. For example, if Delta_SNR > 7 dB, it needs to represent it with 7. And if Delta_SNR < -8dB, it should be -8 in the report field. | need to submit contribution |  | MU | Feedback | [5 empty] | 2011-06-30 17:09 | MU
3288 | Rosdahl, Jon | 178 | 1 | 8.4.1.39 | 43 | 14 | T | Y | 43.14 | 14 | 8.4.1.39 |  |  | Joonsuk |  |  | The packing rules are not specified | Say something like "No padding is present between delta SNRs, even if they correspond to different subcarriers." |  | MU | Feedback | [5 empty] | 2011-06-30 17:09 | MU

## Sounding
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
2026 | Asai, Yusuke | 178 | 1 | 8.3.1.11 | 26 | 10 | T | Y | 26.1 | 10 | 8.3.1.11 |  |  | David Xun Yang |  |  | The maximum number of "n" in STA info field is not defined. Consider the case when AP has eight antenna and eight STAs with single antenna, n is set to maximum value of eight. Although the maximum number of beamformees in DL MU-MIMO transmission is defined as four, in current draft specification, it is not relevant to the maximum number of "n". | Define the maximum number of "n" explicitly. |  | MU | Sounding | [5 empty] | 2011-06-30 17:05 | MU
2159 | Chu, Liwen | 178 | 1 | 8.3.1.11 | 26 | 21 | T | Y | 26.21 | 21 | 8.3.1.11 |  |  | David Xun Yang |  |  | When one STA field is in NDPA for AP as beamformee, for IBSS and mesh BSS, AID in the STA field is already defined to 0. It is good to define AID in the STA field to 0 if only one STA is the destination of NDPA. This can harmonize single destination NDPA. | As proposed. |  | MU | Sounding | [5 empty] | 2011-06-30 17:05 | MU
3250 | Reuss, Edward | 178 | 1 | 8.3.1.11 | 26 | 23 | T | Y | 26.23 | 23 | 8.3.1.11 |  |  | David Xun Yang |  |  | This paragraph only addresses individual STA addresses and the broadcast address. It does not "address" (sorry) group addresses. I can envision applications that could use a group address. | Add a sentence describing that if the NDPA only contains STA Info fields for STAs in a common group, then set the RA field to that group address. I suspect that all of the STAs in that group may need to have STA Info fields, but I'm not certain. This may deserve further discussion. |  | MU | Sounding | [5 empty] | 2011-06-30 17:05 | MU
3750 | Yang, Xun | 178 | 1 | 8.3.1.11 | 26 | 23 | T | Y | 26.23 | 23 | 8.3.1.11 |  |  | David Xun Yang |  |  | To reduce processing overhead, the NDPA frame should include a one-byte field to indicate the number of STAs to be addressed in this frame. Furthermore, the additional field would make the NDPA frame length to be of even number of bytes. | Add one byte after the "sounding sequence field" to indicate the number of STAs to be addressed subsequently. The field name is "Number of STAs". See submission 11-11-xxxx-xx-00ac-resolution-to-comments-xxx for more details. |  | MU | Sounding | [5 empty] | 2011-06-30 17:05 | MU
3115 | Merlin, Simone | 178 | 1 | 8.3.1.11 | 26 | 50 | T | Y | 26.5 | 50 | 8.3.1.11 |  |  | David Xun Yang |  |  | AID is in the range 1-2007 and can be represented in 11 bits; the AID Field in Figure 8-ac6—STA Info field is 12 bits; | Change the AID Field definition by defining AID Field to span B0-B10, and make B11 reserved |  | MU | Sounding | [5 empty] | 2011-06-30 17:05 | MU
3511 | Stacey, Robert | 178 | 1 | 8.5.16.2 | 62 | 30 | T | Y | 62.3 | 30 | 8.5.16.2 | 3477 |  |  |  |  | This section should describe the three formats: null: su and mu. | Add text to describe the three format: null if Remaining Segments = all ones. Su if Remaining segments < all ones and Feedback type = SU, MU if Remaining segments < all ones and Feedback type = MU. |  | MU | Sounding | [5 empty] | 2011-09-15 07:08 | MU
2865 | Lindskog, Erik | 178 | 1 | 9.2 | 70 | 13 | T | Y | 70.13 | 13 | 9.2 | 3355 |  |  |  |  | Compressed beamforming feedback MMPDUs would appear to be an exception to the rule that A-MPDUs cannot contain fragments | Add a NOTE that a non-single A-MPDU may however contain beamforming segments, which are not considered to be fragments (e.g. have a different Sequence Number). |  | MU | Sounding | [5 empty] | 2011-06-30 03:40 | <not set>
2890 | Lindskog, Erik | 178 | 1 | 9.30.5 | 89 |  | T | Y | 89 |  | 9.30.5 | 3381 |  |  |  |  | Why doesn't it say somewhere in here that "A STA obtains the AID for a peer DLS or TDLS STA from the DLS Setup Request, DLS Setup Response, TDLS Setup Request or TDLS Setup Response frame.", as in 9.17a? | Clarify |  | MU | Sounding | [5 empty] | 2011-06-30 01:42 | <not set>
3381 | Rosdahl, Jon | 178 | 1 | 9.30.5 | 89 |  | T | Y | 89 |  | 9.30.5 |  |  | Yong Liu, Tianyu Wu |  |  | Why doesn't it say somewhere in here that "A STA obtains the AID for a peer DLS or TDLS STA from the DLS Setup Request, DLS Setup Response, TDLS Setup Request or TDLS Setup Response frame.", as in 9.17a? | Clarify |  | MU | Sounding | [5 empty] | 2011-06-30 15:09 | MU
3754 | Yang, Xun | 178 | 1 | 9.30.5 | 90 | 61-64 | T | Y | 90 |  | 9.30.5 |  |  | Yong Liu, Tianyu Wu |  |  | "A beamformer that transmits an NDPA frame with more than one STA Info field should transmit any Beamforming Report Poll frames needed to retrieve VHT Compressed Beamforming frame responses from the intended beamformees in the same TXOP that contained the NDPA frame". On the other hand, MFB has a different rule that (line 64-65, P88) "NOTE 1—If an MRQ is included in the last PPDU in a TXOP and there is not enough time for a response, the recipient can transmit the response MFB in a subsequent TXOP." Limit all the BF Report Polls in the same TXOP with NDPA is not so flexible as MFB. Further, retransmitting NDPA and NDP in the subsequent TXOP is redundant. | Add to the end of the subclause 9.30.5: "The BF Report Poll frame shall be allowed in the subsequent TXOP when the remaining TXOP duration is not sufficient for transmitting the VHT compressed beamforming frame(s)". Refer to submission 11-11-xxxx-xx-00ac-resolution-to-comments-xxx for more details. |  | MU | Sounding | [5 empty] | 2011-06-30 15:09 | MU
2683 | Kim, Youhan | 178 | 1 | 9.30.5 | 90 | 37 | T | Y | 90.37 | 37 | 9.30.5 |  |  | Yong Liu, Tianyu Wu |  |  | An MU beamformee capable STA must also be SU beamformee capable. | Delete line 37 |  | MU | Sounding | [5 empty] | 2011-06-30 15:09 | MU
3675 | van Zelst, Allert | 178 | 1 | 9.30.5 | 90 | 37 | T | N | 90.37 | 37 | 9.30.5 |  |  | Yong Liu, Tianyu Wu |  |  | Based on the outcome of "A STA that has the value true for dot11VHTMUBeamformeeActivated shall set the value of dot11VHTSUBeamformeeActivated to true." (line 9), "has the MU Beamformee Capable field is set to 1" is not a valid option. | Remove. |  | MU | Sounding | [5 empty] | 2011-06-30 15:09 | MU
2929 | Loc, Peter | 178 | 1 | 9.30.5 | 91 | 63-65 | T | Y | 91 |  | 9.30.5 |  |  | Yong Liu, Tianyu Wu |  |  | The term "stores" refers to a specific implementation for the construction of the Compressed Beamforming Report. If the VHT STA actually "stores" the Compressed Beamforming report, the beamformer will get an outdated or invalid report when the VHT STA did not receive either the NDPA or NDP frame or both but received a Compressed Beamforming poll. | Change the paragraph to: "A beamformee shall transmit a VHT Compressed Beamforming frame without including the VHT Com-pressed Beamforming Report field and the MU Exclusive Beamforming Report field if: a) The transmission duration of the VHT Compressed Beamforming frame would exceed the maximum PPDU duration; or b) The beamformee does not have any recently computed VHT Compressed Beamforming Report after receiving a Beamforming Report Poll frame." |  | MU | Sounding | [5 empty] | 2011-06-30 15:09 | MU
3187 | Perahia, Eldad | 178 | 1 | 9.30.5 | 91 | 35 | T | N | 91.35 | 35 | 9.30.5 |  |  | Yong Liu, Tianyu Wu |  |  | beamformee has a vague definition that is not dependent on whether the receiving STA is capable of SU or MU beamforming. Given that, it could be interpreted that even a STA that is not capable of SU or MU beamforming, still needs to transmit feedback when it receives the NDPA with its AID. Granted, P90L31 says that STA shall not transmit an NDPA to another STA that is not capable, but I'd prefer to be more explicit on the receive side as well. | restrict requirement to only when it is capable of SU and/or MU beamforming, or include requirement of being SU and/or MU beamforming capable in beamformee definition on P89L54 |  | MU | Sounding | [5 empty] | 2011-06-30 15:09 | MU
3188 | Perahia, Eldad | 178 | 1 | 9.30.5 | 91 | 43 | T | N | 91.43 | 43 | 9.30.5 |  |  | Yong Liu, Tianyu Wu |  |  | beamformee has a vague definition that is not dependent on whether the receiving STA is capable of SU or MU beamforming. Given that, it could be interpreted that even a STA that is not capable of SU or MU beamforming, still needs to transmit feedback when it receives the NDPA with its AID. Granted, P90L31 says that STA shall not transmit an NDPA to another STA that is not capable, but I'd prefer to be more explicit on the receive side as well. | restrict requirement to only when it is capable of SU and/or MU beamforming, or include requirement of being SU and/or MU beamforming capable in beamformee definition on P89L54 |  | MU | Sounding | [5 empty] | 2011-06-30 15:09 | MU
3189 | Perahia, Eldad | 178 | 1 | 9.30.5 | 91 | 58 | T | N | 91.58 | 58 | 9.30.5 |  |  | Yong Liu, Tianyu Wu |  |  | beamformee has a vague definition that is not dependent on whether the receiving STA is capable of SU or MU beamforming. Given that, it could be interpreted that even a STA that is not capable of SU or MU beamforming, still needs to transmit feedback when it receives the NDPA with its AID. Granted, P90L31 says that STA shall not transmit an NDPA to another STA that is not capable, but I'd prefer to be more explicit on the receive side as well. | restrict requirement to only when it is capable of SU and/or MU beamforming, or include requirement of being SU and/or MU beamforming capable in beamformee definition on P89L54 |  | MU | Sounding | [5 empty] | 2011-06-30 15:09 | MU
3575 | Stephens, Adrian | 178 | 1 | 91 | 9.30.5 | 58 | T | Y | 91.58 | 58 | 9.30.5 |  |  | Yong Liu, Tianyu Wu |  |  | "A beamformee shall transmit a VHT Compressed Beamforming frame without including the VHT Compressed Beamforming Report field and the MU Exclusive Beamforming Report field if:" This form of wording is used occasionally in this subclause, and it's wrong. The point of specification is wrongly worded "shall transmit", but the para is not about that the STA shall transmit, but what it shall transmit. The rules under which it transmits are covered elsewhere. This is a statement of what to do when it does transmit. | Reword: "A beamformee that transmits a VHT Compressed Beamforming frame shall omit the VHT Compressed Beamforming Report field or the MU Exclusive Beamforming Report field if:" Likewise rewording at 92.07 |  | MU | Sounding | [5 empty] | 2011-07-12 20:52 | MU
2283 | Fischer, Matthew | 178 | 1 | 9.30.5 | 91 | 64 | T | Y | 91.64 | 64 | 9.30.5 | 2664 |  | Joonsuk |  |  | Not clear how to act for AP when it receives Null FB | need to submit contribution |  | MU | Sounding | [5 empty] | 2011-07-12 20:45 | MU
2664 | Kim, Joonsuk | 178 | 1 | 9.30.5 | 91 | 64 | T | Y | 91.64 | 64 | 9.30.5 |  |  | Joonsuk |  |  | Not clear how to act for AP when it receives Null FB | need to submit contribution |  | MU | Sounding | [5 empty] | 2011-07-12 20:51 | MU
3677 | van Zelst, Allert | 178 | 1 | 9.30.5 | 92 | 10 | T | N | 92.1 | 10 | 9.30.5 |  |  | Yong Liu, Tianyu Wu |  |  | "If the Feedback Type field is set to MU, the STA shall send a feedback with the Nc field value in the VHT MIMO Control field equal to the Nc field value in the corresponding STA Info field in the NDPA pro- vided the Nc requested is not larger than the number of currently active receive antennas." -> What to do if the the number of active RX antennas is less than Nc? | Please clarify; probably something in the direction of feedback Nc = max(Nc in STA Info field, active, Number of active RX antennas) number of columns. |  | MU | Sounding | [5 empty] | 2011-06-30 15:09 | MU
2685 | Kim, Youhan | 178 | 1 | 9.30.5 | 92 | 10 | T | Y | 92.1 | 10 | 9.30.5 |  |  | Yong Liu, Tianyu Wu |  |  | ... pro- vided the Nc requested is not larger than the number of currently active receive antennas'. Please clarify what to do when Nc requested is larger than the number of active receive antennas. | Please clarify. |  | MU | Sounding | [5 empty] | 2011-06-30 15:09 | MU
3777 | Zhang, Hongyuan | 178 | 1 | 9.30.5 | 92 | 13 | T | N | 92.13 | 13 | 9.30.5 |  |  | Yong Liu, Tianyu Wu |  |  | "If the feedback type is set to SU, the Nc field value in the VHT MIMO Control field is detemined by the beamformee"--In this case, similar to the case where BFMer sets Nsts request in MU sounding request, there should also be an upper bound on Nc for SU FB, which is determined by the MCS set at the beamformer and beamformee. It should be the beamformee's responsibility to at least limit the number of columns to be within the common Nss that is upported by both sides, and not compute redundant steering vectors. | Change the sentence to "If the feedback type is set to SU, the Nc field value in the VHT MIMO Control field is determined by the beamformee, and shall not exceed the minimum value of (1) the maximum number of supported spatial streams according to the Tx MCS map in the VHT Supported MCS Set field of the beamformer, and (2) the maximum number of supported spatial streams according to the Rx MCS map in the VHT Supported MCS Set field of the beamformee". |  | MU | Sounding | [5 empty] | 2011-06-30 15:09 | MU
3468 | Shi, Wei | 178 | 1 | 9.30.5 | 92 | 13 | T | Y | 92.13 | 13 | 9.30.5 |  |  | Yong Liu, Tianyu Wu |  |  | Text says "… the Nc field value in the VHT MIMO Control field is determined by the beamformee." This seems to suggest the beamformee has complete freedom in choosing Nc. But this is not true because it is subject to Table 8-ac5. | I would like to modify this part of the sentence to something along the lines of " … determined by the beamformee but limited by values in Table 8-ac." |  | MU | Sounding | [5 empty] | 2011-06-30 15:09 | MU
3654 | SUN, BO | 178 | 1 | 9.30.5 | 92 | 42 | T | Y | 92.42 | 42 | 9.30.5 | 731 |  |  |  |  | Since a VHT Compressed Beamforming frame may be split into segments, when the beamformer fails to receive some of the segments, it should be clarified if segments correctly received could be considered as a valid response to the NDPA or Beamforming Report Poll. | Suggest to modify as follows:A VHT Compressed Beamforming frame sent received as a response to the NDPA, or at least one segment received as a response to the NDPA when the VHT Compressed Beamforming frame is segmented ,SIFS time after the NDP, is considered a valid response to the NDPA in the terms used in 9.19.2.4 (Multiple frame transmission in an EDCA TXOP).When a NDPA is the first frame in a TXOP , receiving at least one of the VHT Compressed Beamforming frame segments is considered that the TXOP has been obtained by the beamformer. |  | MU | Sounding | [5 empty] | 2011-06-30 01:42 | <not set>
3756 | Yang, Xun | 178 | 1 | 9.30.5 | 92 | 52 | T | Y | 92.52 | 52 | 9.30.5 |  |  | Yong Liu, Tianyu Wu |  |  | "All segments shall be sent in a single A-MPDU". Why limit all the segments in a single A-MPDU? Allow to send the segments in different frames is more flexible when the left time in current TXOP is not enough for transmission of the whole A-MPDU. | Change the sentence "All segments shall be sent in a single A-MPDU." to "All segments should be sent in a single A-MPDU if there is sufficient time to transmit in the remaining TxOP"." Further details can be found in submission 11-11-xxxx-xx-00ac-resolution-to-comments-xxx. |  | MU | Sounding | [5 empty] | 2011-06-30 15:09 | MU
3810 | Reuss, Edward | 178 | 1 |  |  |  | E | N | 92.55 | 55 | 9.30.5 |  |  | Yong Liu, Tianyu Wu |  |  | "a beamformer shall transmits a Beamforming Report Poll frame" is incorrect. | Change this to either "a beamformer shall transmit a Beamforming Report Poll frame" or else "a beamformer transmits a Beamforming Report Poll frame". |  | MU | Sounding | [5 empty] | 2011-07-12 21:09 | MU
3458 | Shi, Wei | 178 | 1 | 9.30.6 | 93 | 29-30 | T | Y | 93 |  | 9.30.6 |  |  | Kaiying, Yong |  |  | Text says " … the NUM_STS parameter shall not exceed the value indicated in the Compressed Steering Number of Beamformer Antennas field …" But no where in the draft does it actually say what Nr (as defined in 8.4.1.38) can be set to. Clearly, it cannot be more than NUM_STS. But can it be less than NUM_STS? | Please clarify. |  | MU | Sounding | [5 empty] | 2011-09-15 07:03 | MU
3415 | Seok, Yongho | 178 | 1 | 9.30.6 | 93 | 16 | T | Y | 93.16 | 16 | 9.30.6 | 309 |  |  |  |  | TXVECTOR parameters of an NDP frame such as GID and Partial AID are set differently from normal PPDU. If TXOP power save is allowed in an NDP frame, target STA may enter DOZE state by mistake. | Add the following condition: - TXOP_PS_NOT_ALLOWED set to 1 |  | MU | Sounding | [5 empty] | 2011-06-30 01:53 | <not set>
3400 | Seok, Yongho | 178 | 1 | 9.30.6 | 93 | 16 | T | Y | 93.16 | 16 | 9.30.6 |  |  | Kaiying |  |  | TXVECTOR parameters of an NDP frame such as GID and Partial AID are set differently from normal PPDU. If TXOP power save is allowed in an NDP frame, target STA may enter DOZE state by mistake. | Add the following condition: - TXOP_PS_NOT_ALLOWED set to 1 |  | MU | Sounding | [5 empty] | 2011-07-18 23:15 | MU

## Comments
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
2124 | Chambelin, Philippe | 178 | 1 |  |  |  | T | N | [5 empty] | Brian |  |  | How dynamically the assignment of number of AP's streams to a STA can change ? For instance if the load Element reports a stream under utilized or a bad SNR woulf it be possible to assign the under utilized stream to another STA |  |  | MU | [6 empty] | 2011-09-01 14:32 | MU
2754 | Lanante, Leonardo | 178 | 1 | 7.3.5.2 | general |  | E | Y | 16.36 |  | 7.3.5.2 |  | P | Matt Fischer |  |  | 11ac D1.0 doesn't have this subclause. During 11ac MU-MIMO transmission, DATA is an array of TXVECTOR.NUM_USERS so a modification to the 802.11 standard is needed regarding this subclause. | Add this subclause indicating that DATA is an array of octets when TXVECTOR.FORMAT parameter is VHT. | AGREE IN PRINCIPLE (MU: 2011-09-15 07:45:39Z) - TGac editor shall implement changes found under all headings containing CID 2754 in document 11-11-1144r8 | MU |  |  | Technical comment since a change is required to the baseline text. Moving to MU ad-hoc. |  |  |  | 2011-09-15 07:46 | MU
3796 | Reuss, Edward | 178 | 1 |  |  |  | T | Y | 33.2 | 20 | 8.4.1.37 |  |  | Brian |  |  | For the phrase ", the field is set to all ones", shouldn't the field be set to "Reserved"? Do we have a standard assignment for Reserved fields? Why does this clause explicitly specify this reserved field is set set to all ones? | Change this field to follow the standard behaviour for a reserved field. |  | MU | [6 empty] | 2011-09-01 14:32 | MU
3797 | Reuss, Edward | 178 | 1 |  |  |  | T | Y | 33.34 | 34 | 8.4.1.37 |  |  | Brian |  |  | For the phrase "Sounding Sequence are reserved and set to 0", shouldn't the field be set to "Reserved"? Do we have a standard assignment for Reserved fields? Why does this clause explicitly specify this reserved field is set to all zeros? | Change this field to follow the standard behaviour for a reserved field. |  | MU | [6 empty] | 2011-09-01 14:32 | MU
2281 | Fischer, Matthew | 178 | 1 | 8.4.1.40 | 47 | 40 | T | Y | 47.4 | 40 | 8.4.1.40 | 2662 |  |  |  |  | Description on 'Max Nss for SU Present' in Table 8-ac12 is confusing. For example, "when feedback_type=1…". Feedback_type of what? Beamforming feedback report? | Clarify it |  | MU | [6 empty] | 2011-06-30 03:52 | <not set>
2669 | Kim, Youhan | 178 | 1 | 8.4.1.40 | 49 | 48 | T | Y | 47.48 | 48 | 8.4.1.40 |  |  | Youhan |  |  | The sentence 'A beamformer may ignore this threshold if SU type feedback is used to form a single user beamformmed transmisison' should only apply to 'Rx Nss' with 'Max Nss For SU Present' is set to 1. However, as currently written, it sounds like this sentence applies to all cases. For example, sounds like a beamformer may ignore 'Channel Width' and/or 'Rx Nss' w/ 'Max Nss for SU Present'=0. | Clarify that this sentence applies only to 'Rx Nss' with 'Max Nss For SU Present' is set to 1. |  | MU | [6 empty] | 2011-09-01 14:33 | MU
2668 | Kim, Youhan | 178 | 1 | 8.4.1.40 | 49 | 40 | T | Y | 49.4 | 40 | 8.4.1.40 |  |  | Youhan |  |  | Suppose an AP received a VHT Operating Mode field with 'Rx Nss'=2 and 'Max Nss for SU Present'=0. But the AP has never received a VHT Operating Mode field with 'Max Nss for SU Present'=1. What is the max Nss the AP can use to transmit a beamformed packet to the STA using beamforming steering matrix computed from feedback with feedback type=1? | Please clarify. | Y | MU | [6 empty] | 2011-09-01 14:33 | MU
2670 | Kim, Youhan | 178 | 1 | 8.4.2.100.2 | 52 | 34 | T | Y | 52.34 | 34 | 8.4.2.100.2 |  |  | Youhan |  |  | Suggest to make it more explicit on whether this capability is beamformee's or beamformer's capability. Also, it is not clear what the value should be if the STA is not SU and/or MU beamformee capable. | Change the 'Definition' of 'Compressed Steering Number of Beamformer Antennas Supported' as 'Beamformee's capability indicating the maximum number of beamformer antennas the beamformmee can support when sending compressed beamforming feedback. If both SU Beamformee Capable and MU Beamformee Capable are set to 0, then set to 0.' |  | MU | [6 empty] | 2011-09-01 14:34 | MU
3429 | Shapira, Nir | 178 | 1 | 8.4.2.100.2 | 52 | 40 | T | Y | 52.4 | 40 | 8.4.2.100.2 |  |  | Brian |  |  | Should indicate maximum number of antennas used by beamformer. Beamformer can always choose to use less than its maximum number of antennas, e.g. to serve beamformees that support less antennas | replace "indicates the number of antennas…" by "Indicates the maximum number of antennas…" |  | MU | [6 empty] | 2011-09-01 14:32 | MU
2671 | Kim, Youhan | 178 | 1 | 8.4.2.100.2 | 52 | 40 | T | Y | 52.4 | 40 | 8.4.2.100.2 |  |  | Youhan |  |  | Suggest to make it more explicit on whether this capability is beamformee's or beamformer's capability. Also, it is not clear what the value should be if the STA is not SU and/or MU beamformer capable. | Change the 'Definition' of 'Number of Sounding Dimensions' as 'Beamformer's capability indicating the number of antennas used by the beamformer when sending beamformed transmissions. If both SU Beamformer Capable and MU Beamformer Capable are set to 0, then set to 0.' |  | MU | [6 empty] | 2011-09-01 14:26 | MU
3325 | Rosdahl, Jon | 178 | 1 | 8.4.2.100.2 | 52 | 44 | T | Y | 52.44 | 44 | 8.4.2.100.2 |  |  | Brian |  |  | Is a non-AP STA required to set "MU Beamformer Capable" to 0? | Clarify |  | MU | [6 empty] | 2011-09-01 14:33 | MU
2835 | Lindskog, Erik | 178 | 1 | 8.4.2.100.2 | 52 | 44 | T | Y | 52.44 | 44 | 8.4.2.100.2 | 3325 |  |  |  |  | Is a non-AP STA required to set "MU Beamformer Capable" to 0? | Clarify |  | MU | [6 empty] | 2011-06-30 03:41 | <not set>
3179 | Perahia, Eldad | 178 | 1 | 8.4.2.100.2 | 52 | 45 | T | N | 52.45 | 45 | 8.4.2.100.2 |  |  | Brian |  |  | I thought only AP could be DL MUMIMO beamformer | if so, change "Indicates whether or not the STA supports operation as an MU beamformer" to "Indicates whether or not the AP STA supports operation as an MU beamformer" or combine two capabilities into one conditioned on whether devices is AP or non-AP |  | MU | [6 empty] | 2011-09-01 14:33 | MU
3180 | Perahia, Eldad | 178 | 1 | 8.4.2.100.2 | 52 | 50 | T | N | 52.5 | 50 | 8.4.2.100.2 |  |  | Brian |  |  | I thought only non-AP could be DL MUMIMO beamformee | if so, change "Indicates whether or not the STA supports operation as an MU beamformee" to "Indicates whether or not the non-AP STA supports operation as an MU beamformee" or combine two capabilities into one conditioned on whether devices is AP or non-AP |  | MU | [6 empty] | 2011-09-01 14:33 | MU
3557 | Stephens, Adrian | 178 | 1 | 8.4.2.100.1 | 53 | 38 | T | N | 53.38 | 38 | 8.4.2.100.1 |  |  | Brian |  |  | "NOTE 1—A STA that sets MU Beamformee Capable to 0 is not able to demodulate an MU VHT PPDU with only one non-zero NSTS subfield." This may or may not be true. | Replace with: "...is not required to be able to demodulate..." |  | MU | [6 empty] | 2011-09-01 14:33 | MU
3477 | Stacey, Robert | 178 | 1 | 8.5.16.2 | 62 | 30 | T | Y | 62.3 | 30 | 8.5.16.2 |  |  | Robert |  |  | This section should describe the three formats: null: su and mu. | Add text to describe the three format: null if Remaining Segments = all ones. Su if Remaining segments < all ones and Feedback type = SU, MU if Remaining segments < all ones and Feedback type = MU. |  | MU | [6 empty] | 2011-09-01 14:34 | MU
2678 | Kim, Youhan | 178 | 1 | 8.5.16.2 | 62 | 45 | T | Y | 62.45 | 45 | 8.5.16.2 |  |  | Youhan |  |  | A VHT Compressed Beamforming frame not carrying the Compressed Beamforming Report field will not have the VHT Compressed Beamforming Report and MU Exclusive Beamforming Report (P62L48). | Clarify that VHT Compressed Beamforming Rpoert and MU Exclusive Beamforming Report may not be present in some cases. |  | MU | [6 empty] | 2011-09-01 14:28 | MU
2870 | Lindskog, Erik | 178 | 1 | 9 | missing | missing | T | Y | 70.01 |  | 9 | 3360 |  |  |  |  | The way group ID management is performed is not described | Describe it |  | MU | [6 empty] | 2011-06-30 01:27 | <not set>
3299 | Rosdahl, Jon | 178 | 1 | 8.4.2.100.2 | 52 | 33,39 | T | Y | 85.39 | 3339 | 8.4.2.100.2 |  |  | Brian |  |  | what are Compressed Steering Number of Beamformer Antennas Supported and Number of Sounding Dimensions set to if a device does not support BF? | Say something like "Set to 0 if operation as a beamformee/beamformer [respectively] is not supported" |  | MU | [6 empty] | 2011-09-01 14:33 | MU
3398 | Seok, Yongho | 178 | 1 | 8.4.2.100.2 | 52 | 34,40 | T | Y | 86.4 | 3440 | 8.4.2.100.2 |  |  | Brian |  |  | The number of antennas is not necessarily the same with the number of space-time streams depending on the implementation. Focusing the number of space-time streams seems more reasonable. | Use the number of space-time streams instead of the number of antennas. |  | MU | [6 empty] | 2011-09-01 14:33 | MU
3807 | Reuss, Edward | 178 | 1 |  |  |  | T | Y | 87.56 | 56 | 9.27.3 |  |  | Hongyuan |  |  | "encoded as a 6-bit two's complement number of SNR_average - 22" If I read this correctly, this means the valid range of values for this field are -32 to +31, which should be interpreted as the range -10 to +53 dB. Is this correct? | Clarify the permitted range of values for this field. |  | MU | [6 empty] | 2011-07-12 21:08 | MU
3072 | Merlin, Simone | 178 | 1 | 9.30.5 |  |  | T | Y | 89.49 |  | 9.30.5 |  |  | Yong Liu, Tianyu Wu |  |  | Normative text should be added to define how the subfields of the VHT MIMO control field can be set (in 8.4.1.37), according to the capability of the BFer/BFee | Add normative text for: Nc, Nr, Grouping, Codebook Information, Sounding Sequence (channel width, feedback type, remaining segments, First segment are already described) |  | MU | [6 empty] | 2011-07-17 18:38 | MU
3408 | Seok, Yongho | 178 | 1 | 10.23.15 | general |  | T | Y | 97.28 |  | 10.23.15 |  |  | Illsoo |  |  | "The Directed Multicast Service (DMS) is a service that may be provided by an AP to its associated non-AP STAs that support the DMS service, where the AP transmits group addressed MSDUs as individually addressed A-MSDUs." In order to support DMS in MU-MIMO, an AP should support to transmits group addressed MSDUs as individually addressed A-MPDUs. | Allow DMS in MU-MIMO by including group address information in MU-PPDU. |  | MU | [6 empty] | 2011-07-17 18:38 | MU