## Slide 1: IEEE 802.11ah Closing Report for May 2012
Date: 2012-5-17
Authors:

## Slide 2: Activity in TGah
Work continued on specification framework
  Many straw polls and motions
  Update to the spec framework adopted
  11-11-1137-09-00ah-specification-framework-for-tgah.docx
First Sub Group meetings

## Slide 3: Going forward
Get started on draft text
  Internal Task Group Ballot : January 2013
Start to wrap up on specification framework

## Slide 4: Teleconferences
June 6 at 7 PM ET 1 hour
  MAC
June 20 at 10 AM ET 1 hour
  PHY
July 11 at 7 PM ET 1 hour
  Prepare for July face-to-face meeting

## Slide 5: Timeline
Moved out 2 months
  Internal Task Group Ballot : January 2013
  Initial Letter Ballot : May 2013
  Initial Sponsor Ballot : May 2014
  EC Approval : March 2015
  Revcom Approval : May 2015