## Slide 1: IEEE 802.11mc Closing Report for November 2012
Date: 2012-11-15
Authors:

## Slide 2: Abstract
This document contains the TGmc closing report for November 2012.

## Slide 3: Status: comment resolution
Continued processing comments received in the recent Call for Comments on IEEE Std 802.11™-2012
  372 comments (106 editorial)
  Approximately 150 comments are resolved, 220 remain to be resolved

## Slide 4: Draft Status
Editor has prepared
  TGmc D0.0 = 802.11-2012
  TGmc D0.1 = 802.11-2012ae
  TGmc D0.2 = 802.11-2012aa
  TGmc D0.3 = D0.2+editorial defect fixes
  TGmc D0.4 = D0.3 + September 2012 approved comments
  TGmc D0.5 = D4.0 + speculative editorial comment resolutions
All drafts are posted on members area of the 802.11 website

## Slide 5: TGmc Plan of Record
Slide 5
20 July 2012 – 12 Sept 2012 – Call for Comment/Input
29-30 Aug 2012 – NesCom, SASB PAR Approval
Sept 2012 – Begin to process input
Sept 2012 – 11aa, 11ae integration
Jan – First WG Letter ballot - without 11ad
Dec 2012 – March/May 2013 – 11ad integration – March/May ballot
Feb 2014 – Mandatory Draft Review
Feb-March 2014 – Form Sponsor Pool (45 days)
April/May 2014 – Initial Sponsor Ballot
Dec 2013 – March 2014 – 11ac integration
TBD – integration of additional completed amendments (e.g. 11af)
Nov 2014 – WG/EC Final Approval
March 2015 – RevCom/SASB Approval
Notes: doc.: IEEE 802.11-10/0503r4
May 2010
        Michael Montemurro, Research in Motion
Page 5

## Slide 6: Teleconferences
Conference Calls 10am Eastern
  Nov 30 (2 hours)
  Dec 7, 14 (2 hours)
  Jan 11 (1 hour)

## Slide 7: Next Steps
Continued Comment Resolution
Initial Letter Ballot