## Slide 1: IEEE 802.11mc Closing Report for May 2013
Date: 2013-05-16
Authors:

## Slide 2: Abstract
This document contains the TGmc closing report for May 2013.

## Slide 3: Status: comment resolution
Continued processing comments received in the recent Initial Letter Ballot
  801 comments (713 LB, 88 remaining 2012 Call for comments)
  Approved resolutions to 108 comments
  347 comments remain to be resolved
ISO comments on IEEE Std 802.11-2012
  March 2013: Approved 13 ISO comments (China NB)
  May 2013: Received 11 ISO comments (Swiss NB), plan to resolve in July 2013 meeting

## Slide 4: TGmc Plan of Record
Slide 4
20 July 2012 – 12 Sept 2012 – Call for Comment/Input
29-30 Aug 2012 – NesCom, SASB PAR Approval
Sept 2012 – Begin to process input
Sept 2012 – 11aa, 11ae integration
Jan – First WG Letter ballot - without 11ad
Dec 2012 – March/May 2013 – 11ad integration – July/September ballot on D2.0
Dec 2013 – March 2014 – 11ac integration
Feb 2014 – Mandatory Draft Review
Feb-March 2014 – Form Sponsor Pool (45 days)
April/May 2014 – Initial Sponsor Ballot
TBD – integration of additional completed amendments (e.g. 11af)
Nov 2014 – WG/EC Final Approval
March 2015 – RevCom/SASB Approval
Notes: doc.: IEEE 802.11-10/0503r4
May 2010
        Michael Montemurro, Research in Motion
Page 4

## Slide 5: Teleconferences
Conference Calls 10am Eastern (2 hours)
  May 31, June 7, 21 (Friday)

## Slide 6: Next Steps
Continued Comment Resolution
Recirculation Letter ballot (expect July/September)