## Slide 1: IEEE 802.11mc Closing Report for January 2014
Date: 2014-01-23
Authors:

## Slide 2: Abstract
This document contains the TGmc closing report for January 2014.

## Slide 3: Status
Continued processing comments received in LB 199 – First recirculation LB
  497 comments
  Have approved resolutions to approximately 300 comments (100 this week)
Discussed “deprecation” comments
  Approved Liaison letter to Wi-Fi Alliance
  March 2014 meeting: Weds PM2

## Slide 4: TGmc Plan of Record
Slide 4
20 July 2012 – 12 Sept 2012 – Call for Comment/Input
29-30 Aug 2012 – NesCom, SASB PAR Approval
Sept 2012 – Begin to process input
Sept 2012 – 11aa, 11ae integration
Jan – First WG Letter ballot - without 11ad
Dec 2012 – March/May 2013 – 11ad integration
Sept 2013 – Letter ballot on D2.0
Dec 2013 – March 2014 – 11ac integration
  Letter Ballot on D3.0 (includes 11ac) March 2014
Mar 2014 – April 2014 – 11af integration
  Letter Ballot on D4.0 (includes 11af) July 2014
July 2014 – Mandatory Draft Review
Jul - Aug 2014 – Form Sponsor Pool (45 days)
Nov 14 – Initial Sponsor Ballot
July 2015– WG/EC Final Approval
Sept 2015 – RevCom/SASB Approval
Notes: doc.: IEEE 802.11-10/0503r4
May 2010
        Michael Montemurro, Research in Motion
Page 4

## Slide 5: Teleconferences
Conference Calls 10am Eastern (2 hours)
  February 7, 14, 21, 28

## Slide 6: Next Steps
Comment Resolution of comments received from LB 199 on P802.11REVmc D2.0