## Slide 1: IEEE 802.11 TGmc November 2014 Agenda
Date: 2014-11-03
Authors:

## Slide 2: Abstract
This presentation contains the IEEE 802.11 TGmc agenda for the November 2014 session.

## Slide 3: TGmc Agenda
Attendance reminder: https://murphy.events.ieee.org/imat/
Documents: https://mentor.ieee.org/802.11/documents
Monday PM1
  Chair’s Welcome, Status, Review of Objectives, Approve agenda, minutes
  Editor’s Report
  Comment resolution – 11-14-1358 Mark Hamilton
Tuesday PM2
  11ad Comment resolution: Carlos A, Carlos Cordeiro: 1274, 1275, 1413
  ISO comments 11-13-0123
Thursday PM1
  Comment resolution, ANQP additions
Tuesday PM1
  11-14-1352 – Lisa Ward, 11-14-1052 PHY comments – Edward Au, Mingguan Xu
Wednesday PM1
  11-14-1375 – Guido Hiertz
  Telecon motions
  Location & more CIDs: 11-14-1014, 11-14-1015, 11-14-1276 - Ganesh
Wednesday PM2
  3GPP reference changes, 11-14-1353 extend element ID space
Thursday PM2
  Comment resolution
  Motions
  Plans for January, Schedule
  AOB, Adjourn

## Slide 4: TGmc – Monday PM1
Call Meeting to Order
Policies and Procedures, Attendance reminder
  **IEEE Patent Policy http://standards.ieee.org/board/pat/pat-slideset.ppt
    Are there any patent claim(s)/patent application claim(s) and/or the holder of patent claim(s)/patent application claim(s) that the participant believes may be essential for the use of that standard? Minute any responses that were given, specifically the patent claim(s)/patent application claim(s) and/or the holder of the patent claim(s)/patent application claim(s) that were identified (if any) and by whom.
** Read slide deck
*** Note especially items #7 & #11

## Slide 5
Please review the documents at the following links:
  IEEE Patent Policy: http://standards.ieee.org/board/pat/pat-slideset.ppt
  Patent FAQ: http://standards.ieee.org/board/pat/faq.pdf
  Letter of Assurance Form: http://standards.ieee.org/board/pat/loa.pdf
  Affiliation FAQ: http://standards.ieee.org/faqs/affiliationFAQ.html
  Anti-Trust FAQ: http://standards.ieee.org/resources/antitrust-guidelines.pdf
  Ethics: http://www.ieee.org/portal/cms_docs/about/CoE_poster.pdf
  802 LMSC P&P: http://standards.ieee.org/board/aud/LMSC.pdf
  802 LMSC OM: http://www.ieee802.org/PNP/approved/IEEE_802_OM_v14.pdf
  802 WG P&P: http://grouper.ieee.org/groups/802/PNP/approved/IEEE_802_WG_PandP_v15.pdf
  IEEE 802.11 WG OM: https://mentor.ieee.org/802.11/dcn/14/11-14-0629-02-0000-802-11-operations-manual.docx
  From IEEE 802 Procedural document website: http://www.ieee802.org/devdocs.shtml

## Slide 6: Logistics
Attendance recording procedures
  https://imat.ieee.org
  Must register before logging attendance
  Must log attendance during each 2 hour session
Documentation
  http://mentor.ieee.org
  Use “TGm” for documents relating to the Revision PAR
Notes: doc.: IEEE 802.11-10/0503r4
May 2010
        Michael Montemurro, Research in Motion
Page 6

## Slide 7: Monday PM1 (continued)
Objectives
  Comment resolution
Approve prior meeting minutes
  Athens minutes: https://mentor.ieee.org/802.11/dcn/14/11-14-1008-00-000m-revmc-minutes-for-sept-2014-athens.docx
  Teleconference minutes: https://mentor.ieee.org/802.11/dcn/14/11-14-1336-03-000m-tgmc-telecon-minutes-oct-2014.docx
Editor Report (Adrian Stephens)
  Editor report: https://mentor.ieee.org/802.11/dcn/13/11-13-0095-14-000m-editor-reports.ppt
Notes: doc.: IEEE 802.11-10/0503r4
May 2010
        Michael Montemurro, Research in Motion
Page 7

## Slide 8: TGmc Plan of Record - modified
Slide 8
20 July 2012 – 12 Sept 2012 – Call for Comment/Input
29-30 Aug 2012 – NesCom, SASB PAR Approval
Sept 2012 – Begin to process CC input, 11aa, 11ae integration
Dec 2012 – March/May 2013 – 11ad integration
Jan 2013 – First WG Letter ballot - without 11ad – on D1.0
Sept 2013 – Letter ballot on D2.0
Dec 2013 – May 2014 – 11ac, 11af integration – D3.0 in May 2014
July 2014 – Mandatory Draft Review
Jan 2015 – D4.0 Recirculation, goal to follow with D5.0 unchanged (was Nov 2014) – if no recirc this week
Form Sponsor Pool: Open Dec 15th or so, close Feb 2015 – (min 45 days); good for 6 months (end of July 2015)
EC conditional SB approval March 2015
*new* - plan ad-hoc comment resolution meeting July 2015
Nov 2015/March 2016 – WG/EC Final Approval
March 2016 – RevCom/SASB Approval
Notes: doc.: IEEE 802.11-10/0503r4
May 2010
        Michael Montemurro, Research in Motion
Page 8

## Slide 9: Motion – Teleconference CIDs
  Approve resolutions to comments in
    The “Motion MAC-AF” tab in https://mentor.ieee.org/802.11/dcn/13/11-13-0361-41-000m-revmc-mac-comments.xls
    The “Gen Telecon - Oct” tab in https://mentor.ieee.org/802.11/dcn/14/11-14-0975-09-000m-lb202-gen-adhoc-comments.xlsx
Moved:
Seconded:
Result:

## Slide 10: Motion – Text changes not associated with CIDs
  Incorporate the text changes in the following documents into the TGmc draft:
    https://mentor.ieee.org/802.11/dcn/14/11-14-1275-00-000m-11ad-beamforming-fixes.docx
    https://mentor.ieee.org/802.11/dcn/14/11-14-1352-00-000m-correction-to-23-3-18-4-4.docx
    ANQP element submission
Moved:
Seconded:
Result:

## Slide 11: Motion – ISO comments
  Approve resolutions to comments in
    The “N16035-11ac” and “N16036-11af” tabs in https://https://mentor.ieee.org/802.11/dcn/13/11-13-0123-07-000m-iso-jtc1-sc6-8802-11-2012-comments.xls
Moved:
Seconded:
Result:

## Slide 12: January Meeting Planning
Objectives: Complete comment Resolution
Conference Calls 10am Eastern 2 hour
  Nov 21, Dec 5, 12, Jan 9
Ad-Hoc meeting – Planning 2015 July 7-8-9 (Tues-Thurs, HI location) to process SB comments
Schedule review
Availability of 11mc in the IEEE store
  D3.0 is available
Forward to ISO JTC1/SC6 WG1
  D4.0 after successful ballot

## Slide 13: References
https://mentor.ieee.org/802.11/dcn/12/11-12-0594-02-0000-revision-par-proposal-for-802-11-2012.doc
https://mentor.ieee.org/802.11/dcn/13/11-13-0233-41-000m-revmc-wg-ballot-comments.xls