## Slide 1: IEEE 802.11mc Closing Report for March 2015
Date: 2015-03-11
Authors:

## Slide 2: Abstract
This document contains the TGmc closing report for March 2015.

## Slide 3: Status
Completed processing comments received in LB 206 – Third recirculation (46 comments)
Agenda, includes motions
  https://mentor.ieee.org/802.11/dcn/15/11-15-0221-05-000m-tgmc-agenda-march-2015.pptx
Comment resolution spreadsheet
  https://mentor.ieee.org/802.11/dcn/13/11-13-0233-56-000m-revmc-wg-ballot-comments.xls
Report to EC for conditional approval to go to Sponsor Ballot
  https://mentor.ieee.org/802.11/dcn/15/11-15-0287-05-000m-p802-11revmc-report-to-ec-on-conditional-approval-to-go-to-sponsor-ballot.pptx

## Slide 4: TGmc Plan of Record - modified
Slide 4
20 July 2012 – 12 Sept 2012 – Call for Comment/Input
29-30 Aug 2012 – NesCom, SASB PAR Approval
Sept 2012 – Begin to process CC input, 11aa, 11ae integration
Dec 2012 – March/May 2013 – 11ad integration
Jan 2013 – First WG Letter ballot - without 11ad – on D1.0
Sept 2013 – Letter ballot on D2.0
Dec 2013 – May 2014 – 11ac, 11af integration – D3.0 in May 2014
July 2014 – Mandatory Draft Review
Jan 2015 – D4.0 Recirculation, goal to follow with D4.0 unchanged
Form Sponsor Pool: Open through Feb 20th good for 6 months (end of July 2015)
EC conditional SB approval March 2015
Considering ad-hoc comment resolution meeting July 2015
Nov 2015/Jan 2016 – WG/EC Final Approval
March 2016 – RevCom/SASB Approval
Notes: doc.: IEEE 802.11-10/0503r4
May 2010
        Michael Montemurro, Research in Motion
Page 4

## Slide 5: Teleconferences and next steps
Conference Calls 10am Eastern (2 hours)
  March 30
May 2015
  Begin initial Sponsor Ballot comment resolution as Comment Resolution Committee

## Slide 6: Motion for WGLB on P802.11mc D4.0 (Unchanged)
Having approved comment resolutions for all of the comments received from LB206 on P802.11mc D4.0
Approve a 15 day Working Group Recirculation Ballot asking the question “Should P802.11mc D4.0 be forwarded to Sponsor Ballot?”
Moved: Edward Au
Seconded: Mike Montemurro
Result: 12-0-1 Motion Passes
Approved by WG on Wednesday

## Slide 7: Motion for EC Approval on P802.11mc D4.0
Approve document 11-15-0287r4 as the report to the IEEE 802 Executive Committee on the requirements for conditional approval to forward Draft P802.11-REVmc/D4.0 to sponsor ballot, granting the chair editorial license and
Request the IEEE 802 Executive Committee to conditionally approve forwarding Draft P802.11-REVmc/D4.0 to sponsor ballot.
Moved: Jon Rosdahl
Seconded: Mark Hamilton
Result: 14-0-3 Motion Passes