## Slide 1: IEEE 802.11mc Closing Report for May 2016
Date: 2016-05-19
Authors:

## Slide 2: Abstract
This document contains the TGmc closing report for May 2016.

## Slide 3: Status
Sponsor Ballot Comment resolution
  828 comments received (initial recirc SB, 90% approval) on P802.11REVmc D5.0. Approximately 80 comments remain to be resolved.
Considered available presentations related to comments in initial recirculation ballot
Agenda, includes motions
  https://mentor.ieee.org/802.11/dcn/16/11-16-0511-10-000m-tgmc-agenda-may-2016.pptx
Comment resolution spreadsheet
  https://mentor.ieee.org/802.11/dcn/15/11-15-0532-44-000m-revmc-sponsor-ballot-comments.xls

## Slide 4: TGmc Plan of Record - modified
Slide 4
20 July 2012 – 12 Sept 2012 – Call for Comment/Input
29-30 Aug 2012 – NesCom, SASB PAR Approval
Sept 2012 – Begin to process CC input, 11aa, 11ae integration
Dec 2012 – March/May 2013 – 11ad integration
Jan 2013 – First WG Letter ballot - without 11ad – on D1.0
Sept 2013 – Letter ballot on D2.0
Dec 2013 – May 2014 – 11ac, 11af integration – D3.0 in May 2014
July 2014 – Mandatory Draft Review
Jan 2015 – D4.0 Recirculation
Form Sponsor Pool: Open Dec 15th or so, close Feb 20, 2015 –good for 6 months (end of July 2015)
D4.0 Initial Sponsor Ballot 2015-03-27 through 2015-04-26
D5.0 Jan 2016 Initial SB recirculation
D6.0 May 2016 Second Recirculation <- will be in June
D6.0/D7.0 June Third Recirculation
July 2016 – WG/EC Final Approval
September 2016 – RevCom/SASB Approval
Notes: doc.: IEEE 802.11-10/0503r4
May 2010
        Michael Montemurro, Research in Motion
Page 4

## Slide 5: TGmc SB Planning
Slide 5
Initial Sponsor Ballot 2015-03-27 through 2015-04-26 on D4.0
January/February 2016
  Initial SB recirculation D5.0 2016 -01-11 through 2016-01-26
  Teleconferences, Feb 22-25 2016 BRC Ft. Lauderdale meeting
March/April/May 2016
  Comment resolution
June/July 2016
  2nd, 3rd recirculation D6.0, D6.0 unchanged or D7.0
July 2016 – WG/EC Final Approval
September 2016 – RevCom/SASB Approval
  RevCom Submission date: 05 Aug 2016 for Sept 16 RevCom teleconference
Notes: doc.: IEEE 802.11-10/0503r4
May 2010
        Michael Montemurro, Research in Motion
Page 5

## Slide 6: May – June 2016 Meeting Planning
Objectives: Completer Initial Recirculation Sponsor Ballot comment resolution and open Second recirculation
Conference calls 10am Eastern 3 hours
  Friday May 27, June 3 teleconferences 3 hours
Ballot Resolution Committee meeting –
  None currently scheduled
Availability of 11mc in the IEEE store
  D5.0 is available (add D5.0 after SB approval), see http://www.techstreet.com/ieee/products/1867583
Forward to ISO JTC1/SC6 WG1
  D5.0 forwarded; D6.0 will be forwarded upon SB approval