## Slide 1: P802.11aq Report to EC on Unconditional Approval to go to Sponsor Ballot
Date: 2016-09-27
Authors:

## Slide 2: Introduction
This document contains the report to the IEEE 802 Executive Committee in support of a request for unconditional approval to send IEEE P802.11aq Draft 7.0 to Sponsor Ballot.
Revision 3 of this document was approved during the interim session of the 802.11 working group on 14th September 2016.
  Passed in the Working Group 36 yes, 0 no , 0 abstain

## Slide 3: 802.11 WG Letter Ballot Results – P802.11aq
Ballot ID | Ballot Close Date | Title | Ballot Type | Pool | Return | %Return | Abstain | %Abstain | Approve | Disapprove | %Approve
208 | 2015-02-02 | IEEE 802.11aq Draft 1.0 Technical | Technical | 363 | 259 | 71 | 63 | 24 | 139 | 52 | 73
216 | 2015-10-08 | IEEE 802.11aq Draft 3.0 Technical | Technical | 358 | 260 | 73 | 42 | 16 | 202 | 16 | 93
219 | 2016-04-06 | IEEE 802.11aq Draft 4.0 First Recirculation | Recirculation | 357 | 275 | 77 | 45 | 16 | 213 | 17 | 93
221 | 2016-07-04 | IEEE 802.11aq Draft 5.0 Second Recirculation | Recirculation | 357 | 280 | 78 | 46 | 16 | 218 | 16 | 93
222 | 2016-08-04 | IEEE 802.11aq Draft 6.0 Third Recirculation | Recirculation | 357 | 280 | 78 | 47 | 17 | 223 | 10 | 96
224 | 2016-09-25 | IEEE 802.11aq Draft 7.0 Fourth Recirculation | Recirculation | 357 | 280 | 78 | 47 | 17 | 226 | 7 | 97

## Slide 4: 802.11 WG Letter Ballot Comments – P802.11aq
Ballot ID | Ballot Close Date | Title | Total Number of Comments received (Yes and No votes)
208 | 2015-02-02 | Technical Letter Ballot for TGaq draft 1.0 | 700
216 | 2015-10-08 | Technical Letter Ballot for TGaq draft 3.0 | 400
219 | 2016-04-06 | First Recirculation Ballot for TGaq draft 4.0 | 71
221 | 2016-07-04 | Second Recirculation Ballot for TGaq draft 5.0 | 65
222 | 2016-08-04 | Third Recirculation Ballot for TGaq draft 6.0 | 43
224 | 2016-09-25 | Fourth Recirculation Ballot for TGaq draft 7.0 | 0

## Slide 5: Unsatisfied Technical comments by commenter
Voter | LB216 | LB219 | LB221 | LB222 | LB224 | Total
Adrian Stephens | 1 | 0 | 0 | 0 | 0 | 1
Matthew Fischer | 9 | 0 | 0 | 0 | 0 | 9
Paul Lambert | 1 | 0 | 0 | 0 | 0 | 1
Su Khiong Yong | 0 | 1 | 0 | 21 | 0 | 22
Zhongding Lei | 5 | 0 | 0 | 0 | 0 | 5
Yong Liu | 0 | 0 | 0 | 1 | 0 | 1
Lei Wang | 0 | 0 | 0 | 1 | 0 | 1
Total | 16 | 1 | 0 | 23 | 0 | 40

## Slide 6: Unsatisfied Technical Comments – Topics
Topic | #Comments
Architecture (Cls 4.5.9) | 4
Frame Formats (Cls 8/9) | 5
MLME procedures (Cls. 10/11) | 23
PICS, MIB, Scenarios (Annex B, C, W) | 5
General (Cls 3 or no Cls. specified) | 3
Total | 40

## Slide 7: Unsatisfied comments
The composite of all unsatisfied comments and the resolutions approved by the comment resolution committee received during working group ballot may be found in the embedded document on the right:
  Double click on the icon to the right to open this.
A copy of this same data presented using MyBallot access database report format is attached.
  Double click on the icon to the right to open this.

## Slide 8: TGaq Timeline
 | Open | Close
Fourth recirculation (TGaq D7.0) | 10-Sept-16 | 25-Sept-16
First sponsor ballot | 06-Oct-16 | 05-Nov-16
Second sponsor ballot | 31-Dec-16 | 14-Jan-17
Third sponsor ballot | 23-Jan-17 | 7-Feb-17
Fourth sponsor ballot | 18-Feb-17 | 5-Mar-17
EC to RevCom March-17 |  | 
RevCom to SB March-17 |  | 

## Slide 9: References