## Slide 1: A cascading process for major amendments
Date: 2018-07-11
Authors:

## Slide 2: Abstract
Some history on 802.11 and Wi-Fi Alliance timelines
Brief overview of 3GPP processes and timelines
Motivate for 2-3 year release cadence
Outline of a cascading process

## Slide 3: 802.11ac process and timeline
VHT SG produced two PARs: 11ac and 11ad
11ac process started before 11n publication, but SFD development started late
SFD
LB: D1.0 – D5.0
FR & EM
D0.1–D1.0
VHT SG
TGac
SB: D5.0–Pub
1.5 years
5 years
~2 years
May 2009
Jan 2011
Nov 2008
May 2007
Nov 2013
Sep 2009
Jan 2011
~1 year
2007
2008
2009
2010
2011
2012
2013
Nov 2010
May 2011
6 months
Mar 2013
2 years
Nov 2013
6 months
11n Pub
Sep 2009

## Slide 4: 802.11ax process and timeline
Spent a lot of time on EM
Spent more time on draft than 11ac: 3.6 years vs 3 years
  Reflects greater complexity
SFD
EM
D0.1–D1.0
HEW SG
TGax
SB: D5.0–Pub
1 year
5.5 years
~2 years
May 2014
Jan 2016
May 2014
May 2013
Nov 2019
Jan 2015
May 2016
~1 year
2013
2014
2015
2016
2017
2018
2019
Mar 2016
Nov 2016
8 months
May 2018
2.5 years
Nov 2019
6 months
D1.0–D3.0
D4.0–D5.0
May 2019
11ac Pub
Dec 2013
expected

## Slide 5: WFA certification launch dates
Draft N
Jun 2007
Certified N
Sept 2009
AC R1
Jun 2013
AC R2
Jun 2016
AX R1
Aug 2019
~2 years
(27 months)
~4 years
(45 months)
3 years
(36 months)
~3 years
(38 months)
11ac Pub
Dec 2013
11n Pub
Sep 2009
11ax D3.0
May 2018
Approximately 3 years between WFA certification program launches
Each major 802.11 amendment spawned two WFA programs
2007
2008
2009
2010
2011
2012
2013
2014
2015
2016
2017
2018
2019
11n D2.0
Jan 2007
11ac D2.0
Nov 2012

## Slide 6: Observations on the major 802.11 amendments
A major 802.11 amendment takes 6+ years to complete
The process is effectively serialized
  A new SFD is started after the last amendment is published
  There is some overlap with new PAR development and last sponsor ballot
SFD development takes around 1 year
Draft development takes 3 to 3.6 years
  6 – 8 months for the TG to develop the first draft for WG letter ballot
  2 – 2.5 years in WG letter ballot
  6 months in sponsor ballot
The Wi-Fi Alliance develops two certification programs out of each major amendment
  A major certification program launches every 3 years

## Slide 7: 3GPP releases
3GPP has two releases in progress at a time
Release every 1.25 years (15 months)
Release development takes between 2.5 and 3.5 years
2020
2008
2009
2010
2011
2012
2013
2014
2015
2016
2017
2018
2019
Rel-9
Rel-10
Rel-11
Rel-12
Rel-13
Rel-14
Rel-15
Rel-16
Mar 2010
Jun 2011
Mar 2013
Mar 2015
Mar 2016
Jun 2017
Sep 2018
Dec 2019
Mar 2008
Jan 2009
Jan 2010
Jun 2011
Sep 2012
Sep 2014
Jun 2016
Mar 2017
2 years
1 year
1.25 years
1.25 years
1.25 years
1.75 years
1.25 years
5G
4G
LTE

## Slide 8: A process for major 802.11 amendments
802.11 should move to a cascading release process for major amendments
Establish a predictable release cycle:
  Increase / retain relevance of Wi-Fi in context of alternative technologies and their evolution cycles and marketing messaging
  Provide OEM’s with a predictable product upgrade path driving customer purchase cycles
Reduce the time between releases
  Reduced time between technology introduction in the standard and commercial implementations
  Increased likelihood of commercialization for those technologies that are adopted into the mainstream MAC/PHY spec projects
  Reduces the pressure to get new features into the current amendment late in the process; the next release is just around the corner

## Slide 9: Outline of a cascading process
Set scope
(PAR)
X
Set features
(SFD)
Set scope
X
Project 1
Project 2
Detailed feature
discussion
Draft amendment development
Review topics of interest
Initial WG LB
Establish a timeline with milestones, e.g., date for D1.0
Gating functions: group makes hard decisions to meet timeline
Topics/features not addressed in project 1 are considered in project 2

## Slide 10: Characteristics of a cascading process
Projects complete at a regular cadence, say every 2 or 3 years
Projects overlap in time
  Start a new project once the current project reaches “feature maturity”, not when it completes
Projects complete in less time than current major amendments
  The reduced time for a project requires group discipline:
    A commitment to a project timeline with hard milestones
    A project with limited scope
Gating functions can help the group discipline itself
  Points in time where the group reviews scope or features and makes hard decisions on topics/features that will progress and topics/features that will be dropped
With a regular cadence and shorter, overlapping projects, nobody looses out
  A topic or feature dropped from the current project, can be considered in the next project
  We just prioritize: what does the market really need what can we deliver in the next 2 years?