## Slide 1: TGmd September 2018 Closing Report
Date: 2018-09-13
Authors:

## Slide 2: Abstract
This presentation contains the IEEE 802.11 TGmd closing report for the September 2018 session.

## Slide 3: Work completed this week
Continued comment resolution
  Approximately 470(of 623) comment resolutions approved/ready for motion
Approved teleconferences for the purpose of continued comment resolution:
  September 28, Oct 5, 12, 19, Nov 2 10am Eastern, 2 hours
Updated TGmd schedule
  Recirculation LB on P802.11REVmd D2.0 out of November meeting
Agenda
  https://mentor.ieee.org/802.11/dcn/18/11-18-1388-08-000m-2018-september-tgmd-agenda.pptx

## Slide 4: TGmd schedule - updated
January 2018 – Initial WGLB
November 2018 –D2.0 WGLB Recirculation LB (was Sept)
March 2019 – Form SB Pool (was Feb)
March 2019 – MEC/MDR done
August 2019 – Initial SB (was April)
November 2019 – Recirculation SB (was Oct)
March 2020 – Final WG/EC approval (was July 2020)
May 2020 – RevCom/SASB approval (was Sept 2020)

## Slide 5: References
https://mentor.ieee.org/802.11/dcn/17/11-17-0004-03-0000-revision-par-proposal-tgmd.doc
Approved PARs: https://standards.ieee.org/about/sba/index.html