## Slide 1: TGaz Next Generation Positioning Nov. Closing Report
Date: 20118-11-15
Authors:

## Slide 2: Abstract
This document is the TGaz Next Generation Positioning closing report for the Bangkok, Nov. 2018 meeting.

## Slide 3: TG Status And Work Completed
Published a new draft, P802.11az D0.5.
Reviewed a total of 23 submissions.
Resolved 184 technical comments, roughly similar number remain for resolution during Jan. 2019 meeting in anticipation of the Initial WG ballot target.
Assigned ~100 remaining comments.
Group is on track for Initial WG ballot coming out of Jan. meeting.

## Slide 4: Goals For Jan. Meeting
Publish draft 0.6 of P802.11az in anticipation of initial WG ballot.
Continue comment resolution of remaining comments.
Review of amendment text target at improving draft quality.
Commence Initial WG ballot coming out of January meeting.

## Slide 5: Teleconference Schedule
Dec. 12th (Wed.) 12:00 PM ET, 1:30 hr.
Dec. 19th (Wed.) 12:00 PM ET, 1:30 hr