## Slide 1: TGbd Closing Report – Vietnam
Date: 2019-09-19
Authors:

## Slide 2: Abstract
Closing report for Sep 2019 TGbd meeting in Hanoi, Vietnam

## Slide 3: Completed work items in the week
6 meeting slots were allocated in the week, including two parallel Adhoc slots
Meeting agenda: the last revision of 11-19/1412
Work items completed in this week include:
Approval of the meeting minutes for Jul meeting and Aug CC
Approval of the updated FRD document (11-19/0495r2)
Approval of the updated SFD document (11-19/0497r3)
Liaison update per IEEE 1609’s progress
Approval of the spec draft skeleton proposal (11-19/1638)
Review and update TGbd timeline
  Milestones from D0.1 will be deferred one or two meetings.
Approval of Teleconference plan after Sep meeting
25 tech submissions were presented for the week.
  26 motions passed for developing SFD and FRD
 | MON |  | TUE | WED |  | THU
AM1 |  |  | TGbd |  |  | TGbd
AM2 |  |  |  |  |  | TGbd
PM1 | TGbd/PHY | MAC |  | PHY | MAC | 
PM2 |  |  |  |  |  | TGbd
EVE |  |  |  |  |  | 

## Slide 4: Approved TG Document
TG Document | Baseline Version | Latest Revision
Definition and requirements | 11-19/0202r1 | 11-19/0202r1
Selection Procedure document | 11-19/0030r6 | 11-19/0030r6
Functional Requirement document | 11-19/0495r0 | 11-19/0495r2
Spec Framework document | 11-19/0497r0 | 11-19/0497r3
Liaison response to IEEE VT/ITS 1609 WG | 11-19/0437r3 | 11-19/0437r3
Liaison response to ITU-T CITS | 11-19/0843r0 | 11-19/0843r0
TBbd FRD/SFD Motion Booklet | 11-19/0514r0 | 11-19/0514r10
TGbd Use Case document | 11-19/1342r0 | 11-19/1342r1

## Slide 5: Timeline (updated)
PAR approved Dec 2018
First TG meeting Jan 2019
D0.1 Sept 2019  Nov 2019
D1.0 Letter Ballot Nov 2019  Mar 2020
D2.0 LB recirculation Mar 2020  Jul 2020
Form Sponsor Ballot Pool May 2020  Sep 2020
D3.0 LB recirculation May 2020  Sep 2020
D3.0 unchanged recirculation July 2020  Nov 2020
Initial Sponsor Ballot (D4.0) Sept 2020  Jan 2021
Final 802.11 WG approval July 2021  Nov 2021
802 EC approval July 2021  Nov 2021
RevCom and SASB approval Sept 2021  Dec 2021

## Slide 6: Teleconferences and Goal for Sep meeting
Goal for Nov meeting
  Develop FRD and SFD
  Approval of spec draft D0.1
Planned TC:
  Date: Oct 8
  Time: 6:00pm~8:00pm, ET
New TC plan:
  Date: Oct 22
  Time: 10:00am ~ 11:59am