## Slide 1: Light Communications Task Group (TGbb) September 2019 Closing Report
Date: 2019-09-19
Authors:

## Slide 2: Abstract
This presentation contains the IEEE 802.11 Light Communications Task Group closing report for the September 2019 session.

## Slide 3: TGbb activities at the September meeting
  Content
  TGbb considered proposals for PHY and MAC features
    PHY proposals and simulation results (doc. 11-19/1625r3, doc. 11-19/1647r1, doc. 11-19/1566r2)
    The channel flatness test from 11ax was applied to the LC channels (doc. 11-19/1639r0)
    The use of Fast Session Transfer was agreed as a MAC feature for 11bb (doc. 11-19/1612r1)
    Different channel access mechanisms were considered for the 11bb MAC (doc. 11-19/1666r0)
  Mandatory, common-mode PHY was agreed to be based on the 20 MHz, SISO profile from 11ax
  Copyright request was granted from ITU-T for material related to the LC-optimized PHY (doc. 11-19/1663r1)
  Agreed the general format of the Table of Content for the Draft D0.1
  The timeline for TGbb was revised (doc. 11-18/1290r4), planning to go to WG LB in July 2020 and SA ballot in Mar. 2021
  Meeting agenda and motions are available in doc. 11-19/1413r6
  Minutes of the meeting are available in doc. 11-19/1704r0.

## Slide 4: TGbb plan for Nov. 2019 meeting
  5 slots were requested
  Expect PHY text contributions for the mandatory and optional PHY modes
  PHY contributions to define the electrical spectrum mask and center frequency
  MAC pre-proposals
  Develop and agree Draft D0.1 with initial text